## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 5
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 1
|  | Construction case (1 FC budget, 2 actual) | code | 1
|  | COD delay (sensitivity) | months | 0
|  | Capex factor | factor | 1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1.02
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 0
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 0
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 1
|  | Performance LD prepayment June 2022 (1 = on) | flag | 0
|  | Waiver and amendment 2023 (1 = on) | flag | 0
|  | 2025 bond refinancing (1 = on) | flag | 0
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 1
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-05-01
|  | PPA expiry | date | 2046-04-30
|  | Construction months (NTP to COD) | months | 33
|  | Period containing COD (period number) | index | 6
|  | First debt service period | index | 7
|  | Last month of the funding period (month number) | index | 35
|  | Last operating period (period number) | index | 56
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-05-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-04-30
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 120 | 0
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 520.4953 | 522.6929 | 524.8998 | 527.116 | 529.3416 | 531.5766 | 533.821 | 536.0748 | 538.3382 | 540.6112 | 542.8937 | 545.1859 | 547.4878 | 549.7993 | 552.1207 | 554.4518 | 556.7928 | 559.1437 | 561.5044 | 563.8752 | 566.256 | 568.6468 | 571.0477 | 573.4587 | 575.88 | 578.3114 | 580.7532 | 583.2052 | 585.6676 | 588.1403 | 590.6236 | 593.1173 | 595.6215 | 598.1363 | 600.6617 | 603.1978 | 605.7446 | 608.3021 | 610.8705 | 613.4497 | 616.0398 | 618.6408 | 621.2528 | 623.8758 | 626.5099 | 629.1551 | 631.8115 | 634.4791 | 637.158 | 639.8481 | 642.5497 | 645.2626 | 647.987
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 571.84 | 57.184 | 0.061759 | 0.64789 | 1.8522 | 3.5992 | 5.7836 | 8.2894 | 10.9999 | 13.8002 | 16.5828 | 19.2476 | 21.7053 | 23.8772 | 25.6956 | 27.1081 | 28.0722 | 28.5611 | 28.5611 | 28.0722 | 27.1081 | 25.6956 | 23.8772 | 21.7053 | 19.2476 | 16.5828 | 13.8002 | 10.9999 | 8.2894 | 5.7836 | 3.5992 | 1.8522 | 0.64789 | 42.9498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 46.18 | 5.5416 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 7.62 | 6.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 8.97 | 6.279 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 38.4 | 0 | 0.0050269 | 0.052736 | 0.15076 | 0.29296 | 0.47076 | 0.67472 | 0.89535 | 1.1233 | 1.3498 | 1.5667 | 1.7667 | 1.9435 | 2.0915 | 2.2065 | 2.285 | 2.3248 | 2.3248 | 2.285 | 2.2065 | 2.0915 | 1.9435 | 1.7667 | 1.5667 | 1.3498 | 1.1233 | 0.89535 | 0.67472 | 0.47076 | 0.29296 | 0.15076 | 0.052736 | 0.0050269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 710.99 | 108.1116 | 1.4208 | 2.0547 | 3.357 | 5.2462 | 7.6084 | 10.3182 | 13.2493 | 16.2775 | 19.2866 | 22.1683 | 24.8261 | 27.1747 | 29.1412 | 30.6686 | 31.7112 | 32.2399 | 33.3829 | 31.7112 | 30.6686 | 29.1412 | 27.1747 | 24.8261 | 22.1683 | 19.2866 | 16.2775 | 13.2493 | 10.3182 | 7.6084 | 5.2462 | 3.357 | 2.0547 | 49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 42938.798 | 4293.8798 | 4.6374 | 48.6497 | 139.0788 | 270.2568 | 434.283 | 622.4408 | 825.9707 | 1036.242 | 1245.1822 | 1445.277 | 1629.828 | 1792.9095 | 1929.4549 | 2035.5137 | 2107.9085 | 2144.6212 | 2144.6212 | 2107.9085 | 2035.5137 | 1929.4549 | 1792.9095 | 1629.828 | 1445.277 | 1245.1822 | 1036.242 | 825.9707 | 622.4408 | 434.283 | 270.2568 | 139.0788 | 48.6497 | 3225.0472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 7728.9836 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 7728.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 772.8984 | 773.7331 | 782.49 | 807.5242 | 856.1704 | 934.3414 | 1046.3807 | 1195.0555 | 1381.579 | 832.8134 | 1092.1286 | 1376.7407 | 1674.4302 | 1973.0859 | 2261.3074 | 2528.6916 | 2766.0487 | 2965.5569 | 3120.8477 | 3227.0903 | 3281.0231 | 3281.0231 | 3227.0903 | 3120.8477 | 2965.5569 | 2766.0487 | 2528.6916 | 2261.3074 | 1973.0859 | 1674.4302 | 1376.7407 | 1092.1286 | 1412.4872 | 1188.3544 | 1001.8309 | 853.1561 | 741.1168 | 662.9458 | 614.2996 | 589.2654 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.6349 | 0 | 0.019446 | 0.020031 | 0.019522 | 0.02073 | 0.021887 | 0.021483 | 0.026525 | 0.029193 | 0.034728 | 0.020174 | 0.027222 | 0.034172 | 0.040051 | 0.048562 | 0.053634 | 0.061715 | 0.067224 | 0.06714 | 0.07521 | 0.074946 | 0.078407 | 0.075559 | 0.076471 | 0.073643 | 0.067436 | 0.064723 | 0.057019 | 0.052468 | 0.045588 | 0.034797 | 0.031543 | 0.024113 | 0.03209 | 0.026017 | 0.02257 | 0.019139 | 0.016022 | 0.014747 | 0.013169 | 0.012998 | 0.012751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | KCR per USD, period average | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | US CPI change, current year | % |  |  | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, current year | % |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI change, prior year | % |  |  | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US index, June 2018 (2018 price base) | index | 103.3281
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084 | 191.0761
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 102.7675 | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0055 | 1.0165 | 1.0276 | 1.0388 | 1.0502 | 1.0617 | 1.0733 | 1.085 | 1.0969 | 1.1089 | 1.121 | 1.1333 | 1.1457 | 1.1582 | 1.1709 | 1.1837 | 1.1967 | 1.2097 | 1.223 | 1.2364 | 1.2499 | 1.2636 | 1.2774 | 1.2914 | 1.3055 | 1.3198 | 1.3342 | 1.3488 | 1.3636 | 1.3785 | 1.3936 | 1.4088 | 1.4242 | 1.4398 | 1.4556 | 1.4715 | 1.4876 | 1.5038 | 1.5203 | 1.5369 | 1.5537 | 1.5707 | 1.5879 | 1.6053 | 1.6229 | 1.6406 | 1.6586 | 1.6767 | 1.6951 | 1.7136 | 1.7323 | 1.7513 | 1.7705 | 1.7898 | 1.8094 | 1.8292 | 1.8492
|  | KC index, June 2018 (2018 price base) | index | 112.9227
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682 | 871.105
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 110.8994 | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0182 | 1.0557 | 1.0946 | 1.1349 | 1.1767 | 1.22 | 1.265 | 1.3115 | 1.3598 | 1.4099 | 1.4618 | 1.5156 | 1.5715 | 1.6293 | 1.6893 | 1.7515 | 1.816 | 1.8829 | 1.9522 | 2.0241 | 2.0986 | 2.1759 | 2.256 | 2.3391 | 2.4252 | 2.5145 | 2.6071 | 2.7031 | 2.8027 | 2.9059 | 3.0129 | 3.1238 | 3.2388 | 3.3581 | 3.4817 | 3.6099 | 3.7429 | 3.8807 | 4.0236 | 4.1717 | 4.3254 | 4.4846 | 4.6498 | 4.821 | 4.9985 | 5.1825 | 5.3734 | 5.5712 | 5.7764 | 5.9891 | 6.2096 | 6.4383 | 6.6753 | 6.9211 | 7.176 | 7.4402 | 7.7142
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 26
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 0
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.41667 | 0.91667 | 1.4167 | 1.9167 | 2.4167 | 2.9167 | 3.4167 | 3.9167 | 4.4167 | 4.9167 | 5.4167 | 5.9167 | 6.4167 | 6.9167 | 7.4167 | 7.9167 | 8.4167 | 8.9167 | 9.4167 | 9.9167 | 10.4167 | 10.9167 | 11.4167 | 11.9167 | 12.4167 | 12.9167 | 13.4167 | 13.9167 | 14.4167 | 14.9167 | 15.4167 | 15.9167 | 16.4167 | 16.9167 | 17.4167 | 17.9167 | 18.4167 | 18.9167 | 19.4167 | 19.9167 | 20.4167 | 20.9167 | 21.4167 | 21.9167 | 22.4167 | 22.9167 | 23.4167 | 23.9167 | 24.4167 | 24.8333 | 0
|  | Contracted capacity | MW | 588.4
|  | Plant net heat rate, new and clean | kJ/kWh | 6261
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98988 | 0.98938 | 0.98864 | 0.9879 | 0.98715 | 0.98641 | 0.98567 | 0.98493 | 0.98418 | 0.98344 | 0.9827 | 0.98196 | 0.98121 | 0.98047 | 0.97973 | 0.97899 | 0.97824 | 0.9775 | 0.97676 | 0.97602 | 0.97527 | 0.97453 | 0.97379 | 0.97305 | 0.9723 | 0.97156 | 0.97082 | 0.97008 | 0.96933 | 0.96859 | 0.96785 | 0.96711 | 0.96636 | 0.96562 | 0.96488 | 0.96414 | 0.96339 | 0.96265 | 0.96191 | 0.96117 | 0.96042 | 0.95968 | 0.95894 | 0.9582 | 0.95745 | 0.95671 | 0.95597 | 0.95523 | 0.95448 | 0.95374 | 0.95312 | 0.99
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 610197.8847 | 1829678.2427 | 1822457.6681 | 1809402.8106 | 1813881.5431 | 1824185.7752 | 1802084.1562 | 1759300.8791 | 1778671.879 | 1818693.3077 | 1811507.8661 | 1798523.2747 | 1802966.8742 | 1813200.8402 | 1778990.7603 | 1712018.3752 | 1743507.1072 | 1807708.3727 | 1800558.0641 | 1787643.7388 | 1792052.2052 | 1802215.9051 | 1780364.1212 | 1738080.5141 | 1757201.6791 | 1796723.4376 | 1789608.2621 | 1776764.203 | 1781137.5363 | 1791230.9701 | 1757419.0648 | 1691243.0289 | 1722333.5863 | 1785738.5026 | 1778658.4602 | 1765884.6671 | 1770222.8674 | 1780246.0351 | 1758644.0861 | 1716860.1492 | 1735731.4791 | 1774753.5675 | 1767708.6582 | 1755005.1312 | 1759308.1984 | 1769261.1 | 1735847.3694 | 1670467.6827 | 1701160.0655 | 1763768.6325 | 1175082.9123 | 0
|  | Plant net heat rate | kJ/kWh |  |  | 6585.3679 | 6585.3679 | 6585.3679 | 6585.3679 | 6585.3679 | 6586.0264 | 6588.6606 | 6592.6118 | 6596.563 | 6600.5142 | 6604.4655 | 6608.4167 | 6612.3679 | 6616.3191 | 6620.2703 | 6624.2216 | 6628.1728 | 6632.124 | 6636.0752 | 6640.0264 | 6643.9777 | 6647.9289 | 6651.8801 | 6655.8313 | 6659.7825 | 6663.7338 | 6667.685 | 6671.6362 | 6675.5874 | 6679.5386 | 6683.4899 | 6687.4411 | 6691.3923 | 6695.3435 | 6699.2947 | 6703.246 | 6707.1972 | 6711.1484 | 6715.0996 | 6719.0509 | 6723.0021 | 6726.9533 | 6730.9045 | 6734.8557 | 6738.807 | 6742.7582 | 6746.7094 | 6750.6606 | 6754.6118 | 6758.5631 | 6762.5143 | 6766.4655 | 6770.4167 | 6774.3679 | 6778.3192 | 6781.6118 | 6585.3679
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.968 | 6471.1242 | 6474.3584 | 6477.5926 | 6480.8268 | 6484.061 | 6487.2953 | 6490.5295 | 6493.7637 | 6496.9979 | 6500.2321 | 6503.4663 | 6506.7005 | 6509.9348 | 6513.169 | 6516.4032 | 6519.6374 | 6522.8716 | 6526.1058 | 6529.34 | 6532.5743 | 6535.8085 | 6539.0427 | 6542.2769 | 6545.5111 | 6548.7453 | 6551.9795 | 6555.2138 | 6558.448 | 6561.6822 | 6564.9164 | 6568.1506 | 6571.3848 | 6574.619 | 6577.8533 | 6581.0875 | 6584.3217 | 6587.5559 | 6590.7901 | 6594.0243 | 6597.2585 | 6600.4928 | 6603.727 | 6606.9612 | 6610.1954 | 6613.4296 | 6616.6638 | 6619.898 | 6623.1323 | 6626.3665 | 6629.0617 | 6468.429
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 4220446.6538 | 12660069.9973 | 12617671.0487 | 12534794.6769 | 12573348.1817 | 12652343.8544 | 12506527.2974 | 12216910.0676 | 12358806.4623 | 12644435.3836 | 12601995.5668 | 12519129.4971 | 12557541.8339 | 12636344.585 | 12405313.6656 | 11945403.7643 | 12172347.3107 | 12628071.4586 | 12585593.1061 | 12502742.0035 | 12541010.8398 | 12619616.0042 | 12473991.3645 | 12184946.5172 | 12326288.4123 | 12610978.2221 | 12568463.6664 | 12485632.1962 | 12523755.1993 | 12602158.112 | 12371567.7534 | 11912731.2151 | 12138872.8493 | 12593155.6742 | 12550607.2479 | 12467800.0751 | 12505774.9125 | 12583970.9084 | 12438571.36 | 12150165.2433 | 12290919.4648 | 12574603.8148 | 12532023.8505 | 12449245.6402 | 12487069.9794 | 12565054.3934 | 12334957.4668 | 11877300.0338 | 12102586.8847 | 12555322.644 | 8368848.1647 | 0
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 3533120 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 6950400 | 0
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4395 | 14.4718 | 14.5044 | 14.5374 | 14.5708 | 14.6045 | 14.6386 | 14.6731 | 14.7079 | 14.7431 | 14.7787 | 14.8148 | 14.8511 | 14.8879 | 14.9251 | 14.9627 | 15.0008 | 15.0392 | 15.078 | 15.1173 | 15.157 | 15.1972 | 15.2377 | 15.2788 | 15.3202 | 15.3622 | 15.4045 | 15.4474 | 15.4907 | 15.5345 | 15.5788 | 15.6235 | 15.6688 | 15.7145 | 15.7607 | 15.8075 | 15.8547 | 15.9025 | 15.9508 | 15.9996 | 16.049 | 16.0989 | 16.1493 | 16.2003 | 16.2519 | 16.304 | 16.3567 | 16.4099 | 16.4638 | 16.5182 | 16.5733 | 16.6289 | 16.6851 | 16.742 | 16.7995 | 16.8576 | 16.9163
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3275 | 2.353 | 2.3787 | 2.4047 | 2.431 | 2.4576 | 2.4845 | 2.5117 | 2.5392 | 2.567 | 2.595 | 2.6234 | 2.6521 | 2.6811 | 2.7105 | 2.7401 | 2.7701 | 2.8004 | 2.8311 | 2.862 | 2.8933 | 2.925 | 2.957 | 2.9893 | 3.022 | 3.0551 | 3.0885 | 3.1223 | 3.1565 | 3.191 | 3.2259 | 3.2612 | 3.2969 | 3.333 | 3.3694 | 3.4063 | 3.4435 | 3.4812 | 3.5193 | 3.5578 | 3.5967 | 3.6361 | 3.6759 | 3.7161 | 3.7567 | 3.7978 | 3.8394 | 3.8814 | 3.9238 | 3.9668 | 4.0102 | 4.054 | 4.0984 | 4.1432 | 4.1886 | 4.2344 | 4.2807
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 0
|  | Capacity payment | USD m |  | 3334.8082 | 0 | 0 | 0 | 0 | 0 | 20.0787 | 60.4515 | 60.6691 | 60.8891 | 61.1116 | 61.3364 | 61.5638 | 61.7936 | 62.0259 | 62.2608 | 62.4982 | 62.7383 | 62.9809 | 63.2262 | 63.4742 | 62.8045 | 63.9784 | 64.2347 | 64.4937 | 64.7556 | 65.0203 | 65.2879 | 65.5585 | 65.832 | 66.1085 | 66.388 | 66.6706 | 66.9563 | 67.2451 | 67.5371 | 67.8323 | 67.1465 | 68.4323 | 68.7373 | 69.0456 | 69.3572 | 69.6723 | 69.9908 | 70.3128 | 70.6384 | 70.9675 | 71.3002 | 71.6365 | 71.9765 | 72.3202 | 72.6677 | 73.019 | 72.3143 | 73.7332 | 74.0961 | 49.642 | 0
|  | VOM charge, indexed | USD/MWh |  |  | 3.9056 | 3.9483 | 3.9915 | 4.0352 | 4.0793 | 4.1239 | 4.1691 | 4.2147 | 4.2608 | 4.3074 | 4.3545 | 4.4022 | 4.4503 | 4.499 | 4.5482 | 4.598 | 4.6483 | 4.6991 | 4.7505 | 4.8025 | 4.8551 | 4.9082 | 4.9619 | 5.0162 | 5.071 | 5.1265 | 5.1826 | 5.2393 | 5.2966 | 5.3546 | 5.4131 | 5.4724 | 5.5322 | 5.5927 | 5.6539 | 5.7158 | 5.7783 | 5.8415 | 5.9054 | 5.97 | 6.0354 | 6.1014 | 6.1681 | 6.2356 | 6.3038 | 6.3728 | 6.4425 | 6.513 | 6.5843 | 6.6563 | 6.7291 | 6.8027 | 6.8772 | 6.9524 | 7.0285 | 7.1053 | 7.1831
|  | Variable O&M payment | USD m |  | 485.8117 | 0 | 0 | 0 | 0 | 0 | 2.5164 | 7.628 | 7.6811 | 7.7095 | 7.8131 | 7.9434 | 7.9331 | 7.8294 | 8.0023 | 8.2718 | 8.3293 | 8.36 | 8.4724 | 8.6137 | 8.5436 | 8.3119 | 8.5574 | 8.9696 | 9.0319 | 9.0652 | 9.187 | 9.3402 | 9.3278 | 9.2059 | 9.409 | 9.7259 | 9.7934 | 9.8295 | 9.9615 | 10.1275 | 10.045 | 9.7725 | 10.0611 | 10.5456 | 10.6187 | 10.6578 | 10.8008 | 10.9808 | 10.9662 | 10.8228 | 11.0615 | 11.4339 | 11.5131 | 11.5554 | 11.7105 | 11.9056 | 11.8085 | 11.4881 | 11.8271 | 12.3966 | 8.3494 | 0
|  | Fuel charge (pass-through) | USD m |  | 4886.8261 | 0 | 0 | 0 | 0 | 0 | 25.7791 | 77.3244 | 78.5989 | 78.0749 | 79.8734 | 80.3672 | 81.0218 | 79.1376 | 81.6498 | 83.5286 | 84.9048 | 84.3382 | 86.2804 | 86.8132 | 86.922 | 83.6912 | 86.9783 | 90.2258 | 91.7118 | 91.0991 | 93.1964 | 93.7714 | 94.5338 | 92.3343 | 95.2642 | 97.4549 | 99.0593 | 98.3969 | 100.6615 | 101.2818 | 101.4074 | 97.6369 | 101.4704 | 105.2576 | 106.9897 | 106.2736 | 108.7188 | 109.388 | 110.276 | 107.7088 | 111.125 | 113.679 | 115.5489 | 114.7747 | 117.4147 | 118.1367 | 118.2815 | 113.8822 | 118.3519 | 122.7675 | 83.4617 | 0
|  | GTA reservation charge (pass-through) | USD m |  | 690.3467 | 0 | 0 | 0 | 0 | 0 | 3.8163 | 11.5116 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 10.893 | 0
|  | GTA commodity charge (pass-through) | USD m |  | 149.3581 | 0 | 0 | 0 | 0 | 0 | 0.83851 | 2.5153 | 2.5445 | 2.5278 | 2.5736 | 2.5897 | 2.5983 | 2.5381 | 2.6061 | 2.6663 | 2.6973 | 2.6795 | 2.7281 | 2.7452 | 2.7354 | 2.634 | 2.7243 | 2.8263 | 2.859 | 2.8402 | 2.8916 | 2.9098 | 2.9193 | 2.8517 | 2.928 | 2.9957 | 3.0303 | 3.0104 | 3.0649 | 3.084 | 3.073 | 2.9591 | 3.0605 | 3.175 | 3.2117 | 3.1905 | 3.2483 | 3.2686 | 3.2793 | 3.2032 | 3.2889 | 3.3649 | 3.4038 | 3.3813 | 3.4424 | 3.4639 | 3.4515 | 3.3234 | 3.4373 | 3.5659 | 2.4125 | 0
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 3820.6199 | 0 | 0 | 0 | 0 | 0 | 22.5951 | 68.0795 | 68.3502 | 68.5986 | 68.9247 | 69.2799 | 69.4968 | 69.623 | 70.0282 | 70.5326 | 70.8275 | 71.0983 | 71.4533 | 71.8399 | 72.0179 | 71.1164 | 72.5359 | 73.2043 | 73.5256 | 73.8208 | 74.2073 | 74.6281 | 74.8863 | 75.0379 | 75.5175 | 76.1139 | 76.464 | 76.7858 | 77.2066 | 77.6646 | 77.8773 | 76.9191 | 78.4934 | 79.2828 | 79.6642 | 80.015 | 80.4731 | 80.9716 | 81.2791 | 81.4612 | 82.0289 | 82.734 | 83.1496 | 83.5319 | 84.0307 | 84.5733 | 84.8275 | 83.8024 | 85.5603 | 86.4927 | 57.9914 | 0
|  | Total revenue | USD m |  | 9547.151 | 0 | 0 | 0 | 0 | 0 | 53.0291 | 159.4308 | 160.9873 | 160.8855 | 163.0378 | 164.0963 | 165.0234 | 163.3362 | 166.3029 | 168.9455 | 170.6286 | 170.5172 | 172.8438 | 173.9856 | 174.3125 | 170.2177 | 174.9947 | 179.2241 | 181.044 | 180.9223 | 183.4371 | 184.6689 | 185.7522 | 183.784 | 187.2488 | 190.328 | 192.2958 | 192.1629 | 194.8812 | 196.2099 | 196.5934 | 191.9072 | 197.3941 | 202.3235 | 204.4511 | 204.3062 | 207.2443 | 208.6778 | 209.9436 | 207.6485 | 211.6945 | 215.2823 | 217.5827 | 217.4249 | 220.6004 | 222.147 | 222.597 | 217.2206 | 223.537 | 229.2819 | 154.7587 | 0
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 279.3596 | 0 | 0 | 0 | 0 | 0 | 1.399 | 4.2428 | 4.2892 | 4.3361 | 4.3835 | 4.4315 | 4.48 | 4.529 | 4.5785 | 4.6286 | 4.6793 | 4.7305 | 4.7822 | 4.8345 | 4.8874 | 4.9409 | 4.9949 | 5.0496 | 5.1048 | 5.1607 | 5.2171 | 5.2742 | 5.3319 | 5.3902 | 5.4492 | 5.5088 | 5.5691 | 5.63 | 5.6916 | 5.7539 | 5.8168 | 5.8805 | 5.9448 | 6.0098 | 6.0756 | 6.1421 | 6.2093 | 6.2772 | 6.3459 | 6.4153 | 6.4855 | 6.5564 | 6.6282 | 6.7007 | 6.774 | 6.8481 | 6.923 | 6.9987 | 7.0753 | 7.1527 | 4.8206 | 0
|  | O&M availability incentive | USD m |  | 4.108 | 0 | 0 | 0 | 0 | 0 | 0.0637 | 0.19319 | 0.16275 | 0.098721 | 0.13307 | 0.20179 | 0.083108 | -0.1604 | -0.038608 | 0.21076 | 0.17756 | 0.1077 | 0.14517 | 0.22014 | 0.012364 | -0.37497 | -0.20217 | 0.22993 | 0.1937 | 0.11749 | 0.15837 | 0.24016 | 0.098913 | -0.1909 | -0.045949 | 0.25084 | 0.21132 | 0.12818 | 0.17278 | 0.262 | 0.014715 | -0.44627 | -0.24062 | 0.27365 | 0.23054 | 0.13984 | 0.18849 | 0.28583 | 0.11772 | -0.2272 | -0.054687 | 0.29854 | 0.25151 | 0.15256 | 0.20563 | 0.31182 | 0.017513 | -0.53114 | -0.28637 | 0.32569 | 0.2195 | 0
|  | LTSA fixed fee | USD m |  | 93.2833 | 0 | 0 | 0 | 0 | 0 | 0.46714 | 1.4167 | 1.4322 | 1.4479 | 1.4637 | 1.4798 | 1.4959 | 1.5123 | 1.5289 | 1.5456 | 1.5625 | 1.5796 | 1.5969 | 1.6143 | 1.632 | 1.6499 | 1.6679 | 1.6862 | 1.7046 | 1.7232 | 1.7421 | 1.7612 | 1.7804 | 1.7999 | 1.8196 | 1.8395 | 1.8596 | 1.88 | 1.9005 | 1.9213 | 1.9423 | 1.9636 | 1.9851 | 2.0068 | 2.0288 | 2.0509 | 2.0734 | 2.0961 | 2.119 | 2.1422 | 2.1656 | 2.1893 | 2.2133 | 2.2375 | 2.262 | 2.2867 | 2.3117 | 2.337 | 2.3626 | 2.3884 | 1.6097 | 0
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 2813 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 5626 | 0
|  | LTSA variable fee | USD m |  | 289.8393 | 0 | 0 | 0 | 0 | 0 | 1.4514 | 4.4019 | 4.4501 | 4.4988 | 4.548 | 4.5977 | 4.648 | 4.6989 | 4.7503 | 4.8023 | 4.8548 | 4.9079 | 4.9616 | 5.0159 | 5.0708 | 5.1262 | 5.1823 | 5.239 | 5.2963 | 5.3543 | 5.4129 | 5.4721 | 5.5319 | 5.5925 | 5.6536 | 5.7155 | 5.778 | 5.8412 | 5.9051 | 5.9697 | 6.035 | 6.1011 | 6.1678 | 6.2353 | 6.3035 | 6.3725 | 6.4422 | 6.5127 | 6.5839 | 6.6559 | 6.7288 | 6.8024 | 6.8768 | 6.952 | 7.0281 | 7.105 | 7.1827 | 7.2613 | 7.3407 | 7.421 | 5.0015 | 0
|  | Operational insurance | USD m |  | 154.4122 | 0 | 0 | 0 | 0 | 0 | 0.77325 | 2.3451 | 2.3708 | 2.3967 | 2.4229 | 2.4495 | 2.4762 | 2.5033 | 2.5307 | 2.5584 | 2.5864 | 2.6147 | 2.6433 | 2.6722 | 2.7015 | 2.731 | 2.7609 | 2.7911 | 2.8216 | 2.8525 | 2.8837 | 2.9153 | 2.9471 | 2.9794 | 3.012 | 3.0449 | 3.0782 | 3.1119 | 3.146 | 3.1804 | 3.2152 | 3.2504 | 3.2859 | 3.3219 | 3.3582 | 3.3949 | 3.4321 | 3.4696 | 3.5076 | 3.546 | 3.5848 | 3.624 | 3.6636 | 3.7037 | 3.7442 | 3.7852 | 3.8266 | 3.8685 | 3.9108 | 3.9536 | 2.6645 | 0
|  | G&A | USD m |  | 112.0828 | 0 | 0 | 0 | 0 | 0 | 0.56128 | 1.7023 | 1.7209 | 1.7397 | 1.7587 | 1.778 | 1.7974 | 1.8171 | 1.837 | 1.8571 | 1.8774 | 1.8979 | 1.9187 | 1.9397 | 1.9609 | 1.9824 | 2.004 | 2.026 | 2.0481 | 2.0705 | 2.0932 | 2.1161 | 2.1392 | 2.1626 | 2.1863 | 2.2102 | 2.2344 | 2.2588 | 2.2836 | 2.3085 | 2.3338 | 2.3593 | 2.3851 | 2.4112 | 2.4376 | 2.4643 | 2.4912 | 2.5185 | 2.546 | 2.5739 | 2.6021 | 2.6305 | 2.6593 | 2.6884 | 2.7178 | 2.7475 | 2.7776 | 2.808 | 2.8387 | 2.8698 | 1.9341 | 0
|  | Land lease and permits | USD m |  | 25.0349 | 0 | 0 | 0 | 0 | 0 | 0.12537 | 0.38022 | 0.38438 | 0.38858 | 0.39283 | 0.39713 | 0.40148 | 0.40587 | 0.41031 | 0.4148 | 0.41933 | 0.42392 | 0.42856 | 0.43325 | 0.43799 | 0.44278 | 0.44762 | 0.45252 | 0.45747 | 0.46248 | 0.46754 | 0.47265 | 0.47782 | 0.48305 | 0.48833 | 0.49368 | 0.49908 | 0.50454 | 0.51006 | 0.51564 | 0.52128 | 0.52698 | 0.53275 | 0.53857 | 0.54447 | 0.55042 | 0.55644 | 0.56253 | 0.56869 | 0.57491 | 0.5812 | 0.58756 | 0.59398 | 0.60048 | 0.60705 | 0.61369 | 0.62041 | 0.62719 | 0.63406 | 0.64099 | 0.432 | 0
|  | Community fund and OREK levy | USD m |  | 21.0134 | 0 | 0 | 0 | 0 | 0 | 0.12427 | 0.37444 | 0.37593 | 0.37729 | 0.37909 | 0.38104 | 0.38223 | 0.38293 | 0.38515 | 0.38793 | 0.38955 | 0.39104 | 0.39299 | 0.39512 | 0.3961 | 0.39114 | 0.39895 | 0.40262 | 0.40439 | 0.40601 | 0.40814 | 0.41045 | 0.41187 | 0.41271 | 0.41535 | 0.41863 | 0.42055 | 0.42232 | 0.42464 | 0.42716 | 0.42833 | 0.42305 | 0.43171 | 0.43606 | 0.43815 | 0.44008 | 0.4426 | 0.44534 | 0.44703 | 0.44804 | 0.45116 | 0.45504 | 0.45732 | 0.45943 | 0.46217 | 0.46515 | 0.46655 | 0.46091 | 0.47058 | 0.47571 | 0.31895 | 0
|  | Variable consumables | USD m |  | 134.8703 | 0 | 0 | 0 | 0 | 0 | 0.69861 | 2.1177 | 2.1324 | 2.1403 | 2.1691 | 2.2052 | 2.2024 | 2.1736 | 2.2216 | 2.2964 | 2.3124 | 2.3209 | 2.3521 | 2.3913 | 2.3719 | 2.3076 | 2.3757 | 2.4901 | 2.5074 | 2.5167 | 2.5505 | 2.593 | 2.5896 | 2.5557 | 2.6121 | 2.7001 | 2.7188 | 2.7288 | 2.7655 | 2.8116 | 2.7887 | 2.713 | 2.7931 | 2.9276 | 2.9479 | 2.9588 | 2.9985 | 3.0485 | 3.0444 | 3.0046 | 3.0709 | 3.1743 | 3.1962 | 3.208 | 3.251 | 3.3052 | 3.2783 | 3.1893 | 3.2834 | 3.4415 | 2.3179 | 0
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0.0425 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.085 | 0
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0.051875 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.10375 | 0
|  | Operating costs before pass-through items | USD m |  | 1128.16 | 0 | 0 | 0 | 0 | 0 | 5.7584 | 17.4575 | 17.6017 | 17.7072 | 17.9341 | 18.2048 | 18.2499 | 18.1457 | 18.4869 | 18.985 | 19.1423 | 19.2573 | 19.5046 | 19.7996 | 19.754 | 19.48 | 19.9133 | 20.6501 | 20.8216 | 20.947 | 21.2166 | 21.5382 | 21.592 | 21.4684 | 21.8737 | 22.4653 | 22.6523 | 22.789 | 23.0829 | 23.4334 | 23.3793 | 23.0547 | 23.5689 | 24.4441 | 24.6479 | 24.797 | 25.1173 | 25.4993 | 25.5634 | 25.4168 | 25.8983 | 26.6011 | 26.8233 | 26.9858 | 27.3351 | 27.7515 | 27.6875 | 27.3029 | 27.9129 | 28.9525 | 19.5076 | 0
|  | Gas purchases | USD m |  | 4988.3647 | 0 | 0 | 0 | 0 | 0 | 26.2456 | 78.7289 | 80.0345 | 79.5089 | 81.3485 | 81.8596 | 82.5345 | 80.6232 | 83.1908 | 85.1135 | 86.5243 | 85.9554 | 87.9435 | 88.4954 | 88.615 | 85.3297 | 88.6898 | 92.0103 | 93.5348 | 92.9191 | 95.0676 | 95.6634 | 96.4507 | 94.2158 | 97.2148 | 99.4601 | 101.1073 | 100.441 | 102.7626 | 103.4059 | 103.5441 | 99.7039 | 103.6285 | 107.5067 | 109.2863 | 108.5653 | 111.0739 | 111.7684 | 112.6865 | 110.0737 | 113.5758 | 116.1973 | 118.1199 | 117.3396 | 120.0501 | 120.7998 | 120.9594 | 116.4715 | 121.0544 | 125.5828 | 85.3824 | 0
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5828.0696 | 0 | 0 | 0 | 0 | 0 | 30.9005 | 92.7558 | 94.0728 | 93.7209 | 95.5882 | 96.3088 | 97.0393 | 95.1987 | 97.8157 | 99.9978 | 101.4206 | 101.0361 | 103.0536 | 103.8278 | 103.9876 | 100.7398 | 104.1704 | 107.8043 | 109.3415 | 108.9215 | 111.1011 | 111.9329 | 112.7827 | 110.6275 | 113.6819 | 116.2192 | 117.8798 | 117.4213 | 119.7757 | 120.6694 | 120.8529 | 117.0551 | 121.0588 | 125.2897 | 127.0835 | 126.583 | 129.1263 | 130.0865 | 131.075 | 128.5522 | 132.1164 | 135.0665 | 137.004 | 136.4579 | 139.2051 | 140.2368 | 140.4474 | 136.0076 | 140.6792 | 145.6045 | 98.6879 | 0
|  | VAT facility interest after the funding period | USD m |  | 0.1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0.098646 | 0.012751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7663 | 0 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Handback reserve contribution required | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
|  | Handback works at PPA expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
|  | Total operating costs | USD m |  | 7027.1083 | 0 | 0 | 0 | 0 | 0 | 36.6588 | 110.3119 | 111.6873 | 111.4281 | 113.5223 | 114.5136 | 115.2893 | 115.8421 | 116.3026 | 118.9828 | 120.5629 | 120.2934 | 122.5582 | 123.6274 | 123.7416 | 132.0562 | 124.0837 | 128.4545 | 130.1631 | 129.8685 | 132.3177 | 133.471 | 134.3747 | 135.0684 | 135.5556 | 138.6846 | 140.5321 | 140.2102 | 142.8586 | 144.1028 | 144.2322 | 154.1972 | 144.6277 | 149.7338 | 151.7313 | 151.3799 | 154.2436 | 155.5858 | 156.6384 | 157.5068 | 158.0147 | 161.6677 | 163.8274 | 163.4438 | 166.5402 | 167.9883 | 168.1348 | 180.0767 | 168.5921 | 174.557 | 137.2647 | 0
|  | EBITDA | USD m |  | 2520.0427 | 0 | 0 | 0 | 0 | 0 | 16.3703 | 49.1189 | 49.3001 | 49.4574 | 49.5155 | 49.5828 | 49.7342 | 47.4941 | 50.0003 | 49.9628 | 50.0657 | 50.2238 | 50.2855 | 50.3582 | 50.5709 | 38.1615 | 50.911 | 50.7696 | 50.8809 | 51.0538 | 51.1195 | 51.1978 | 51.3775 | 48.7155 | 51.6932 | 51.6434 | 51.7637 | 51.9527 | 52.0226 | 52.1071 | 52.3612 | 37.71 | 52.7664 | 52.5897 | 52.7197 | 52.9263 | 53.0007 | 53.0919 | 53.3052 | 50.1417 | 53.6798 | 53.6147 | 53.7553 | 53.9811 | 54.0602 | 54.1587 | 54.4622 | 37.1439 | 54.9449 | 54.7249 | 17.4939 | 0
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.1198 | 38.9912 | 40.0245 | 39.347 | 40.5343 | 40.1323 | 40.8025 | 39.9464 | 41.346 | 41.3182 | 42.4215 | 41.7026 | 42.9722 | 42.5508 | 43.0992 | 41.6293 | 43.507 | 43.832 | 45.0109 | 44.2473 | 45.6059 | 45.1636 | 45.9277 | 44.9472 | 46.5536 | 46.5476 | 47.8083 | 46.9964 | 48.4511 | 47.9861 | 48.6083 | 46.9338 | 49.0759 | 49.4813 | 50.8304 | 49.9662 | 51.5248 | 51.0353 | 51.9091 | 50.7836 | 52.6312 | 52.6506 | 54.0951 | 53.1746 | 54.8454 | 54.3294 | 55.0377 | 53.1246 | 55.5755 | 56.0744 | 0 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 19.3615 | 19.2544 | 19.8981 | 19.4451 | 20.2248 | 20.02 | 20.4069 | 19.7176 | 20.6828 | 20.8158 | 21.5116 | 21.0217 | 21.8644 | 21.6429 | 21.9103 | 20.8687 | 22.05 | 22.5025 | 23.2545 | 22.7248 | 23.6356 | 23.3959 | 23.8477 | 23.0419 | 24.1694 | 24.3245 | 25.1372 | 24.5644 | 25.5487 | 25.2895 | 25.6016 | 24.3841 | 25.764 | 26.2924 | 27.1706 | 26.5513 | 27.615 | 27.3347 | 27.862 | 26.9202 | 28.2371 | 28.4178 | 29.3668 | 28.6972 | 29.8467 | 29.5434 | 29.9076 | 28.4849 | 30.0964 | 30.7132 | 0 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.2893 | 2.287 | 2.3268 | 2.3172 | 2.3602 | 2.3559 | 2.3909 | 2.3764 | 2.424 | 2.4268 | 2.469 | 2.4588 | 2.5044 | 2.4999 | 2.5339 | 2.5125 | 2.5658 | 2.5751 | 2.6199 | 2.6091 | 2.6575 | 2.6526 | 2.6921 | 2.6758 | 2.7294 | 2.7325 | 2.78 | 2.7685 | 2.8199 | 2.8147 | 2.8531 | 2.829 | 2.889 | 2.8994 | 2.9498 | 2.9377 | 2.9921 | 2.9867 | 3.0311 | 3.0128 | 3.073 | 3.0765 | 3.13 | 3.1171 | 3.1749 | 3.1691 | 3.2123 | 3.1852 | 3.2527 | 3.2644 | 0 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.6629 | 1.6719 | 1.7129 | 1.6926 | 1.745 | 1.7463 | 1.7649 | 1.725 | 1.7932 | 1.824 | 1.8686 | 1.8466 | 1.9037 | 1.9051 | 1.9125 | 1.8492 | 1.9298 | 1.9899 | 2.0386 | 2.0145 | 2.0769 | 2.0784 | 2.1005 | 2.053 | 2.1342 | 2.1709 | 2.224 | 2.1977 | 2.2658 | 2.2674 | 2.2762 | 2.2009 | 2.2968 | 2.3683 | 2.4263 | 2.3976 | 2.4718 | 2.4737 | 2.5 | 2.4434 | 2.5401 | 2.5837 | 2.6469 | 2.6157 | 2.6966 | 2.6986 | 2.7091 | 2.6194 | 2.7335 | 2.8187 | 0 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.1691 | 1.1744 | 1.2046 | 1.1944 | 1.2275 | 1.2218 | 1.2433 | 1.2336 | 1.2709 | 1.2714 | 1.3041 | 1.2932 | 1.3291 | 1.3231 | 1.3436 | 1.3268 | 1.3708 | 1.377 | 1.4125 | 1.4008 | 1.4397 | 1.4332 | 1.4586 | 1.4473 | 1.4912 | 1.492 | 1.5305 | 1.5179 | 1.5601 | 1.5532 | 1.5775 | 1.558 | 1.6097 | 1.6171 | 1.659 | 1.6454 | 1.6913 | 1.6838 | 1.7138 | 1.7006 | 1.7525 | 1.7534 | 1.7989 | 1.7842 | 1.834 | 1.8261 | 1.8548 | 1.8321 | 1.8929 | 1.9018 | 0 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 14.6371 | 14.6036 | 14.8822 | 14.6977 | 14.9768 | 14.7882 | 14.9965 | 14.8937 | 15.1751 | 14.9802 | 15.2681 | 15.0823 | 15.3706 | 15.1799 | 15.3988 | 15.0721 | 15.5906 | 15.3875 | 15.6854 | 15.4982 | 15.7963 | 15.6033 | 15.8288 | 15.7292 | 16.0293 | 15.8278 | 16.1367 | 15.9479 | 16.2567 | 16.0613 | 16.2999 | 15.9618 | 16.5164 | 16.304 | 16.6247 | 16.4343 | 16.7546 | 16.5565 | 16.8023 | 16.7066 | 17.0286 | 16.8191 | 17.1525 | 16.9604 | 17.2932 | 17.0922 | 17.354 | 17.0029 | 17.5999 | 17.3763 | 0 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 14.6371 | -0.033512 | 0.27862 | -0.18451 | 0.27913 | -0.18858 | 0.20825 | -0.10274 | 0.28134 | -0.19484 | 0.28791 | -0.18585 | 0.28826 | -0.19067 | 0.21896 | -0.32678 | 0.51856 | -0.20315 | 0.29796 | -0.18728 | 0.29812 | -0.19293 | 0.22547 | -0.099659 | 0.30015 | -0.20148 | 0.30884 | -0.18879 | 0.30878 | -0.19539 | 0.23859 | -0.33806 | 0.55464 | -0.2124 | 0.32062 | -0.1904 | 0.32031 | -0.19806 | 0.24575 | -0.095707 | 0.32203 | -0.20948 | 0.33338 | -0.1921 | 0.33277 | -0.20095 | 0.26178 | -0.35106 | 0.59699 | -0.22365 | -17.3763 | 0
|  | Release of spares inventory at expiry | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| Tax depreciation (straight line from COD) | USD m |  | 836.6866 | 0 | 0 | 0 | 0 | 0 | 7.5302 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 21.7539 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 13.6659 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.55779 | 0
| Depreciation of holiday months (deemed deferred) | USD m |  | 225.9054 | 0 | 0 | 0 | 0 | 0 | 7.5302 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 22.5905 | 15.0604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 610.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6935 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 20.0805 | 13.6659 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.83669 | 0.55779 | 0
| Shareholder loan interest accrued | USD m |  | 229.6832 | 0 | 0 | 0 | 0 | 0 | 3.2017 | 9.8109 | 9.486 | 9.5716 | 9.3063 | 9.3761 | 9.1601 | 9.1812 | 8.8953 | 8.8562 | 8.5818 | 8.6171 | 8.3404 | 8.6228 | 8.6421 | 8.8709 | 8.8076 | 9.0081 | 8.888 | 9.042 | 8.8497 | 8.908 | 8.6479 | 8.1239 | 6.9694 | 5.8918 | 4.6501 | 2.6164 | 0.75974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 0.66002 | 0.78537 | 0.88601 | 0.99904 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 225.3986 | 0 | 0 | 0 | 0 | 0 | 2.1132 | 7.7052 | 8.4047 | 9.5624 | 9.3063 | 9.3761 | 9.1601 | 9.1812 | 8.8953 | 8.8562 | 8.5818 | 8.6171 | 8.3404 | 8.6228 | 8.6421 | 8.8709 | 8.8076 | 9.0081 | 8.888 | 9.042 | 8.8497 | 8.908 | 8.6479 | 8.1239 | 6.9694 | 5.8918 | 4.6501 | 2.6164 | 0.75974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 315.1468 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7562 | 21.0118 | 20.6842 | 19.8935 | 19.5092 | 18.7469 | 18.2344 | 17.3567 | 16.8339 | 16.4681 | 15.9362 | 15.0282 | 14.1678 | 12.9827 | 11.9949 | 10.6864 | 9.5665 | 8.4227 | 7.2065 | 5.7987 | 4.5049 | 3.1122 | 2.1737 | 1.5812 | 0.99209 | 0.49725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Taxable income before losses and deferred depreciation | USD m |  | 1148.0903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6451 | 5.59 | 6.8364 | 7.4871 | 8.8656 | -2.7847 | 11.3365 | 12.1146 | 13.4897 | 14.7248 | 16.3905 | 17.7045 | 19.5369 | 18.3375 | 23.0621 | 24.679 | 26.5358 | 29.2558 | 31.1823 | 32.0266 | 32.2807 | 17.6296 | 32.6859 | 32.5092 | 32.6393 | 32.8459 | 32.9202 | 33.0115 | 33.2247 | 30.0612 | 40.0139 | 52.778 | 52.9186 | 53.1444 | 53.2236 | 53.322 | 53.6255 | 36.3072 | 54.1082 | 53.8882 | 16.9362 | 0
| Tax losses used | USD m |  | 2.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 225.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6451 | 5.59 | 6.8364 | 7.4871 | 8.8656 | 0 | 8.5519 | 12.1146 | 13.4897 | 14.7248 | 16.3905 | 17.7045 | 19.5369 | 18.3375 | 23.0621 | 24.679 | 26.5358 | 0.35377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 7.5302 | 30.1207 | 52.7113 | 75.3018 | 97.8923 | 120.4829 | 143.0734 | 165.6639 | 188.2545 | 210.845 | 224.2603 | 218.6702 | 211.8338 | 204.3467 | 195.4811 | 195.4811 | 186.9292 | 174.8146 | 161.3249 | 146.6001 | 130.2096 | 112.5051 | 92.9682 | 74.6307 | 51.5687 | 26.8896 | 0.35377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 922.1849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.902 | 31.1823 | 32.0266 | 32.2807 | 17.6296 | 32.6859 | 32.5092 | 32.6393 | 32.8459 | 32.9202 | 33.0115 | 33.2247 | 30.0612 | 40.0139 | 52.778 | 52.9186 | 53.1444 | 53.2236 | 53.322 | 53.6255 | 36.3072 | 54.1082 | 53.8882 | 16.9362 | 0
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| Corporate income tax | USD m |  | 276.6555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6706 | 9.3547 | 9.608 | 9.6842 | 5.2889 | 9.8058 | 9.7528 | 9.7918 | 9.8538 | 9.8761 | 9.9034 | 9.9674 | 9.0184 | 12.0042 | 15.8334 | 15.8756 | 15.9433 | 15.9671 | 15.9966 | 16.0876 | 10.8922 | 16.2325 | 16.1665 | 5.0808 | 0
| Minimum turnover tax | USD m |  | 15.6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11805 | 0.35549 | 0.35727 | 0.3592 | 0.36009 | 0.35558 | 0.36268 | 0.36602 | 0.36763 | 0.3691 | 0.37104 | 0.37314 | 0.37443 | 0.37519 | 0.37759 | 0.38057 | 0.38232 | 0.38393 | 0.38603 | 0.38832 | 0.38939 | 0.3846 | 0.39247 | 0.39641 | 0.39832 | 0.40007 | 0.40237 | 0.40486 | 0.4064 | 0.40731 | 0.41014 | 0.41367 | 0.41575 | 0.41766 | 0.42015 | 0.42287 | 0.42414 | 0.41901 | 0.4278 | 0.43246 | 0.28996 | 0
| Tax paid = max(CIT, MTT) | USD m |  | 282.6609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11805 | 0.35549 | 0.35727 | 0.3592 | 0.36009 | 0.35558 | 0.36268 | 0.36602 | 0.36763 | 0.3691 | 0.37104 | 0.37314 | 0.37443 | 0.37519 | 0.37759 | 0.38057 | 0.38232 | 8.6706 | 9.3547 | 9.608 | 9.6842 | 5.2889 | 9.8058 | 9.7528 | 9.7918 | 9.8538 | 9.8761 | 9.9034 | 9.9674 | 9.0184 | 12.0042 | 15.8334 | 15.8756 | 15.9433 | 15.9671 | 15.9966 | 16.0876 | 10.8922 | 16.2325 | 16.1665 | 5.0808 | 0
| Thin-cap disallowance | USD m |  | 4.2847 | 0 | 0 | 0 | 0 | 0 | 1.0885 | 2.1057 | 1.0813 | 0.0092024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.74057
|  | Gearing used in the closed-form gross-up | fraction | 0.75
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97559
|  | First installment share of remaining profile | fraction | 0.02446
|  | DSRA coefficient per USD of E balance | factor | 0.047154
|  | DSRA coefficient per USD of A balance | factor | 0.058909
|  | DSRA coefficient per USD of B balance | factor | 0.057632
|  | DSRA coefficient per USD of C balance | factor | 0.07051
|  | DSRA coefficient per USD of standby balance | factor | 0.064102
|  | DSRA constant (swap net payment) | USD m | -0.53616
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0054193 | 0.0052445 | 0.0054193 | 0.0052445 | 0.0054193 | 0.0056617 | 0.0051138 | 0.0056617 | 0.005479 | 0.0056617 | 0.005479 | 0.0057963 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0058681 | 0.0054895 | 0.0058681 | 0.0056788 | 0.0058681 | 0.0056788 | 0.005904 | 0.005904 | 0.0057135 | 0.005904 | 0.0057135 | 0.005904 | 0.0059309 | 0.0053569 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059488 | 0.0053731 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 108.1566 | 1.5102 | 2.1407 | 3.4476 | 5.3342 | 7.6797 | 10.4073 | 13.3259 | 16.3644 | 19.3724 | 22.2492 | 24.8877 | 27.2421 | 29.2265 | 30.7476 | 31.8103 | 32.329 | 33.4585 | 31.8282 | 30.7461 | 29.2412 | 27.2497 | 24.9244 | 22.2235 | 19.3363 | 16.3517 | 13.2855 | 10.3799 | 7.6291 | 5.2476 | 3.4576 | 2.0402 | 49.6739 | -0.55737 | 0.01016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 83.1473 | 84.5898 | 86.5315 | 89.4749 | 93.8887 | 100.1386 | 108.4727 | 119.1169 | 132.1221 | 147.5019 | 165.1324 | 184.8908 | 206.5341 | 229.7597 | 254.2679 | 279.6549 | 305.5679 | 332.4643 | 358.1282 | 383.1413 | 407.0462 | 429.5594 | 450.3184 | 469.1465 | 485.8278 | 500.2186 | 512.3686 | 522.2679 | 530.1547 | 536.2523 | 540.7956 | 544.4688 | 584.7072 | 586.5544 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715 | 588.7715
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0095643 | 0.010081 | 0.010617 | 0.011137 | 0.011677 | 0.01222 | 0.012713 | 0.013261 | 0.013792 | 0.014344 | 0.014879 | 0.015436 | 0.015995 | 0.016538 | 0.017102 | 0.017649 | 0.018216 | 0.018787 | 0.019323 | 0.019897 | 0.020456 | 0.021035 | 0.021598 | 0.022182 | 0.022768 | 0.023338 | 0.023929 | 0.024503 | 0.025098 | 0.025697 | 0.026239 | 0.026842 | 0.027427 | 0.062435 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155 | 0.063155
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 857.2111
|  | Senior debt (committed tranches) | USD m | 633.256
|  | Debt share of monthly funding | fraction | 0.74057
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 27.0144 | 27.5696 | 28.2773 | 29.2778 | 30.7185 | 32.7038 | 35.2936 | 38.5809 | 42.5633 | 47.2536 | 52.6064 | 58.5942 | 65.1404 | 72.151 | 79.5459 | 87.1969 | 95.0081 | 103.1109 | 110.84 | 118.3854 | 125.5982 | 132.4036 | 138.6852 | 144.3997 | 149.4788 | 153.8753 | 157.6131 | 160.6802 | 163.1562 | 165.1029 | 166.576 | 167.8056 | 179.8594 | 189.1501 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 19.8105 | 20.2177 | 20.7367 | 21.4704 | 22.5269 | 23.9828 | 25.882 | 28.2926 | 31.2131 | 34.6527 | 38.578 | 42.9691 | 47.7696 | 52.9107 | 58.3337 | 63.9444 | 69.6726 | 75.6147 | 81.2827 | 86.8159 | 92.1054 | 97.096 | 101.7024 | 105.8931 | 109.6178 | 112.8419 | 115.5829 | 117.8321 | 119.6479 | 121.0754 | 122.1557 | 123.0574 | 131.8969 | 138.7101 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 9.0048 | 9.1899 | 9.4258 | 9.7593 | 10.2395 | 10.9013 | 11.7645 | 12.8603 | 14.1878 | 15.7512 | 17.5355 | 19.5314 | 21.7135 | 24.0503 | 26.5153 | 29.0656 | 31.6694 | 34.3703 | 36.9467 | 39.4618 | 41.8661 | 44.1345 | 46.2284 | 48.1332 | 49.8263 | 51.2918 | 52.5377 | 53.5601 | 54.3854 | 55.0343 | 55.5253 | 55.9352 | 59.9531 | 63.05 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 34.2182 | 34.9215 | 35.8179 | 37.0853 | 38.9101 | 41.4248 | 44.7052 | 48.8691 | 53.9136 | 59.8546 | 66.6347 | 74.2193 | 82.5112 | 91.3912 | 100.7582 | 110.4494 | 120.3437 | 130.6072 | 140.3973 | 149.9548 | 159.0911 | 167.7112 | 175.6679 | 182.9063 | 189.3398 | 194.9087 | 199.6433 | 203.5282 | 206.6645 | 209.1303 | 210.9963 | 212.5538 | 227.8219 | 239.5901 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11
|  | ECA-covered tranche: interest | USD m |  | 12.4338 | 0 | 0.087121 | 0.091876 | 0.091194 | 0.097568 | 0.10951 | 0.10531 | 0.12582 | 0.1331 | 0.15174 | 0.16303 | 0.19434 | 0.21646 | 0.23288 | 0.26654 | 0.28438 | 0.32212 | 0.35752 | 0.36298 | 0.4171 | 0.43112 | 0.47263 | 0.48217 | 0.52666 | 0.54836 | 0.54933 | 0.58434 | 0.57923 | 0.61018 | 0.6238 | 0.57016 | 0.63688 | 0.62088 | 0.68766 | 0.69986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 13.9281 | 0 | 0.10186 | 0.10742 | 0.10662 | 0.11407 | 0.12492 | 0.12013 | 0.14353 | 0.15184 | 0.17309 | 0.18597 | 0.21892 | 0.24384 | 0.26233 | 0.30025 | 0.32035 | 0.36287 | 0.40017 | 0.40628 | 0.46686 | 0.48255 | 0.52902 | 0.53969 | 0.58764 | 0.61186 | 0.61295 | 0.65201 | 0.6463 | 0.68084 | 0.69442 | 0.6347 | 0.70898 | 0.69117 | 0.76551 | 0.77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 6.0933 | 0 | 0.044424 | 0.046848 | 0.0465 | 0.049751 | 0.054579 | 0.052483 | 0.062708 | 0.066338 | 0.075625 | 0.08125 | 0.095734 | 0.10663 | 0.11472 | 0.1313 | 0.14009 | 0.15868 | 0.17508 | 0.17775 | 0.20425 | 0.21112 | 0.23145 | 0.23612 | 0.25716 | 0.26775 | 0.26823 | 0.28532 | 0.28283 | 0.29794 | 0.30394 | 0.2778 | 0.31031 | 0.30252 | 0.33505 | 0.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 28.5367 | 0 | 0.20974 | 0.22119 | 0.21955 | 0.2349 | 0.25651 | 0.24666 | 0.29471 | 0.31177 | 0.35541 | 0.38185 | 0.44884 | 0.49993 | 0.53785 | 0.61559 | 0.65679 | 0.74397 | 0.81982 | 0.83234 | 0.95644 | 0.98859 | 1.0838 | 1.1057 | 1.2034 | 1.253 | 1.2553 | 1.3352 | 1.3236 | 1.3943 | 1.4217 | 1.2994 | 1.4515 | 1.4151 | 1.5673 | 1.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 3.6874 | 0 | 0.029109 | 0.030697 | 0.03047 | 0.032599 | 0.034204 | 0.03289 | 0.039298 | 0.041572 | 0.047392 | 0.050917 | 0.058575 | 0.065242 | 0.070191 | 0.080337 | 0.085713 | 0.09709 | 0.10579 | 0.1074 | 0.12342 | 0.12756 | 0.13985 | 0.14267 | 0.15442 | 0.16078 | 0.16107 | 0.17133 | 0.16983 | 0.17891 | 0.18167 | 0.16604 | 0.18547 | 0.18082 | 0.20026 | 0.20382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | -0.78015 | 0 | 0.025634 | 0.021014 | 0.026832 | 0.022316 | 0.0043689 | 0.024928 | 0.0050195 | 0.01346 | 0.0060535 | 0.016486 | -0.010638 | -0.011849 | 0.0010133 | -0.014591 | 0.0012374 | -0.017633 | -0.036666 | 0.0063394 | -0.042776 | -0.019205 | -0.048472 | -0.021479 | -0.066261 | -0.068991 | -0.037536 | -0.073518 | -0.039578 | -0.076769 | -0.089192 | 0.023114 | -0.091062 | -0.053325 | -0.098323 | -0.060108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 9.3037 | 0.54978 | 0.45639 | 0.46999 | 0.45285 | 0.46505 | 0.46088 | 0.41109 | 0.44764 | 0.42399 | 0.4266 | 0.3997 | 0.39754 | 0.38021 | 0.34961 | 0.34098 | 0.30927 | 0.29744 | 0.27483 | 0.23516 | 0.22901 | 0.2005 | 0.18631 | 0.16124 | 0.14843 | 0.1319 | 0.11342 | 0.10447 | 0.090636 | 0.084782 | 0.077616 | 0.065017 | 0.06772 | 0.062092 | 0.029279 | 0.0023152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.8165 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 9.9548 | 9.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.74375 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 37.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 118.6612 | 2.4388 | 3.1088 | 4.3948 | 6.3282 | 8.7203 | 11.3758 | 14.4396 | 17.4931 | 20.6023 | 23.5119 | 26.3016 | 28.7544 | 30.7941 | 32.4826 | 33.6069 | 34.3112 | 35.5917 | 33.9501 | 33.1431 | 31.6826 | 29.8927 | 27.592 | 25.1013 | 22.3099 | 19.3119 | 16.4183 | 13.4722 | 10.8761 | 8.5507 | 6.4708 | 5.401 | 52.9464 | 40.8097 | 3.6313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 633.256 | 543.2081 | 541.3574 | 538.9983 | 535.6632 | 530.861 | 524.2435 | 515.6107 | 504.653 | 491.3782 | 475.7438 | 457.9015 | 437.942 | 416.1213 | 392.7528 | 368.1029 | 342.5997 | 316.5622 | 289.5528 | 263.7893 | 238.6381 | 214.5953 | 191.9107 | 170.9721 | 151.9236 | 134.9934 | 120.3382 | 107.879 | 97.6554 | 89.4019 | 82.9131 | 78.0026 | 73.9039 | 33.7247 | 2.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior tranche drawdown (pro rata) | USD m |  | 633.256 | 90.0479 | 1.8507 | 2.3591 | 3.335 | 4.8022 | 6.6175 | 8.6327 | 10.9577 | 13.2749 | 15.6343 | 17.8424 | 19.9594 | 21.8207 | 23.3686 | 24.6499 | 25.5031 | 26.0376 | 27.0093 | 25.7635 | 25.1512 | 24.0429 | 22.6846 | 20.9386 | 19.0485 | 16.9302 | 14.6552 | 12.4592 | 10.2236 | 8.2535 | 6.4889 | 4.9105 | 4.0987 | 40.1792 | 30.9691 | 2.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 20.6125 | 2.9311 | 0.060241 | 0.07679 | 0.10856 | 0.15631 | 0.2154 | 0.281 | 0.35667 | 0.4321 | 0.5089 | 0.58077 | 0.64968 | 0.71026 | 0.76065 | 0.80235 | 0.83013 | 0.84752 | 0.87915 | 0.8386 | 0.81867 | 0.78259 | 0.73838 | 0.68155 | 0.62003 | 0.55108 | 0.47703 | 0.40555 | 0.33278 | 0.26865 | 0.21121 | 0.15984 | 0.13341 | 1.3078 | 1.008 | 0.089696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 855.0897 | 121.5922 | 2.499 | 3.1855 | 4.5033 | 6.4845 | 8.9357 | 11.6568 | 14.7962 | 17.9252 | 21.1112 | 24.0927 | 26.9513 | 29.4646 | 31.5547 | 33.2849 | 34.437 | 35.1587 | 36.4709 | 34.7887 | 33.9618 | 32.4652 | 30.6311 | 28.2735 | 25.7213 | 22.861 | 19.789 | 16.8238 | 13.805 | 11.1447 | 8.7619 | 6.6306 | 5.5345 | 54.2542 | 41.8178 | 3.721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 855.0897 | 121.5922 | 2.499 | 3.1855 | 4.5033 | 6.4845 | 8.9357 | 11.6568 | 14.7962 | 17.9252 | 21.1112 | 24.0927 | 26.9513 | 29.4646 | 31.5547 | 33.2849 | 34.437 | 35.1587 | 36.4709 | 34.7887 | 33.9618 | 32.4652 | 30.6311 | 28.2735 | 25.7213 | 22.861 | 19.789 | 16.8238 | 13.805 | 11.1447 | 8.7619 | 6.6306 | 5.5345 | 54.2542 | 41.8178 | 3.721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.323e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility drawdown (75%) | USD m |  | 1.7422e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7422e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 5.8075e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8075e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 189.9768 | 27.0144 | 0.55522 | 0.70774 | 1.0005 | 1.4407 | 1.9853 | 2.5898 | 3.2873 | 3.9825 | 4.6903 | 5.3527 | 5.9878 | 6.5462 | 7.0106 | 7.395 | 7.6509 | 7.8113 | 8.1028 | 7.7291 | 7.5454 | 7.2129 | 6.8054 | 6.2816 | 5.7145 | 5.0791 | 4.3965 | 3.7378 | 3.0671 | 2.476 | 1.9467 | 1.4731 | 1.2296 | 12.0538 | 9.2907 | 0.8267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 139.3163 | 19.8105 | 0.40716 | 0.51901 | 0.73371 | 1.0565 | 1.4559 | 1.8992 | 2.4107 | 2.9205 | 3.4396 | 3.9253 | 4.3911 | 4.8006 | 5.1411 | 5.423 | 5.6107 | 5.7283 | 5.9421 | 5.668 | 5.5333 | 5.2894 | 4.9906 | 4.6065 | 4.1907 | 3.7247 | 3.2241 | 2.741 | 2.2492 | 1.8158 | 1.4275 | 1.0803 | 0.90171 | 8.8394 | 6.8132 | 0.60624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 63.3256 | 9.0048 | 0.18507 | 0.23591 | 0.3335 | 0.48022 | 0.66175 | 0.86327 | 1.0958 | 1.3275 | 1.5634 | 1.7842 | 1.9959 | 2.1821 | 2.3369 | 2.465 | 2.5503 | 2.6038 | 2.7009 | 2.5764 | 2.5151 | 2.4043 | 2.2685 | 2.0939 | 1.9048 | 1.693 | 1.4655 | 1.2459 | 1.0224 | 0.82535 | 0.64889 | 0.49105 | 0.40987 | 4.0179 | 3.0969 | 0.27557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 240.6373 | 34.2182 | 0.70327 | 0.89647 | 1.2673 | 1.8248 | 2.5147 | 3.2804 | 4.1639 | 5.0445 | 5.9411 | 6.7801 | 7.5846 | 8.2919 | 8.8801 | 9.367 | 9.6912 | 9.8943 | 10.2635 | 9.7901 | 9.5574 | 9.1363 | 8.6201 | 7.9567 | 7.2384 | 6.4335 | 5.569 | 4.7345 | 3.885 | 3.1363 | 2.4658 | 1.866 | 1.5575 | 15.2681 | 11.7683 | 1.0471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 27.0144 | 27.5696 | 28.2773 | 29.2778 | 30.7185 | 32.7038 | 35.2936 | 38.5809 | 42.5633 | 47.2536 | 52.6064 | 58.5942 | 65.1404 | 72.151 | 79.5459 | 87.1969 | 95.0081 | 103.1109 | 110.84 | 118.3854 | 125.5982 | 132.4036 | 138.6852 | 144.3997 | 149.4788 | 153.8753 | 157.6131 | 160.6802 | 163.1562 | 165.1029 | 166.576 | 167.8056 | 179.8594 | 189.1501 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768 | 189.9768
|  | ABDB A-loan: closing balance | USD m |  |  | 19.8105 | 20.2177 | 20.7367 | 21.4704 | 22.5269 | 23.9828 | 25.882 | 28.2926 | 31.2131 | 34.6527 | 38.578 | 42.9691 | 47.7696 | 52.9107 | 58.3337 | 63.9444 | 69.6726 | 75.6147 | 81.2827 | 86.8159 | 92.1054 | 97.096 | 101.7024 | 105.8931 | 109.6178 | 112.8419 | 115.5829 | 117.8321 | 119.6479 | 121.0754 | 122.1557 | 123.0574 | 131.8969 | 138.7101 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163 | 139.3163
|  | ABDB B-loan: closing balance | USD m |  |  | 9.0048 | 9.1899 | 9.4258 | 9.7593 | 10.2395 | 10.9013 | 11.7645 | 12.8603 | 14.1878 | 15.7512 | 17.5355 | 19.5314 | 21.7135 | 24.0503 | 26.5153 | 29.0656 | 31.6694 | 34.3703 | 36.9467 | 39.4618 | 41.8661 | 44.1345 | 46.2284 | 48.1332 | 49.8263 | 51.2918 | 52.5377 | 53.5601 | 54.3854 | 55.0343 | 55.5253 | 55.9352 | 59.9531 | 63.05 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256 | 63.3256
|  | Commercial tranche: closing balance | USD m |  |  | 34.2182 | 34.9215 | 35.8179 | 37.0853 | 38.9101 | 41.4248 | 44.7052 | 48.8691 | 53.9136 | 59.8546 | 66.6347 | 74.2193 | 82.5112 | 91.3912 | 100.7582 | 110.4494 | 120.3437 | 130.6072 | 140.3973 | 149.9548 | 159.0911 | 167.7112 | 175.6679 | 182.9063 | 189.3398 | 194.9087 | 199.6433 | 203.5282 | 206.6645 | 209.1303 | 210.9963 | 212.5538 | 227.8219 | 239.5901 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373 | 240.6373
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11 | 1.7422e-11
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 221.8338 | 31.5444 | 0.64832 | 0.82642 | 1.1683 | 1.6823 | 2.3182 | 3.0241 | 3.8386 | 4.6503 | 5.4768 | 6.2503 | 6.9919 | 7.6439 | 8.1862 | 8.635 | 8.9339 | 9.1211 | 9.4615 | 9.0251 | 8.8106 | 8.4224 | 7.9465 | 7.3349 | 6.6728 | 5.9308 | 5.1338 | 4.3646 | 3.5814 | 2.8912 | 2.2731 | 1.7202 | 1.4358 | 14.075 | 10.8487 | 0.96532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 207.6338 | 17.3444 | 0.64832 | 0.82642 | 1.1683 | 1.6823 | 2.3182 | 3.0241 | 3.8386 | 4.6503 | 5.4768 | 6.2503 | 6.9919 | 7.6439 | 8.1862 | 8.635 | 8.9339 | 9.1211 | 9.4615 | 9.0251 | 8.8106 | 8.4224 | 7.9465 | 7.3349 | 6.6728 | 5.9308 | 5.1338 | 4.3646 | 3.5814 | 2.8912 | 2.2731 | 1.7202 | 1.4358 | 14.075 | 10.8487 | 0.96532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 44.3668 | 6.3089 | 0.12966 | 0.16528 | 0.23366 | 0.33645 | 0.46363 | 0.60482 | 0.76771 | 0.93006 | 1.0954 | 1.2501 | 1.3984 | 1.5288 | 1.6372 | 1.727 | 1.7868 | 1.8242 | 1.8923 | 1.805 | 1.7621 | 1.6845 | 1.5893 | 1.467 | 1.3346 | 1.1862 | 1.0268 | 0.87291 | 0.71628 | 0.57825 | 0.45462 | 0.34403 | 0.28716 | 2.815 | 2.1697 | 0.19306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 177.467 | 25.2355 | 0.51866 | 0.66113 | 0.93463 | 1.3458 | 1.8545 | 2.4193 | 3.0708 | 3.7202 | 4.3815 | 5.0002 | 5.5935 | 6.1151 | 6.5489 | 6.908 | 7.1471 | 7.2969 | 7.5692 | 7.2201 | 7.0485 | 6.7379 | 6.3572 | 5.8679 | 5.3382 | 4.7446 | 4.107 | 3.4916 | 2.8651 | 2.313 | 1.8185 | 1.3761 | 1.1486 | 11.26 | 8.6789 | 0.77226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 24.1927 | 0 | 0.19704 | 0.20939 | 0.20943 | 0.22564 | 0.23832 | 0.23051 | 0.27659 | 0.2938 | 0.33598 | 0.36198 | 0.41731 | 0.46581 | 0.50217 | 0.5758 | 0.61566 | 0.69882 | 0.76333 | 0.77698 | 0.89509 | 0.92824 | 1.021 | 1.0457 | 1.1363 | 1.1886 | 1.1966 | 1.2793 | 1.2752 | 1.3512 | 1.3807 | 1.2704 | 1.4279 | 1.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 25.2355 | 25.9512 | 26.8217 | 27.9658 | 29.5372 | 31.6301 | 34.2799 | 37.6273 | 41.6413 | 46.3587 | 51.721 | 57.7318 | 64.3128 | 71.3639 | 78.8477 | 86.6105 | 94.6062 | 102.9388 | 110.9359 | 118.8794 | 126.5456 | 133.9238 | 140.8375 | 147.3121 | 153.2453 | 158.5489 | 163.3198 | 167.4602 | 171.1243 | 174.3235 | 176.97 | 179.5466 | 192.2085 | 200.8875 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597 | 201.6597
|  | Total debt drawdowns (incl. standby) | USD m |  | 633.256 | 90.0479 | 1.8507 | 2.3591 | 3.335 | 4.8022 | 6.6175 | 8.6327 | 10.9577 | 13.2749 | 15.6343 | 17.8424 | 19.9594 | 21.8207 | 23.3686 | 24.6499 | 25.5031 | 26.0376 | 27.0093 | 25.7635 | 25.1512 | 24.0429 | 22.6846 | 20.9386 | 19.0485 | 16.9302 | 14.6552 | 12.4592 | 10.2236 | 8.2535 | 6.4889 | 4.9105 | 4.0987 | 40.1792 | 30.9691 | 2.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 106.8538 | 13.4806 | 1.0782 | 1.1309 | 1.1463 | 1.2383 | 1.3273 | 1.3387 | 1.5469 | 1.6476 | 1.8246 | 1.9244 | 2.1252 | 2.2899 | 2.4135 | 2.6163 | 2.7258 | 2.9188 | 3.0879 | 3.0775 | 3.2932 | 3.324 | 3.4564 | 3.4474 | 3.553 | 3.5744 | 3.5114 | 3.5745 | 3.4869 | 3.5363 | 3.5158 | 3.2736 | 3.4798 | 4.5954 | 4.5719 | 3.721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 855.0897
|  | Capitalized cost (book and tax) | USD m | 836.6866

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01978 | 0.020815 | 0.021927 | 0.022093 | 0.02254 | 0.022323 | 0.022693 | 0.022424 | 0.022796 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847
|  | ABDB A-loan: rate per period | factor |  |  | 0.031536 | 0.032379 | 0.033682 | 0.033721 | 0.034296 | 0.033887 | 0.034449 | 0.033988 | 0.034551 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602
|  | ABDB B-loan: rate per period | factor |  |  | 0.030258 | 0.031122 | 0.032404 | 0.032457 | 0.033018 | 0.03263 | 0.033171 | 0.032731 | 0.033273 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324
|  | Commercial tranche: rate per period | factor |  |  | 0.037595 | 0.03849 | 0.03998 | 0.039995 | 0.040662 | 0.040166 | 0.040832 | 0.040278 | 0.040946 | 0.040334 | 0.041002 | 0.040557 | 0.041002 | 0.040334 | 0.041002 | 0.043127 | 0.043842 | 0.043127 | 0.043842 | 0.043365 | 0.043842 | 0.043127 | 0.043842 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037387 | 0.038824 | 0.038833 | 0.039478 | 0.038995 | 0.039642 | 0.039103 | 0.039751 | 0.039156 | 0.039805 | 0.039373 | 0.039805 | 0.039156 | 0.039805 | 0.040832 | 0.041509 | 0.040832 | 0.041509 | 0.041058 | 0.041509 | 0.040832 | 0.041509 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97554 | 0.95004 | 0.92329 | 0.89575 | 0.86695 | 0.83722 | 0.80555 | 0.77292 | 0.74119 | 0.70944 | 0.67638 | 0.64236 | 0.60671 | 0.56988 | 0.52966 | 0.48772 | 0.4443 | 0.40007 | 0.35363 | 0.30582 | 0.2557 | 0.20396 | 0.14909 | 0.093089 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.026135 | 0.028158 | 0.029828 | 0.032159 | 0.034287 | 0.037824 | 0.040513 | 0.041052 | 0.042829 | 0.046599 | 0.050303 | 0.055498 | 0.060706 | 0.07057 | 0.079192 | 0.08902 | 0.099542 | 0.1161 | 0.1352 | 0.16389 | 0.20235 | 0.269 | 0.37563 | 0.49632 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.9768 | 185.3299 | 180.4863 | 175.4041 | 170.1722 | 164.6996 | 159.0525 | 153.0364 | 146.8365 | 140.8086 | 134.7779 | 128.4974 | 122.0335 | 115.2609 | 108.2639 | 100.6237 | 92.6551 | 84.407 | 76.0049 | 67.1811 | 58.0981 | 48.5766 | 38.747 | 28.3242 | 17.6848 | 8.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 65.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3112 | 4.1558 | 4.1143 | 3.9421 | 3.8879 | 3.7219 | 3.6338 | 3.4394 | 3.3547 | 3.1646 | 3.0792 | 2.8879 | 2.7881 | 2.6047 | 2.4735 | 2.2614 | 2.1169 | 1.897 | 1.7365 | 1.5098 | 1.3273 | 1.0978 | 0.88524 | 0.63656 | 0.40404 | 0.20019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 189.9768 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6469 | 4.8436 | 5.0822 | 5.2319 | 5.4726 | 5.6471 | 6.0161 | 6.2 | 6.0279 | 6.0307 | 6.2805 | 6.4638 | 6.7726 | 6.997 | 7.6402 | 7.9686 | 8.2481 | 8.4021 | 8.8239 | 9.083 | 9.5215 | 9.8297 | 10.4228 | 10.6394 | 8.7774 | 8.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 189.9768 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6469 | 4.8436 | 5.0822 | 5.2319 | 5.4726 | 5.6471 | 6.0161 | 6.2 | 6.0279 | 6.0307 | 6.2805 | 6.4638 | 6.7726 | 6.997 | 7.6402 | 7.9686 | 8.2481 | 8.4021 | 8.8239 | 9.083 | 9.5215 | 9.8297 | 10.4228 | 10.6394 | 8.7774 | 8.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 185.3299 | 180.4863 | 175.4041 | 170.1722 | 164.6996 | 159.0525 | 153.0364 | 146.8365 | 140.8086 | 134.7779 | 128.4974 | 122.0335 | 115.2609 | 108.2639 | 100.6237 | 92.6551 | 84.407 | 76.0049 | 67.1811 | 58.0981 | 48.5766 | 38.747 | 28.3242 | 17.6848 | 8.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 189.9768 | 185.3299 | 180.4863 | 175.4041 | 170.1722 | 164.6996 | 159.0525 | 153.0364 | 146.8365 | 140.8086 | 134.7779 | 128.4974 | 122.0335 | 115.2609 | 108.2639 | 100.6237 | 92.6551 | 84.407 | 76.0049 | 67.1811 | 58.0981 | 48.5766 | 38.747 | 28.3242 | 17.6848 | 8.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 139.3163 | 135.9086 | 132.3566 | 128.6297 | 124.7929 | 120.7797 | 116.6385 | 112.2267 | 107.6801 | 103.2596 | 98.8371 | 94.2314 | 89.4913 | 84.5247 | 79.3935 | 73.7907 | 67.9471 | 61.8985 | 55.7369 | 49.2661 | 42.6053 | 35.6229 | 28.4144 | 20.7711 | 12.9689 | 6.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 72.9127 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7993 | 4.6192 | 4.5731 | 4.3783 | 4.3181 | 4.1338 | 4.036 | 3.82 | 3.726 | 3.5148 | 3.42 | 3.2075 | 3.0966 | 2.893 | 2.7472 | 2.5117 | 2.3511 | 2.1069 | 1.9286 | 1.6769 | 1.4742 | 1.2192 | 0.9832 | 0.70701 | 0.44875 | 0.22234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 139.3163 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4077 | 3.552 | 3.7269 | 3.8367 | 4.0132 | 4.1412 | 4.4118 | 4.5466 | 4.4204 | 4.4225 | 4.6057 | 4.7401 | 4.9666 | 5.1311 | 5.6028 | 5.8436 | 6.0486 | 6.1615 | 6.4708 | 6.6608 | 6.9824 | 7.2084 | 7.6434 | 7.8022 | 6.4367 | 6.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 139.3163 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4077 | 3.552 | 3.7269 | 3.8367 | 4.0132 | 4.1412 | 4.4118 | 4.5466 | 4.4204 | 4.4225 | 4.6057 | 4.7401 | 4.9666 | 5.1311 | 5.6028 | 5.8436 | 6.0486 | 6.1615 | 6.4708 | 6.6608 | 6.9824 | 7.2084 | 7.6434 | 7.8022 | 6.4367 | 6.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 135.9086 | 132.3566 | 128.6297 | 124.7929 | 120.7797 | 116.6385 | 112.2267 | 107.6801 | 103.2596 | 98.8371 | 94.2314 | 89.4913 | 84.5247 | 79.3935 | 73.7907 | 67.9471 | 61.8985 | 55.7369 | 49.2661 | 42.6053 | 35.6229 | 28.4144 | 20.7711 | 12.9689 | 6.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 139.3163 | 135.9086 | 132.3566 | 128.6297 | 124.7929 | 120.7797 | 116.6385 | 112.2267 | 107.6801 | 103.2596 | 98.8371 | 94.2314 | 89.4913 | 84.5247 | 79.3935 | 73.7907 | 67.9471 | 61.8985 | 55.7369 | 49.2661 | 42.6053 | 35.6229 | 28.4144 | 20.7711 | 12.9689 | 6.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.3256 | 61.7766 | 60.1621 | 58.468 | 56.7241 | 54.8999 | 53.0175 | 51.0121 | 48.9455 | 46.9362 | 44.926 | 42.8325 | 40.6778 | 38.4203 | 36.088 | 33.5412 | 30.885 | 28.1357 | 25.335 | 22.3937 | 19.366 | 16.1922 | 12.9157 | 9.4414 | 5.8949 | 2.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 31.9177 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1006 | 2.022 | 2.0018 | 1.9166 | 1.8903 | 1.8096 | 1.7668 | 1.6722 | 1.6311 | 1.5386 | 1.4971 | 1.4041 | 1.3556 | 1.2664 | 1.2026 | 1.0995 | 1.0292 | 0.92232 | 0.84427 | 0.73409 | 0.64536 | 0.53373 | 0.43041 | 0.3095 | 0.19645 | 0.097332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 63.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 1.549 | 1.6145 | 1.6941 | 1.744 | 1.8242 | 1.8824 | 2.0054 | 2.0667 | 2.0093 | 2.0102 | 2.0935 | 2.1546 | 2.2575 | 2.3323 | 2.5467 | 2.6562 | 2.7494 | 2.8007 | 2.9413 | 3.0277 | 3.1738 | 3.2766 | 3.4743 | 3.5465 | 2.9258 | 2.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 63.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 1.549 | 1.6145 | 1.6941 | 1.744 | 1.8242 | 1.8824 | 2.0054 | 2.0667 | 2.0093 | 2.0102 | 2.0935 | 2.1546 | 2.2575 | 2.3323 | 2.5467 | 2.6562 | 2.7494 | 2.8007 | 2.9413 | 3.0277 | 3.1738 | 3.2766 | 3.4743 | 3.5465 | 2.9258 | 2.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 61.7766 | 60.1621 | 58.468 | 56.7241 | 54.8999 | 53.0175 | 51.0121 | 48.9455 | 46.9362 | 44.926 | 42.8325 | 40.6778 | 38.4203 | 36.088 | 33.5412 | 30.885 | 28.1357 | 25.335 | 22.3937 | 19.366 | 16.1922 | 12.9157 | 9.4414 | 5.8949 | 2.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 63.3256 | 61.7766 | 60.1621 | 58.468 | 56.7241 | 54.8999 | 53.0175 | 51.0121 | 48.9455 | 46.9362 | 44.926 | 42.8325 | 40.6778 | 38.4203 | 36.088 | 33.5412 | 30.885 | 28.1357 | 25.335 | 22.3937 | 19.366 | 16.1922 | 12.9157 | 9.4414 | 5.8949 | 2.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 240.6373 | 234.7512 | 228.616 | 222.1786 | 215.5515 | 208.6195 | 201.4665 | 193.8461 | 185.9928 | 178.3576 | 170.7187 | 162.7633 | 149.2445 | 134.7261 | 120.6983 | 105.0378 | 89.0491 | 72.6831 | 56.7001 | 40.1225 | 24.0018 | 7.7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 136.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 9.8257 | 9.4553 | 9.3608 | 8.9613 | 8.8381 | 8.4609 | 8.2606 | 7.8186 | 7.6262 | 7.6921 | 7.4846 | 7.0195 | 6.5432 | 5.8425 | 5.2917 | 4.53 | 3.9041 | 3.3376 | 2.6468 | 1.8424 | 1.1204 | 0.35619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 152.0227 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8861 | 6.1352 | 6.4374 | 6.6271 | 6.932 | 7.153 | 7.6203 | 7.8533 | 7.6353 | 7.6389 | 7.9553 | 8.1875 | 8.2828 | 8.1786 | 8.5177 | 8.3181 | 7.9271 | 7.2351 | 6.5827 | 5.4246 | 3.9336 | 1.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 152.0227 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8861 | 6.1352 | 6.4374 | 6.6271 | 6.932 | 7.153 | 7.6203 | 7.8533 | 7.6353 | 7.6389 | 7.9553 | 8.1875 | 8.2828 | 8.1786 | 8.5177 | 8.3181 | 7.9271 | 7.2351 | 6.5827 | 5.4246 | 3.9336 | 1.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 234.7512 | 228.616 | 222.1786 | 215.5515 | 208.6195 | 201.4665 | 193.8461 | 185.9928 | 178.3576 | 170.7187 | 162.7633 | 154.5758 | 140.9618 | 126.5474 | 112.1806 | 96.7196 | 81.1219 | 65.4481 | 50.1174 | 34.6979 | 20.0682 | 6.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 88.6146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.9949 | 10.6961 | 12.3542 | 6.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 240.6373 | 234.7512 | 228.616 | 222.1786 | 215.5515 | 208.6195 | 201.4665 | 193.8461 | 185.9928 | 178.3576 | 170.7187 | 162.7633 | 149.2445 | 134.7261 | 120.6983 | 105.0378 | 89.0491 | 72.6831 | 56.7001 | 40.1225 | 24.0018 | 7.7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.7422e-11 | 1.6996e-11 | 1.6552e-11 | 1.6086e-11 | 1.5606e-11 | 1.5104e-11 | 1.4586e-11 | 1.4035e-11 | 1.3466e-11 | 1.2913e-11 | 1.236e-11 | 1.1784e-11 | 1.1191e-11 | 1.057e-11 | 9.9287e-12 | 9.228e-12 | 8.4972e-12 | 7.7408e-12 | 6.9703e-12 | 6.161e-12 | 5.3281e-12 | 4.4549e-12 | 3.5534e-12 | 2.5976e-12 | 1.6218e-12 | 8.1688e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 1.0768e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9065e-13 | 6.646e-13 | 6.5796e-13 | 6.2987e-13 | 6.2121e-13 | 5.947e-13 | 5.8062e-13 | 5.4955e-13 | 5.3602e-13 | 5.2728e-13 | 5.1306e-13 | 4.8118e-13 | 4.6455e-13 | 4.34e-13 | 4.1213e-13 | 3.768e-13 | 3.5271e-13 | 3.2905e-13 | 3.012e-13 | 2.6189e-13 | 2.3024e-13 | 1.9041e-13 | 1.5355e-13 | 1.1042e-13 | 7.0084e-14 | 3.4724e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 1.7422e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2616e-13 | 4.442e-13 | 4.6608e-13 | 4.7981e-13 | 5.0188e-13 | 5.1789e-13 | 5.5172e-13 | 5.6859e-13 | 5.528e-13 | 5.5306e-13 | 5.7598e-13 | 5.9278e-13 | 6.211e-13 | 6.4168e-13 | 7.0067e-13 | 7.3078e-13 | 7.5642e-13 | 7.7054e-13 | 8.0922e-13 | 8.3298e-13 | 8.7319e-13 | 9.0146e-13 | 9.5585e-13 | 9.7572e-13 | 8.0496e-13 | 8.1688e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 1.7422e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2616e-13 | 4.442e-13 | 4.6608e-13 | 4.7981e-13 | 5.0188e-13 | 5.1789e-13 | 5.5172e-13 | 5.6859e-13 | 5.528e-13 | 5.5306e-13 | 5.7598e-13 | 5.9278e-13 | 6.211e-13 | 6.4168e-13 | 7.0067e-13 | 7.3078e-13 | 7.5642e-13 | 7.7054e-13 | 8.0922e-13 | 8.3298e-13 | 8.7319e-13 | 9.0146e-13 | 9.5585e-13 | 9.7572e-13 | 8.0496e-13 | 8.1688e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.6996e-11 | 1.6552e-11 | 1.6086e-11 | 1.5606e-11 | 1.5104e-11 | 1.4586e-11 | 1.4035e-11 | 1.3466e-11 | 1.2913e-11 | 1.236e-11 | 1.1784e-11 | 1.1191e-11 | 1.057e-11 | 9.9287e-12 | 9.228e-12 | 8.4972e-12 | 7.7408e-12 | 6.9703e-12 | 6.161e-12 | 5.3281e-12 | 4.4549e-12 | 3.5534e-12 | 2.5976e-12 | 1.6218e-12 | 8.1688e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7422e-11 | 1.6996e-11 | 1.6552e-11 | 1.6086e-11 | 1.5606e-11 | 1.5104e-11 | 1.4586e-11 | 1.4035e-11 | 1.3466e-11 | 1.2913e-11 | 1.236e-11 | 1.1784e-11 | 1.1191e-11 | 1.057e-11 | 9.9287e-12 | 9.228e-12 | 8.4972e-12 | 7.7408e-12 | 6.9703e-12 | 6.161e-12 | 5.3281e-12 | 4.4549e-12 | 3.5534e-12 | 2.5976e-12 | 1.6218e-12 | 8.1688e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 0
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 0
|  | Bond face amount | USD m | 0
|  | Swap unwind receipt | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | -8.3342 | 0 | 0 | 0 | 0 | 0 | 0 | -0.53616 | -0.44548 | -0.55857 | -0.44514 | -0.54985 | -0.45603 | -0.51392 | -0.38837 | -0.47444 | -0.35734 | -0.43548 | -0.3261 | -0.3943 | -0.31914 | -0.34981 | -0.25536 | -0.29938 | -0.21421 | -0.24558 | -0.17049 | -0.18772 | -0.1345 | -0.1252 | -0.071881 | -0.057142 | -0.022605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 16.8001 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2555 | 1.2049 | 1.1928 | 1.1403 | 1.1246 | 1.0766 | 1.0512 | 0.99491 | 0.97042 | 0.91541 | 0.89073 | 0.83538 | 0.77869 | 0.6953 | 0.62975 | 0.5391 | 0.46462 | 0.37304 | 0.29583 | 0.20593 | 0.12523 | 0.039811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 306.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 21.0368 | 20.2524 | 20.05 | 19.1984 | 18.9344 | 18.1263 | 17.6972 | 16.7502 | 16.3379 | 15.91 | 15.481 | 14.5189 | 13.7834 | 12.6065 | 11.7149 | 10.4026 | 9.4013 | 8.2638 | 7.1562 | 5.7633 | 4.5674 | 3.2069 | 2.2988 | 1.6531 | 1.0492 | 0.51986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 315.1468 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7562 | 21.0118 | 20.6842 | 19.8935 | 19.5092 | 18.7469 | 18.2344 | 17.3567 | 16.8339 | 16.4681 | 15.9362 | 15.0282 | 14.1678 | 12.9827 | 11.9949 | 10.6864 | 9.5665 | 8.4227 | 7.2065 | 5.7987 | 4.5049 | 3.1122 | 2.1737 | 1.5812 | 0.99209 | 0.49725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 544.6414 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4897 | 16.1453 | 16.9406 | 17.4398 | 18.242 | 18.8238 | 20.0535 | 20.6665 | 20.0929 | 20.1023 | 20.9351 | 21.5461 | 22.2795 | 22.6391 | 24.3075 | 24.7866 | 24.9733 | 24.5993 | 24.8187 | 24.1961 | 23.6113 | 21.8756 | 21.5404 | 21.9881 | 18.1399 | 18.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 859.7882 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2459 | 37.157 | 37.6248 | 37.3333 | 37.7512 | 37.5707 | 38.2879 | 38.0232 | 36.9268 | 36.5704 | 36.8714 | 36.5743 | 36.4473 | 35.6218 | 36.3023 | 35.4729 | 34.5398 | 33.022 | 32.0251 | 29.9948 | 28.1161 | 24.9878 | 23.714 | 23.5693 | 19.132 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 633.256 | 617.7663 | 601.621 | 584.6804 | 567.2407 | 548.9987 | 530.1749 | 510.1214 | 489.4549 | 469.362 | 449.2597 | 428.3245 | 401.4472 | 372.9319 | 344.4437 | 312.9935 | 280.5363 | 247.1242 | 213.7769 | 178.9634 | 144.0712 | 108.1058 | 80.0771 | 58.5367 | 36.5486 | 18.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 633.256 | 617.7663 | 601.621 | 584.6804 | 567.2407 | 548.9987 | 530.1749 | 510.1214 | 489.4549 | 469.362 | 449.2597 | 428.3245 | 401.4472 | 372.9319 | 344.4437 | 312.9935 | 280.5363 | 247.1242 | 213.7769 | 178.9634 | 144.0712 | 108.1058 | 80.0771 | 58.5367 | 36.5486 | 18.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 240.6373 | 234.7512 | 228.616 | 222.1786 | 215.5515 | 208.6195 | 201.4665 | 193.8461 | 185.9928 | 178.3576 | 170.7187 | 162.7633 | 154.5758 | 140.9618 | 126.5474 | 112.1806 | 96.7196 | 81.1219 | 65.4481 | 50.1174 | 34.6979 | 20.0682 | 6.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 8.9581 | 8.9994 | 9.1965 | 9.174 | 9.3605 | 9.3691 | 9.6499 | 9.6393 | 9.3826 | 9.1953 | 9.3598 | 9.3517 | 9.5607 | 9.6017 | 10.1137 | 10.23 | 10.365 | 10.2991 | 10.5603 | 10.5928 | 10.8488 | 10.9274 | 11.308 | 11.276 | 9.1814 | 9.1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 8.207 | 8.1712 | 8.3 | 8.2151 | 8.3314 | 8.275 | 8.4477 | 8.3666 | 8.1464 | 7.9373 | 8.0257 | 7.9476 | 8.0632 | 8.0241 | 8.35 | 8.3553 | 8.3998 | 8.2684 | 8.3995 | 8.3378 | 8.4566 | 8.4276 | 8.6266 | 8.5092 | 6.8855 | 6.7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 3.6496 | 3.6365 | 3.6958 | 3.6606 | 3.7145 | 3.692 | 3.7721 | 3.7389 | 3.6404 | 3.5489 | 3.5906 | 3.5587 | 3.6131 | 3.5987 | 3.7493 | 3.7557 | 3.7786 | 3.723 | 3.7856 | 3.7617 | 3.8192 | 3.8103 | 3.9047 | 3.856 | 3.1222 | 3.0665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 15.7118 | 15.5905 | 15.7982 | 15.5885 | 15.7701 | 15.614 | 15.881 | 15.6719 | 15.2615 | 15.3309 | 15.44 | 15.207 | 15.3556 | 14.67 | 14.4786 | 13.7218 | 12.8503 | 11.8002 | 10.6535 | 9.0773 | 7.3063 | 4.9875 | 1.9424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.1168e-12 | 1.1088e-12 | 1.124e-12 | 1.1097e-12 | 1.1231e-12 | 1.1126e-12 | 1.1323e-12 | 1.1181e-12 | 1.0888e-12 | 1.0803e-12 | 1.089e-12 | 1.074e-12 | 1.0857e-12 | 1.0757e-12 | 1.1128e-12 | 1.1076e-12 | 1.1091e-12 | 1.0996e-12 | 1.1104e-12 | 1.0949e-12 | 1.1034e-12 | 1.0919e-12 | 1.1094e-12 | 1.0861e-12 | 8.7504e-13 | 8.5161e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 37.2459 | 37.157 | 37.6248 | 37.3333 | 37.7512 | 37.5707 | 38.2879 | 38.0232 | 36.9268 | 36.5704 | 36.8714 | 36.5743 | 37.0047 | 36.3029 | 37.002 | 36.3833 | 35.599 | 34.2929 | 33.4947 | 31.8564 | 30.4242 | 28.1219 | 25.6885 | 23.5693 | 19.132 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.034356 | 0.034012 | 0.034381 | 0.034025 | 0.034393 | 0.034147 | 0.034393 | 0.034025 | 0.034393 | 0.035086 | 0.035472 | 0.035086 | 0.035472 | 0.035215 | 0.035472 | 0.035086 | 0.035472 | 0.036147 | 0.036551 | 0.036147 | 0.036551 | 0.036282 | 0.036551 | 0.036147 | 0.036551 | 0.036147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 833.6327 | 813.5369 | 792.6021 | 770.6268 | 748.027 | 724.399 | 700.0257 | 674.0074 | 647.2213 | 621.2965 | 595.4083 | 568.4474 | 540.7247 | 511.6884 | 481.6883 | 448.8057 | 414.5227 | 379.1154 | 343.0996 | 305.2638 | 266.3435 | 225.5564 | 183.458 | 138.751 | 92.7511 | 47.0248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.3164
|  | Debt capacity at the 1.35x target | USD m | 617.5057
|  | Debt at the 75% gearing cap (closed form) | USD m | 642.9083
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37.0217 | 36.9222 | 37.3935 | 37.0854 | 37.4918 | 37.3054 | 38.0535 | 37.7682 | 36.6029 | 36.2247 | 36.5243 | 36.2097 | 36.6272 | 36.477 | 37.9583 | 38.0043 | 38.0663 | 37.7689 | 38.2677 | 37.9474 | 38.3784 | 38.196 | 39.0547 | 38.7531 | 37.3105 | 37.0129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 633.256 | 617.9905 | 602.0877 | 585.3945 | 568.2269 | 550.2783 | 531.7635 | 511.9991 | 491.6515 | 471.9581 | 452.2926 | 431.8121 | 410.753 | 388.6961 | 365.9069 | 340.9282 | 314.8857 | 287.9891 | 260.6302 | 231.8888 | 202.3236 | 171.3404 | 139.361 | 105.4 | 70.4569 | 35.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.2655 | 15.9028 | 16.6932 | 17.1675 | 17.9487 | 18.5147 | 19.7644 | 20.3476 | 19.6934 | 19.6655 | 20.4805 | 21.0591 | 22.0569 | 22.7891 | 24.9788 | 26.0425 | 26.8966 | 27.3588 | 28.7414 | 29.5652 | 30.9832 | 31.9794 | 33.9609 | 34.9431 | 34.7352 | 35.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0 | 0 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 0 | 0 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0 | 0 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 0 | 0 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0 | 0 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 0 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.83254 | 1.2488 | 1.6651 | 2.0813 | 2.4976 | 0 | 0 | 1.9727 | 3.9455 | 5.9182 | 7.891 | 9.8637 | 11.8365 | 0 | 0 | 0.49543 | 0.99086 | 1.4863 | 1.9817 | 2.4771 | 2.9726 | 0 | 0 | 2.3479 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 3.5378 | 0 | 0 | 2.7944 | 5.5888 | 8.3831 | 11.1775 | 13.9719 | 16.7663 | 0 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 37.2459 | 37.2459 | 37.157 | 37.6248 | 37.3333 | 37.7512 | 37.5707 | 38.2879 | 38.0232 | 36.9268 | 36.5704 | 36.8714 | 36.5743 | 37.0047 | 36.3029 | 37.002 | 36.3833 | 35.599 | 34.2929 | 33.4947 | 31.8564 | 30.4242 | 28.1219 | 25.6885 | 23.5693 | 19.132 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 3.0335 | 0 | 0 | 0 | 0 | 0 | 1.1156e-12 | 0 | 0.46777 | 0 | 0.41791 | 0 | 0.71723 | 0 | 0 | 0 | 0.30097 | 0 | 0.43046 | 0 | 0.69914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 40.2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088879 | 0 | 0.29147 | 0 | 0.18053 | 0 | 0.26469 | 1.0964 | 0.3564 | 0 | 0.29708 | 0 | 0.70184 | 0 | 0.61876 | 0.78433 | 1.3061 | 0.79813 | 1.6383 | 1.4322 | 2.3023 | 2.4334 | 2.1192 | 4.4373 | 0.22611 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 37.2459 | 37.157 | 37.6248 | 37.3333 | 37.7512 | 37.5707 | 38.2879 | 38.0232 | 36.9268 | 36.5704 | 36.8714 | 36.5743 | 37.0047 | 36.3029 | 37.002 | 36.3833 | 35.599 | 34.2929 | 33.4947 | 31.8564 | 30.4242 | 28.1219 | 25.6885 | 23.5693 | 19.132 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
| Handback reserve release at expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.9961 | 3.5137 | 5.0479 | 6.5988 | 8.1668 | 9.7518 | 11.3543 | 12.9742 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2242.7318 | 0 | 0 | 0 | 0 | 0 | 1.7332 | 48.7362 | 48.6052 | 49.2257 | 48.82 | 49.3551 | 49.1096 | 50.0945 | 49.7189 | 48.1849 | 47.687 | 48.0814 | 47.6673 | 48.2169 | 48.0191 | 49.9692 | 50.0298 | 50.1113 | 49.7199 | 50.3765 | 49.9549 | 50.5222 | 50.2821 | 51.4126 | 51.0154 | 49.1164 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.5024 | 44.7569 | 41.3536 | 35.1964 | 34.752 | 35.4355 | 34.966 | 35.5687 | 35.3184 | 43.369 | 38.1154 | 38.7821 | 35.1394 | 0
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7332 | 50.4694 | 48.6052 | 49.2257 | 48.82 | 49.3551 | 49.1096 | 50.0945 | 49.7189 | 48.1849 | 47.687 | 48.0814 | 47.6673 | 48.2169 | 48.0191 | 49.9692 | 50.0298 | 50.1113 | 49.7199 | 50.3765 | 49.9549 | 50.5222 | 50.2821 | 51.4126 | 51.0154 | 49.1164 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.5024 | 44.7569 | 41.3536 | 35.1964 | 34.752 | 35.4355 | 34.966 | 35.5687 | 35.3184 | 43.369 | 38.1154 | 38.7821 | 35.1394 | 0
|  | Senior debt service and fees due | USD m |  | 859.7882 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2459 | 37.157 | 37.6248 | 37.3333 | 37.7512 | 37.5707 | 38.2879 | 38.0232 | 36.9268 | 36.5704 | 36.8714 | 36.5743 | 36.4473 | 35.6218 | 36.3023 | 35.4729 | 34.5398 | 33.022 | 32.0251 | 29.9948 | 28.1161 | 24.9878 | 23.714 | 23.5693 | 19.132 | 18.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7332 | 13.2235 | 11.4482 | 11.6009 | 11.4867 | 11.6039 | 11.5389 | 11.8066 | 11.6957 | 11.2581 | 11.1166 | 11.2101 | 11.093 | 11.7696 | 12.3974 | 13.6669 | 14.5568 | 15.5715 | 16.6979 | 18.3514 | 19.9601 | 22.406 | 25.2943 | 27.6985 | 27.4461 | 29.9844 | 29.8187 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.5024 | 44.7569 | 41.3536 | 35.1964 | 34.752 | 35.4355 | 34.966 | 35.5687 | 35.3184 | 43.369 | 38.1154 | 38.7821 | 35.1394 | 0
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7332 | 13.3124 | 10.9804 | 11.8924 | 11.0688 | 11.7844 | 10.8217 | 12.0712 | 12.7921 | 11.6145 | 10.8156 | 11.5071 | 10.6625 | 12.4714 | 11.6982 | 14.2856 | 15.3412 | 16.8776 | 17.496 | 19.9898 | 21.3922 | 24.7083 | 27.7277 | 29.8178 | 31.8834 | 30.2105 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.5024 | 44.7569 | 41.3536 | 35.1964 | 34.752 | 35.4355 | 34.966 | 35.5687 | 35.3184 | 43.369 | 38.1154 | 38.7821 | 35.1394 | 0
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7332 | 13.3124 | 10.9804 | 11.8924 | 11.0688 | 11.7844 | 10.8217 | 12.0712 | 12.7921 | 11.6145 | 10.8156 | 11.5071 | 10.6625 | 12.4714 | 11.6982 | 14.2856 | 15.3412 | 16.8776 | 17.496 | 19.9898 | 21.3922 | 24.7083 | 27.7277 | 29.8178 | 31.8834 | 30.2105 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 53.0806 | 0
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3085 | 1.3081 | 1.3083 | 1.3077 | 1.3074 | 1.3071 | 1.3084 | 1.3076 | 1.3049 | 1.304 | 1.304 | 1.3033 | 1.3229 | 1.348 | 1.3765 | 1.4104 | 1.4508 | 1.5057 | 1.573 | 1.6655 | 1.7969 | 2.0123 | 2.168 | 2.1645 | 2.5672 | 2.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3085 | 1.3083 | 1.3082 | 1.308 | 1.3075 | 1.3073 | 1.3078 | 1.308 | 1.3063 | 1.3044 | 1.304 | 1.3037 | 1.3131 | 1.3353 | 1.3624 | 1.3932 | 1.4303 | 1.4776 | 1.5388 | 1.6177 | 1.7291 | 1.8982 | 2.0881 | 2.1663 | 2.3449 | 2.5722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 88.6146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.9949 | 10.6961 | 12.3542 | 6.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1331.575 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3124 | 10.9804 | 11.8924 | 11.0688 | 11.7844 | 10.8217 | 12.0712 | 12.7921 | 11.6145 | 10.8156 | 11.5071 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.9949 | 10.6961 | 12.3542 | 21.5746 | 29.8178 | 31.8834 | 30.2105 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 53.0806 | 0
|  | Share capital contributed | USD m | 44.3668
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 201.6597 | 204.8614 | 201.3599 | 199.8655 | 197.5448 | 195.7822 | 193.3739 | 191.7123 | 188.8222 | 184.9255 | 182.1671 | 179.9333 | 177.0433 | 180.0524 | 182.4395 | 185.2325 | 186.9606 | 188.0976 | 188.6669 | 188.8069 | 187.8541 | 186.0077 | 182.5615 | 169.6348 | 147.9409 | 123.0269 | 98.7082 | 54.6337 | 16.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 214.7179 | 0 | 0 | 0 | 0 | 0 | 0 | 9.8109 | 9.486 | 9.5716 | 9.3063 | 9.3761 | 9.1601 | 9.1812 | 8.8953 | 8.8562 | 8.5818 | 8.6171 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.042 | 8.8497 | 8.908 | 8.6479 | 8.1239 | 6.9694 | 5.8918 | 4.6501 | 2.6164 | 0.75974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 216.625 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5015 | 1.4944 | 2.3207 | 1.7626 | 2.4083 | 1.6616 | 2.8901 | 3.8968 | 2.7583 | 2.2338 | 2.8901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95284 | 1.8464 | 3.4462 | 12.9267 | 21.6939 | 24.914 | 24.3187 | 44.0745 | 38.5065 | 16.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 204.8614 | 201.3599 | 199.8655 | 197.5448 | 195.7822 | 193.3739 | 191.7123 | 188.8222 | 184.9255 | 182.1671 | 179.9333 | 177.0433 | 180.0524 | 182.4395 | 185.2325 | 186.9606 | 188.0976 | 188.6669 | 188.8069 | 187.8541 | 186.0077 | 182.5615 | 169.6348 | 147.9409 | 123.0269 | 98.7082 | 54.6337 | 16.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.2641 | 15.1023 | 22.191 | 29.679 | 38.281 | 47.2649 | 57.3784 | 65.7433 | 77.7779 | 90.337 | 101.0196 | 106.9198 | 113.6908 | 120.9153 | 129.1038 | 128.3063 | 139.0573 | 149.5142 | 160.9321 | 173.2131 | 186.6582 | 201.0209 | 216.665 | 231.4688 | 249.5774 | 268.8148 | 289.3503 | 312.1721 | 336.3425 | 337.9795 | 322.5721 | 297.165 | 275.5413 | 258.2345 | 240.965 | 224.2821 | 206.9957 | 190.2318 | 173.0348 | 154.413 | 137.0195 | 123.0001 | 115.253 | 108.1252 | 100.3862 | 93.2027 | 85.6464 | 66.2351 | 51.2515 | 41.3855 | 8.7138 | 0
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1243 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 8.7138 | 0
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.3668 | 0
|  | Liquidation distribution at PPA expiry | USD m |  | 44.3668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.3668 | 0
|  | Dividends | USD m |  | 900.2321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1243 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 53.0806 | 0
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.2641 | 15.1023 | 22.191 | 29.679 | 38.281 | 47.2649 | 57.3784 | 65.7433 | 77.7779 | 90.337 | 101.0196 | 106.9198 | 113.6908 | 120.9153 | 129.1038 | 128.3063 | 139.0573 | 149.5142 | 160.9321 | 173.2131 | 186.6582 | 201.0209 | 216.665 | 231.4688 | 249.5774 | 268.8148 | 289.3503 | 312.1721 | 313.2181 | 297.6329 | 282.4816 | 250.3184 | 233.1353 | 215.7748 | 198.9473 | 181.6088 | 164.781 | 147.4348 | 131.0274 | 111.1573 | 97.1835 | 89.338 | 82.052 | 74.2576 | 67.0052 | 59.2365 | 51.948 | 24.5037 | 14.7917 | 4.2771 | -44.3668 | -44.3668
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1331.575 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3124 | 10.9804 | 11.8924 | 11.0688 | 11.7844 | 10.8217 | 12.0712 | 12.7921 | 11.6145 | 10.8156 | 11.5071 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.9949 | 10.6961 | 12.3542 | 21.5746 | 29.8178 | 31.8834 | 30.2105 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 53.0806 | 0

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 836.6866 | 0 | 0 | 0 | 0 | 0 | 5.5779 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 16.7337 | 11.1558 | 0
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 544.83 | 0 | 0 | 0 | 0 | 0 | 3.2017 | 31.5671 | 30.4977 | 30.2559 | 29.1998 | 28.8853 | 27.907 | 27.4156 | 26.252 | 25.6901 | 25.0499 | 24.5533 | 23.3687 | 22.7906 | 21.6248 | 20.8657 | 19.494 | 18.5746 | 17.3107 | 16.2485 | 14.6485 | 13.4129 | 11.7601 | 10.2975 | 8.5506 | 6.8839 | 5.1474 | 2.6164 | 0.75974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 836.6866 | 836.6866 | 836.6866 | 836.6866 | 836.6866 | 829.1564 | 806.5658 | 783.9753 | 761.3848 | 738.7942 | 716.2037 | 693.6132 | 671.0226 | 648.4321 | 625.8415 | 604.0877 | 584.0072 | 563.9267 | 543.8463 | 523.7658 | 503.6853 | 483.6048 | 463.5244 | 443.4439 | 423.3634 | 403.2829 | 383.2024 | 363.122 | 343.0415 | 322.961 | 302.8805 | 282.8001 | 262.7196 | 242.6391 | 222.5586 | 202.4781 | 182.3977 | 162.3172 | 142.2367 | 122.1562 | 102.0758 | 81.9953 | 61.9148 | 41.8343 | 21.7539 | 8.088 | 7.2513 | 6.4146 | 5.5779 | 4.7412 | 3.9045 | 3.0679 | 2.2312 | 1.3945 | 0.55779 | 0 | 0
|  | Book value of plant (from COD) | USD m |  |  | 836.6866 | 836.6866 | 836.6866 | 836.6866 | 836.6866 | 831.1086 | 814.3749 | 797.6412 | 780.9074 | 764.1737 | 747.44 | 730.7063 | 713.9725 | 697.2388 | 680.5051 | 663.7713 | 647.0376 | 630.3039 | 613.5701 | 596.8364 | 580.1027 | 563.3689 | 546.6352 | 529.9015 | 513.1678 | 496.434 | 479.7003 | 462.9666 | 446.2328 | 429.4991 | 412.7654 | 396.0316 | 379.2979 | 362.5642 | 345.8304 | 329.0967 | 312.363 | 295.6292 | 278.8955 | 262.1618 | 245.4281 | 228.6943 | 211.9606 | 195.2269 | 178.4931 | 161.7594 | 145.0257 | 128.2919 | 111.5582 | 94.8245 | 78.0907 | 61.357 | 44.6233 | 27.8896 | 11.1558 | 0 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | -1.6734 | -6.6935 | -11.7136 | -16.7337 | -21.7539 | -26.774 | -31.7941 | -36.8142 | -41.8343 | -46.8544 | -49.373 | -46.692 | -43.637 | -40.3868 | -36.7231 | -35.7191 | -32.1495 | -27.5111 | -22.4602 | -17.0387 | -11.1175 | -4.8022 | 2.0629 | 8.5682 | 16.4908 | 24.8986 | 33.8633 | 34.9735 | 35.9775 | 36.9815 | 37.9856 | 38.9896 | 39.9936 | 40.9976 | 42.0017 | 43.0057 | 44.0097 | 45.0137 | 46.0178 | 47.0218 | 46.1014 | 41.3323 | 36.5632 | 31.7941 | 27.025 | 22.2559 | 17.4867 | 12.7176 | 7.9485 | 3.1794 | 0 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | -1.6734 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -5.0201 | -2.5185 | 2.681 | 3.0549 | 3.2502 | 3.6637 | 1.004 | 3.5696 | 4.6384 | 5.0509 | 5.4215 | 5.9212 | 6.3154 | 6.8651 | 6.5053 | 7.9226 | 8.4077 | 8.9648 | 1.1102 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | 1.004 | -0.92036 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -4.7691 | -3.1794 | 0
|  | Net income | USD m |  | 855.8653 | 0 | 0 | 0 | 0 | 0 | 9.2641 | 5.8382 | 7.0887 | 7.488 | 8.602 | 8.9838 | 10.1135 | 8.3649 | 12.0346 | 12.5591 | 10.6826 | 5.9002 | 6.7709 | 7.2245 | 8.1886 | -0.79751 | 10.751 | 10.4569 | 11.4179 | 12.281 | 13.4451 | 14.3627 | 15.6441 | 14.8038 | 18.1086 | 19.2375 | 20.5355 | 22.8218 | 24.1704 | 24.7614 | 24.9392 | 14.6834 | 25.2229 | 25.0992 | 25.1902 | 25.3348 | 25.3869 | 25.4508 | 25.6 | 23.3855 | 25.8622 | 25.8167 | 25.9151 | 26.0732 | 26.1286 | 26.1975 | 26.4099 | 14.2871 | 26.7478 | 26.5938 | 4.4367 | 0
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 139.1061 | 239.3611 | 433.488 | 635.5096 | 753.0815 | 831.1086 | 814.3749 | 797.6412 | 780.9074 | 764.1737 | 747.44 | 730.7063 | 713.9725 | 697.2388 | 680.5051 | 663.7713 | 647.0376 | 630.3039 | 613.5701 | 596.8364 | 580.1027 | 563.3689 | 546.6352 | 529.9015 | 513.1678 | 496.434 | 479.7003 | 462.9666 | 446.2328 | 429.4991 | 412.7654 | 396.0316 | 379.2979 | 362.5642 | 345.8304 | 329.0967 | 312.363 | 295.6292 | 278.8955 | 262.1618 | 245.4281 | 228.6943 | 211.9606 | 195.2269 | 178.4931 | 161.7594 | 145.0257 | 128.2919 | 111.5582 | 94.8245 | 78.0907 | 61.357 | 44.6233 | 27.8896 | 11.1558 | 0 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 38.9791 | 37.5733 | 38.4573 | 38.5821 | 39.4163 | 39.652 | 40.7855 | 38.0232 | 36.9268 | 38.5431 | 40.8168 | 42.4925 | 44.8957 | 46.1666 | 48.8385 | 36.3833 | 35.599 | 34.7883 | 34.4856 | 33.3427 | 32.4059 | 30.5991 | 28.6611 | 23.5693 | 19.132 | 21.2538 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 4.0328 | 1.9961 | 3.5137 | 7.8422 | 12.1876 | 16.5499 | 20.9293 | 25.3261 | 29.7405 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.1198 | 38.9912 | 40.0245 | 39.347 | 40.5343 | 40.1323 | 40.8025 | 39.9464 | 41.346 | 41.3182 | 42.4215 | 41.7026 | 42.9722 | 42.5508 | 43.0992 | 41.6293 | 43.507 | 43.832 | 45.0109 | 44.2473 | 45.6059 | 45.1636 | 45.9277 | 44.9472 | 46.5536 | 46.5476 | 47.8083 | 46.9964 | 48.4511 | 47.9861 | 48.6083 | 46.9338 | 49.0759 | 49.4813 | 50.8304 | 49.9662 | 51.5248 | 51.0353 | 51.9091 | 50.7836 | 52.6312 | 52.6506 | 54.0951 | 53.1746 | 54.8454 | 54.3294 | 55.0377 | 53.1246 | 55.5755 | 56.0744 | 0 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 0 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.6734 | 6.6935 | 11.7136 | 16.7337 | 21.7539 | 26.774 | 31.7941 | 36.8142 | 41.8343 | 46.8544 | 49.373 | 46.692 | 43.637 | 40.3868 | 36.7231 | 35.7191 | 32.1495 | 27.5111 | 22.4602 | 17.0387 | 11.1175 | 4.8022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 139.1061 | 239.3611 | 433.488 | 635.5096 | 753.0815 | 916.231 | 902.9829 | 893.1866 | 880.9203 | 871.2281 | 859.3482 | 849.4384 | 834.1063 | 822.6959 | 812.5708 | 801.7326 | 783.2747 | 767.1588 | 748.0244 | 730.8473 | 699.1844 | 679.9744 | 658.1166 | 637.2082 | 613.1465 | 590.9134 | 565.6151 | 542.9054 | 520.0993 | 500.5347 | 485.9168 | 453.8858 | 438.6879 | 425.7569 | 410.906 | 397.1423 | 364.6468 | 350.0551 | 334.3164 | 319.5215 | 302.5132 | 287.9277 | 271.2941 | 256.5188 | 236.6228 | 223.2543 | 210.8685 | 199.9247 | 186.6326 | 175.9492 | 163.0963 | 151.4852 | 117.7098 | 105.0825 | 90.5214 | 0 | 0
|  | Senior debt | USD m |  |  | 102.395 | 175.3545 | 316.6938 | 462.2839 | 543.8541 | 633.256 | 617.7663 | 601.621 | 584.6804 | 567.2407 | 548.9987 | 530.1749 | 510.1214 | 489.4549 | 469.362 | 449.2597 | 428.3245 | 401.4472 | 372.9319 | 344.4437 | 312.9935 | 280.5363 | 247.1242 | 213.7769 | 178.9634 | 144.0712 | 108.1058 | 80.0771 | 58.5367 | 36.5486 | 18.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 29.5372 | 51.721 | 94.6062 | 140.8375 | 171.1243 | 204.8614 | 201.3599 | 199.8655 | 197.5448 | 195.7822 | 193.3739 | 191.7123 | 188.8222 | 184.9255 | 182.1671 | 179.9333 | 177.0433 | 180.0524 | 182.4395 | 185.2325 | 186.9606 | 188.0976 | 188.6669 | 188.8069 | 187.8541 | 186.0077 | 182.5615 | 169.6348 | 147.9409 | 123.0269 | 98.7082 | 54.6337 | 16.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 24.4828 | 24.3877 | 25.1423 | 24.6493 | 25.5574 | 25.344 | 25.806 | 25.0526 | 26.1709 | 26.338 | 27.1533 | 26.6203 | 27.6017 | 27.3709 | 27.7004 | 26.5573 | 27.9164 | 28.4445 | 29.3255 | 28.7491 | 29.8096 | 29.5602 | 30.0989 | 29.218 | 30.5243 | 30.7198 | 31.6717 | 31.0485 | 32.1945 | 31.9249 | 32.3084 | 30.972 | 32.5594 | 33.1772 | 34.2057 | 33.5319 | 34.7703 | 34.4788 | 35.1069 | 34.077 | 35.6027 | 35.8315 | 36.9426 | 36.2142 | 37.5522 | 37.2372 | 37.6837 | 36.1217 | 37.9756 | 38.6981 | 0 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0629 | 8.5682 | 16.4908 | 24.8986 | 33.8633 | 34.9735 | 35.9775 | 36.9815 | 37.9856 | 38.9896 | 39.9936 | 40.9976 | 42.0017 | 43.0057 | 44.0097 | 45.0137 | 46.0178 | 47.0218 | 46.1014 | 41.3323 | 36.5632 | 31.7941 | 27.025 | 22.2559 | 17.4867 | 12.7176 | 7.9485 | 3.1794 | 0 | 0
|  | Share capital | USD m |  |  | 7.1739 | 12.2856 | 22.188 | 32.3882 | 38.1031 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668 | 44.3668
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.2641 | 15.1023 | 22.191 | 29.679 | 38.281 | 47.2649 | 57.3784 | 65.7433 | 77.7779 | 90.337 | 101.0196 | 106.9198 | 113.6908 | 120.9153 | 129.1038 | 128.3063 | 139.0573 | 149.5142 | 160.9321 | 173.2131 | 186.6582 | 201.0209 | 216.665 | 231.4688 | 249.5774 | 268.8148 | 289.3503 | 312.1721 | 313.2181 | 297.6329 | 282.4816 | 250.3184 | 233.1353 | 215.7748 | 198.9473 | 181.6088 | 164.781 | 147.4348 | 131.0274 | 111.1573 | 97.1835 | 89.338 | 82.052 | 74.2576 | 67.0052 | 59.2365 | 51.948 | 24.5037 | 14.7917 | 4.2771 | -44.3668 | -44.3668
|  | Total liabilities and equity | USD m |  |  | 139.1061 | 239.3611 | 433.488 | 635.5096 | 753.0815 | 916.231 | 902.9829 | 893.1866 | 880.9203 | 871.2281 | 859.3482 | 849.4384 | 834.1063 | 822.6959 | 812.5708 | 801.7326 | 783.2747 | 767.1588 | 748.0244 | 730.8473 | 699.1844 | 679.9744 | 658.1166 | 637.2082 | 613.1465 | 590.9134 | 565.6151 | 542.9054 | 520.0993 | 500.5347 | 485.9168 | 453.8858 | 438.6879 | 425.7569 | 410.906 | 397.1423 | 364.6468 | 350.0551 | 334.3164 | 319.5215 | 302.5132 | 287.9277 | 271.2941 | 256.5188 | 236.6228 | 223.2543 | 210.8685 | 199.9247 | 186.6326 | 175.9492 | 163.0963 | 151.4852 | 117.7098 | 105.0825 | 90.5214 | -3.0553e-13 | -3.0553e-13
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.034356 | 0.034012 | 0.034381 | 0.034025 | 0.034393 | 0.034147 | 0.034393 | 0.034025 | 0.034393 | 0.035086 | 0.035472 | 0.035086 | 0.035292 | 0.034812 | 0.034824 | 0.034142 | 0.034101 | 0.034083 | 0.03371 | 0.032402 | 0.031269 | 0.028789 | 0.027145 | 0.027012 | 0.027145 | 0.027012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 32
| Rate in final maturity period | factor | 0.027012
| Discount rate used | factor |  |  | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.034356 | 0.034012 | 0.034381 | 0.034025 | 0.034393 | 0.034147 | 0.034393 | 0.034025 | 0.034393 | 0.035086 | 0.035472 | 0.035086 | 0.035292 | 0.034812 | 0.034824 | 0.034142 | 0.034101 | 0.034083 | 0.03371 | 0.032402 | 0.031269 | 0.028789 | 0.027145 | 0.027012 | 0.027145 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012 | 0.027012
| PV of CFADS to final maturity | USD m |  |  | 716.9537 | 736.32 | 756.2094 | 776.6361 | 797.6146 | 819.1597 | 839.5535 | 819.6611 | 798.9346 | 777.177 | 754.8001 | 731.405 | 707.271 | 681.5019 | 654.9708 | 629.3125 | 603.7056 | 577.0389 | 549.6177 | 520.7977 | 490.9089 | 458.035 | 423.6437 | 387.979 | 351.4825 | 312.9545 | 273.1399 | 231.1584 | 187.531 | 141.2089 | 94.0077 | 47.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 975.7371 | 1002.0936 | 1029.1621 | 1056.9618 | 1085.5124 | 1114.8341 | 1143.2148 | 1133.7549 | 1123.7116 | 1113.12 | 1102.1735 | 1090.7256 | 1078.8616 | 1065.8726 | 1052.4196 | 1040.4308 | 1029.2484 | 1017.6767 | 1005.7157 | 992.9923 | 979.5417 | 963.6839 | 946.5567 | 928.7238 | 910.6573 | 890.9792 | 869.8936 | 846.5717 | 820.6612 | 791.5251 | 761.8903 | 733.455 | 704.5424 | 682.4505 | 660.8736 | 638.3784 | 615.5318 | 585.3119 | 558.7163 | 531.3486 | 503.6837 | 474.6158 | 445.2214 | 414.4508 | 383.1435 | 348.7361 | 316.8026 | 290.1636 | 263.2496 | 234.9249 | 206.3047 | 176.3087 | 145.7528 | 106.3208 | 71.0773 | 34.2152 | 0
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3846 | 1.387 | 1.3905 | 1.3931 | 1.3972 | 1.4007 | 1.4063 | 1.4105 | 1.4136 | 1.4187 | 1.4259 | 1.4326 | 1.4613 | 1.4938 | 1.5326 | 1.5796 | 1.637 | 1.7087 | 1.8008 | 1.9267 | 2.107 | 2.3984 | 2.6627 | 2.815 | 3.0956 | 3.6042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3258 | 1.3268 | 1.328 | 1.3292 | 1.3307 | 1.3323 | 1.334 | 1.336 | 1.3382 | 1.3408 | 1.3438 | 1.3472 | 1.3691 | 1.3965 | 1.4252 | 1.4634 | 1.5101 | 1.57 | 1.6442 | 1.7487 | 1.8959 | 2.1383 | 2.3419 | 2.4123 | 2.5721 | 2.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8053 | 1.8352 | 1.8678 | 1.9038 | 1.943 | 1.9868 | 2.0349 | 2.0894 | 2.1502 | 2.2167 | 2.291 | 2.3759 | 2.5052 | 2.6627 | 2.8438 | 3.0789 | 3.3741 | 3.7581 | 4.2598 | 4.9786 | 6.0379 | 7.831 | 10.2484 | 13.5219 | 20.846 | 39.8429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR (debt-service weighted) | x | #VALUE!
| LLCR at first debt service period | x | 1.3846
| PLCR at first debt service period | x | 1.8053

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1109.7412 | -14.2 | -17.3444 | -0.64832 | -0.82642 | -1.1683 | -1.6823 | -2.3182 | -3.0241 | -3.8386 | -4.6503 | -5.4768 | -6.2503 | -6.9919 | -7.6439 | -8.1862 | -8.635 | -8.9339 | -9.1211 | -9.4615 | -9.0251 | -8.8106 | -8.4224 | -7.9465 | -7.3349 | -6.6728 | -5.9308 | -5.1338 | -4.3646 | -3.5814 | -2.8912 | -2.2731 | -1.7202 | -1.4358 | -14.075 | -10.8487 | -0.96532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3124 | 10.9804 | 11.8924 | 11.0688 | 11.7844 | 10.8217 | 12.0712 | 12.7921 | 11.6145 | 10.8156 | 11.5071 | 5.3313 | 6.2357 | 5.8491 | 7.1428 | 7.6706 | 8.4388 | 8.748 | 9.9949 | 10.6961 | 12.3542 | 21.5746 | 29.8178 | 31.8834 | 30.2105 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.0074 | 43.2557 | 39.836 | 33.6622 | 33.201 | 33.8676 | 33.3809 | 33.9662 | 33.6984 | 41.7314 | 36.4599 | 37.1084 | 53.0806 | 0
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1531.7418 | 0 | -108.1116 | -1.4208 | -2.0547 | -3.357 | -5.2462 | -7.6084 | -10.3182 | -13.2493 | -16.2775 | -19.2866 | -22.1683 | -24.8261 | -27.1747 | -29.1412 | -30.6686 | -31.7112 | -32.2399 | -33.3829 | -31.7112 | -30.6686 | -29.1412 | -27.1747 | -24.8261 | -22.1683 | -19.2866 | -16.2775 | -13.2493 | -10.3182 | -7.6084 | -5.2462 | -3.357 | -2.0547 | -49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7332 | 48.7362 | 48.6052 | 49.2257 | 48.82 | 49.3551 | 49.1096 | 50.0945 | 49.7189 | 48.1849 | 47.687 | 48.0814 | 47.6673 | 48.2169 | 48.0191 | 49.9692 | 50.0298 | 50.1113 | 49.7199 | 50.3765 | 49.9549 | 50.5222 | 50.2821 | 51.4126 | 51.0154 | 49.1164 | 48.7246 | 41.123 | 40.0112 | 40.3466 | 40.0905 | 46.8466 | 42.406 | 42.4597 | 42.0177 | 42.6733 | 42.2147 | 42.7969 | 42.5024 | 44.7569 | 41.3536 | 35.1964 | 34.752 | 35.4355 | 34.966 | 35.5687 | 35.3184 | 43.369 | 38.1154 | 38.7821 | 35.1394 | 0
| Project cash flow, pre-tax | USD m |  | 1814.4027 | 0 | -108.1116 | -1.4208 | -2.0547 | -3.357 | -5.2462 | -7.6084 | -10.3182 | -13.2493 | -16.2775 | -19.2866 | -22.1683 | -24.8261 | -27.1747 | -29.1412 | -30.6686 | -31.7112 | -32.2399 | -33.3829 | -31.7112 | -30.6686 | -29.1412 | -27.1747 | -24.8261 | -22.1683 | -19.2866 | -16.2775 | -13.2493 | -10.3182 | -7.6084 | -5.2462 | -3.357 | -2.0547 | -49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7332 | 48.7362 | 48.6052 | 49.2257 | 48.82 | 49.3551 | 49.1096 | 50.0945 | 49.7189 | 48.1849 | 47.805 | 48.4369 | 48.0245 | 48.5761 | 48.3792 | 50.3248 | 50.3924 | 50.4774 | 50.0875 | 50.7456 | 50.3259 | 50.8953 | 50.6566 | 51.7878 | 51.393 | 49.497 | 49.1069 | 49.7936 | 49.3659 | 49.9546 | 49.7747 | 52.1354 | 52.2118 | 52.2125 | 51.8095 | 52.5271 | 52.0908 | 52.7004 | 52.4698 | 53.7752 | 53.3578 | 51.0298 | 50.6275 | 51.3788 | 50.9331 | 51.5653 | 51.406 | 54.2612 | 54.3479 | 54.9486 | 40.2202 | 0
| Cumulative equity cash flow | USD m |  |  | -14.2 | -31.5444 | -32.1927 | -33.0191 | -34.1874 | -35.8696 | -38.1878 | -41.2119 | -45.0505 | -49.7007 | -55.1776 | -61.4279 | -68.4198 | -76.0637 | -84.2499 | -92.8849 | -101.8188 | -110.9399 | -120.4015 | -129.4266 | -138.2373 | -146.6596 | -154.6062 | -161.9411 | -168.6139 | -174.5447 | -179.6785 | -184.043 | -187.6244 | -190.5157 | -192.7888 | -194.5089 | -195.9447 | -210.0198 | -220.8684 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -221.8338 | -208.5214 | -197.541 | -185.6486 | -174.5798 | -162.7954 | -151.9737 | -139.9024 | -127.1103 | -115.4959 | -104.6802 | -93.1731 | -87.8418 | -81.6061 | -75.757 | -68.6142 | -60.9436 | -52.5048 | -43.7568 | -33.7619 | -23.0658 | -10.7116 | 10.863 | 40.6808 | 72.5642 | 102.7747 | 151.4994 | 192.6223 | 232.6335 | 272.9802 | 313.0707 | 359.9172 | 402.3232 | 444.7829 | 486.8006 | 529.474 | 571.6886 | 614.4856 | 656.493 | 699.7487 | 739.5847 | 773.2469 | 806.4479 | 840.3155 | 873.6964 | 907.6627 | 941.3611 | 983.0924 | 1019.5523 | 1056.6607 | 1109.7412 | 1109.7412
| Equity IRR (XIRR) | % | 12.54%
| Project IRR, post-tax (XIRR) | % | 10.62%
| Project IRR, pre-tax (XIRR) | % | 11.18%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -54.6046

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 0
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 0

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 855.0897
| Senior debt (four tranches) | USD m | 633.256
| Equity (incl. LNTP) | USD m | 221.8338
| Gearing (debt incl. standby / total funding) | % | 74.06%
| Interest during construction incl. swap and PRI | USD m | 63.8991
| Commitment, upfront and agency fees | USD m | 20.8187
| ECA premium | USD m | 20.6125
| DSRA initial funding | USD m | 37.2459
| Standby drawn | USD m | 1.7422e-11
| Contingent equity drawn | USD m | 5.8075e-12
| Minimum DSCR | x | #VALUE!
| Average DSCR | x | #VALUE!
| LLCR at first debt service period (incl. DSRA) | x | 1.3846
| PLCR at first debt service period | x | 1.8053
| Equity IRR | % | 12.54%
| Project IRR, post-tax | % | 10.62%
| Equity NPV at 16.0% (at FC) | USD m | -54.6046
| All checks | check | 0