## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 7
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 1
|  | Construction case (1 FC budget, 2 actual) | code | 1
|  | COD delay (sensitivity) | months | 0
|  | Capex factor | factor | 1.1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 0
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 0
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 1
|  | Performance LD prepayment June 2022 (1 = on) | flag | 0
|  | Waiver and amendment 2023 (1 = on) | flag | 0
|  | 2025 bond refinancing (1 = on) | flag | 0
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 2
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-05-01
|  | PPA expiry | date | 2046-04-30
|  | Construction months (NTP to COD) | months | 33
|  | Period containing COD (period number) | index | 6
|  | First debt service period | index | 7
|  | Last month of the funding period (month number) | index | 35
|  | Last operating period (period number) | index | 56
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-05-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-04-30
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 120 | 0
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 520.4953 | 522.6929 | 524.8998 | 527.116 | 529.3416 | 531.5766 | 533.821 | 536.0748 | 538.3382 | 540.6112 | 542.8937 | 545.1859 | 547.4878 | 549.7993 | 552.1207 | 554.4518 | 556.7928 | 559.1437 | 561.5044 | 563.8752 | 566.256 | 568.6468 | 571.0477 | 573.4587 | 575.88 | 578.3114 | 580.7532 | 583.2052 | 585.6676 | 588.1403 | 590.6236 | 593.1173 | 595.6215 | 598.1363 | 600.6617 | 603.1978 | 605.7446 | 608.3021 | 610.8705 | 613.4497 | 616.0398 | 618.6408 | 621.2528 | 623.8758 | 626.5099 | 629.1551 | 631.8115 | 634.4791 | 637.158 | 639.8481 | 642.5497 | 645.2626 | 647.987
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 629.024 | 62.9024 | 0.067935 | 0.71268 | 2.0374 | 3.9591 | 6.3619 | 9.1183 | 12.0999 | 15.1802 | 18.2411 | 21.1723 | 23.8759 | 26.2649 | 28.2652 | 29.8189 | 30.8794 | 31.4172 | 31.4172 | 30.8794 | 29.8189 | 28.2652 | 26.2649 | 23.8759 | 21.1723 | 18.2411 | 15.1802 | 12.0999 | 9.1183 | 6.3619 | 3.9591 | 2.0374 | 0.71268 | 47.2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 50.798 | 6.0958 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 1.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 8.382 | 7.1247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 9.867 | 6.9069 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0.092503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 42.24 | 0 | 0.0055296 | 0.05801 | 0.16584 | 0.32225 | 0.51784 | 0.7422 | 0.98488 | 1.2356 | 1.4847 | 1.7233 | 1.9434 | 2.1379 | 2.3007 | 2.4271 | 2.5135 | 2.5572 | 2.5572 | 2.5135 | 2.4271 | 2.3007 | 2.1379 | 1.9434 | 1.7233 | 1.4847 | 1.2356 | 0.98488 | 0.7422 | 0.51784 | 0.32225 | 0.16584 | 0.05801 | 0.0055296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 778.826 | 115.6598 | 1.5629 | 2.2601 | 3.6927 | 5.7708 | 8.3692 | 11.35 | 14.5742 | 17.9053 | 21.2153 | 24.3851 | 27.3087 | 29.8922 | 32.0553 | 33.7355 | 34.8823 | 35.4639 | 36.7212 | 34.8823 | 33.7355 | 32.0553 | 29.8922 | 27.3087 | 24.3851 | 21.2153 | 17.9053 | 14.5742 | 11.35 | 8.3692 | 5.7708 | 3.6927 | 2.2601 | 54.6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 47232.6778 | 4723.2678 | 5.1011 | 53.5146 | 152.9866 | 297.2825 | 477.7113 | 684.6849 | 908.5678 | 1139.8662 | 1369.7004 | 1589.8047 | 1792.8108 | 1972.2005 | 2122.4004 | 2239.0651 | 2318.6994 | 2359.0833 | 2359.0833 | 2318.6994 | 2239.0651 | 2122.4004 | 1972.2005 | 1792.8108 | 1589.8047 | 1369.7004 | 1139.8662 | 908.5678 | 684.6849 | 477.7113 | 297.2825 | 152.9866 | 53.5146 | 3547.552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 8501.882 | 850.1882 | 0.9182 | 9.6326 | 27.5376 | 53.5108 | 85.988 | 123.2433 | 163.5422 | 205.1759 | 246.5461 | 286.1648 | 322.7059 | 354.9961 | 382.0321 | 403.0317 | 417.3659 | 424.635 | 424.635 | 417.3659 | 403.0317 | 382.0321 | 354.9961 | 322.7059 | 286.1648 | 246.5461 | 205.1759 | 163.5422 | 123.2433 | 85.988 | 53.5108 | 27.5376 | 9.6326 | 638.5594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 8501.882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.1882 | 0.9182 | 9.6326 | 27.5376 | 53.5108 | 85.988 | 123.2433 | 163.5422 | 205.1759 | 246.5461 | 286.1648 | 322.7059 | 354.9961 | 382.0321 | 403.0317 | 417.3659 | 424.635 | 424.635 | 417.3659 | 403.0317 | 382.0321 | 354.9961 | 322.7059 | 286.1648 | 246.5461 | 205.1759 | 163.5422 | 123.2433 | 85.988 | 53.5108 | 27.5376 | 9.6326 | 638.5594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 850.1882 | 851.1064 | 860.739 | 888.2766 | 941.7875 | 1027.7755 | 1151.0188 | 1314.561 | 1519.7369 | 916.0948 | 1201.3414 | 1514.4147 | 1841.8732 | 2170.3944 | 2487.4381 | 2781.5607 | 3042.6535 | 3262.1126 | 3432.9324 | 3549.7993 | 3609.1254 | 3609.1254 | 3549.7993 | 3432.9324 | 3262.1126 | 3042.6535 | 2781.5607 | 2487.4381 | 2170.3944 | 1841.8732 | 1514.4147 | 1201.3414 | 1553.7359 | 1307.1899 | 1102.0139 | 938.4717 | 815.2285 | 729.2404 | 675.7296 | 648.192 | 638.5594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.7984 | 0 | 0.02139 | 0.022034 | 0.021474 | 0.022803 | 0.024076 | 0.023631 | 0.029177 | 0.032112 | 0.038201 | 0.022191 | 0.029944 | 0.037589 | 0.044056 | 0.053419 | 0.058998 | 0.067887 | 0.073947 | 0.073853 | 0.082732 | 0.08244 | 0.086248 | 0.083115 | 0.084118 | 0.081007 | 0.07418 | 0.071195 | 0.062721 | 0.057715 | 0.050147 | 0.038277 | 0.034697 | 0.026524 | 0.035299 | 0.028619 | 0.024827 | 0.021053 | 0.017624 | 0.016222 | 0.014486 | 0.014298 | 0.014027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | KCR per USD, period average | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | US CPI change, current year | % |  |  | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, current year | % |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI change, prior year | % |  |  | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US index, June 2018 (2018 price base) | index | 103.3281
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084 | 191.0761
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 102.7675 | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0055 | 1.0165 | 1.0276 | 1.0388 | 1.0502 | 1.0617 | 1.0733 | 1.085 | 1.0969 | 1.1089 | 1.121 | 1.1333 | 1.1457 | 1.1582 | 1.1709 | 1.1837 | 1.1967 | 1.2097 | 1.223 | 1.2364 | 1.2499 | 1.2636 | 1.2774 | 1.2914 | 1.3055 | 1.3198 | 1.3342 | 1.3488 | 1.3636 | 1.3785 | 1.3936 | 1.4088 | 1.4242 | 1.4398 | 1.4556 | 1.4715 | 1.4876 | 1.5038 | 1.5203 | 1.5369 | 1.5537 | 1.5707 | 1.5879 | 1.6053 | 1.6229 | 1.6406 | 1.6586 | 1.6767 | 1.6951 | 1.7136 | 1.7323 | 1.7513 | 1.7705 | 1.7898 | 1.8094 | 1.8292 | 1.8492
|  | KC index, June 2018 (2018 price base) | index | 112.9227
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682 | 871.105
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 110.8994 | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0182 | 1.0557 | 1.0946 | 1.1349 | 1.1767 | 1.22 | 1.265 | 1.3115 | 1.3598 | 1.4099 | 1.4618 | 1.5156 | 1.5715 | 1.6293 | 1.6893 | 1.7515 | 1.816 | 1.8829 | 1.9522 | 2.0241 | 2.0986 | 2.1759 | 2.256 | 2.3391 | 2.4252 | 2.5145 | 2.6071 | 2.7031 | 2.8027 | 2.9059 | 3.0129 | 3.1238 | 3.2388 | 3.3581 | 3.4817 | 3.6099 | 3.7429 | 3.8807 | 4.0236 | 4.1717 | 4.3254 | 4.4846 | 4.6498 | 4.821 | 4.9985 | 5.1825 | 5.3734 | 5.5712 | 5.7764 | 5.9891 | 6.2096 | 6.4383 | 6.6753 | 6.9211 | 7.176 | 7.4402 | 7.7142
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 26
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 0
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.41667 | 0.91667 | 1.4167 | 1.9167 | 2.4167 | 2.9167 | 3.4167 | 3.9167 | 4.4167 | 4.9167 | 5.4167 | 5.9167 | 6.4167 | 6.9167 | 7.4167 | 7.9167 | 8.4167 | 8.9167 | 9.4167 | 9.9167 | 10.4167 | 10.9167 | 11.4167 | 11.9167 | 12.4167 | 12.9167 | 13.4167 | 13.9167 | 14.4167 | 14.9167 | 15.4167 | 15.9167 | 16.4167 | 16.9167 | 17.4167 | 17.9167 | 18.4167 | 18.9167 | 19.4167 | 19.9167 | 20.4167 | 20.9167 | 21.4167 | 21.9167 | 22.4167 | 22.9167 | 23.4167 | 23.9167 | 24.4167 | 24.8333 | 0
|  | Contracted capacity | MW | 588.4
|  | Plant net heat rate, new and clean | kJ/kWh | 6261
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98988 | 0.98938 | 0.98864 | 0.9879 | 0.98715 | 0.98641 | 0.98567 | 0.98493 | 0.98418 | 0.98344 | 0.9827 | 0.98196 | 0.98121 | 0.98047 | 0.97973 | 0.97899 | 0.97824 | 0.9775 | 0.97676 | 0.97602 | 0.97527 | 0.97453 | 0.97379 | 0.97305 | 0.9723 | 0.97156 | 0.97082 | 0.97008 | 0.96933 | 0.96859 | 0.96785 | 0.96711 | 0.96636 | 0.96562 | 0.96488 | 0.96414 | 0.96339 | 0.96265 | 0.96191 | 0.96117 | 0.96042 | 0.95968 | 0.95894 | 0.9582 | 0.95745 | 0.95671 | 0.95597 | 0.95523 | 0.95448 | 0.95374 | 0.95312 | 0.99
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 610197.8847 | 1829678.2427 | 1822457.6681 | 1809402.8106 | 1813881.5431 | 1824185.7752 | 1802084.1562 | 1759300.8791 | 1778671.879 | 1818693.3077 | 1811507.8661 | 1798523.2747 | 1802966.8742 | 1813200.8402 | 1778990.7603 | 1712018.3752 | 1743507.1072 | 1807708.3727 | 1800558.0641 | 1787643.7388 | 1792052.2052 | 1802215.9051 | 1780364.1212 | 1738080.5141 | 1757201.6791 | 1796723.4376 | 1789608.2621 | 1776764.203 | 1781137.5363 | 1791230.9701 | 1757419.0648 | 1691243.0289 | 1722333.5863 | 1785738.5026 | 1778658.4602 | 1765884.6671 | 1770222.8674 | 1780246.0351 | 1758644.0861 | 1716860.1492 | 1735731.4791 | 1774753.5675 | 1767708.6582 | 1755005.1312 | 1759308.1984 | 1769261.1 | 1735847.3694 | 1670467.6827 | 1701160.0655 | 1763768.6325 | 1175082.9123 | 0
|  | Plant net heat rate | kJ/kWh |  |  | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.8886 | 6459.4711 | 6463.3449 | 6467.2186 | 6471.0924 | 6474.9661 | 6478.8399 | 6482.7136 | 6486.5874 | 6490.4611 | 6494.3349 | 6498.2086 | 6502.0823 | 6505.9561 | 6509.8298 | 6513.7036 | 6517.5773 | 6521.4511 | 6525.3248 | 6529.1986 | 6533.0723 | 6536.9461 | 6540.8198 | 6544.6936 | 6548.5673 | 6552.441 | 6556.3148 | 6560.1885 | 6564.0623 | 6567.936 | 6571.8098 | 6575.6835 | 6579.5573 | 6583.431 | 6587.3048 | 6591.1785 | 6595.0522 | 6598.926 | 6602.7997 | 6606.6735 | 6610.5472 | 6614.421 | 6618.2947 | 6622.1685 | 6626.0422 | 6629.916 | 6633.7897 | 6637.6635 | 6641.5372 | 6645.4109 | 6648.6391 | 6456.243
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.968 | 6471.1242 | 6474.3584 | 6477.5926 | 6480.8268 | 6484.061 | 6487.2953 | 6490.5295 | 6493.7637 | 6496.9979 | 6500.2321 | 6503.4663 | 6506.7005 | 6509.9348 | 6513.169 | 6516.4032 | 6519.6374 | 6522.8716 | 6526.1058 | 6529.34 | 6532.5743 | 6535.8085 | 6539.0427 | 6542.2769 | 6545.5111 | 6548.7453 | 6551.9795 | 6555.2138 | 6558.448 | 6561.6822 | 6564.9164 | 6568.1506 | 6571.3848 | 6574.619 | 6577.8533 | 6581.0875 | 6584.3217 | 6587.5559 | 6590.7901 | 6594.0243 | 6597.2585 | 6600.4928 | 6603.727 | 6606.9612 | 6610.1954 | 6613.4296 | 6616.6638 | 6619.898 | 6623.1323 | 6626.3665 | 6629.0617 | 6468.429
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 4137692.7979 | 12411833.3307 | 12370265.7341 | 12289014.3891 | 12326811.9429 | 12404258.6808 | 12261301.272 | 11977362.8114 | 12116476.9239 | 12396505.2781 | 12354897.6145 | 12273656.3697 | 12311315.5234 | 12388573.1226 | 12162072.2212 | 11711180.1611 | 11933673.834 | 12380462.2143 | 12338816.7706 | 12257590.1995 | 12295108.6664 | 12372172.5532 | 12229403.2985 | 11946025.9973 | 12084596.4827 | 12363704.1393 | 12322023.2024 | 12240815.8786 | 12278191.3719 | 12355056.9726 | 12128987.9936 | 11679148.2501 | 11900855.7346 | 12346231.0531 | 12304516.9097 | 12223333.4069 | 12260563.6397 | 12337226.3808 | 12194677.8039 | 11911926.7092 | 12049921.0439 | 12328042.9557 | 12286297.8926 | 12205142.7845 | 12242225.47 | 12318680.7778 | 12093095.5557 | 11644411.7978 | 11865281.2595 | 12309139.8471 | 8204753.1026 | 0
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 3533120 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 6950400 | 0
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4395 | 14.4718 | 14.5044 | 14.5374 | 14.5708 | 14.6045 | 14.6386 | 14.6731 | 14.7079 | 14.7431 | 14.7787 | 14.8148 | 14.8511 | 14.8879 | 14.9251 | 14.9627 | 15.0008 | 15.0392 | 15.078 | 15.1173 | 15.157 | 15.1972 | 15.2377 | 15.2788 | 15.3202 | 15.3622 | 15.4045 | 15.4474 | 15.4907 | 15.5345 | 15.5788 | 15.6235 | 15.6688 | 15.7145 | 15.7607 | 15.8075 | 15.8547 | 15.9025 | 15.9508 | 15.9996 | 16.049 | 16.0989 | 16.1493 | 16.2003 | 16.2519 | 16.304 | 16.3567 | 16.4099 | 16.4638 | 16.5182 | 16.5733 | 16.6289 | 16.6851 | 16.742 | 16.7995 | 16.8576 | 16.9163
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3275 | 2.353 | 2.3787 | 2.4047 | 2.431 | 2.4576 | 2.4845 | 2.5117 | 2.5392 | 2.567 | 2.595 | 2.6234 | 2.6521 | 2.6811 | 2.7105 | 2.7401 | 2.7701 | 2.8004 | 2.8311 | 2.862 | 2.8933 | 2.925 | 2.957 | 2.9893 | 3.022 | 3.0551 | 3.0885 | 3.1223 | 3.1565 | 3.191 | 3.2259 | 3.2612 | 3.2969 | 3.333 | 3.3694 | 3.4063 | 3.4435 | 3.4812 | 3.5193 | 3.5578 | 3.5967 | 3.6361 | 3.6759 | 3.7161 | 3.7567 | 3.7978 | 3.8394 | 3.8814 | 3.9238 | 3.9668 | 4.0102 | 4.054 | 4.0984 | 4.1432 | 4.1886 | 4.2344 | 4.2807
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 0
|  | Capacity payment | USD m |  | 3334.8082 | 0 | 0 | 0 | 0 | 0 | 20.0787 | 60.4515 | 60.6691 | 60.8891 | 61.1116 | 61.3364 | 61.5638 | 61.7936 | 62.0259 | 62.2608 | 62.4982 | 62.7383 | 62.9809 | 63.2262 | 63.4742 | 62.8045 | 63.9784 | 64.2347 | 64.4937 | 64.7556 | 65.0203 | 65.2879 | 65.5585 | 65.832 | 66.1085 | 66.388 | 66.6706 | 66.9563 | 67.2451 | 67.5371 | 67.8323 | 67.1465 | 68.4323 | 68.7373 | 69.0456 | 69.3572 | 69.6723 | 69.9908 | 70.3128 | 70.6384 | 70.9675 | 71.3002 | 71.6365 | 71.9765 | 72.3202 | 72.6677 | 73.019 | 72.3143 | 73.7332 | 74.0961 | 49.642 | 0
|  | VOM charge, indexed | USD/MWh |  |  | 3.9056 | 3.9483 | 3.9915 | 4.0352 | 4.0793 | 4.1239 | 4.1691 | 4.2147 | 4.2608 | 4.3074 | 4.3545 | 4.4022 | 4.4503 | 4.499 | 4.5482 | 4.598 | 4.6483 | 4.6991 | 4.7505 | 4.8025 | 4.8551 | 4.9082 | 4.9619 | 5.0162 | 5.071 | 5.1265 | 5.1826 | 5.2393 | 5.2966 | 5.3546 | 5.4131 | 5.4724 | 5.5322 | 5.5927 | 5.6539 | 5.7158 | 5.7783 | 5.8415 | 5.9054 | 5.97 | 6.0354 | 6.1014 | 6.1681 | 6.2356 | 6.3038 | 6.3728 | 6.4425 | 6.513 | 6.5843 | 6.6563 | 6.7291 | 6.8027 | 6.8772 | 6.9524 | 7.0285 | 7.1053 | 7.1831
|  | Variable O&M payment | USD m |  | 485.8117 | 0 | 0 | 0 | 0 | 0 | 2.5164 | 7.628 | 7.6811 | 7.7095 | 7.8131 | 7.9434 | 7.9331 | 7.8294 | 8.0023 | 8.2718 | 8.3293 | 8.36 | 8.4724 | 8.6137 | 8.5436 | 8.3119 | 8.5574 | 8.9696 | 9.0319 | 9.0652 | 9.187 | 9.3402 | 9.3278 | 9.2059 | 9.409 | 9.7259 | 9.7934 | 9.8295 | 9.9615 | 10.1275 | 10.045 | 9.7725 | 10.0611 | 10.5456 | 10.6187 | 10.6578 | 10.8008 | 10.9808 | 10.9662 | 10.8228 | 11.0615 | 11.4339 | 11.5131 | 11.5554 | 11.7105 | 11.9056 | 11.8085 | 11.4881 | 11.8271 | 12.3966 | 8.3494 | 0
|  | Fuel charge (pass-through) | USD m |  | 4886.8261 | 0 | 0 | 0 | 0 | 0 | 25.7791 | 77.3244 | 78.5989 | 78.0749 | 79.8734 | 80.3672 | 81.0218 | 79.1376 | 81.6498 | 83.5286 | 84.9048 | 84.3382 | 86.2804 | 86.8132 | 86.922 | 83.6912 | 86.9783 | 90.2258 | 91.7118 | 91.0991 | 93.1964 | 93.7714 | 94.5338 | 92.3343 | 95.2642 | 97.4549 | 99.0593 | 98.3969 | 100.6615 | 101.2818 | 101.4074 | 97.6369 | 101.4704 | 105.2576 | 106.9897 | 106.2736 | 108.7188 | 109.388 | 110.276 | 107.7088 | 111.125 | 113.679 | 115.5489 | 114.7747 | 117.4147 | 118.1367 | 118.2815 | 113.8822 | 118.3519 | 122.7675 | 83.4617 | 0
|  | GTA reservation charge (pass-through) | USD m |  | 690.3467 | 0 | 0 | 0 | 0 | 0 | 3.8163 | 11.5116 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 10.893 | 0
|  | GTA commodity charge (pass-through) | USD m |  | 146.4295 | 0 | 0 | 0 | 0 | 0 | 0.82207 | 2.466 | 2.4946 | 2.4782 | 2.5231 | 2.539 | 2.5473 | 2.4883 | 2.555 | 2.6141 | 2.6444 | 2.627 | 2.6746 | 2.6913 | 2.6818 | 2.5823 | 2.6709 | 2.7709 | 2.803 | 2.7845 | 2.8349 | 2.8527 | 2.8621 | 2.7958 | 2.8706 | 2.9369 | 2.9709 | 2.9513 | 3.0048 | 3.0236 | 3.0128 | 2.901 | 3.0005 | 3.1127 | 3.1488 | 3.128 | 3.1846 | 3.2045 | 3.215 | 3.1404 | 3.2245 | 3.2989 | 3.337 | 3.315 | 3.3749 | 3.396 | 3.3838 | 3.2583 | 3.3699 | 3.4959 | 2.3652 | 0
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 3820.6199 | 0 | 0 | 0 | 0 | 0 | 22.5951 | 68.0795 | 68.3502 | 68.5986 | 68.9247 | 69.2799 | 69.4968 | 69.623 | 70.0282 | 70.5326 | 70.8275 | 71.0983 | 71.4533 | 71.8399 | 72.0179 | 71.1164 | 72.5359 | 73.2043 | 73.5256 | 73.8208 | 74.2073 | 74.6281 | 74.8863 | 75.0379 | 75.5175 | 76.1139 | 76.464 | 76.7858 | 77.2066 | 77.6646 | 77.8773 | 76.9191 | 78.4934 | 79.2828 | 79.6642 | 80.015 | 80.4731 | 80.9716 | 81.2791 | 81.4612 | 82.0289 | 82.734 | 83.1496 | 83.5319 | 84.0307 | 84.5733 | 84.8275 | 83.8024 | 85.5603 | 86.4927 | 57.9914 | 0
|  | Total revenue | USD m |  | 9544.2224 | 0 | 0 | 0 | 0 | 0 | 53.0127 | 159.3815 | 160.9374 | 160.836 | 162.9873 | 164.0456 | 164.9725 | 163.2864 | 166.2518 | 168.8932 | 170.5757 | 170.4647 | 172.7903 | 173.9318 | 174.2588 | 170.1661 | 174.9413 | 179.1687 | 180.988 | 180.8666 | 183.3804 | 184.6118 | 185.6949 | 183.7281 | 187.1914 | 190.2692 | 192.2363 | 192.1039 | 194.8211 | 196.1495 | 196.5331 | 191.8492 | 197.3341 | 202.2612 | 204.3881 | 204.2437 | 207.1806 | 208.6137 | 209.8793 | 207.5857 | 211.6301 | 215.2164 | 217.5159 | 217.3586 | 220.5329 | 222.079 | 222.5293 | 217.1555 | 223.4696 | 229.212 | 154.7114 | 0
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 279.3596 | 0 | 0 | 0 | 0 | 0 | 1.399 | 4.2428 | 4.2892 | 4.3361 | 4.3835 | 4.4315 | 4.48 | 4.529 | 4.5785 | 4.6286 | 4.6793 | 4.7305 | 4.7822 | 4.8345 | 4.8874 | 4.9409 | 4.9949 | 5.0496 | 5.1048 | 5.1607 | 5.2171 | 5.2742 | 5.3319 | 5.3902 | 5.4492 | 5.5088 | 5.5691 | 5.63 | 5.6916 | 5.7539 | 5.8168 | 5.8805 | 5.9448 | 6.0098 | 6.0756 | 6.1421 | 6.2093 | 6.2772 | 6.3459 | 6.4153 | 6.4855 | 6.5564 | 6.6282 | 6.7007 | 6.774 | 6.8481 | 6.923 | 6.9987 | 7.0753 | 7.1527 | 4.8206 | 0
|  | O&M availability incentive | USD m |  | 4.108 | 0 | 0 | 0 | 0 | 0 | 0.0637 | 0.19319 | 0.16275 | 0.098721 | 0.13307 | 0.20179 | 0.083108 | -0.1604 | -0.038608 | 0.21076 | 0.17756 | 0.1077 | 0.14517 | 0.22014 | 0.012364 | -0.37497 | -0.20217 | 0.22993 | 0.1937 | 0.11749 | 0.15837 | 0.24016 | 0.098913 | -0.1909 | -0.045949 | 0.25084 | 0.21132 | 0.12818 | 0.17278 | 0.262 | 0.014715 | -0.44627 | -0.24062 | 0.27365 | 0.23054 | 0.13984 | 0.18849 | 0.28583 | 0.11772 | -0.2272 | -0.054687 | 0.29854 | 0.25151 | 0.15256 | 0.20563 | 0.31182 | 0.017513 | -0.53114 | -0.28637 | 0.32569 | 0.2195 | 0
|  | LTSA fixed fee | USD m |  | 93.2833 | 0 | 0 | 0 | 0 | 0 | 0.46714 | 1.4167 | 1.4322 | 1.4479 | 1.4637 | 1.4798 | 1.4959 | 1.5123 | 1.5289 | 1.5456 | 1.5625 | 1.5796 | 1.5969 | 1.6143 | 1.632 | 1.6499 | 1.6679 | 1.6862 | 1.7046 | 1.7232 | 1.7421 | 1.7612 | 1.7804 | 1.7999 | 1.8196 | 1.8395 | 1.8596 | 1.88 | 1.9005 | 1.9213 | 1.9423 | 1.9636 | 1.9851 | 2.0068 | 2.0288 | 2.0509 | 2.0734 | 2.0961 | 2.119 | 2.1422 | 2.1656 | 2.1893 | 2.2133 | 2.2375 | 2.262 | 2.2867 | 2.3117 | 2.337 | 2.3626 | 2.3884 | 1.6097 | 0
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 2813 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 5626 | 0
|  | LTSA variable fee | USD m |  | 289.8393 | 0 | 0 | 0 | 0 | 0 | 1.4514 | 4.4019 | 4.4501 | 4.4988 | 4.548 | 4.5977 | 4.648 | 4.6989 | 4.7503 | 4.8023 | 4.8548 | 4.9079 | 4.9616 | 5.0159 | 5.0708 | 5.1262 | 5.1823 | 5.239 | 5.2963 | 5.3543 | 5.4129 | 5.4721 | 5.5319 | 5.5925 | 5.6536 | 5.7155 | 5.778 | 5.8412 | 5.9051 | 5.9697 | 6.035 | 6.1011 | 6.1678 | 6.2353 | 6.3035 | 6.3725 | 6.4422 | 6.5127 | 6.5839 | 6.6559 | 6.7288 | 6.8024 | 6.8768 | 6.952 | 7.0281 | 7.105 | 7.1827 | 7.2613 | 7.3407 | 7.421 | 5.0015 | 0
|  | Operational insurance | USD m |  | 154.4122 | 0 | 0 | 0 | 0 | 0 | 0.77325 | 2.3451 | 2.3708 | 2.3967 | 2.4229 | 2.4495 | 2.4762 | 2.5033 | 2.5307 | 2.5584 | 2.5864 | 2.6147 | 2.6433 | 2.6722 | 2.7015 | 2.731 | 2.7609 | 2.7911 | 2.8216 | 2.8525 | 2.8837 | 2.9153 | 2.9471 | 2.9794 | 3.012 | 3.0449 | 3.0782 | 3.1119 | 3.146 | 3.1804 | 3.2152 | 3.2504 | 3.2859 | 3.3219 | 3.3582 | 3.3949 | 3.4321 | 3.4696 | 3.5076 | 3.546 | 3.5848 | 3.624 | 3.6636 | 3.7037 | 3.7442 | 3.7852 | 3.8266 | 3.8685 | 3.9108 | 3.9536 | 2.6645 | 0
|  | G&A | USD m |  | 112.0828 | 0 | 0 | 0 | 0 | 0 | 0.56128 | 1.7023 | 1.7209 | 1.7397 | 1.7587 | 1.778 | 1.7974 | 1.8171 | 1.837 | 1.8571 | 1.8774 | 1.8979 | 1.9187 | 1.9397 | 1.9609 | 1.9824 | 2.004 | 2.026 | 2.0481 | 2.0705 | 2.0932 | 2.1161 | 2.1392 | 2.1626 | 2.1863 | 2.2102 | 2.2344 | 2.2588 | 2.2836 | 2.3085 | 2.3338 | 2.3593 | 2.3851 | 2.4112 | 2.4376 | 2.4643 | 2.4912 | 2.5185 | 2.546 | 2.5739 | 2.6021 | 2.6305 | 2.6593 | 2.6884 | 2.7178 | 2.7475 | 2.7776 | 2.808 | 2.8387 | 2.8698 | 1.9341 | 0
|  | Land lease and permits | USD m |  | 25.0349 | 0 | 0 | 0 | 0 | 0 | 0.12537 | 0.38022 | 0.38438 | 0.38858 | 0.39283 | 0.39713 | 0.40148 | 0.40587 | 0.41031 | 0.4148 | 0.41933 | 0.42392 | 0.42856 | 0.43325 | 0.43799 | 0.44278 | 0.44762 | 0.45252 | 0.45747 | 0.46248 | 0.46754 | 0.47265 | 0.47782 | 0.48305 | 0.48833 | 0.49368 | 0.49908 | 0.50454 | 0.51006 | 0.51564 | 0.52128 | 0.52698 | 0.53275 | 0.53857 | 0.54447 | 0.55042 | 0.55644 | 0.56253 | 0.56869 | 0.57491 | 0.5812 | 0.58756 | 0.59398 | 0.60048 | 0.60705 | 0.61369 | 0.62041 | 0.62719 | 0.63406 | 0.64099 | 0.432 | 0
|  | Community fund and OREK levy | USD m |  | 21.0134 | 0 | 0 | 0 | 0 | 0 | 0.12427 | 0.37444 | 0.37593 | 0.37729 | 0.37909 | 0.38104 | 0.38223 | 0.38293 | 0.38515 | 0.38793 | 0.38955 | 0.39104 | 0.39299 | 0.39512 | 0.3961 | 0.39114 | 0.39895 | 0.40262 | 0.40439 | 0.40601 | 0.40814 | 0.41045 | 0.41187 | 0.41271 | 0.41535 | 0.41863 | 0.42055 | 0.42232 | 0.42464 | 0.42716 | 0.42833 | 0.42305 | 0.43171 | 0.43606 | 0.43815 | 0.44008 | 0.4426 | 0.44534 | 0.44703 | 0.44804 | 0.45116 | 0.45504 | 0.45732 | 0.45943 | 0.46217 | 0.46515 | 0.46655 | 0.46091 | 0.47058 | 0.47571 | 0.31895 | 0
|  | Variable consumables | USD m |  | 134.8703 | 0 | 0 | 0 | 0 | 0 | 0.69861 | 2.1177 | 2.1324 | 2.1403 | 2.1691 | 2.2052 | 2.2024 | 2.1736 | 2.2216 | 2.2964 | 2.3124 | 2.3209 | 2.3521 | 2.3913 | 2.3719 | 2.3076 | 2.3757 | 2.4901 | 2.5074 | 2.5167 | 2.5505 | 2.593 | 2.5896 | 2.5557 | 2.6121 | 2.7001 | 2.7188 | 2.7288 | 2.7655 | 2.8116 | 2.7887 | 2.713 | 2.7931 | 2.9276 | 2.9479 | 2.9588 | 2.9985 | 3.0485 | 3.0444 | 3.0046 | 3.0709 | 3.1743 | 3.1962 | 3.208 | 3.251 | 3.3052 | 3.2783 | 3.1893 | 3.2834 | 3.4415 | 2.3179 | 0
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0.0425 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.085 | 0
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0.051875 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.10375 | 0
|  | Operating costs before pass-through items | USD m |  | 1128.16 | 0 | 0 | 0 | 0 | 0 | 5.7584 | 17.4575 | 17.6017 | 17.7072 | 17.9341 | 18.2048 | 18.2499 | 18.1457 | 18.4869 | 18.985 | 19.1423 | 19.2573 | 19.5046 | 19.7996 | 19.754 | 19.48 | 19.9133 | 20.6501 | 20.8216 | 20.947 | 21.2166 | 21.5382 | 21.592 | 21.4684 | 21.8737 | 22.4653 | 22.6523 | 22.789 | 23.0829 | 23.4334 | 23.3793 | 23.0547 | 23.5689 | 24.4441 | 24.6479 | 24.797 | 25.1173 | 25.4993 | 25.5634 | 25.4168 | 25.8983 | 26.6011 | 26.8233 | 26.9858 | 27.3351 | 27.7515 | 27.6875 | 27.3029 | 27.9129 | 28.9525 | 19.5076 | 0
|  | Gas purchases | USD m |  | 4890.5537 | 0 | 0 | 0 | 0 | 0 | 25.731 | 77.1852 | 78.4652 | 77.9499 | 79.7534 | 80.2545 | 80.9161 | 79.0424 | 81.5596 | 83.4446 | 84.8278 | 84.27 | 86.2191 | 86.7602 | 86.8774 | 83.6566 | 86.9508 | 90.2062 | 91.7008 | 91.0971 | 93.2035 | 93.7877 | 94.5595 | 92.3684 | 95.3087 | 97.5099 | 99.1248 | 98.4715 | 100.7477 | 101.3784 | 101.5138 | 97.7489 | 101.5966 | 105.3987 | 107.1434 | 106.4365 | 108.8959 | 109.5768 | 110.477 | 107.9154 | 111.3489 | 113.9189 | 115.8038 | 115.0389 | 117.6962 | 118.4312 | 118.5877 | 114.1878 | 118.6808 | 123.1204 | 83.7082 | 0
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5727.3299 | 0 | 0 | 0 | 0 | 0 | 30.3694 | 91.1628 | 92.4536 | 92.1123 | 93.9427 | 94.653 | 95.3701 | 93.5681 | 96.1334 | 98.2766 | 99.6712 | 99.2982 | 101.2757 | 102.0388 | 102.1964 | 99.015 | 102.378 | 105.9448 | 107.4514 | 107.0439 | 109.1803 | 110.0001 | 110.8343 | 108.7242 | 111.7183 | 114.2103 | 115.8379 | 115.3928 | 117.7007 | 118.5814 | 118.7623 | 115.0421 | 118.9669 | 123.1195 | 124.8776 | 124.3917 | 126.8847 | 127.8309 | 128.8012 | 126.3311 | 129.825 | 132.7222 | 134.6212 | 134.0908 | 136.7837 | 137.8003 | 138.0079 | 133.6587 | 138.2382 | 143.0722 | 96.9664 | 0
|  | VAT facility interest after the funding period | USD m |  | 0.12254 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10851 | 0.014027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7663 | 0 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Handback reserve contribution required | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
|  | Handback works at PPA expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
|  | Total operating costs | USD m |  | 6926.3797 | 0 | 0 | 0 | 0 | 0 | 36.1278 | 108.7287 | 110.0693 | 109.8195 | 111.8768 | 112.8577 | 113.62 | 114.2115 | 114.6203 | 117.2616 | 118.8135 | 118.5555 | 120.7803 | 121.8384 | 121.9504 | 130.3314 | 122.2913 | 126.5949 | 128.273 | 127.9909 | 130.3969 | 131.5382 | 132.4263 | 133.1652 | 133.592 | 136.6756 | 138.4902 | 138.1818 | 140.7836 | 142.0148 | 142.1417 | 152.1842 | 142.5357 | 147.5636 | 149.5255 | 149.1886 | 152.002 | 153.3302 | 154.3646 | 155.2857 | 155.7233 | 159.3233 | 161.4445 | 161.0767 | 164.1188 | 165.5517 | 165.6954 | 177.7278 | 166.1511 | 172.0247 | 135.5432 | 0
|  | EBITDA | USD m |  | 2617.8426 | 0 | 0 | 0 | 0 | 0 | 16.8849 | 50.6528 | 50.8681 | 51.0164 | 51.1105 | 51.1879 | 51.3525 | 49.075 | 51.6314 | 51.6317 | 51.7622 | 51.9092 | 52.0099 | 52.0934 | 52.3085 | 39.8347 | 52.65 | 52.5738 | 52.7149 | 52.8757 | 52.9835 | 53.0736 | 53.2687 | 50.5629 | 53.5993 | 53.5936 | 53.7462 | 53.9221 | 54.0375 | 54.1347 | 54.3915 | 39.665 | 54.7983 | 54.6977 | 54.8626 | 55.0551 | 55.1786 | 55.2835 | 55.5147 | 52.3 | 55.9068 | 55.893 | 56.0714 | 56.2819 | 56.4142 | 56.5273 | 56.8339 | 39.4276 | 57.3185 | 57.1873 | 19.1681 | 0
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.1077 | 38.9792 | 40.0121 | 39.3349 | 40.5217 | 40.1198 | 40.7899 | 39.9342 | 41.3333 | 41.3054 | 42.4083 | 41.6897 | 42.9589 | 42.5377 | 43.086 | 41.6167 | 43.4937 | 43.8184 | 44.997 | 44.2337 | 45.5918 | 45.1496 | 45.9136 | 44.9335 | 46.5393 | 46.5332 | 47.7936 | 46.9819 | 48.4362 | 47.9713 | 48.5934 | 46.9196 | 49.061 | 49.4661 | 50.8147 | 49.9509 | 51.509 | 51.0197 | 51.8932 | 50.7682 | 52.6152 | 52.6344 | 54.0785 | 53.1583 | 54.8286 | 54.3128 | 55.021 | 53.1087 | 55.5587 | 56.0573 | 0 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 18.9819 | 18.8768 | 19.5079 | 19.0638 | 19.8282 | 19.6275 | 20.0067 | 19.331 | 20.2773 | 20.4076 | 21.0898 | 20.6095 | 21.4357 | 21.2185 | 21.4807 | 20.4595 | 21.6176 | 22.0613 | 22.7985 | 22.2792 | 23.1721 | 22.9372 | 23.3801 | 22.5901 | 23.6955 | 23.8475 | 24.6443 | 24.0827 | 25.0478 | 24.7936 | 25.0996 | 23.906 | 25.2588 | 25.7769 | 26.6379 | 26.0307 | 27.0736 | 26.7987 | 27.3157 | 26.3924 | 27.6834 | 27.8606 | 28.791 | 28.1345 | 29.2615 | 28.9642 | 29.3211 | 27.9264 | 29.5063 | 30.111 | 0 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.2812 | 2.2789 | 2.3185 | 2.3091 | 2.3518 | 2.3476 | 2.3825 | 2.3683 | 2.4155 | 2.4183 | 2.4602 | 2.4503 | 2.4956 | 2.4911 | 2.5251 | 2.5041 | 2.557 | 2.5661 | 2.6106 | 2.6 | 2.6481 | 2.6433 | 2.6827 | 2.6667 | 2.7198 | 2.7229 | 2.7701 | 2.7589 | 2.8099 | 2.8048 | 2.8432 | 2.8195 | 2.8791 | 2.8893 | 2.9394 | 2.9275 | 2.9816 | 2.9762 | 3.0205 | 3.0026 | 3.0623 | 3.0658 | 3.1189 | 3.1063 | 3.1637 | 3.158 | 3.2011 | 3.1746 | 3.2416 | 3.253 | 0 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.6629 | 1.6719 | 1.7129 | 1.6926 | 1.745 | 1.7463 | 1.7649 | 1.725 | 1.7932 | 1.824 | 1.8686 | 1.8466 | 1.9037 | 1.9051 | 1.9125 | 1.8492 | 1.9298 | 1.9899 | 2.0386 | 2.0145 | 2.0769 | 2.0784 | 2.1005 | 2.053 | 2.1342 | 2.1709 | 2.224 | 2.1977 | 2.2658 | 2.2674 | 2.2762 | 2.2009 | 2.2968 | 2.3683 | 2.4263 | 2.3976 | 2.4718 | 2.4737 | 2.5 | 2.4434 | 2.5401 | 2.5837 | 2.6469 | 2.6157 | 2.6966 | 2.6986 | 2.7091 | 2.6194 | 2.7335 | 2.8187 | 0 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.1691 | 1.1744 | 1.2046 | 1.1944 | 1.2275 | 1.2218 | 1.2433 | 1.2336 | 1.2709 | 1.2714 | 1.3041 | 1.2932 | 1.3291 | 1.3231 | 1.3436 | 1.3268 | 1.3708 | 1.377 | 1.4125 | 1.4008 | 1.4397 | 1.4332 | 1.4586 | 1.4473 | 1.4912 | 1.492 | 1.5305 | 1.5179 | 1.5601 | 1.5532 | 1.5775 | 1.558 | 1.6097 | 1.6171 | 1.659 | 1.6454 | 1.6913 | 1.6838 | 1.7138 | 1.7006 | 1.7525 | 1.7534 | 1.7989 | 1.7842 | 1.834 | 1.8261 | 1.8548 | 1.8321 | 1.8929 | 1.9018 | 0 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 15.0127 | 14.9771 | 15.2682 | 15.0749 | 15.3692 | 15.1766 | 15.3924 | 15.2763 | 15.5764 | 15.3841 | 15.6856 | 15.4902 | 15.7948 | 15.5999 | 15.824 | 15.477 | 16.0186 | 15.8242 | 16.1368 | 15.9392 | 16.255 | 16.0574 | 16.2917 | 16.1764 | 16.4985 | 16.3 | 16.6246 | 16.4247 | 16.7526 | 16.5522 | 16.7969 | 16.4352 | 17.0166 | 16.8145 | 17.1522 | 16.9498 | 17.2908 | 17.0873 | 17.3433 | 17.2293 | 17.5769 | 17.3709 | 17.7228 | 17.5177 | 17.8728 | 17.666 | 17.9348 | 17.5562 | 18.1845 | 17.9728 | 0 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.0127 | -0.035591 | 0.29113 | -0.1933 | 0.29428 | -0.19255 | 0.21577 | -0.11612 | 0.30009 | -0.19226 | 0.30143 | -0.19536 | 0.30463 | -0.19497 | 0.22417 | -0.34699 | 0.5415 | -0.19436 | 0.31258 | -0.19756 | 0.31582 | -0.19759 | 0.23426 | -0.1153 | 0.32206 | -0.19847 | 0.32464 | -0.19991 | 0.32792 | -0.20042 | 0.24468 | -0.3617 | 0.58145 | -0.20214 | 0.3377 | -0.20242 | 0.34099 | -0.2035 | 0.25601 | -0.114 | 0.34763 | -0.20597 | 0.35184 | -0.2051 | 0.35512 | -0.20684 | 0.26888 | -0.37869 | 0.62831 | -0.21167 | -17.9728 | 0
|  | Release of spares inventory at expiry | USD m |  | 5.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.885 | 0

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| Tax depreciation (straight line from COD) | USD m |  | 916.0992 | 0 | 0 | 0 | 0 | 0 | 8.2449 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 23.8186 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 14.963 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.61073 | 0
| Depreciation of holiday months (deemed deferred) | USD m |  | 247.3468 | 0 | 0 | 0 | 0 | 0 | 8.2449 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 24.7347 | 16.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 668.7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3288 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 21.9864 | 14.963 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.9161 | 0.61073 | 0
| Shareholder loan interest accrued | USD m |  | 345.254 | 0 | 0 | 0 | 0 | 0 | 3.5046 | 10.7392 | 10.5325 | 10.7851 | 10.6525 | 10.908 | 10.843 | 11.0628 | 10.932 | 11.1173 | 10.9996 | 11.28 | 11.1709 | 11.6801 | 11.8581 | 12.3303 | 12.4314 | 12.9283 | 12.9929 | 13.4826 | 13.5023 | 13.9459 | 13.9634 | 14.2335 | 13.5193 | 12.7653 | 11.7284 | 10.0569 | 7.9457 | 6.0167 | 3.7921 | 1.5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 0.66033 | 0.77182 | 0.81723 | 0.87069 | 0.92953 | 0.99925 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 337.5347 | 0 | 0 | 0 | 0 | 0 | 2.3142 | 8.2887 | 8.6075 | 9.3905 | 9.9018 | 10.8998 | 10.843 | 11.0628 | 10.932 | 11.1173 | 10.9996 | 11.28 | 11.1709 | 11.6801 | 11.8581 | 12.3303 | 12.4314 | 12.9283 | 12.9929 | 13.4826 | 13.5023 | 13.9459 | 13.9634 | 14.2335 | 13.5193 | 12.7653 | 11.7284 | 10.0569 | 7.9457 | 6.0167 | 3.7921 | 1.5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 350.357 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8768 | 23.0529 | 22.705 | 21.8283 | 21.4174 | 20.5737 | 20.0179 | 19.0447 | 18.4804 | 18.0686 | 17.4936 | 16.4888 | 15.6233 | 14.3907 | 13.3874 | 12.0187 | 10.8781 | 9.7081 | 8.4601 | 6.9703 | 5.6275 | 4.1422 | 2.7252 | 1.7384 | 1.0919 | 0.54671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Taxable income before losses and deferred depreciation | USD m |  | 1055.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2359 | 1.1492 | 2.3638 | 2.8037 | 4.0733 | -7.8694 | 6.2134 | 6.781 | 8.0276 | 8.9466 | 10.5246 | 11.5138 | 13.1767 | 11.6178 | 16.3552 | 17.75 | 19.4847 | 21.8788 | 24.1054 | 26.1316 | 28.613 | 16.1253 | 32.8119 | 32.7113 | 32.8762 | 33.0687 | 33.1922 | 33.2971 | 33.5283 | 30.3136 | 40.9438 | 54.9769 | 55.1553 | 55.3658 | 55.4981 | 55.6112 | 55.9178 | 38.5115 | 56.4024 | 56.2712 | 18.5574 | 0
| Tax losses used | USD m |  | 7.8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2134 | 1.6559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 247.3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2359 | 1.1492 | 2.3638 | 2.8037 | 4.0733 | 0 | 0 | 5.1251 | 8.0276 | 8.9466 | 10.5246 | 11.5138 | 13.1767 | 11.6178 | 16.3552 | 17.75 | 19.4847 | 21.8788 | 24.1054 | 26.1316 | 28.613 | 13.4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 8.2449 | 32.9796 | 57.7143 | 82.4489 | 107.1836 | 131.9183 | 156.653 | 181.3876 | 206.1223 | 230.857 | 247.1109 | 245.9617 | 243.598 | 240.7943 | 236.7211 | 236.7211 | 236.7211 | 231.596 | 223.5684 | 214.6218 | 204.0973 | 192.5835 | 179.4068 | 167.789 | 151.4338 | 133.6838 | 114.1992 | 92.3203 | 68.2149 | 42.0833 | 13.4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8694 | 1.6559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 807.666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6551 | 32.8119 | 32.7113 | 32.8762 | 33.0687 | 33.1922 | 33.2971 | 33.5283 | 30.3136 | 40.9438 | 54.9769 | 55.1553 | 55.3658 | 55.4981 | 55.6112 | 55.9178 | 38.5115 | 56.4024 | 56.2712 | 18.5574 | 0
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| Corporate income tax | USD m |  | 242.2998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79653 | 9.8436 | 9.8134 | 9.8629 | 9.9206 | 9.9577 | 9.9891 | 10.0585 | 9.0941 | 12.2831 | 16.4931 | 16.5466 | 16.6097 | 16.6494 | 16.6834 | 16.7753 | 11.5535 | 16.9207 | 16.8814 | 5.5672 | 0
| Minimum turnover tax | USD m |  | 15.6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11805 | 0.35549 | 0.35727 | 0.3592 | 0.36009 | 0.35558 | 0.36268 | 0.36602 | 0.36763 | 0.3691 | 0.37104 | 0.37314 | 0.37443 | 0.37519 | 0.37759 | 0.38057 | 0.38232 | 0.38393 | 0.38603 | 0.38832 | 0.38939 | 0.3846 | 0.39247 | 0.39641 | 0.39832 | 0.40007 | 0.40237 | 0.40486 | 0.4064 | 0.40731 | 0.41014 | 0.41367 | 0.41575 | 0.41766 | 0.42015 | 0.42287 | 0.42414 | 0.41901 | 0.4278 | 0.43246 | 0.28996 | 0
| Tax paid = max(CIT, MTT) | USD m |  | 249.8529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11805 | 0.35549 | 0.35727 | 0.3592 | 0.36009 | 0.35558 | 0.36268 | 0.36602 | 0.36763 | 0.3691 | 0.37104 | 0.37314 | 0.37443 | 0.37519 | 0.37759 | 0.38057 | 0.38232 | 0.38393 | 0.38603 | 0.38832 | 0.38939 | 0.79653 | 9.8436 | 9.8134 | 9.8629 | 9.9206 | 9.9577 | 9.9891 | 10.0585 | 9.0941 | 12.2831 | 16.4931 | 16.5466 | 16.6097 | 16.6494 | 16.6834 | 16.7753 | 11.5535 | 16.9207 | 16.8814 | 5.5672 | 0
| Thin-cap disallowance | USD m |  | 7.7194 | 0 | 0 | 0 | 0 | 0 | 1.1904 | 2.4505 | 1.925 | 1.3946 | 0.75073 | 0.0081508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.74057
|  | Gearing used in the closed-form gross-up | fraction | 0.74057
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97589
|  | First installment share of remaining profile | fraction | 0.02446
|  | DSRA coefficient per USD of E balance | factor | 0.047154
|  | DSRA coefficient per USD of A balance | factor | 0.058909
|  | DSRA coefficient per USD of B balance | factor | 0.057632
|  | DSRA coefficient per USD of C balance | factor | 0.07051
|  | DSRA coefficient per USD of standby balance | factor | 0.064102
|  | DSRA constant (swap net payment) | USD m | -0.53616
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0054193 | 0.0052445 | 0.0054193 | 0.0052445 | 0.0054193 | 0.0056617 | 0.0051138 | 0.0056617 | 0.005479 | 0.0056617 | 0.005479 | 0.0057963 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0058681 | 0.0054895 | 0.0058681 | 0.0056788 | 0.0058681 | 0.0056788 | 0.005904 | 0.005904 | 0.0057135 | 0.005904 | 0.0057135 | 0.005904 | 0.0059309 | 0.0053569 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059488 | 0.0053731 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 115.7048 | 1.6542 | 2.3482 | 3.7852 | 5.8609 | 8.4427 | 11.4413 | 14.6535 | 17.9951 | 21.3045 | 24.468 | 27.373 | 29.963 | 32.1446 | 33.8193 | 34.9868 | 35.5592 | 36.8035 | 35.006 | 33.8204 | 32.1628 | 29.975 | 27.4146 | 24.448 | 21.2723 | 17.9862 | 14.6169 | 11.4174 | 8.3952 | 5.7767 | 3.7968 | 2.2488 | 54.6422 | -0.55416 | 0.012761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 87.8044 | 89.3531 | 91.4437 | 94.6218 | 99.3963 | 106.1647 | 115.1959 | 126.7349 | 140.8369 | 157.5165 | 176.639 | 198.072 | 221.5506 | 246.7459 | 273.333 | 300.8725 | 328.9823 | 358.1595 | 385.9956 | 413.1253 | 439.0495 | 463.4623 | 485.9681 | 506.3779 | 524.4559 | 540.0445 | 553.2006 | 563.9107 | 572.4365 | 579.0195 | 583.9101 | 587.8599 | 631.5116 | 633.5173 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824 | 635.8824
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0093225 | 0.0098258 | 0.010348 | 0.010854 | 0.01138 | 0.011909 | 0.012389 | 0.012922 | 0.01344 | 0.013976 | 0.014498 | 0.01504 | 0.015584 | 0.016113 | 0.016661 | 0.017193 | 0.017745 | 0.018301 | 0.018822 | 0.019381 | 0.019925 | 0.020488 | 0.021036 | 0.021604 | 0.022174 | 0.022729 | 0.023303 | 0.023862 | 0.024441 | 0.025023 | 0.02555 | 0.026136 | 0.026705 | 0.060826 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525 | 0.061525
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 936.4325
|  | Senior debt (committed tranches) | USD m | 693.4962
|  | Debt share of monthly funding | fraction | 0.74057
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 28.9603 | 29.5663 | 30.3401 | 31.4359 | 33.0158 | 35.195 | 38.0392 | 41.6506 | 46.0267 | 51.1813 | 57.0645 | 63.6467 | 70.8432 | 78.5503 | 86.6804 | 95.0918 | 103.6799 | 112.589 | 121.0863 | 129.3824 | 137.3123 | 144.7944 | 151.7 | 157.9826 | 163.5662 | 168.3985 | 172.5068 | 175.8767 | 178.5971 | 180.7354 | 182.3508 | 183.7004 | 196.9559 | 207.1431 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 21.2375 | 21.682 | 22.2494 | 23.053 | 24.2116 | 25.8097 | 27.8954 | 30.5438 | 33.7529 | 37.533 | 41.8473 | 46.6743 | 51.9517 | 57.6035 | 63.5656 | 69.734 | 76.0319 | 82.5653 | 88.7966 | 94.8804 | 100.6957 | 106.1826 | 111.2466 | 115.8539 | 119.9485 | 123.4922 | 126.505 | 128.9762 | 130.9712 | 132.5393 | 133.7239 | 134.7136 | 144.4343 | 151.905 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 9.6534 | 9.8554 | 10.1134 | 10.4786 | 11.0053 | 11.7317 | 12.6797 | 13.8835 | 15.3422 | 17.0604 | 19.0215 | 21.2156 | 23.6144 | 26.1834 | 28.8935 | 31.6973 | 34.56 | 37.5297 | 40.3621 | 43.1275 | 45.7708 | 48.2648 | 50.5667 | 52.6609 | 54.5221 | 56.1328 | 57.5023 | 58.6256 | 59.5324 | 60.2451 | 60.7836 | 61.2335 | 65.652 | 69.0477 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 36.683 | 37.4506 | 38.4308 | 39.8188 | 41.82 | 44.5804 | 48.183 | 52.7575 | 58.3004 | 64.8297 | 72.2817 | 80.6192 | 89.7347 | 99.497 | 109.7952 | 120.4496 | 131.3279 | 142.6128 | 153.376 | 163.8844 | 173.9289 | 183.4063 | 192.1533 | 200.1112 | 207.1839 | 213.3047 | 218.5086 | 222.7771 | 226.223 | 228.9316 | 230.9777 | 232.6872 | 249.4774 | 262.3813 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14
|  | ECA-covered tranche: interest | USD m |  | 13.5752 | 0 | 0.093397 | 0.09853 | 0.097847 | 0.10476 | 0.1177 | 0.11333 | 0.13561 | 0.14369 | 0.16409 | 0.17658 | 0.21081 | 0.23512 | 0.25326 | 0.29018 | 0.30988 | 0.35129 | 0.39015 | 0.39634 | 0.45565 | 0.47117 | 0.51671 | 0.52729 | 0.57608 | 0.59994 | 0.60111 | 0.63949 | 0.63396 | 0.66789 | 0.68284 | 0.62414 | 0.69719 | 0.67969 | 0.75303 | 0.76643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 15.2059 | 0 | 0.1092 | 0.1152 | 0.1144 | 0.12248 | 0.13427 | 0.12928 | 0.1547 | 0.16392 | 0.18718 | 0.20143 | 0.23747 | 0.26486 | 0.2853 | 0.32688 | 0.34908 | 0.39572 | 0.4367 | 0.44363 | 0.51001 | 0.52738 | 0.57836 | 0.5902 | 0.64279 | 0.66941 | 0.67071 | 0.71354 | 0.70737 | 0.74523 | 0.76014 | 0.6948 | 0.77612 | 0.75664 | 0.83828 | 0.8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 6.6523 | 0 | 0.047624 | 0.050241 | 0.049893 | 0.053418 | 0.058661 | 0.056482 | 0.067586 | 0.071616 | 0.081778 | 0.088003 | 0.10385 | 0.11583 | 0.12476 | 0.14295 | 0.15265 | 0.17305 | 0.19106 | 0.19409 | 0.22314 | 0.23073 | 0.25304 | 0.25822 | 0.28129 | 0.29294 | 0.29351 | 0.31225 | 0.30955 | 0.32612 | 0.3327 | 0.3041 | 0.3397 | 0.33117 | 0.3669 | 0.37343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 31.1546 | 0 | 0.22485 | 0.23721 | 0.23557 | 0.25221 | 0.27569 | 0.26545 | 0.31764 | 0.33657 | 0.38433 | 0.41359 | 0.48688 | 0.54304 | 0.58494 | 0.67019 | 0.7157 | 0.81132 | 0.89465 | 0.90885 | 1.0449 | 1.0804 | 1.1849 | 1.2091 | 1.3164 | 1.3709 | 1.3736 | 1.4613 | 1.4486 | 1.5262 | 1.5563 | 1.4225 | 1.589 | 1.5491 | 1.7162 | 1.7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 4.0254 | 0 | 0.031206 | 0.032921 | 0.032692 | 0.035002 | 0.036762 | 0.035396 | 0.042355 | 0.04488 | 0.051248 | 0.05515 | 0.063539 | 0.070868 | 0.076336 | 0.087462 | 0.093401 | 0.10588 | 0.11544 | 0.11727 | 0.13482 | 0.13941 | 0.15289 | 0.15602 | 0.16891 | 0.17591 | 0.17625 | 0.1875 | 0.18588 | 0.19583 | 0.19886 | 0.18177 | 0.20304 | 0.19794 | 0.2193 | 0.2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | -0.78015 | 0 | 0.025634 | 0.021014 | 0.026832 | 0.022316 | 0.0043689 | 0.024928 | 0.0050195 | 0.01346 | 0.0060535 | 0.016486 | -0.010638 | -0.011849 | 0.0010133 | -0.014591 | 0.0012374 | -0.017633 | -0.036666 | 0.0063394 | -0.042776 | -0.019205 | -0.048472 | -0.021479 | -0.066261 | -0.068991 | -0.037536 | -0.073518 | -0.039578 | -0.076769 | -0.089192 | 0.023114 | -0.091062 | -0.053325 | -0.098323 | -0.060108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 10.2221 | 0.60207 | 0.50155 | 0.51651 | 0.49768 | 0.5111 | 0.50653 | 0.45181 | 0.49199 | 0.46601 | 0.46888 | 0.43932 | 0.43693 | 0.41789 | 0.38425 | 0.37476 | 0.3399 | 0.32689 | 0.30203 | 0.25843 | 0.25166 | 0.22031 | 0.20471 | 0.17715 | 0.16307 | 0.14489 | 0.12458 | 0.11474 | 0.099538 | 0.093103 | 0.085231 | 0.071393 | 0.074368 | 0.068189 | 0.032102 | 0.0025365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.8165 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 10.9018 | 10.9018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.74375 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 40.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 127.2086 | 2.662 | 3.3988 | 4.8133 | 6.9399 | 9.5723 | 12.493 | 15.8633 | 19.2218 | 22.642 | 25.8421 | 28.9125 | 31.6106 | 33.8535 | 35.7117 | 36.9474 | 37.7233 | 39.1336 | 37.3246 | 36.4406 | 34.8322 | 32.8656 | 30.3326 | 27.5965 | 24.5263 | 21.2259 | 18.0457 | 14.8023 | 11.9495 | 9.3928 | 7.0955 | 5.9282 | 58.2249 | 44.7479 | 3.9783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 693.4962 | 596.9619 | 594.9418 | 592.3626 | 588.7099 | 583.4435 | 576.1794 | 566.6989 | 554.6607 | 540.074 | 522.8917 | 503.281 | 481.3403 | 457.3522 | 431.6619 | 404.5615 | 376.5234 | 347.8965 | 318.1994 | 289.875 | 262.2215 | 235.7885 | 210.848 | 187.8297 | 166.8876 | 148.2755 | 132.1679 | 118.4736 | 107.2406 | 98.1726 | 91.0447 | 85.6602 | 81.1615 | 36.9766 | 3.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior tranche drawdown (pro rata) | USD m |  | 693.4962 | 96.5342 | 2.0201 | 2.5792 | 3.6527 | 5.2664 | 7.2641 | 9.4805 | 12.0381 | 14.5868 | 17.1823 | 19.6107 | 21.9407 | 23.9882 | 25.6902 | 27.1004 | 28.0381 | 28.6269 | 29.6971 | 28.3244 | 27.6535 | 26.433 | 24.9405 | 23.0184 | 20.942 | 18.6121 | 16.1076 | 13.6943 | 11.233 | 9.0681 | 7.1279 | 5.3845 | 4.4987 | 44.1849 | 33.9576 | 3.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 22.5733 | 3.1422 | 0.065754 | 0.083954 | 0.11889 | 0.17142 | 0.23645 | 0.30859 | 0.39184 | 0.4748 | 0.55928 | 0.63833 | 0.71417 | 0.78081 | 0.83622 | 0.88212 | 0.91264 | 0.93181 | 0.96664 | 0.92196 | 0.90012 | 0.86039 | 0.81181 | 0.74925 | 0.68166 | 0.60583 | 0.5243 | 0.44575 | 0.36563 | 0.29517 | 0.23201 | 0.17527 | 0.14643 | 1.4382 | 1.1053 | 0.098269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 936.4325 | 130.3508 | 2.7278 | 3.4828 | 4.9322 | 7.1113 | 9.8088 | 12.8016 | 16.2552 | 19.6966 | 23.2013 | 26.4804 | 29.6267 | 32.3914 | 34.6897 | 36.5938 | 37.8601 | 38.6551 | 40.1002 | 38.2466 | 37.3407 | 35.6926 | 33.6774 | 31.0818 | 28.2782 | 25.1321 | 21.7502 | 18.4915 | 15.1679 | 12.2447 | 9.6248 | 7.2708 | 6.0746 | 59.6631 | 45.8532 | 4.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 936.4325 | 130.3508 | 2.7278 | 3.4828 | 4.9322 | 7.1113 | 9.8088 | 12.8016 | 16.2552 | 19.6966 | 23.2013 | 26.4804 | 29.6267 | 32.3914 | 34.6897 | 36.5938 | 37.8601 | 38.6551 | 40.1002 | 38.2466 | 37.3407 | 35.6926 | 33.6774 | 31.0818 | 28.2782 | 25.1321 | 21.7502 | 18.4915 | 15.1679 | 12.2447 | 9.6248 | 7.2708 | 6.0746 | 59.6631 | 45.8532 | 4.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3061e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility drawdown (75%) | USD m |  | 4.7296e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7296e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 1.5765e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5765e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 208.0488 | 28.9603 | 0.60603 | 0.77377 | 1.0958 | 1.5799 | 2.1792 | 2.8442 | 3.6114 | 4.376 | 5.1547 | 5.8832 | 6.5822 | 7.1964 | 7.7071 | 8.1301 | 8.4114 | 8.5881 | 8.9091 | 8.4973 | 8.296 | 7.9299 | 7.4822 | 6.9055 | 6.2826 | 5.5836 | 4.8323 | 4.1083 | 3.3699 | 2.7204 | 2.1384 | 1.6154 | 1.3496 | 13.2555 | 10.1873 | 0.90571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 152.5692 | 21.2375 | 0.44442 | 0.56743 | 0.80359 | 1.1586 | 1.5981 | 2.0857 | 2.6484 | 3.2091 | 3.7801 | 4.3143 | 4.827 | 5.2774 | 5.6519 | 5.9621 | 6.1684 | 6.2979 | 6.5334 | 6.2314 | 6.0838 | 5.8153 | 5.4869 | 5.064 | 4.6072 | 4.0947 | 3.5437 | 3.0127 | 2.4713 | 1.995 | 1.5681 | 1.1846 | 0.98971 | 9.7207 | 7.4707 | 0.66419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 69.3496 | 9.6534 | 0.20201 | 0.25792 | 0.36527 | 0.52664 | 0.72641 | 0.94805 | 1.2038 | 1.4587 | 1.7182 | 1.9611 | 2.1941 | 2.3988 | 2.569 | 2.71 | 2.8038 | 2.8627 | 2.9697 | 2.8324 | 2.7653 | 2.6433 | 2.4941 | 2.3018 | 2.0942 | 1.8612 | 1.6108 | 1.3694 | 1.1233 | 0.90681 | 0.71279 | 0.53845 | 0.44987 | 4.4185 | 3.3958 | 0.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 263.5285 | 36.683 | 0.76764 | 0.98011 | 1.388 | 2.0012 | 2.7604 | 3.6026 | 4.5745 | 5.543 | 6.5293 | 7.4521 | 8.3375 | 9.1155 | 9.7623 | 10.2982 | 10.6545 | 10.8782 | 11.2849 | 10.7633 | 10.5083 | 10.0445 | 9.4774 | 8.747 | 7.958 | 7.0726 | 6.1209 | 5.2038 | 4.2685 | 3.4459 | 2.7086 | 2.0461 | 1.7095 | 16.7902 | 12.9039 | 1.1472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 28.9603 | 29.5663 | 30.3401 | 31.4359 | 33.0158 | 35.195 | 38.0392 | 41.6506 | 46.0267 | 51.1813 | 57.0645 | 63.6467 | 70.8432 | 78.5503 | 86.6804 | 95.0918 | 103.6799 | 112.589 | 121.0863 | 129.3824 | 137.3123 | 144.7944 | 151.7 | 157.9826 | 163.5662 | 168.3985 | 172.5068 | 175.8767 | 178.5971 | 180.7354 | 182.3508 | 183.7004 | 196.9559 | 207.1431 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488 | 208.0488
|  | ABDB A-loan: closing balance | USD m |  |  | 21.2375 | 21.682 | 22.2494 | 23.053 | 24.2116 | 25.8097 | 27.8954 | 30.5438 | 33.7529 | 37.533 | 41.8473 | 46.6743 | 51.9517 | 57.6035 | 63.5656 | 69.734 | 76.0319 | 82.5653 | 88.7966 | 94.8804 | 100.6957 | 106.1826 | 111.2466 | 115.8539 | 119.9485 | 123.4922 | 126.505 | 128.9762 | 130.9712 | 132.5393 | 133.7239 | 134.7136 | 144.4343 | 151.905 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692 | 152.5692
|  | ABDB B-loan: closing balance | USD m |  |  | 9.6534 | 9.8554 | 10.1134 | 10.4786 | 11.0053 | 11.7317 | 12.6797 | 13.8835 | 15.3422 | 17.0604 | 19.0215 | 21.2156 | 23.6144 | 26.1834 | 28.8935 | 31.6973 | 34.56 | 37.5297 | 40.3621 | 43.1275 | 45.7708 | 48.2648 | 50.5667 | 52.6609 | 54.5221 | 56.1328 | 57.5023 | 58.6256 | 59.5324 | 60.2451 | 60.7836 | 61.2335 | 65.652 | 69.0477 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496 | 69.3496
|  | Commercial tranche: closing balance | USD m |  |  | 36.683 | 37.4506 | 38.4308 | 39.8188 | 41.82 | 44.5804 | 48.183 | 52.7575 | 58.3004 | 64.8297 | 72.2817 | 80.6192 | 89.7347 | 99.497 | 109.7952 | 120.4496 | 131.3279 | 142.6128 | 153.376 | 163.8844 | 173.9289 | 183.4063 | 192.1533 | 200.1112 | 207.1839 | 213.3047 | 218.5086 | 222.7771 | 226.223 | 228.9316 | 230.9777 | 232.6872 | 249.4774 | 262.3813 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285 | 263.5285
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14 | 4.7296e-14
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 242.9363 | 33.8166 | 0.70766 | 0.90353 | 1.2796 | 1.8449 | 2.5447 | 3.3211 | 4.217 | 5.1098 | 6.0191 | 6.8697 | 7.686 | 8.4032 | 8.9995 | 9.4934 | 9.8219 | 10.0282 | 10.4031 | 9.9222 | 9.6872 | 9.2596 | 8.7368 | 8.0635 | 7.3361 | 6.52 | 5.6426 | 4.7972 | 3.935 | 3.1766 | 2.4969 | 1.8862 | 1.5759 | 15.4782 | 11.8956 | 1.0576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 228.7363 | 19.6166 | 0.70766 | 0.90353 | 1.2796 | 1.8449 | 2.5447 | 3.3211 | 4.217 | 5.1098 | 6.0191 | 6.8697 | 7.686 | 8.4032 | 8.9995 | 9.4934 | 9.8219 | 10.0282 | 10.4031 | 9.9222 | 9.6872 | 9.2596 | 8.7368 | 8.0635 | 7.3361 | 6.52 | 5.6426 | 4.7972 | 3.935 | 3.1766 | 2.4969 | 1.8862 | 1.5759 | 15.4782 | 11.8956 | 1.0576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 48.5873 | 6.7633 | 0.14153 | 0.18071 | 0.25591 | 0.36897 | 0.50893 | 0.66422 | 0.84341 | 1.022 | 1.2038 | 1.3739 | 1.5372 | 1.6806 | 1.7999 | 1.8987 | 1.9644 | 2.0056 | 2.0806 | 1.9844 | 1.9374 | 1.8519 | 1.7474 | 1.6127 | 1.4672 | 1.304 | 1.1285 | 0.95944 | 0.787 | 0.63532 | 0.49939 | 0.37725 | 0.31518 | 3.0956 | 2.3791 | 0.21152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 194.349 | 27.0533 | 0.56613 | 0.72282 | 1.0236 | 1.4759 | 2.0357 | 2.6569 | 3.3736 | 4.0879 | 4.8152 | 5.4958 | 6.1488 | 6.7226 | 7.1996 | 7.5948 | 7.8576 | 8.0226 | 8.3225 | 7.9378 | 7.7498 | 7.4077 | 6.9895 | 6.4508 | 5.8689 | 5.216 | 4.5141 | 3.8378 | 3.148 | 2.5413 | 1.9975 | 1.509 | 1.2607 | 12.3826 | 9.5165 | 0.84607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 26.3918 | 0 | 0.21124 | 0.22455 | 0.2247 | 0.24227 | 0.25613 | 0.24805 | 0.29806 | 0.31711 | 0.36323 | 0.39194 | 0.45251 | 0.50578 | 0.5459 | 0.62659 | 0.67057 | 0.76174 | 0.83261 | 0.848 | 0.97737 | 1.014 | 1.1157 | 1.143 | 1.2424 | 1.2998 | 1.3087 | 1.3993 | 1.3951 | 1.4782 | 1.5107 | 1.39 | 1.5624 | 1.534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 27.0533 | 27.8306 | 28.778 | 30.0263 | 31.7445 | 34.0364 | 36.9413 | 40.613 | 45.018 | 50.1964 | 56.0842 | 62.6855 | 69.9138 | 77.6593 | 85.8806 | 94.4088 | 103.1931 | 112.3482 | 121.1339 | 129.8611 | 138.2828 | 146.388 | 153.9818 | 161.0931 | 167.6088 | 173.4316 | 178.6687 | 183.2118 | 187.2313 | 190.7395 | 193.6386 | 196.4617 | 210.3783 | 219.8948 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408 | 220.7408
|  | Total debt drawdowns (incl. standby) | USD m |  | 693.4962 | 96.5342 | 2.0201 | 2.5792 | 3.6527 | 5.2664 | 7.2641 | 9.4805 | 12.0381 | 14.5868 | 17.1823 | 19.6107 | 21.9407 | 23.9882 | 25.6902 | 27.1004 | 28.0381 | 28.6269 | 29.6971 | 28.3244 | 27.6535 | 26.433 | 24.9405 | 23.0184 | 20.942 | 18.6121 | 16.1076 | 13.6943 | 11.233 | 9.0681 | 7.1279 | 5.3845 | 4.4987 | 44.1849 | 33.9576 | 3.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 116.7664 | 14.691 | 1.1649 | 1.2226 | 1.2395 | 1.3405 | 1.4395 | 1.4516 | 1.6809 | 1.7913 | 1.9861 | 2.0953 | 2.318 | 2.4992 | 2.6344 | 2.8584 | 2.9777 | 3.1912 | 3.379 | 3.3642 | 3.6052 | 3.6373 | 3.7852 | 3.7731 | 3.893 | 3.9168 | 3.8449 | 3.9173 | 3.818 | 3.8755 | 3.854 | 3.5781 | 3.8145 | 5.0384 | 5.0132 | 4.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 936.4325
|  | Capitalized cost (book and tax) | USD m | 916.0992

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01978 | 0.020815 | 0.021927 | 0.022093 | 0.02254 | 0.022323 | 0.022693 | 0.022424 | 0.022796 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847
|  | ABDB A-loan: rate per period | factor |  |  | 0.031536 | 0.032379 | 0.033682 | 0.033721 | 0.034296 | 0.033887 | 0.034449 | 0.033988 | 0.034551 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602
|  | ABDB B-loan: rate per period | factor |  |  | 0.030258 | 0.031122 | 0.032404 | 0.032457 | 0.033018 | 0.03263 | 0.033171 | 0.032731 | 0.033273 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324
|  | Commercial tranche: rate per period | factor |  |  | 0.037595 | 0.03849 | 0.03998 | 0.039995 | 0.040662 | 0.040166 | 0.040832 | 0.040278 | 0.040946 | 0.040334 | 0.041002 | 0.040557 | 0.041002 | 0.040334 | 0.041002 | 0.043127 | 0.043842 | 0.043127 | 0.043842 | 0.043365 | 0.043842 | 0.043127 | 0.043842 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037387 | 0.038824 | 0.038833 | 0.039478 | 0.038995 | 0.039642 | 0.039103 | 0.039751 | 0.039156 | 0.039805 | 0.039373 | 0.039805 | 0.039156 | 0.039805 | 0.040832 | 0.041509 | 0.040832 | 0.041509 | 0.041058 | 0.041509 | 0.040832 | 0.041509 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97554 | 0.95004 | 0.92329 | 0.89575 | 0.86695 | 0.83722 | 0.80555 | 0.77292 | 0.74119 | 0.70944 | 0.67638 | 0.64236 | 0.60671 | 0.56988 | 0.52966 | 0.48772 | 0.4443 | 0.40007 | 0.35363 | 0.30582 | 0.2557 | 0.20396 | 0.14909 | 0.093089 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.026135 | 0.028158 | 0.029828 | 0.032159 | 0.034287 | 0.037824 | 0.040513 | 0.041052 | 0.042829 | 0.046599 | 0.050303 | 0.055498 | 0.060706 | 0.07057 | 0.079192 | 0.08902 | 0.099542 | 0.1161 | 0.1352 | 0.16389 | 0.20235 | 0.269 | 0.37563 | 0.49632 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 208.0488 | 202.9599 | 197.6555 | 192.0899 | 186.3603 | 180.3671 | 174.1828 | 167.5944 | 160.8047 | 154.2034 | 147.599 | 140.721 | 133.6423 | 126.2254 | 118.5628 | 110.1958 | 101.4692 | 92.4364 | 83.2351 | 73.5718 | 63.6248 | 53.1976 | 42.4329 | 31.0186 | 19.3671 | 9.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 71.8751 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7213 | 4.5511 | 4.5057 | 4.3171 | 4.2577 | 4.076 | 3.9795 | 3.7665 | 3.6739 | 3.4656 | 3.3721 | 3.1626 | 3.0533 | 2.8525 | 2.7088 | 2.4766 | 2.3182 | 2.0774 | 1.9016 | 1.6535 | 1.4536 | 1.2022 | 0.96945 | 0.69712 | 0.44247 | 0.21923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 208.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 5.089 | 5.3043 | 5.5656 | 5.7296 | 5.9932 | 6.1843 | 6.5883 | 6.7897 | 6.6013 | 6.6044 | 6.878 | 7.0787 | 7.4169 | 7.6626 | 8.367 | 8.7266 | 9.0328 | 9.2013 | 9.6633 | 9.947 | 10.4272 | 10.7647 | 11.4143 | 11.6515 | 9.6124 | 9.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 208.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 5.089 | 5.3043 | 5.5656 | 5.7296 | 5.9932 | 6.1843 | 6.5883 | 6.7897 | 6.6013 | 6.6044 | 6.878 | 7.0787 | 7.4169 | 7.6626 | 8.367 | 8.7266 | 9.0328 | 9.2013 | 9.6633 | 9.947 | 10.4272 | 10.7647 | 11.4143 | 11.6515 | 9.6124 | 9.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 202.9599 | 197.6555 | 192.0899 | 186.3603 | 180.3671 | 174.1828 | 167.5944 | 160.8047 | 154.2034 | 147.599 | 140.721 | 133.6423 | 126.2254 | 118.5628 | 110.1958 | 101.4692 | 92.4364 | 83.2351 | 73.5718 | 63.6248 | 53.1976 | 42.4329 | 31.0186 | 19.3671 | 9.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 208.0488 | 202.9599 | 197.6555 | 192.0899 | 186.3603 | 180.3671 | 174.1828 | 167.5944 | 160.8047 | 154.2034 | 147.599 | 140.721 | 133.6423 | 126.2254 | 118.5628 | 110.1958 | 101.4692 | 92.4364 | 83.2351 | 73.5718 | 63.6248 | 53.1976 | 42.4329 | 31.0186 | 19.3671 | 9.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 152.5692 | 148.8372 | 144.9474 | 140.8659 | 136.6642 | 132.2692 | 127.734 | 122.9026 | 117.9234 | 113.0825 | 108.2393 | 103.1954 | 98.0044 | 92.5653 | 86.9461 | 80.8103 | 74.4107 | 67.7867 | 61.0391 | 53.9527 | 46.6582 | 39.0116 | 31.1174 | 22.747 | 14.2025 | 7.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 79.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2558 | 5.0586 | 5.0081 | 4.7948 | 4.7289 | 4.5271 | 4.4199 | 4.1834 | 4.0804 | 3.8491 | 3.7453 | 3.5126 | 3.3912 | 3.1682 | 3.0085 | 2.7506 | 2.5748 | 2.3073 | 2.1121 | 1.8364 | 1.6145 | 1.3352 | 1.0767 | 0.77426 | 0.49144 | 0.24349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 152.5692 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7319 | 3.8898 | 4.0815 | 4.2017 | 4.395 | 4.5352 | 4.8315 | 4.9791 | 4.8409 | 4.8432 | 5.0439 | 5.1911 | 5.4391 | 5.6192 | 6.1358 | 6.3995 | 6.624 | 6.7477 | 7.0864 | 7.2945 | 7.6466 | 7.8941 | 8.3705 | 8.5444 | 7.0491 | 7.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 152.5692 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7319 | 3.8898 | 4.0815 | 4.2017 | 4.395 | 4.5352 | 4.8315 | 4.9791 | 4.8409 | 4.8432 | 5.0439 | 5.1911 | 5.4391 | 5.6192 | 6.1358 | 6.3995 | 6.624 | 6.7477 | 7.0864 | 7.2945 | 7.6466 | 7.8941 | 8.3705 | 8.5444 | 7.0491 | 7.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 148.8372 | 144.9474 | 140.8659 | 136.6642 | 132.2692 | 127.734 | 122.9026 | 117.9234 | 113.0825 | 108.2393 | 103.1954 | 98.0044 | 92.5653 | 86.9461 | 80.8103 | 74.4107 | 67.7867 | 61.0391 | 53.9527 | 46.6582 | 39.0116 | 31.1174 | 22.747 | 14.2025 | 7.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 152.5692 | 148.8372 | 144.9474 | 140.8659 | 136.6642 | 132.2692 | 127.734 | 122.9026 | 117.9234 | 113.0825 | 108.2393 | 103.1954 | 98.0044 | 92.5653 | 86.9461 | 80.8103 | 74.4107 | 67.7867 | 61.0391 | 53.9527 | 46.6582 | 39.0116 | 31.1174 | 22.747 | 14.2025 | 7.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 69.3496 | 67.6533 | 65.8852 | 64.03 | 62.1201 | 60.1224 | 58.0609 | 55.8648 | 53.6016 | 51.4011 | 49.1997 | 46.907 | 44.5474 | 42.0751 | 39.5209 | 36.7319 | 33.8231 | 30.8121 | 27.745 | 24.5239 | 21.2083 | 17.7325 | 14.1443 | 10.3395 | 6.4557 | 3.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 34.9539 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3004 | 2.2143 | 2.1922 | 2.099 | 2.0701 | 1.9818 | 1.9348 | 1.8313 | 1.7862 | 1.685 | 1.6396 | 1.5377 | 1.4845 | 1.3869 | 1.317 | 1.2041 | 1.1271 | 1.0101 | 0.92459 | 0.80392 | 0.70675 | 0.5845 | 0.47135 | 0.33894 | 0.21513 | 0.10659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 69.3496 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6963 | 1.7681 | 1.8552 | 1.9099 | 1.9977 | 2.0614 | 2.1961 | 2.2632 | 2.2004 | 2.2015 | 2.2927 | 2.3596 | 2.4723 | 2.5542 | 2.789 | 2.9089 | 3.0109 | 3.0671 | 3.2211 | 3.3157 | 3.4757 | 3.5882 | 3.8048 | 3.8838 | 3.2041 | 3.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 69.3496 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6963 | 1.7681 | 1.8552 | 1.9099 | 1.9977 | 2.0614 | 2.1961 | 2.2632 | 2.2004 | 2.2015 | 2.2927 | 2.3596 | 2.4723 | 2.5542 | 2.789 | 2.9089 | 3.0109 | 3.0671 | 3.2211 | 3.3157 | 3.4757 | 3.5882 | 3.8048 | 3.8838 | 3.2041 | 3.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 67.6533 | 65.8852 | 64.03 | 62.1201 | 60.1224 | 58.0609 | 55.8648 | 53.6016 | 51.4011 | 49.1997 | 46.907 | 44.5474 | 42.0751 | 39.5209 | 36.7319 | 33.8231 | 30.8121 | 27.745 | 24.5239 | 21.2083 | 17.7325 | 14.1443 | 10.3395 | 6.4557 | 3.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 69.3496 | 67.6533 | 65.8852 | 64.03 | 62.1201 | 60.1224 | 58.0609 | 55.8648 | 53.6016 | 51.4011 | 49.1997 | 46.907 | 44.5474 | 42.0751 | 39.5209 | 36.7319 | 33.8231 | 30.8121 | 27.745 | 24.5239 | 21.2083 | 17.7325 | 14.1443 | 10.3395 | 6.4557 | 3.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 263.5285 | 257.0825 | 250.3637 | 243.3139 | 236.0564 | 228.465 | 220.6315 | 212.2863 | 203.6859 | 195.3243 | 186.9587 | 178.2466 | 164.8738 | 150.4823 | 136.628 | 121.0703 | 105.1236 | 88.6824 | 72.5911 | 55.7647 | 39.3139 | 22.4949 | 6.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 153.1626 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7604 | 10.3548 | 10.2513 | 9.8138 | 9.6789 | 9.2658 | 9.0464 | 8.5623 | 8.3516 | 8.4238 | 8.1966 | 7.6873 | 7.2284 | 6.5257 | 5.99 | 5.2214 | 4.6088 | 4.0723 | 3.3887 | 2.5607 | 1.8352 | 1.0387 | 0.29943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 178.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 6.446 | 6.7188 | 7.0498 | 7.2575 | 7.5914 | 7.8335 | 8.3452 | 8.6003 | 8.3616 | 8.3656 | 8.7121 | 8.9664 | 9.1502 | 9.1351 | 9.6419 | 9.5878 | 9.3581 | 8.8277 | 8.4275 | 7.5395 | 6.443 | 4.5519 | 1.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 178.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 6.446 | 6.7188 | 7.0498 | 7.2575 | 7.5914 | 7.8335 | 8.3452 | 8.6003 | 8.3616 | 8.3656 | 8.7121 | 8.9664 | 9.1502 | 9.1351 | 9.6419 | 9.5878 | 9.3581 | 8.8277 | 8.4275 | 7.5395 | 6.443 | 4.5519 | 1.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 257.0825 | 250.3637 | 243.3139 | 236.0564 | 228.465 | 220.6315 | 212.2863 | 203.6859 | 195.3243 | 186.9587 | 178.2466 | 169.2803 | 155.7236 | 141.3472 | 126.9861 | 111.4825 | 95.7655 | 79.8548 | 64.1636 | 48.2252 | 32.8709 | 17.943 | 4.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 84.8922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 4.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 263.5285 | 257.0825 | 250.3637 | 243.3139 | 236.0564 | 228.465 | 220.6315 | 212.2863 | 203.6859 | 195.3243 | 186.9587 | 178.2466 | 164.8738 | 150.4823 | 136.628 | 121.0703 | 105.1236 | 88.6824 | 72.5911 | 55.7647 | 39.3139 | 22.4949 | 6.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7296e-14 | 4.6139e-14 | 4.4933e-14 | 4.3668e-14 | 4.2365e-14 | 4.1003e-14 | 3.9597e-14 | 3.8099e-14 | 3.6556e-14 | 3.5055e-14 | 3.3554e-14 | 3.199e-14 | 3.0381e-14 | 2.8695e-14 | 2.6953e-14 | 2.5051e-14 | 2.3067e-14 | 2.1013e-14 | 1.8922e-14 | 1.6725e-14 | 1.4464e-14 | 1.2093e-14 | 9.6462e-15 | 7.0514e-15 | 4.4027e-15 | 2.2175e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 2.9232e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8749e-15 | 1.8041e-15 | 1.7861e-15 | 1.7099e-15 | 1.6864e-15 | 1.6144e-15 | 1.5762e-15 | 1.4918e-15 | 1.4551e-15 | 1.4314e-15 | 1.3928e-15 | 1.3062e-15 | 1.2611e-15 | 1.1781e-15 | 1.1188e-15 | 1.0229e-15 | 9.5748e-16 | 8.9324e-16 | 8.1766e-16 | 7.1095e-16 | 6.2502e-16 | 5.1691e-16 | 4.1684e-16 | 2.9974e-16 | 1.9025e-16 | 9.4263e-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 4.7296e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1569e-15 | 1.2058e-15 | 1.2652e-15 | 1.3025e-15 | 1.3624e-15 | 1.4059e-15 | 1.4977e-15 | 1.5435e-15 | 1.5007e-15 | 1.5014e-15 | 1.5636e-15 | 1.6092e-15 | 1.6861e-15 | 1.7419e-15 | 1.9021e-15 | 1.9838e-15 | 2.0534e-15 | 2.0917e-15 | 2.1967e-15 | 2.2612e-15 | 2.3704e-15 | 2.4471e-15 | 2.5948e-15 | 2.6487e-15 | 2.1852e-15 | 2.2175e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 4.7296e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1569e-15 | 1.2058e-15 | 1.2652e-15 | 1.3025e-15 | 1.3624e-15 | 1.4059e-15 | 1.4977e-15 | 1.5435e-15 | 1.5007e-15 | 1.5014e-15 | 1.5636e-15 | 1.6092e-15 | 1.6861e-15 | 1.7419e-15 | 1.9021e-15 | 1.9838e-15 | 2.0534e-15 | 2.0917e-15 | 2.1967e-15 | 2.2612e-15 | 2.3704e-15 | 2.4471e-15 | 2.5948e-15 | 2.6487e-15 | 2.1852e-15 | 2.2175e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.6139e-14 | 4.4933e-14 | 4.3668e-14 | 4.2365e-14 | 4.1003e-14 | 3.9597e-14 | 3.8099e-14 | 3.6556e-14 | 3.5055e-14 | 3.3554e-14 | 3.199e-14 | 3.0381e-14 | 2.8695e-14 | 2.6953e-14 | 2.5051e-14 | 2.3067e-14 | 2.1013e-14 | 1.8922e-14 | 1.6725e-14 | 1.4464e-14 | 1.2093e-14 | 9.6462e-15 | 7.0514e-15 | 4.4027e-15 | 2.2175e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 4.7296e-14 | 4.6139e-14 | 4.4933e-14 | 4.3668e-14 | 4.2365e-14 | 4.1003e-14 | 3.9597e-14 | 3.8099e-14 | 3.6556e-14 | 3.5055e-14 | 3.3554e-14 | 3.199e-14 | 3.0381e-14 | 2.8695e-14 | 2.6953e-14 | 2.5051e-14 | 2.3067e-14 | 2.1013e-14 | 1.8922e-14 | 1.6725e-14 | 1.4464e-14 | 1.2093e-14 | 9.6462e-15 | 7.0514e-15 | 4.4027e-15 | 2.2175e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 0
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 0
|  | Bond face amount | USD m | 0
|  | Swap unwind receipt | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | -8.3342 | 0 | 0 | 0 | 0 | 0 | 0 | -0.53616 | -0.44548 | -0.55857 | -0.44514 | -0.54985 | -0.45603 | -0.51392 | -0.38837 | -0.47444 | -0.35734 | -0.43548 | -0.3261 | -0.3943 | -0.31914 | -0.34981 | -0.25536 | -0.29938 | -0.21421 | -0.24558 | -0.17049 | -0.18772 | -0.1345 | -0.1252 | -0.071881 | -0.057142 | -0.022605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 18.8508 | 0 | 0 | 0 | 0 | 0 | 0 | 1.375 | 1.3195 | 1.3063 | 1.2488 | 1.2316 | 1.1791 | 1.1512 | 1.0896 | 1.0627 | 1.0025 | 0.97546 | 0.91484 | 0.86023 | 0.77661 | 0.71286 | 0.62139 | 0.54849 | 0.45516 | 0.37875 | 0.28621 | 0.20512 | 0.11609 | 0.033467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 339.8403 | 0 | 0 | 0 | 0 | 0 | 0 | 23.038 | 22.1789 | 21.9573 | 21.0246 | 20.7356 | 19.8506 | 19.3807 | 18.3436 | 17.8921 | 17.4235 | 16.9537 | 15.9001 | 15.1574 | 13.9333 | 13.0243 | 11.6527 | 10.629 | 9.4671 | 8.327 | 6.8546 | 5.6101 | 4.1606 | 2.817 | 1.8103 | 1.149 | 0.56931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 350.357 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8768 | 23.0529 | 22.705 | 21.8283 | 21.4174 | 20.5737 | 20.0179 | 19.0447 | 18.4804 | 18.0686 | 17.4936 | 16.4888 | 15.6233 | 14.3907 | 13.3874 | 12.0187 | 10.8781 | 9.7081 | 8.4601 | 6.9703 | 5.6275 | 4.1422 | 2.7252 | 1.7384 | 1.0919 | 0.54671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 608.604 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9632 | 17.6811 | 18.5521 | 19.0988 | 19.9773 | 20.6144 | 21.9612 | 22.6325 | 22.0043 | 22.0146 | 22.9266 | 23.5957 | 24.4784 | 24.9712 | 26.9337 | 27.6228 | 28.0258 | 27.8438 | 28.3983 | 28.0966 | 27.9926 | 26.799 | 25.3149 | 24.0798 | 19.8655 | 20.1598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 958.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 40.84 | 40.7341 | 41.2571 | 40.9271 | 41.3947 | 41.1881 | 41.979 | 41.6772 | 40.4847 | 40.0832 | 40.4203 | 40.0845 | 40.1017 | 39.3619 | 40.3211 | 39.6415 | 38.9039 | 37.5519 | 36.8584 | 35.0669 | 33.6201 | 30.9412 | 28.0402 | 25.8182 | 20.9574 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 693.4962 | 676.5329 | 658.8518 | 640.2997 | 621.201 | 601.2236 | 580.6092 | 558.6481 | 536.0156 | 514.0113 | 491.9967 | 469.07 | 441.0679 | 411.3481 | 381.6578 | 348.8083 | 314.8266 | 279.7177 | 244.6103 | 207.8131 | 170.8053 | 132.4366 | 94.109 | 64.1051 | 40.0254 | 20.1598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 693.4962 | 676.5329 | 658.8518 | 640.2997 | 621.201 | 601.2236 | 580.6092 | 558.6481 | 536.0156 | 514.0113 | 491.9967 | 469.07 | 441.0679 | 411.3481 | 381.6578 | 348.8083 | 314.8266 | 279.7177 | 244.6103 | 207.8131 | 170.8053 | 132.4366 | 94.109 | 64.1051 | 40.0254 | 20.1598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 263.5285 | 257.0825 | 250.3637 | 243.3139 | 236.0564 | 228.465 | 220.6315 | 212.2863 | 203.6859 | 195.3243 | 186.9587 | 178.2466 | 169.2803 | 155.7236 | 141.3472 | 126.9861 | 111.4825 | 95.7655 | 79.8548 | 64.1636 | 48.2252 | 32.8709 | 17.943 | 4.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.8103 | 9.8555 | 10.0713 | 10.0467 | 10.2509 | 10.2603 | 10.5678 | 10.5563 | 10.2751 | 10.07 | 10.2501 | 10.2413 | 10.4702 | 10.5151 | 11.0758 | 11.2032 | 11.351 | 11.2788 | 11.5649 | 11.6005 | 11.8808 | 11.9669 | 12.3837 | 12.3486 | 10.0548 | 9.974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 8.9877 | 8.9485 | 9.0896 | 8.9965 | 9.1239 | 9.0622 | 9.2513 | 9.1625 | 8.9214 | 8.6923 | 8.7892 | 8.7036 | 8.8302 | 8.7874 | 9.1443 | 9.1501 | 9.1988 | 9.055 | 9.1985 | 9.1309 | 9.2611 | 9.2294 | 9.4472 | 9.3187 | 7.5405 | 7.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 3.9967 | 3.9825 | 4.0474 | 4.0089 | 4.0678 | 4.0432 | 4.131 | 4.0946 | 3.9867 | 3.8864 | 3.9322 | 3.8972 | 3.9568 | 3.9411 | 4.106 | 4.113 | 4.1381 | 4.0772 | 4.1457 | 4.1196 | 4.1825 | 4.1727 | 4.2761 | 4.2228 | 3.4193 | 3.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 17.2064 | 17.0736 | 17.3011 | 17.0713 | 17.2703 | 17.0993 | 17.3917 | 17.1627 | 16.7132 | 16.7893 | 16.9088 | 16.6536 | 16.8163 | 16.2063 | 16.1718 | 15.5328 | 14.8118 | 13.9303 | 12.9986 | 11.6214 | 10.1547 | 8.1693 | 5.6642 | 1.9766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 3.0317e-15 | 3.01e-15 | 3.0513e-15 | 3.0124e-15 | 3.0488e-15 | 3.0203e-15 | 3.0739e-15 | 3.0353e-15 | 2.9558e-15 | 2.9327e-15 | 2.9563e-15 | 2.9154e-15 | 2.9471e-15 | 2.9201e-15 | 3.0208e-15 | 3.0067e-15 | 3.0109e-15 | 2.985e-15 | 3.0144e-15 | 2.9722e-15 | 2.9954e-15 | 2.964e-15 | 3.0116e-15 | 2.9485e-15 | 2.3754e-15 | 2.3118e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 40.84 | 40.7341 | 41.2571 | 40.9271 | 41.3947 | 41.1881 | 41.979 | 41.6772 | 40.4847 | 40.0832 | 40.4203 | 40.0845 | 40.5624 | 39.9344 | 40.8856 | 40.3955 | 39.7819 | 38.6185 | 38.0787 | 36.6312 | 35.543 | 33.5735 | 31.7396 | 27.8189 | 20.9574 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03443 | 0.034075 | 0.034461 | 0.034091 | 0.034477 | 0.03422 | 0.034477 | 0.034091 | 0.034477 | 0.035152 | 0.035556 | 0.035152 | 0.035556 | 0.035287 | 0.035556 | 0.035152 | 0.035556 | 0.036214 | 0.036635 | 0.036214 | 0.036635 | 0.036354 | 0.036635 | 0.036214 | 0.036635 | 0.036214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 861.6978 | 841.0936 | 819.5933 | 797.0442 | 773.8161 | 749.5311 | 724.4594 | 697.7482 | 670.2036 | 643.4593 | 616.7083 | 588.8598 | 560.1843 | 530.146 | 499.1018 | 465.1855 | 429.792 | 393.1671 | 355.8659 | 316.6944 | 276.3618 | 234.0839 | 190.4293 | 144.1301 | 96.4499 | 48.9198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.2425
|  | Debt capacity at the 1.35x target | USD m | 638.2947
|  | Debt at the 75% gearing cap (closed form) | USD m | 702.3243
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40.4591 | 40.3694 | 40.8787 | 40.562 | 41.016 | 40.8199 | 41.5992 | 41.3116 | 40.1203 | 39.7331 | 40.0601 | 39.7373 | 40.205 | 40.0401 | 41.5781 | 41.6452 | 41.7746 | 41.4789 | 42.0177 | 41.6897 | 42.1737 | 41.9821 | 42.8763 | 42.5738 | 41.0961 | 40.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 693.4962 | 676.9139 | 659.6103 | 641.4628 | 622.7688 | 603.2242 | 583.0464 | 561.5491 | 539.3812 | 517.8573 | 496.3281 | 473.9156 | 450.8374 | 426.6626 | 401.6781 | 374.3822 | 345.8974 | 316.4217 | 286.4016 | 254.8763 | 222.4166 | 188.3912 | 153.2579 | 115.9962 | 77.6231 | 39.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.5823 | 17.3035 | 18.1475 | 18.694 | 19.5446 | 20.1778 | 21.4972 | 22.1679 | 21.5239 | 21.5293 | 22.4125 | 23.0782 | 24.1749 | 24.9845 | 27.2959 | 28.4848 | 29.4757 | 30.0201 | 31.5253 | 32.4598 | 34.0254 | 35.1333 | 37.2616 | 38.3731 | 38.2524 | 39.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0 | 0 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 0 | 0 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0 | 0 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 0 | 0 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0 | 0 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 0 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.83254 | 1.2488 | 1.6651 | 2.0813 | 2.4976 | 0 | 0 | 1.9727 | 3.9455 | 5.9182 | 7.891 | 9.8637 | 11.8365 | 0 | 0 | 0.49543 | 0.99086 | 1.4863 | 1.9817 | 2.4771 | 2.9726 | 0 | 0 | 2.3479 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 3.5378 | 0 | 0 | 2.7944 | 5.5888 | 8.3831 | 11.1775 | 13.9719 | 16.7663 | 0 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 40.84 | 40.84 | 40.7341 | 41.2571 | 40.9271 | 41.3947 | 41.1881 | 41.979 | 41.6772 | 40.4847 | 40.0832 | 40.4203 | 40.0845 | 40.5624 | 39.9344 | 40.8856 | 40.3955 | 39.7819 | 38.6185 | 38.0787 | 36.6312 | 35.543 | 33.5735 | 31.7396 | 27.8189 | 20.9574 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 3.5477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52302 | 0 | 0.46762 | 0 | 0.79096 | 0 | 0 | 0 | 0.33704 | 0 | 0.4779 | 0 | 0.95119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 44.3877 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10596 | 0 | 0.32999 | 0 | 0.20662 | 0 | 0.30182 | 1.1925 | 0.40145 | 0 | 0.33574 | 0 | 0.62802 | 0 | 0.49009 | 0.61362 | 1.1634 | 0.53986 | 1.4475 | 1.0882 | 1.9695 | 1.8339 | 3.9207 | 6.8615 | 0.2509 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 40.84 | 40.7341 | 41.2571 | 40.9271 | 41.3947 | 41.1881 | 41.979 | 41.6772 | 40.4847 | 40.0832 | 40.4203 | 40.0845 | 40.5624 | 39.9344 | 40.8856 | 40.3955 | 39.7819 | 38.6185 | 38.0787 | 36.6312 | 35.543 | 33.5735 | 31.7396 | 27.8189 | 20.9574 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
| Handback reserve release at expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.9961 | 3.5137 | 5.0479 | 6.5988 | 8.1668 | 9.7518 | 11.3543 | 12.9742 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2373.8748 | 0 | 0 | 0 | 0 | 0 | 1.8722 | 50.2721 | 50.1607 | 50.7935 | 50.4 | 50.9641 | 50.7204 | 51.6887 | 51.3314 | 49.8512 | 49.37 | 49.7763 | 49.3753 | 49.9564 | 49.7515 | 51.6625 | 51.7458 | 51.9067 | 51.5393 | 52.2087 | 51.8012 | 52.4026 | 52.1645 | 53.2756 | 52.8997 | 51.0636 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.6106 | 46.8577 | 43.276 | 36.8116 | 36.3786 | 37.0829 | 36.6152 | 37.2564 | 36.9953 | 45.0191 | 39.7695 | 40.5176 | 37.4587 | 0
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8722 | 52.1443 | 50.1607 | 50.7935 | 50.4 | 50.9641 | 50.7204 | 51.6887 | 51.3314 | 49.8512 | 49.37 | 49.7763 | 49.3753 | 49.9564 | 49.7515 | 51.6625 | 51.7458 | 51.9067 | 51.5393 | 52.2087 | 51.8012 | 52.4026 | 52.1645 | 53.2756 | 52.8997 | 51.0636 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.6106 | 46.8577 | 43.276 | 36.8116 | 36.3786 | 37.0829 | 36.6152 | 37.2564 | 36.9953 | 45.0191 | 39.7695 | 40.5176 | 37.4587 | 0
|  | Senior debt service and fees due | USD m |  | 958.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 40.84 | 40.7341 | 41.2571 | 40.9271 | 41.3947 | 41.1881 | 41.979 | 41.6772 | 40.4847 | 40.0832 | 40.4203 | 40.0845 | 40.1017 | 39.3619 | 40.3211 | 39.6415 | 38.9039 | 37.5519 | 36.8584 | 35.0669 | 33.6201 | 30.9412 | 28.0402 | 25.8182 | 20.9574 | 20.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8722 | 11.3043 | 9.4266 | 9.5364 | 9.4729 | 9.5694 | 9.5323 | 9.7096 | 9.6541 | 9.3665 | 9.2868 | 9.3561 | 9.2908 | 9.8547 | 10.3896 | 11.3415 | 12.1043 | 13.0028 | 13.9874 | 15.3503 | 16.7344 | 18.7825 | 21.2233 | 25.2354 | 27.0815 | 30.1062 | 29.9848 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.6106 | 46.8577 | 43.276 | 36.8116 | 36.3786 | 37.0829 | 36.6152 | 37.2564 | 36.9953 | 45.0191 | 39.7695 | 40.5176 | 37.4587 | 0
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8722 | 11.4103 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 8.8129 | 10.4827 | 9.4384 | 11.8316 | 12.7179 | 14.1662 | 14.5273 | 16.7978 | 17.8226 | 20.752 | 23.0572 | 29.1561 | 33.943 | 30.3571 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.6106 | 46.8577 | 43.276 | 36.8116 | 36.3786 | 37.0829 | 36.6152 | 37.2564 | 36.9953 | 45.0191 | 39.7695 | 40.5176 | 37.4587 | 0
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8722 | 11.4103 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 8.8129 | 10.4827 | 9.4384 | 11.8316 | 12.7179 | 14.1662 | 14.5273 | 16.7978 | 17.8226 | 20.752 | 23.0572 | 29.1561 | 33.943 | 30.3571 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 55.3999 | 0
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.231 | 1.2314 | 1.2311 | 1.2315 | 1.2312 | 1.2314 | 1.2313 | 1.2316 | 1.2314 | 1.2317 | 1.2315 | 1.2318 | 1.2457 | 1.2639 | 1.2813 | 1.3053 | 1.3342 | 1.3725 | 1.4165 | 1.4772 | 1.5587 | 1.6859 | 1.9 | 2.0489 | 2.4365 | 2.4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.231 | 1.2312 | 1.2313 | 1.2313 | 1.2313 | 1.2313 | 1.2314 | 1.2315 | 1.2315 | 1.2315 | 1.2316 | 1.2316 | 1.2388 | 1.2548 | 1.2727 | 1.2932 | 1.3197 | 1.353 | 1.3943 | 1.4461 | 1.5171 | 1.6197 | 1.7877 | 1.9714 | 2.2226 | 2.4423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 84.8922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 4.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1370.8617 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4103 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 24.4672 | 33.943 | 30.3571 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 55.3999 | 0
|  | Share capital contributed | USD m | 48.5873
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 220.7408 | 224.2455 | 223.5744 | 225.2033 | 226.122 | 227.7692 | 228.9011 | 231.0028 | 232.0541 | 232.1394 | 233.4887 | 235.5385 | 237.1268 | 243.8913 | 250.33 | 257.4689 | 263.8834 | 269.9559 | 275.8011 | 281.5303 | 286.614 | 291.205 | 294.7749 | 297.2098 | 286.9761 | 266.5525 | 248.9607 | 209.9978 | 168.6645 | 125.6345 | 80.0523 | 32.4349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 268.114 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7392 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 14.2335 | 13.5193 | 12.7653 | 11.7284 | 10.0569 | 7.9457 | 6.0167 | 3.7921 | 1.5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 297.8809 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2337 | 20.4236 | 17.5918 | 38.9629 | 41.3333 | 43.03 | 45.5822 | 47.6175 | 32.4349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 224.2455 | 223.5744 | 225.2033 | 226.122 | 227.7692 | 228.9011 | 231.0028 | 232.0541 | 232.1394 | 233.4887 | 235.5385 | 237.1268 | 243.8913 | 250.33 | 257.4689 | 263.8834 | 269.9559 | 275.8011 | 281.5303 | 286.614 | 291.205 | 294.7749 | 297.2098 | 286.9761 | 266.5525 | 248.9607 | 209.9978 | 168.6645 | 125.6345 | 80.0523 | 32.4349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.1052 | 12.3165 | 16.7738 | 21.4748 | 27.2791 | 33.3162 | 40.4266 | 45.5955 | 54.4248 | 63.6334 | 71.1146 | 74.1286 | 77.9911 | 82.1595 | 87.2158 | 81.5559 | 89.9717 | 97.4143 | 105.231 | 113.6896 | 123.2509 | 133.5024 | 144.9168 | 155.2391 | 168.8752 | 183.4847 | 199.3068 | 216.8031 | 235.8559 | 256.3248 | 278.5296 | 292.3824 | 298.5865 | 279.6762 | 260.7579 | 242.3986 | 223.451 | 205.0338 | 186.1605 | 165.8294 | 146.7822 | 131.3235 | 122.4707 | 114.215 | 105.3646 | 97.0782 | 88.3825 | 67.7811 | 51.6973 | 40.7891 | 6.8126 | 0
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3294 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 6.8126 | 0
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.5873 | 0
|  | Liquidation distribution at PPA expiry | USD m |  | 48.5873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.5873 | 0
|  | Dividends | USD m |  | 804.8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3294 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 55.3999 | 0
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.1052 | 12.3165 | 16.7738 | 21.4748 | 27.2791 | 33.3162 | 40.4266 | 45.5955 | 54.4248 | 63.6334 | 71.1146 | 74.1286 | 77.9911 | 82.1595 | 87.2158 | 81.5559 | 89.9717 | 97.4143 | 105.231 | 113.6896 | 123.2509 | 133.5024 | 144.9168 | 155.2391 | 168.8752 | 183.4847 | 199.3068 | 216.8031 | 235.8559 | 256.3248 | 278.5296 | 273.0531 | 254.2132 | 235.1794 | 216.6855 | 197.6514 | 179.1607 | 160.1255 | 142.0449 | 120.4729 | 105.0238 | 96.0462 | 87.6431 | 78.7001 | 70.3344 | 61.4242 | 53.0072 | 24.3997 | 13.5834 | 1.9452 | -48.5873 | -48.5873
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1370.8617 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4103 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 24.4672 | 33.943 | 30.3571 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 55.3999 | 0

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 916.0992 | 0 | 0 | 0 | 0 | 0 | 6.1073 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 18.322 | 12.2147 | 0
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 695.611 | 0 | 0 | 0 | 0 | 0 | 3.5046 | 34.616 | 33.5854 | 33.4901 | 32.4808 | 32.3254 | 31.4167 | 31.0807 | 29.9767 | 29.5977 | 29.0682 | 28.7737 | 27.6598 | 27.3033 | 26.2488 | 25.7177 | 24.4502 | 23.8064 | 22.701 | 21.9428 | 20.4726 | 19.5734 | 18.1056 | 16.9587 | 15.2578 | 13.8572 | 12.2751 | 10.0569 | 7.9457 | 6.0167 | 3.7921 | 1.5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 916.0992 | 916.0992 | 916.0992 | 916.0992 | 916.0992 | 907.8543 | 883.1196 | 858.385 | 833.6503 | 808.9156 | 784.1809 | 759.4463 | 734.7116 | 709.9769 | 685.2422 | 661.4236 | 639.4373 | 617.4509 | 595.4645 | 573.4781 | 551.4917 | 529.5053 | 507.519 | 485.5326 | 463.5462 | 441.5598 | 419.5734 | 397.5871 | 375.6007 | 353.6143 | 331.6279 | 309.6415 | 287.6552 | 265.6688 | 243.6824 | 221.696 | 199.7096 | 177.7232 | 155.7369 | 133.7505 | 111.7641 | 89.7777 | 67.7913 | 45.805 | 23.8186 | 8.8556 | 7.9395 | 7.0234 | 6.1073 | 5.1912 | 4.2751 | 3.359 | 2.4429 | 1.5268 | 0.61073 | 0 | 0
|  | Book value of plant (from COD) | USD m |  |  | 916.0992 | 916.0992 | 916.0992 | 916.0992 | 916.0992 | 909.9919 | 891.6699 | 873.3479 | 855.0259 | 836.704 | 818.382 | 800.06 | 781.738 | 763.416 | 745.094 | 726.772 | 708.4501 | 690.1281 | 671.8061 | 653.4841 | 635.1621 | 616.8401 | 598.5182 | 580.1962 | 561.8742 | 543.5522 | 525.2302 | 506.9082 | 488.5863 | 470.2643 | 451.9423 | 433.6203 | 415.2983 | 396.9763 | 378.6543 | 360.3324 | 342.0104 | 323.6884 | 305.3664 | 287.0444 | 268.7224 | 250.4005 | 232.0785 | 213.7565 | 195.4345 | 177.1125 | 158.7905 | 140.4685 | 122.1466 | 103.8246 | 85.5026 | 67.1806 | 48.8586 | 30.5366 | 12.2147 | 0 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | -1.8322 | -7.3288 | -12.8254 | -18.322 | -23.8186 | -29.3152 | -34.8118 | -40.3084 | -45.805 | -51.3016 | -54.5287 | -53.0847 | -51.2762 | -49.3358 | -47.0145 | -45.9152 | -44.8159 | -42.179 | -38.6715 | -34.8882 | -30.6315 | -26.078 | -21.0257 | -16.441 | -10.4352 | -4.0108 | 2.9339 | 10.5969 | 18.9278 | 27.8666 | 37.5498 | 42.6902 | 43.7895 | 44.8889 | 45.9882 | 47.0875 | 48.1868 | 49.2861 | 50.3855 | 51.4848 | 50.4771 | 45.2553 | 40.0335 | 34.8118 | 29.59 | 24.3682 | 19.1465 | 13.9247 | 8.7029 | 3.4812 | 0 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | -1.8322 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -5.4966 | -3.2272 | 1.4441 | 1.8084 | 1.9404 | 2.3213 | 1.0993 | 1.0993 | 2.6368 | 3.5076 | 3.7833 | 4.2567 | 4.5535 | 5.0523 | 4.5847 | 6.0059 | 6.4243 | 6.9447 | 7.663 | 8.3309 | 8.9388 | 9.6832 | 5.1404 | 1.0993 | 1.0993 | 1.0993 | 1.0993 | 1.0993 | 1.0993 | 1.0993 | 1.0993 | -1.0077 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -5.2218 | -3.4812 | 0
|  | Net income | USD m |  | 756.2796 | 0 | 0 | 0 | 0 | 0 | 9.1052 | 3.2114 | 4.4573 | 4.701 | 5.8043 | 6.0371 | 7.1104 | 5.1689 | 8.8293 | 9.2086 | 7.4812 | 3.014 | 3.8624 | 4.1684 | 5.0563 | -5.6599 | 8.4158 | 7.4425 | 7.8167 | 8.4586 | 9.5613 | 10.2516 | 11.4143 | 10.3223 | 13.6361 | 14.6095 | 15.822 | 17.4963 | 19.0528 | 20.4689 | 22.2048 | 13.8528 | 25.5334 | 25.463 | 25.5784 | 25.7132 | 25.7997 | 25.8731 | 26.0349 | 23.7846 | 26.3094 | 26.2997 | 26.4246 | 26.5719 | 26.6645 | 26.7437 | 26.9583 | 14.774 | 27.2976 | 27.2057 | 4.8674 | 0
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 149.5076 | 259.626 | 473.0059 | 695.0759 | 824.2641 | 909.9919 | 891.6699 | 873.3479 | 855.0259 | 836.704 | 818.382 | 800.06 | 781.738 | 763.416 | 745.094 | 726.772 | 708.4501 | 690.1281 | 671.8061 | 653.4841 | 635.1621 | 616.8401 | 598.5182 | 580.1962 | 561.8742 | 543.5522 | 525.2302 | 506.9082 | 488.5863 | 470.2643 | 451.9423 | 433.6203 | 415.2983 | 396.9763 | 378.6543 | 360.3324 | 342.0104 | 323.6884 | 305.3664 | 287.0444 | 268.7224 | 250.4005 | 232.0785 | 213.7565 | 195.4345 | 177.1125 | 158.7905 | 140.4685 | 122.1466 | 103.8246 | 85.5026 | 67.1806 | 48.8586 | 30.5366 | 12.2147 | 0 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 42.7123 | 41.1503 | 42.0896 | 42.1759 | 43.0598 | 43.2694 | 44.4767 | 41.6772 | 40.4847 | 42.056 | 44.3658 | 46.0028 | 48.4534 | 49.7981 | 52.7221 | 40.3955 | 39.7819 | 39.114 | 39.0695 | 38.1175 | 37.5247 | 36.0506 | 34.7122 | 27.8189 | 20.9574 | 23.0544 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 4.0328 | 1.9961 | 3.5137 | 7.8422 | 12.1876 | 16.5499 | 20.9293 | 25.3261 | 29.7405 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.1077 | 38.9792 | 40.0121 | 39.3349 | 40.5217 | 40.1198 | 40.7899 | 39.9342 | 41.3333 | 41.3054 | 42.4083 | 41.6897 | 42.9589 | 42.5377 | 43.086 | 41.6167 | 43.4937 | 43.8184 | 44.997 | 44.2337 | 45.5918 | 45.1496 | 45.9136 | 44.9335 | 46.5393 | 46.5332 | 47.7936 | 46.9819 | 48.4362 | 47.9713 | 48.5934 | 46.9196 | 49.061 | 49.4661 | 50.8147 | 49.9509 | 51.509 | 51.0197 | 51.8932 | 50.7682 | 52.6152 | 52.6344 | 54.0785 | 53.1583 | 54.8286 | 54.3128 | 55.021 | 53.1087 | 55.5587 | 56.0573 | 0 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 5.885 | 0 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.8322 | 7.3288 | 12.8254 | 18.322 | 23.8186 | 29.3152 | 34.8118 | 40.3084 | 45.805 | 51.3016 | 54.5287 | 53.0847 | 51.2762 | 49.3358 | 47.0145 | 45.9152 | 44.8159 | 42.179 | 38.6715 | 34.8882 | 30.6315 | 26.078 | 21.0257 | 16.441 | 10.4352 | 4.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 149.5076 | 259.626 | 473.0059 | 695.0759 | 824.2641 | 999.5291 | 985.0132 | 974.16 | 960.7437 | 949.989 | 936.9714 | 926.0233 | 909.5428 | 896.924 | 885.642 | 873.9599 | 855.1122 | 838.7016 | 819.3627 | 802.1917 | 768.9745 | 750.8166 | 729.5146 | 708.8192 | 684.9985 | 663.1852 | 638.3935 | 614.4447 | 583.6647 | 554.0812 | 531.4258 | 491.9946 | 475.2089 | 460.6891 | 444.2501 | 428.8981 | 394.815 | 378.6343 | 361.3071 | 344.9234 | 326.3273 | 310.153 | 291.9313 | 275.5675 | 254.0839 | 239.1264 | 225.1522 | 212.6197 | 197.7398 | 185.4675 | 171.0265 | 157.8271 | 122.4642 | 108.2479 | 92.0981 | 0 | 0
|  | Senior debt | USD m |  |  | 110.0527 | 190.2151 | 345.5997 | 505.6665 | 595.3236 | 693.4962 | 676.5329 | 658.8518 | 640.2997 | 621.201 | 601.2236 | 580.6092 | 558.6481 | 536.0156 | 514.0113 | 491.9967 | 469.07 | 441.0679 | 411.3481 | 381.6578 | 348.8083 | 314.8266 | 279.7177 | 244.6103 | 207.8131 | 170.8053 | 132.4366 | 94.109 | 64.1051 | 40.0254 | 20.1598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 31.7445 | 56.0842 | 103.1931 | 153.9818 | 187.2313 | 224.2455 | 223.5744 | 225.2033 | 226.122 | 227.7692 | 228.9011 | 231.0028 | 232.0541 | 232.1394 | 233.4887 | 235.5385 | 237.1268 | 243.8913 | 250.33 | 257.4689 | 263.8834 | 269.9559 | 275.8011 | 281.5303 | 286.614 | 291.205 | 294.7749 | 297.2098 | 286.9761 | 266.5525 | 248.9607 | 209.9978 | 168.6645 | 125.6345 | 80.0523 | 32.4349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 24.095 | 24.0021 | 24.7439 | 24.26 | 25.1525 | 24.9432 | 25.3975 | 24.6579 | 25.7569 | 25.9213 | 26.7228 | 26.1995 | 27.1641 | 26.9378 | 27.2619 | 26.1397 | 27.4751 | 27.9942 | 28.8602 | 28.2945 | 29.3368 | 29.0922 | 29.6219 | 28.7571 | 30.0408 | 30.2332 | 31.1689 | 30.5572 | 31.6835 | 31.4191 | 31.7965 | 30.4844 | 32.0443 | 32.6516 | 33.6625 | 33.0011 | 34.2182 | 33.9324 | 34.55 | 33.539 | 35.0383 | 35.2635 | 36.3558 | 35.6407 | 36.9558 | 36.6468 | 37.0861 | 35.5525 | 37.3743 | 38.0845 | 0 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9339 | 10.5969 | 18.9278 | 27.8666 | 37.5498 | 42.6902 | 43.7895 | 44.8889 | 45.9882 | 47.0875 | 48.1868 | 49.2861 | 50.3855 | 51.4848 | 50.4771 | 45.2553 | 40.0335 | 34.8118 | 29.59 | 24.3682 | 19.1465 | 13.9247 | 8.7029 | 3.4812 | 0 | 0
|  | Share capital | USD m |  |  | 7.7104 | 13.3267 | 24.2132 | 35.4277 | 41.7092 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873 | 48.5873
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.1052 | 12.3165 | 16.7738 | 21.4748 | 27.2791 | 33.3162 | 40.4266 | 45.5955 | 54.4248 | 63.6334 | 71.1146 | 74.1286 | 77.9911 | 82.1595 | 87.2158 | 81.5559 | 89.9717 | 97.4143 | 105.231 | 113.6896 | 123.2509 | 133.5024 | 144.9168 | 155.2391 | 168.8752 | 183.4847 | 199.3068 | 216.8031 | 235.8559 | 256.3248 | 278.5296 | 273.0531 | 254.2132 | 235.1794 | 216.6855 | 197.6514 | 179.1607 | 160.1255 | 142.0449 | 120.4729 | 105.0238 | 96.0462 | 87.6431 | 78.7001 | 70.3344 | 61.4242 | 53.0072 | 24.3997 | 13.5834 | 1.9452 | -48.5873 | -48.5873
|  | Total liabilities and equity | USD m |  |  | 149.5076 | 259.626 | 473.0059 | 695.0759 | 824.2641 | 999.5291 | 985.0132 | 974.16 | 960.7437 | 949.989 | 936.9714 | 926.0233 | 909.5428 | 896.924 | 885.642 | 873.9599 | 855.1122 | 838.7016 | 819.3627 | 802.1917 | 768.9745 | 750.8166 | 729.5146 | 708.8192 | 684.9985 | 663.1852 | 638.3935 | 614.4447 | 583.6647 | 554.0812 | 531.4258 | 491.9946 | 475.2089 | 460.6891 | 444.2501 | 428.8981 | 394.815 | 378.6343 | 361.3071 | 344.9234 | 326.3273 | 310.153 | 291.9313 | 275.5675 | 254.0839 | 239.1264 | 225.1522 | 212.6197 | 197.7398 | 185.4675 | 171.0265 | 157.8271 | 122.4642 | 108.2479 | 92.0981 | 0 | 0
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03443 | 0.034075 | 0.034461 | 0.034091 | 0.034477 | 0.03422 | 0.034477 | 0.034091 | 0.034477 | 0.035152 | 0.035556 | 0.035152 | 0.035422 | 0.034984 | 0.035077 | 0.034457 | 0.034553 | 0.034707 | 0.034586 | 0.033541 | 0.032947 | 0.031277 | 0.028958 | 0.027119 | 0.02728 | 0.027119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 32
| Rate in final maturity period | factor | 0.027119
| Discount rate used | factor |  |  | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.03443 | 0.034075 | 0.034461 | 0.034091 | 0.034477 | 0.03422 | 0.034477 | 0.034091 | 0.034477 | 0.035152 | 0.035556 | 0.035152 | 0.035422 | 0.034984 | 0.035077 | 0.034457 | 0.034553 | 0.034707 | 0.034586 | 0.033541 | 0.032947 | 0.031277 | 0.028958 | 0.027119 | 0.02728 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119 | 0.027119
| PV of CFADS to final maturity | USD m |  |  | 739.5455 | 759.6009 | 780.2002 | 801.3582 | 823.0899 | 845.4109 | 866.4651 | 846.025 | 824.6927 | 802.3194 | 779.2711 | 755.1742 | 730.2955 | 703.7855 | 676.4468 | 649.9177 | 623.3937 | 595.783 | 567.3508 | 537.4908 | 506.5431 | 472.6486 | 437.1886 | 400.3879 | 362.7448 | 323.082 | 282.1173 | 239.0096 | 194.3205 | 146.6721 | 97.7499 | 49.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 1020.8624 | 1048.5468 | 1076.9819 | 1106.1881 | 1136.1864 | 1166.9982 | 1196.7733 | 1187.7056 | 1178.0161 | 1167.8188 | 1157.2307 | 1146.1649 | 1134.6658 | 1122.0974 | 1109.0192 | 1097.4042 | 1086.6103 | 1075.4699 | 1063.8998 | 1051.6283 | 1038.6673 | 1023.438 | 1006.9564 | 989.8427 | 972.6576 | 954.0894 | 934.2894 | 912.6687 | 889.0493 | 861.5191 | 831.9826 | 803.6157 | 774.7173 | 744.3364 | 713.546 | 681.2975 | 648.3638 | 612.629 | 584.8694 | 556.2334 | 527.2453 | 496.7962 | 465.9783 | 433.7067 | 400.8577 | 364.8707 | 331.4894 | 303.6674 | 275.5239 | 245.9128 | 215.9664 | 184.5667 | 152.5766 | 111.6951 | 74.9546 | 36.4697 | 0
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3083 | 1.3107 | 1.3143 | 1.317 | 1.3211 | 1.3246 | 1.3301 | 1.3344 | 1.3375 | 1.3424 | 1.3492 | 1.3556 | 1.3783 | 1.4037 | 1.4343 | 1.4708 | 1.515 | 1.5695 | 1.6386 | 1.7309 | 1.8598 | 2.0582 | 2.4021 | 2.722 | 2.9658 | 3.4752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2494 | 1.2505 | 1.2517 | 1.253 | 1.2545 | 1.2561 | 1.2578 | 1.2598 | 1.262 | 1.2644 | 1.2671 | 1.2701 | 1.2863 | 1.3067 | 1.3272 | 1.355 | 1.3887 | 1.4314 | 1.4829 | 1.5547 | 1.6517 | 1.8047 | 2.0648 | 2.288 | 2.4422 | 2.4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.7257 | 1.7556 | 1.788 | 1.8239 | 1.8629 | 1.9064 | 1.9543 | 2.0086 | 2.069 | 2.135 | 2.2086 | 2.2928 | 2.4121 | 2.5565 | 2.7215 | 2.9341 | 3.1984 | 3.5387 | 3.9764 | 4.5911 | 5.4699 | 6.8914 | 9.447 | 13.4392 | 20.7864 | 39.8622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR (debt-service weighted) | x | #VALUE!
| LLCR at first debt service period | x | 1.3083
| PLCR at first debt service period | x | 1.7257

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1127.9254 | -14.2 | -19.6166 | -0.70766 | -0.90353 | -1.2796 | -1.8449 | -2.5447 | -3.3211 | -4.217 | -5.1098 | -6.0191 | -6.8697 | -7.686 | -8.4032 | -8.9995 | -9.4934 | -9.8219 | -10.0282 | -10.4031 | -9.9222 | -9.6872 | -9.2596 | -8.7368 | -8.0635 | -7.3361 | -6.52 | -5.6426 | -4.7972 | -3.935 | -3.1766 | -2.4969 | -1.8862 | -1.5759 | -15.4782 | -11.8956 | -1.0576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4103 | 8.9036 | 9.8664 | 9.0053 | 9.7761 | 8.7414 | 10.0115 | 10.8467 | 9.7679 | 8.9498 | 9.6918 | 4.4064 | 5.2414 | 4.7192 | 5.9158 | 6.359 | 7.0831 | 7.2636 | 8.3989 | 8.9113 | 10.376 | 11.5286 | 24.4672 | 33.943 | 30.3571 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.1156 | 45.3566 | 41.7584 | 35.2774 | 34.8276 | 35.5149 | 35.0302 | 35.654 | 35.3754 | 43.3814 | 38.1139 | 38.8439 | 55.3999 | 0
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1595.0488 | 0 | -115.6598 | -1.5629 | -2.2601 | -3.6927 | -5.7708 | -8.3692 | -11.35 | -14.5742 | -17.9053 | -21.2153 | -24.3851 | -27.3087 | -29.8922 | -32.0553 | -33.7355 | -34.8823 | -35.4639 | -36.7212 | -34.8823 | -33.7355 | -32.0553 | -29.8922 | -27.3087 | -24.3851 | -21.2153 | -17.9053 | -14.5742 | -11.35 | -8.3692 | -5.7708 | -3.6927 | -2.2601 | -54.6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8722 | 50.2721 | 50.1607 | 50.7935 | 50.4 | 50.9641 | 50.7204 | 51.6887 | 51.3314 | 49.8512 | 49.37 | 49.7763 | 49.3753 | 49.9564 | 49.7515 | 51.6625 | 51.7458 | 51.9067 | 51.5393 | 52.2087 | 51.8012 | 52.4026 | 52.1645 | 53.2756 | 52.8997 | 51.0636 | 50.6913 | 51.3902 | 50.9757 | 51.5989 | 51.4095 | 53.3175 | 44.3733 | 44.4968 | 44.0724 | 44.7472 | 44.2903 | 44.9082 | 44.6106 | 46.8577 | 43.276 | 36.8116 | 36.3786 | 37.0829 | 36.6152 | 37.2564 | 36.9953 | 45.0191 | 39.7695 | 40.5176 | 37.4587 | 0
| Project cash flow, pre-tax | USD m |  | 1844.9016 | 0 | -115.6598 | -1.5629 | -2.2601 | -3.6927 | -5.7708 | -8.3692 | -11.35 | -14.5742 | -17.9053 | -21.2153 | -24.3851 | -27.3087 | -29.8922 | -32.0553 | -33.7355 | -34.8823 | -35.4639 | -36.7212 | -34.8823 | -33.7355 | -32.0553 | -29.8922 | -27.3087 | -24.3851 | -21.2153 | -17.9053 | -14.5742 | -11.35 | -8.3692 | -5.7708 | -3.6927 | -2.2601 | -54.6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8722 | 50.2721 | 50.1607 | 50.7935 | 50.4 | 50.9641 | 50.7204 | 51.6887 | 51.3314 | 49.8512 | 49.4881 | 50.1318 | 49.7326 | 50.3156 | 50.1115 | 52.0181 | 52.1085 | 52.2727 | 51.9069 | 52.5778 | 52.1723 | 52.7757 | 52.539 | 53.6508 | 53.2773 | 51.4442 | 51.0736 | 51.7741 | 51.3617 | 51.9872 | 51.7989 | 54.1141 | 54.2169 | 54.3102 | 53.9353 | 54.6679 | 54.248 | 54.8973 | 54.6691 | 55.9518 | 55.5591 | 53.3046 | 52.9252 | 53.6926 | 53.2647 | 53.9398 | 53.7707 | 56.5726 | 56.6902 | 57.399 | 43.0259 | 0
| Cumulative equity cash flow | USD m |  |  | -14.2 | -33.8166 | -34.5242 | -35.4278 | -36.7073 | -38.5522 | -41.0968 | -44.4179 | -48.635 | -53.7448 | -59.7639 | -66.6336 | -74.3196 | -82.7228 | -91.7223 | -101.2157 | -111.0377 | -121.0659 | -131.4689 | -141.3912 | -151.0784 | -160.338 | -169.0748 | -177.1383 | -184.4745 | -190.9944 | -196.637 | -201.4342 | -205.3692 | -208.5458 | -211.0427 | -212.929 | -214.5049 | -229.9831 | -241.8787 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -242.9363 | -231.526 | -222.6224 | -212.756 | -203.7508 | -193.9747 | -185.2333 | -175.2219 | -164.3752 | -154.6073 | -145.6575 | -135.9657 | -131.5593 | -126.3179 | -121.5987 | -115.6829 | -109.324 | -102.2409 | -94.9773 | -86.5784 | -77.6671 | -67.2911 | -55.7625 | -31.2953 | 2.6477 | 33.0048 | 83.6961 | 135.0863 | 186.062 | 237.6609 | 289.0704 | 342.3879 | 386.7612 | 431.258 | 475.3304 | 520.0777 | 564.368 | 609.2762 | 653.3918 | 698.7484 | 740.5068 | 775.7842 | 810.6118 | 846.1267 | 881.1569 | 916.8109 | 952.1863 | 995.5677 | 1033.6816 | 1072.5255 | 1127.9254 | 1127.9254
| Equity IRR (XIRR) | % | 11.44%
| Project IRR, post-tax (XIRR) | % | 10.11%
| Project IRR, pre-tax (XIRR) | % | 10.55%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -79.9756

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 0
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 0

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 936.4325
| Senior debt (four tranches) | USD m | 693.4962
| Equity (incl. LNTP) | USD m | 242.9363
| Gearing (debt incl. standby / total funding) | % | 74.06%
| Interest during construction incl. swap and PRI | USD m | 69.8332
| Commitment, upfront and agency fees | USD m | 22.6841
| ECA premium | USD m | 22.5733
| DSRA initial funding | USD m | 40.84
| Standby drawn | USD m | 4.7296e-14
| Contingent equity drawn | USD m | 1.5765e-14
| Minimum DSCR | x | #VALUE!
| Average DSCR | x | #VALUE!
| LLCR at first debt service period (incl. DSRA) | x | 1.3083
| PLCR at first debt service period | x | 1.7257
| Equity IRR | % | 11.44%
| Project IRR, post-tax | % | 10.11%
| Equity NPV at 16.0% (at FC) | USD m | -79.9756
| All checks | check | 0