## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 8
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 1
|  | Construction case (1 FC budget, 2 actual) | code | 1
|  | COD delay (sensitivity) | months | 6
|  | Capex factor | factor | 1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 0
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 0
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 1
|  | Performance LD prepayment June 2022 (1 = on) | flag | 0
|  | Waiver and amendment 2023 (1 = on) | flag | 0
|  | 2025 bond refinancing (1 = on) | flag | 0
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 2
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-11-01
|  | PPA expiry | date | 2046-10-31
|  | Construction months (NTP to COD) | months | 39
|  | Period containing COD (period number) | index | 7
|  | First debt service period | index | 8
|  | Last month of the funding period (month number) | index | 41
|  | Last operating period (period number) | index | 57
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-11-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-10-31
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 123
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 520.4953 | 522.6929 | 524.8998 | 527.116 | 529.3416 | 531.5766 | 533.821 | 536.0748 | 538.3382 | 540.6112 | 542.8937 | 545.1859 | 547.4878 | 549.7993 | 552.1207 | 554.4518 | 556.7928 | 559.1437 | 561.5044 | 563.8752 | 566.256 | 568.6468 | 571.0477 | 573.4587 | 575.88 | 578.3114 | 580.7532 | 583.2052 | 585.6676 | 588.1403 | 590.6236 | 593.1173 | 595.6215 | 598.1363 | 600.6617 | 603.1978 | 605.7446 | 608.3021 | 610.8705 | 613.4497 | 616.0398 | 618.6408 | 621.2528 | 623.8758 | 626.5099 | 629.1551 | 631.8115 | 634.4791 | 637.158 | 639.8481 | 642.5497 | 645.2626 | 647.987
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 571.84 | 57.184 | 0.061759 | 0.64789 | 1.8522 | 3.5992 | 5.7836 | 8.2894 | 10.9999 | 13.8002 | 16.5828 | 19.2476 | 21.7053 | 23.8772 | 25.6956 | 27.1081 | 28.0722 | 28.5611 | 28.5611 | 28.0722 | 27.1081 | 25.6956 | 23.8772 | 21.7053 | 19.2476 | 16.5828 | 13.8002 | 10.9999 | 8.2894 | 5.7836 | 3.5992 | 1.8522 | 0.64789 | 0.061759 | 0 | 0 | 0 | 0 | 0 | 42.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 53.7997 | 5.5416 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 7.62 | 6.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 8.97 | 6.279 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0.070816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 38.4 | 0 | 0.0050269 | 0.052736 | 0.15076 | 0.29296 | 0.47076 | 0.67472 | 0.89535 | 1.1233 | 1.3498 | 1.5667 | 1.7667 | 1.9435 | 2.0915 | 2.2065 | 2.285 | 2.3248 | 2.3248 | 2.285 | 2.2065 | 2.0915 | 1.9435 | 1.7667 | 1.5667 | 1.3498 | 1.1233 | 0.89535 | 0.67472 | 0.47076 | 0.29296 | 0.15076 | 0.052736 | 0.0050269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 718.6097 | 108.1116 | 1.4076 | 2.0414 | 3.3437 | 5.2329 | 7.5951 | 10.3049 | 13.236 | 16.2643 | 19.2733 | 22.155 | 24.8128 | 27.1615 | 29.1279 | 30.6553 | 31.6979 | 32.2266 | 33.3696 | 31.6979 | 30.6553 | 29.1279 | 27.1615 | 24.8128 | 22.155 | 19.2733 | 16.2643 | 13.236 | 10.3049 | 7.5951 | 5.2329 | 3.3437 | 2.0414 | 1.4076 | 1.3408 | 1.3408 | 1.3408 | 1.3408 | 1.3408 | 49.5788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 42938.798 | 4293.8798 | 4.6374 | 48.6497 | 139.0788 | 270.2568 | 434.283 | 622.4408 | 825.9707 | 1036.242 | 1245.1822 | 1445.277 | 1629.828 | 1792.9095 | 1929.4549 | 2035.5137 | 2107.9085 | 2144.6212 | 2144.6212 | 2107.9085 | 2035.5137 | 1929.4549 | 1792.9095 | 1629.828 | 1445.277 | 1245.1822 | 1036.242 | 825.9707 | 622.4408 | 434.283 | 270.2568 | 139.0788 | 48.6497 | 4.6374 | 0 | 0 | 0 | 0 | 0 | 3220.4099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 7728.9836 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 0.83473 | 0 | 0 | 0 | 0 | 0 | 579.6738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 7728.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 0.83473 | 0 | 0 | 0 | 0 | 0 | 579.6738 | 0 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 772.8984 | 773.7331 | 782.49 | 807.5242 | 856.1704 | 934.3414 | 1046.3807 | 1195.0555 | 1381.579 | 832.8134 | 1092.1286 | 1376.7407 | 1674.4302 | 1973.0859 | 2261.3074 | 2528.6916 | 2766.0487 | 2965.5569 | 3120.8477 | 3227.0903 | 3281.0231 | 3281.0231 | 3227.0903 | 3120.8477 | 2965.5569 | 2766.0487 | 2528.6916 | 2261.3074 | 1973.0859 | 1674.4302 | 1376.7407 | 1092.1286 | 832.8134 | 608.6806 | 422.1571 | 273.4824 | 161.443 | 83.2721 | 614.2996 | 589.2654 | 580.5085 | 579.6738 | 579.6738 | 579.6738 | 579.6738 | 579.6738 | 579.6738 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.6308 | 0 | 0.019446 | 0.020031 | 0.019522 | 0.02073 | 0.021887 | 0.021483 | 0.026525 | 0.029193 | 0.034728 | 0.020174 | 0.027222 | 0.034172 | 0.040051 | 0.048562 | 0.053634 | 0.061715 | 0.067224 | 0.06714 | 0.07521 | 0.074946 | 0.078407 | 0.075559 | 0.076471 | 0.073643 | 0.067436 | 0.064723 | 0.057019 | 0.052468 | 0.045588 | 0.034797 | 0.031543 | 0.024113 | 0.018921 | 0.013326 | 0.0095105 | 0.0061352 | 0.0034902 | 0.0018524 | 0.013169 | 0.012998 | 0.012751 | 0.011453 | 0.012626 | 0.012168 | 0.01252 | 0.012065 | 0.012415 | 0 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | KCR per USD, period average | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | US CPI change, current year | % |  |  | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, current year | % |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI change, prior year | % |  |  | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US index, June 2018 (2018 price base) | index | 103.3281
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084 | 191.0761
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 102.7675 | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0055 | 1.0165 | 1.0276 | 1.0388 | 1.0502 | 1.0617 | 1.0733 | 1.085 | 1.0969 | 1.1089 | 1.121 | 1.1333 | 1.1457 | 1.1582 | 1.1709 | 1.1837 | 1.1967 | 1.2097 | 1.223 | 1.2364 | 1.2499 | 1.2636 | 1.2774 | 1.2914 | 1.3055 | 1.3198 | 1.3342 | 1.3488 | 1.3636 | 1.3785 | 1.3936 | 1.4088 | 1.4242 | 1.4398 | 1.4556 | 1.4715 | 1.4876 | 1.5038 | 1.5203 | 1.5369 | 1.5537 | 1.5707 | 1.5879 | 1.6053 | 1.6229 | 1.6406 | 1.6586 | 1.6767 | 1.6951 | 1.7136 | 1.7323 | 1.7513 | 1.7705 | 1.7898 | 1.8094 | 1.8292 | 1.8492
|  | KC index, June 2018 (2018 price base) | index | 112.9227
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682 | 871.105
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 110.8994 | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0182 | 1.0557 | 1.0946 | 1.1349 | 1.1767 | 1.22 | 1.265 | 1.3115 | 1.3598 | 1.4099 | 1.4618 | 1.5156 | 1.5715 | 1.6293 | 1.6893 | 1.7515 | 1.816 | 1.8829 | 1.9522 | 2.0241 | 2.0986 | 2.1759 | 2.256 | 2.3391 | 2.4252 | 2.5145 | 2.6071 | 2.7031 | 2.8027 | 2.9059 | 3.0129 | 3.1238 | 3.2388 | 3.3581 | 3.4817 | 3.6099 | 3.7429 | 3.8807 | 4.0236 | 4.1717 | 4.3254 | 4.4846 | 4.6498 | 4.821 | 4.9985 | 5.1825 | 5.3734 | 5.5712 | 5.7764 | 5.9891 | 6.2096 | 6.4383 | 6.6753 | 6.9211 | 7.176 | 7.4402 | 7.7142
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.41667 | 0.91667 | 1.4167 | 1.9167 | 2.4167 | 2.9167 | 3.4167 | 3.9167 | 4.4167 | 4.9167 | 5.4167 | 5.9167 | 6.4167 | 6.9167 | 7.4167 | 7.9167 | 8.4167 | 8.9167 | 9.4167 | 9.9167 | 10.4167 | 10.9167 | 11.4167 | 11.9167 | 12.4167 | 12.9167 | 13.4167 | 13.9167 | 14.4167 | 14.9167 | 15.4167 | 15.9167 | 16.4167 | 16.9167 | 17.4167 | 17.9167 | 18.4167 | 18.9167 | 19.4167 | 19.9167 | 20.4167 | 20.9167 | 21.4167 | 21.9167 | 22.4167 | 22.9167 | 23.4167 | 23.9167 | 24.4167 | 24.8333
|  | Contracted capacity | MW | 588.4
|  | Plant net heat rate, new and clean | kJ/kWh | 6261
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98988 | 0.98938 | 0.98864 | 0.9879 | 0.98715 | 0.98641 | 0.98567 | 0.98493 | 0.98418 | 0.98344 | 0.9827 | 0.98196 | 0.98121 | 0.98047 | 0.97973 | 0.97899 | 0.97824 | 0.9775 | 0.97676 | 0.97602 | 0.97527 | 0.97453 | 0.97379 | 0.97305 | 0.9723 | 0.97156 | 0.97082 | 0.97008 | 0.96933 | 0.96859 | 0.96785 | 0.96711 | 0.96636 | 0.96562 | 0.96488 | 0.96414 | 0.96339 | 0.96265 | 0.96191 | 0.96117 | 0.96042 | 0.95968 | 0.95894 | 0.9582 | 0.95745 | 0.95671 | 0.95597 | 0.95523 | 0.95448 | 0.95374 | 0.95312
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 610197.8847 | 1829678.2427 | 1822457.6681 | 1809402.8106 | 1813881.5431 | 1824185.7752 | 1802084.1562 | 1759300.8791 | 1778671.879 | 1818693.3077 | 1811507.8661 | 1798523.2747 | 1802966.8742 | 1813200.8402 | 1778990.7603 | 1712018.3752 | 1743507.1072 | 1807708.3727 | 1800558.0641 | 1787643.7388 | 1792052.2052 | 1802215.9051 | 1780364.1212 | 1738080.5141 | 1757201.6791 | 1796723.4376 | 1789608.2621 | 1776764.203 | 1781137.5363 | 1791230.9701 | 1757419.0648 | 1691243.0289 | 1722333.5863 | 1785738.5026 | 1778658.4602 | 1765884.6671 | 1770222.8674 | 1780246.0351 | 1758644.0861 | 1716860.1492 | 1735731.4791 | 1774753.5675 | 1767708.6582 | 1755005.1312 | 1759308.1984 | 1769261.1 | 1735847.3694 | 1670467.6827 | 1701160.0655 | 1763768.6325 | 1175082.9123
|  | Plant net heat rate | kJ/kWh |  |  | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.8886 | 6459.4711 | 6463.3449 | 6467.2186 | 6471.0924 | 6474.9661 | 6478.8399 | 6482.7136 | 6486.5874 | 6490.4611 | 6494.3349 | 6498.2086 | 6502.0823 | 6505.9561 | 6509.8298 | 6513.7036 | 6517.5773 | 6521.4511 | 6525.3248 | 6529.1986 | 6533.0723 | 6536.9461 | 6540.8198 | 6544.6936 | 6548.5673 | 6552.441 | 6556.3148 | 6560.1885 | 6564.0623 | 6567.936 | 6571.8098 | 6575.6835 | 6579.5573 | 6583.431 | 6587.3048 | 6591.1785 | 6595.0522 | 6598.926 | 6602.7997 | 6606.6735 | 6610.5472 | 6614.421 | 6618.2947 | 6622.1685 | 6626.0422 | 6629.916 | 6633.7897 | 6637.6635 | 6641.5372 | 6645.4109 | 6648.6391
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.968 | 6471.1242 | 6474.3584 | 6477.5926 | 6480.8268 | 6484.061 | 6487.2953 | 6490.5295 | 6493.7637 | 6496.9979 | 6500.2321 | 6503.4663 | 6506.7005 | 6509.9348 | 6513.169 | 6516.4032 | 6519.6374 | 6522.8716 | 6526.1058 | 6529.34 | 6532.5743 | 6535.8085 | 6539.0427 | 6542.2769 | 6545.5111 | 6548.7453 | 6551.9795 | 6555.2138 | 6558.448 | 6561.6822 | 6564.9164 | 6568.1506 | 6571.3848 | 6574.619 | 6577.8533 | 6581.0875 | 6584.3217 | 6587.5559 | 6590.7901 | 6594.0243 | 6597.2585 | 6600.4928 | 6603.727 | 6606.9612 | 6610.1954 | 6613.4296 | 6616.6638 | 6619.898 | 6623.1323 | 6626.3665 | 6629.0617
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4137692.7979 | 12411833.3307 | 12370265.7341 | 12289014.3891 | 12326811.9429 | 12404258.6808 | 12261301.272 | 11977362.8114 | 12116476.9239 | 12396505.2781 | 12354897.6145 | 12273656.3697 | 12311315.5234 | 12388573.1226 | 12162072.2212 | 11711180.1611 | 11933673.834 | 12380462.2143 | 12338816.7706 | 12257590.1995 | 12295108.6664 | 12372172.5532 | 12229403.2985 | 11946025.9973 | 12084596.4827 | 12363704.1393 | 12322023.2024 | 12240815.8786 | 12278191.3719 | 12355056.9726 | 12128987.9936 | 11679148.2501 | 11900855.7346 | 12346231.0531 | 12304516.9097 | 12223333.4069 | 12260563.6397 | 12337226.3808 | 12194677.8039 | 11911926.7092 | 12049921.0439 | 12328042.9557 | 12286297.8926 | 12205142.7845 | 12242225.47 | 12318680.7778 | 12093095.5557 | 11644411.7978 | 11865281.2595 | 12309139.8471 | 8204753.1026
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3533120 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 7124160
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4395 | 14.4718 | 14.5044 | 14.5374 | 14.5708 | 14.6045 | 14.6386 | 14.6731 | 14.7079 | 14.7431 | 14.7787 | 14.8148 | 14.8511 | 14.8879 | 14.9251 | 14.9627 | 15.0008 | 15.0392 | 15.078 | 15.1173 | 15.157 | 15.1972 | 15.2377 | 15.2788 | 15.3202 | 15.3622 | 15.4045 | 15.4474 | 15.4907 | 15.5345 | 15.5788 | 15.6235 | 15.6688 | 15.7145 | 15.7607 | 15.8075 | 15.8547 | 15.9025 | 15.9508 | 15.9996 | 16.049 | 16.0989 | 16.1493 | 16.2003 | 16.2519 | 16.304 | 16.3567 | 16.4099 | 16.4638 | 16.5182 | 16.5733 | 16.6289 | 16.6851 | 16.742 | 16.7995 | 16.8576 | 16.9163
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3275 | 2.353 | 2.3787 | 2.4047 | 2.431 | 2.4576 | 2.4845 | 2.5117 | 2.5392 | 2.567 | 2.595 | 2.6234 | 2.6521 | 2.6811 | 2.7105 | 2.7401 | 2.7701 | 2.8004 | 2.8311 | 2.862 | 2.8933 | 2.925 | 2.957 | 2.9893 | 3.022 | 3.0551 | 3.0885 | 3.1223 | 3.1565 | 3.191 | 3.2259 | 3.2612 | 3.2969 | 3.333 | 3.3694 | 3.4063 | 3.4435 | 3.4812 | 3.5193 | 3.5578 | 3.5967 | 3.6361 | 3.6759 | 3.7161 | 3.7567 | 3.7978 | 3.8394 | 3.8814 | 3.9238 | 3.9668 | 4.0102 | 4.054 | 4.0984 | 4.1432 | 4.1886 | 4.2344 | 4.2807
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 1 | 1 | 1
|  | Capacity payment | USD m |  | 3349.1256 | 0 | 0 | 0 | 0 | 0 | 0 | 20.1505 | 60.6691 | 60.8891 | 61.1116 | 61.3364 | 61.5638 | 61.7936 | 62.0259 | 62.2608 | 62.4982 | 62.7383 | 62.9809 | 63.2262 | 63.4742 | 63.725 | 63.0543 | 64.2347 | 64.4937 | 64.7556 | 65.0203 | 65.2879 | 65.5585 | 65.832 | 66.1085 | 66.388 | 66.6706 | 66.9563 | 67.2451 | 67.5371 | 67.8323 | 68.1307 | 67.4438 | 68.7373 | 69.0456 | 69.3572 | 69.6723 | 69.9908 | 70.3128 | 70.6384 | 70.9675 | 71.3002 | 71.6365 | 71.9765 | 72.3202 | 72.6677 | 73.019 | 73.3741 | 72.6681 | 74.0961 | 74.463 | 49.8893
|  | VOM charge, indexed | USD/MWh |  |  | 3.9056 | 3.9483 | 3.9915 | 4.0352 | 4.0793 | 4.1239 | 4.1691 | 4.2147 | 4.2608 | 4.3074 | 4.3545 | 4.4022 | 4.4503 | 4.499 | 4.5482 | 4.598 | 4.6483 | 4.6991 | 4.7505 | 4.8025 | 4.8551 | 4.9082 | 4.9619 | 5.0162 | 5.071 | 5.1265 | 5.1826 | 5.2393 | 5.2966 | 5.3546 | 5.4131 | 5.4724 | 5.5322 | 5.5927 | 5.6539 | 5.7158 | 5.7783 | 5.8415 | 5.9054 | 5.97 | 6.0354 | 6.1014 | 6.1681 | 6.2356 | 6.3038 | 6.3728 | 6.4425 | 6.513 | 6.5843 | 6.6563 | 6.7291 | 6.8027 | 6.8772 | 6.9524 | 7.0285 | 7.1053 | 7.1831
|  | Variable O&M payment | USD m |  | 491.1266 | 0 | 0 | 0 | 0 | 0 | 0 | 2.544 | 7.7115 | 7.7651 | 7.7938 | 7.8986 | 8.0304 | 8.0198 | 7.9151 | 8.0898 | 8.3623 | 8.4204 | 8.4515 | 8.5651 | 8.7079 | 8.6371 | 8.4029 | 8.6511 | 9.0677 | 9.1307 | 9.1644 | 9.2875 | 9.4423 | 9.4299 | 9.3066 | 9.512 | 9.8323 | 9.9005 | 9.937 | 10.0704 | 10.2383 | 10.1549 | 9.8795 | 10.1711 | 10.6609 | 10.7348 | 10.7744 | 10.919 | 11.1009 | 11.0862 | 10.9412 | 11.1825 | 11.559 | 11.6391 | 11.6818 | 11.8386 | 12.0358 | 11.9377 | 11.6137 | 11.9565 | 12.5322 | 8.4407
|  | Fuel charge (pass-through) | USD m |  | 4935.373 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7791 | 78.8709 | 78.5989 | 79.6364 | 79.8734 | 81.9746 | 81.0218 | 80.7204 | 81.6498 | 85.1992 | 84.9048 | 86.0249 | 86.2804 | 88.5495 | 86.922 | 85.3651 | 86.9783 | 92.0304 | 91.7118 | 92.9211 | 93.1964 | 95.6468 | 94.5338 | 94.181 | 95.2642 | 99.404 | 99.0593 | 100.3648 | 100.6615 | 103.3075 | 101.4074 | 99.5897 | 101.4704 | 107.3628 | 106.9897 | 108.399 | 108.7188 | 111.5758 | 110.276 | 109.863 | 111.125 | 115.9526 | 115.5489 | 117.0702 | 117.4147 | 120.4994 | 118.2815 | 116.1598 | 118.3519 | 125.2229 | 83.4617
|  | GTA reservation charge (pass-through) | USD m |  | 695.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8163 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 16.4303 | 11.1654
|  | GTA commodity charge (pass-through) | USD m |  | 147.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82207 | 2.503 | 2.4946 | 2.5154 | 2.5231 | 2.577 | 2.5473 | 2.5257 | 2.555 | 2.6533 | 2.6444 | 2.6664 | 2.6746 | 2.7317 | 2.6818 | 2.6211 | 2.6709 | 2.8124 | 2.803 | 2.8263 | 2.8349 | 2.8955 | 2.8621 | 2.8377 | 2.8706 | 2.981 | 2.9709 | 2.9956 | 3.0048 | 3.0689 | 3.0128 | 2.9446 | 3.0005 | 3.1594 | 3.1488 | 3.1749 | 3.1846 | 3.2526 | 3.215 | 3.1875 | 3.2245 | 3.3484 | 3.337 | 3.3647 | 3.3749 | 3.4469 | 3.3838 | 3.3072 | 3.3699 | 3.5484 | 2.3652
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 3840.2522 | 0 | 0 | 0 | 0 | 0 | 0 | 22.6944 | 68.3806 | 68.6542 | 68.9054 | 69.235 | 69.5941 | 69.8134 | 69.941 | 70.3506 | 70.8605 | 71.1587 | 71.4324 | 71.7913 | 72.1822 | 72.3621 | 71.4572 | 72.8857 | 73.5614 | 73.8862 | 74.1847 | 74.5754 | 75.0008 | 75.2619 | 75.4152 | 75.9 | 76.5029 | 76.8568 | 77.1821 | 77.6075 | 78.0706 | 78.2856 | 77.3233 | 78.9084 | 79.7065 | 80.0921 | 80.4467 | 80.9098 | 81.4138 | 81.7246 | 81.9087 | 82.4826 | 83.1955 | 83.6155 | 84.0021 | 84.5063 | 85.0548 | 85.3118 | 84.2819 | 86.0526 | 86.9952 | 58.33
|  | Total revenue | USD m |  | 9618.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 53.112 | 161.2482 | 161.432 | 162.7233 | 163.491 | 166.0523 | 165.4199 | 165.2059 | 166.7734 | 170.912 | 171.1091 | 172.5058 | 173.3335 | 176.1006 | 174.7419 | 172.1996 | 175.5026 | 181.3519 | 181.5632 | 183.0739 | 183.9664 | 186.9558 | 186.2179 | 185.9729 | 187.7983 | 192.6301 | 192.8569 | 194.4908 | 195.4532 | 198.6827 | 197.0979 | 194.2274 | 197.9873 | 204.8141 | 205.0577 | 206.8248 | 207.8627 | 211.3514 | 210.4909 | 210.2108 | 212.3366 | 217.9768 | 218.2385 | 220.1496 | 221.269 | 225.0376 | 223.1898 | 219.9364 | 224.2302 | 232.1969 | 155.3223
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 282.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4143 | 4.2892 | 4.3361 | 4.3835 | 4.4315 | 4.48 | 4.529 | 4.5785 | 4.6286 | 4.6793 | 4.7305 | 4.7822 | 4.8345 | 4.8874 | 4.9409 | 4.9949 | 5.0496 | 5.1048 | 5.1607 | 5.2171 | 5.2742 | 5.3319 | 5.3902 | 5.4492 | 5.5088 | 5.5691 | 5.63 | 5.6916 | 5.7539 | 5.8168 | 5.8805 | 5.9448 | 6.0098 | 6.0756 | 6.1421 | 6.2093 | 6.2772 | 6.3459 | 6.4153 | 6.4855 | 6.5564 | 6.6282 | 6.7007 | 6.774 | 6.8481 | 6.923 | 6.9987 | 7.0753 | 7.1527 | 7.231 | 4.8734
|  | O&M availability incentive | USD m |  | 4.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0.064397 | 0.19531 | 0.16453 | 0.099801 | 0.13452 | 0.20399 | 0.084017 | -0.16215 | -0.03903 | 0.21307 | 0.1795 | 0.10888 | 0.14676 | 0.22255 | 0.012499 | -0.37907 | -0.20438 | 0.23245 | 0.19582 | 0.11878 | 0.16011 | 0.24279 | 0.099995 | -0.19299 | -0.046452 | 0.25359 | 0.21363 | 0.12958 | 0.17467 | 0.26487 | 0.014876 | -0.45115 | -0.24325 | 0.27665 | 0.23306 | 0.14137 | 0.19055 | 0.28895 | 0.11901 | -0.22969 | -0.055286 | 0.30181 | 0.25426 | 0.15422 | 0.20788 | 0.31523 | 0.017705 | -0.53695 | -0.28951 | 0.32926 | 0.22191
|  | LTSA fixed fee | USD m |  | 94.3038 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47225 | 1.4322 | 1.4479 | 1.4637 | 1.4798 | 1.4959 | 1.5123 | 1.5289 | 1.5456 | 1.5625 | 1.5796 | 1.5969 | 1.6143 | 1.632 | 1.6499 | 1.6679 | 1.6862 | 1.7046 | 1.7232 | 1.7421 | 1.7612 | 1.7804 | 1.7999 | 1.8196 | 1.8395 | 1.8596 | 1.88 | 1.9005 | 1.9213 | 1.9423 | 1.9636 | 1.9851 | 2.0068 | 2.0288 | 2.0509 | 2.0734 | 2.0961 | 2.119 | 2.1422 | 2.1656 | 2.1893 | 2.2133 | 2.2375 | 2.262 | 2.2867 | 2.3117 | 2.337 | 2.3626 | 2.3884 | 2.4146 | 1.6273
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2813 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 5626
|  | LTSA variable fee | USD m |  | 293.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4673 | 4.4501 | 4.4988 | 4.548 | 4.5977 | 4.648 | 4.6989 | 4.7503 | 4.8023 | 4.8548 | 4.9079 | 4.9616 | 5.0159 | 5.0708 | 5.1262 | 5.1823 | 5.239 | 5.2963 | 5.3543 | 5.4129 | 5.4721 | 5.5319 | 5.5925 | 5.6536 | 5.7155 | 5.778 | 5.8412 | 5.9051 | 5.9697 | 6.035 | 6.1011 | 6.1678 | 6.2353 | 6.3035 | 6.3725 | 6.4422 | 6.5127 | 6.5839 | 6.6559 | 6.7288 | 6.8024 | 6.8768 | 6.952 | 7.0281 | 7.105 | 7.1827 | 7.2613 | 7.3407 | 7.421 | 7.5022 | 5.0562
|  | Operational insurance | USD m |  | 156.1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78171 | 2.3708 | 2.3967 | 2.4229 | 2.4495 | 2.4762 | 2.5033 | 2.5307 | 2.5584 | 2.5864 | 2.6147 | 2.6433 | 2.6722 | 2.7015 | 2.731 | 2.7609 | 2.7911 | 2.8216 | 2.8525 | 2.8837 | 2.9153 | 2.9471 | 2.9794 | 3.012 | 3.0449 | 3.0782 | 3.1119 | 3.146 | 3.1804 | 3.2152 | 3.2504 | 3.2859 | 3.3219 | 3.3582 | 3.3949 | 3.4321 | 3.4696 | 3.5076 | 3.546 | 3.5848 | 3.624 | 3.6636 | 3.7037 | 3.7442 | 3.7852 | 3.8266 | 3.8685 | 3.9108 | 3.9536 | 3.9968 | 2.6937
|  | G&A | USD m |  | 113.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56742 | 1.7209 | 1.7397 | 1.7587 | 1.778 | 1.7974 | 1.8171 | 1.837 | 1.8571 | 1.8774 | 1.8979 | 1.9187 | 1.9397 | 1.9609 | 1.9824 | 2.004 | 2.026 | 2.0481 | 2.0705 | 2.0932 | 2.1161 | 2.1392 | 2.1626 | 2.1863 | 2.2102 | 2.2344 | 2.2588 | 2.2836 | 2.3085 | 2.3338 | 2.3593 | 2.3851 | 2.4112 | 2.4376 | 2.4643 | 2.4912 | 2.5185 | 2.546 | 2.5739 | 2.6021 | 2.6305 | 2.6593 | 2.6884 | 2.7178 | 2.7475 | 2.7776 | 2.808 | 2.8387 | 2.8698 | 2.9012 | 1.9553
|  | Land lease and permits | USD m |  | 25.3088 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12674 | 0.38438 | 0.38858 | 0.39283 | 0.39713 | 0.40148 | 0.40587 | 0.41031 | 0.4148 | 0.41933 | 0.42392 | 0.42856 | 0.43325 | 0.43799 | 0.44278 | 0.44762 | 0.45252 | 0.45747 | 0.46248 | 0.46754 | 0.47265 | 0.47782 | 0.48305 | 0.48833 | 0.49368 | 0.49908 | 0.50454 | 0.51006 | 0.51564 | 0.52128 | 0.52698 | 0.53275 | 0.53857 | 0.54447 | 0.55042 | 0.55644 | 0.56253 | 0.56869 | 0.57491 | 0.5812 | 0.58756 | 0.59398 | 0.60048 | 0.60705 | 0.61369 | 0.62041 | 0.62719 | 0.63406 | 0.64099 | 0.648 | 0.43673
|  | Community fund and OREK levy | USD m |  | 21.1214 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12482 | 0.37609 | 0.3776 | 0.37898 | 0.38079 | 0.38277 | 0.38397 | 0.38468 | 0.38693 | 0.38973 | 0.39137 | 0.39288 | 0.39485 | 0.397 | 0.39799 | 0.39301 | 0.40087 | 0.40459 | 0.40637 | 0.40802 | 0.41016 | 0.4125 | 0.41394 | 0.41478 | 0.41745 | 0.42077 | 0.42271 | 0.4245 | 0.42684 | 0.42939 | 0.43057 | 0.42528 | 0.434 | 0.43839 | 0.44051 | 0.44246 | 0.445 | 0.44778 | 0.44949 | 0.4505 | 0.45365 | 0.45758 | 0.45989 | 0.46201 | 0.46478 | 0.4678 | 0.46922 | 0.46355 | 0.47329 | 0.47847 | 0.32082
|  | Variable consumables | USD m |  | 136.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70625 | 2.1409 | 2.1557 | 2.1637 | 2.1928 | 2.2294 | 2.2265 | 2.1974 | 2.2459 | 2.3215 | 2.3377 | 2.3463 | 2.3778 | 2.4175 | 2.3978 | 2.3328 | 2.4017 | 2.5174 | 2.5348 | 2.5442 | 2.5784 | 2.6214 | 2.6179 | 2.5837 | 2.6407 | 2.7296 | 2.7486 | 2.7587 | 2.7957 | 2.8423 | 2.8192 | 2.7427 | 2.8237 | 2.9597 | 2.9802 | 2.9912 | 3.0313 | 3.0818 | 3.0777 | 3.0375 | 3.1045 | 3.209 | 3.2312 | 3.2431 | 3.2866 | 3.3414 | 3.3141 | 3.2242 | 3.3194 | 3.4792 | 2.3433
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0425 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.085
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051875 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.10375
|  | Operating costs before pass-through items | USD m |  | 1140.2255 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8195 | 17.6429 | 17.7888 | 17.8954 | 18.1248 | 18.3984 | 18.4441 | 18.3387 | 18.6837 | 19.1871 | 19.3462 | 19.4624 | 19.7125 | 20.0107 | 19.9646 | 19.6876 | 20.1256 | 20.8705 | 21.0439 | 21.1706 | 21.4432 | 21.7683 | 21.8227 | 21.6977 | 22.1075 | 22.7056 | 22.8946 | 23.0328 | 23.3299 | 23.6842 | 23.6296 | 23.3015 | 23.8212 | 24.706 | 24.912 | 25.0627 | 25.3866 | 25.7728 | 25.8375 | 25.6893 | 26.1761 | 26.8866 | 27.1112 | 27.2755 | 27.6286 | 28.0495 | 27.9848 | 27.5961 | 28.2127 | 29.2637 | 19.7173
|  | Gas purchases | USD m |  | 4939.1368 | 0 | 0 | 0 | 0 | 0 | 0 | 25.731 | 78.7289 | 78.4652 | 79.5089 | 79.7534 | 81.8596 | 80.9161 | 80.6232 | 81.5596 | 85.1135 | 84.8278 | 85.9554 | 86.2191 | 88.4954 | 86.8774 | 85.3297 | 86.9508 | 92.0103 | 91.7008 | 92.9191 | 93.2035 | 95.6634 | 94.5595 | 94.2158 | 95.3087 | 99.4601 | 99.1248 | 100.441 | 100.7477 | 103.4059 | 101.5138 | 99.7039 | 101.5966 | 107.5067 | 107.1434 | 108.5653 | 108.8959 | 111.7684 | 110.477 | 110.0737 | 111.3489 | 116.1973 | 115.8038 | 117.3396 | 117.6962 | 120.7998 | 118.5877 | 116.4715 | 118.6808 | 125.5828 | 83.7082
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5782.1969 | 0 | 0 | 0 | 0 | 0 | 0 | 30.3694 | 92.7256 | 92.6441 | 93.6904 | 94.136 | 96.3432 | 95.5009 | 95.1676 | 96.3326 | 99.9658 | 99.8734 | 101.0038 | 101.4809 | 103.8643 | 102.3353 | 100.7071 | 102.5894 | 107.7704 | 107.666 | 108.8872 | 109.3981 | 111.9716 | 110.9817 | 110.5925 | 111.9427 | 116.1832 | 116.0656 | 117.3849 | 117.9319 | 120.7106 | 118.9188 | 117.0183 | 119.2051 | 125.2515 | 125.1194 | 126.5443 | 127.1301 | 130.1302 | 128.9672 | 128.5129 | 130.0777 | 135.026 | 134.8778 | 136.417 | 137.0441 | 140.2832 | 138.1842 | 135.9662 | 138.5065 | 145.5615 | 97.2388
|  | VAT facility interest after the funding period | USD m |  | 0.085999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.073584 | 0.012415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 52.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9497 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4
|  | Handback reserve contribution required | USD m |  | 19.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50038 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.692 | 1.1404
|  | Handback works at PPA expiry | USD m |  | 19.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2778
|  | Total operating costs | USD m |  | 6994.0499 | 0 | 0 | 0 | 0 | 0 | 0 | 36.1889 | 110.4421 | 110.4453 | 111.5858 | 112.2608 | 114.7416 | 113.945 | 116.0313 | 115.0163 | 119.1529 | 119.2196 | 120.4662 | 121.1934 | 123.875 | 122.2998 | 132.3606 | 122.715 | 128.6409 | 128.7099 | 130.0579 | 130.8413 | 133.7399 | 132.8043 | 135.2953 | 134.0502 | 138.8888 | 138.9602 | 140.4176 | 141.2618 | 144.3948 | 142.5483 | 154.5612 | 143.0262 | 149.9575 | 150.0314 | 151.607 | 152.5166 | 155.903 | 154.8048 | 157.7787 | 156.2539 | 161.9126 | 161.989 | 163.6925 | 164.6727 | 168.3327 | 166.169 | 180.512 | 166.7192 | 174.8252 | 136.2339
|  | EBITDA | USD m |  | 2624.6356 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9231 | 50.8061 | 50.9867 | 51.1375 | 51.2302 | 51.3107 | 51.475 | 49.1746 | 51.7572 | 51.7591 | 51.8895 | 52.0396 | 52.1401 | 52.2256 | 52.4421 | 39.839 | 52.7875 | 52.7109 | 52.8533 | 53.016 | 53.1251 | 53.2159 | 53.4135 | 50.6776 | 53.7481 | 53.7413 | 53.8967 | 54.0732 | 54.1915 | 54.2879 | 54.5495 | 39.6662 | 54.961 | 54.8566 | 55.0263 | 55.2177 | 55.3461 | 55.4484 | 55.6861 | 52.4321 | 56.0827 | 56.0642 | 56.2494 | 56.4571 | 56.5963 | 56.7049 | 57.0209 | 39.4244 | 57.511 | 57.3716 | 19.0884
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.181 | 40.0893 | 39.4807 | 40.4561 | 39.9842 | 41.0569 | 40.456 | 41.0733 | 40.787 | 42.4919 | 41.8473 | 42.8882 | 42.3913 | 43.5414 | 42.7358 | 42.8121 | 42.9218 | 45.0875 | 44.4041 | 45.5156 | 44.9918 | 46.2253 | 45.5424 | 46.2364 | 45.9289 | 47.8915 | 47.1661 | 48.3541 | 47.8011 | 49.1248 | 48.2033 | 48.2886 | 48.4208 | 50.9206 | 50.15 | 51.4205 | 50.836 | 52.2572 | 51.4787 | 52.2624 | 51.9301 | 54.1931 | 53.3735 | 54.7333 | 54.1147 | 55.6412 | 54.5845 | 54.6803 | 54.8389 | 57.7285 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18.9819 | 19.5735 | 19.1899 | 19.7674 | 19.5049 | 20.24 | 19.7893 | 20.0444 | 19.9466 | 21.1608 | 20.7459 | 21.3701 | 21.0862 | 21.8807 | 21.2472 | 21.2146 | 21.2651 | 22.8755 | 22.4268 | 23.1014 | 22.7943 | 23.653 | 23.126 | 23.4238 | 23.3092 | 24.7277 | 24.2425 | 24.9715 | 24.6394 | 25.5674 | 24.8268 | 24.7883 | 24.847 | 26.7282 | 26.2036 | 26.9914 | 26.6322 | 27.635 | 27.0188 | 27.3664 | 27.2321 | 28.8888 | 28.3216 | 29.1728 | 28.7844 | 29.8681 | 29.0024 | 28.957 | 29.0252 | 31.2222 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.2812 | 2.3199 | 2.3118 | 2.3505 | 2.345 | 2.3874 | 2.3779 | 2.4107 | 2.4086 | 2.4617 | 2.4531 | 2.4942 | 2.4883 | 2.5333 | 2.5203 | 2.5487 | 2.5498 | 2.6122 | 2.603 | 2.6467 | 2.6404 | 2.6882 | 2.6775 | 2.7144 | 2.7121 | 2.7718 | 2.7621 | 2.8084 | 2.8018 | 2.8524 | 2.8378 | 2.8698 | 2.8709 | 2.9411 | 2.9309 | 2.98 | 2.973 | 3.0267 | 3.0147 | 3.0562 | 3.0536 | 3.1208 | 3.1099 | 3.162 | 3.1546 | 3.2115 | 3.1951 | 3.2312 | 3.2325 | 3.3114 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.6811 | 1.7183 | 1.7034 | 1.7395 | 1.7354 | 1.7848 | 1.7648 | 1.7727 | 1.7833 | 1.8745 | 1.8583 | 1.8977 | 1.8932 | 1.9472 | 1.9124 | 1.9005 | 1.9191 | 2.045 | 2.0273 | 2.0703 | 2.0654 | 2.1242 | 2.1004 | 2.1099 | 2.1224 | 2.231 | 2.2117 | 2.2586 | 2.2532 | 2.3174 | 2.2761 | 2.2619 | 2.284 | 2.4339 | 2.4128 | 2.464 | 2.4581 | 2.5282 | 2.4999 | 2.5111 | 2.526 | 2.6553 | 2.6322 | 2.6881 | 2.6817 | 2.7581 | 2.7089 | 2.692 | 2.7184 | 2.8967 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.181 | 1.206 | 1.197 | 1.2266 | 1.2198 | 1.2479 | 1.2424 | 1.2668 | 1.263 | 1.3057 | 1.296 | 1.3281 | 1.3208 | 1.3513 | 1.3427 | 1.3627 | 1.3623 | 1.4142 | 1.4038 | 1.4386 | 1.4308 | 1.4639 | 1.4576 | 1.4864 | 1.4821 | 1.5324 | 1.5211 | 1.559 | 1.5506 | 1.5866 | 1.5766 | 1.6003 | 1.5999 | 1.661 | 1.6489 | 1.69 | 1.681 | 1.7201 | 1.7128 | 1.7468 | 1.7418 | 1.8011 | 1.7881 | 1.8327 | 1.823 | 1.8654 | 1.8538 | 1.8819 | 1.8815 | 1.9536 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.0558 | 15.2717 | 15.0787 | 15.3721 | 15.1792 | 15.3968 | 15.2816 | 15.5786 | 15.3854 | 15.6892 | 15.4941 | 15.798 | 15.6028 | 15.8288 | 15.7132 | 15.7856 | 15.8256 | 16.1406 | 15.9431 | 16.2586 | 16.0608 | 16.2959 | 16.1809 | 16.5019 | 16.3032 | 16.6287 | 16.4287 | 16.7566 | 16.5561 | 16.801 | 16.6861 | 16.7684 | 16.819 | 17.1564 | 16.9538 | 17.2952 | 17.0918 | 17.3472 | 17.2326 | 17.5819 | 17.3766 | 17.7272 | 17.5218 | 17.8777 | 17.6711 | 17.938 | 17.8242 | 17.9182 | 17.9814 | 18.3445 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0558 | 0.21587 | -0.19305 | 0.29338 | -0.19287 | 0.21758 | -0.11522 | 0.29704 | -0.19315 | 0.3038 | -0.19519 | 0.30398 | -0.19521 | 0.22601 | -0.11563 | 0.072417 | 0.039942 | 0.31506 | -0.19748 | 0.31545 | -0.19773 | 0.2351 | -0.11507 | 0.32099 | -0.19868 | 0.32548 | -0.19995 | 0.32788 | -0.20046 | 0.2449 | -0.11491 | 0.082281 | 0.050575 | 0.33744 | -0.20259 | 0.34134 | -0.20341 | 0.25548 | -0.11468 | 0.34929 | -0.20525 | 0.35057 | -0.20542 | 0.35593 | -0.2066 | 0.2669 | -0.11376 | 0.093977 | 0.063167 | 0.36315 | -18.3445
|  | Release of spares inventory at expiry | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4
| Tax depreciation (straight line from COD) | USD m |  | 876.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8881 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 22.7879 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 14.3155 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.5843
| Depreciation of holiday months (deemed deferred) | USD m |  | 236.6435 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8881 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 23.6643 | 15.7762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 639.8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0117 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 21.035 | 14.3155 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.87646 | 0.5843
| Shareholder loan interest accrued | USD m |  | 285.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4544 | 10.4126 | 10.512 | 10.3185 | 10.4955 | 10.3589 | 10.496 | 10.3171 | 10.4048 | 10.1134 | 10.278 | 10.076 | 10.4871 | 10.5913 | 10.9586 | 11.0176 | 11.399 | 11.3696 | 11.7129 | 11.6344 | 11.9069 | 11.7931 | 11.8527 | 10.7306 | 9.8606 | 8.5892 | 6.7168 | 4.5051 | 2.3538 | 0.40577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.6354 | 0.75276 | 0.83622 | 0.92218 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 278.7638 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1949 | 7.8382 | 8.7903 | 9.5155 | 10.4955 | 10.3589 | 10.496 | 10.3171 | 10.4048 | 10.1134 | 10.278 | 10.076 | 10.4871 | 10.5913 | 10.9586 | 11.0176 | 11.399 | 11.3696 | 11.7129 | 11.6344 | 11.9069 | 11.7931 | 11.8527 | 10.7306 | 9.8606 | 8.5892 | 6.7168 | 4.5051 | 2.3538 | 0.40577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 315.1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.4002 | 22.0588 | 21.2096 | 20.8072 | 19.9895 | 19.4476 | 18.5049 | 17.9539 | 17.5568 | 16.9956 | 16.0217 | 15.1442 | 13.9122 | 12.9018 | 11.5749 | 10.4378 | 9.2486 | 7.9942 | 6.5179 | 5.1747 | 3.7061 | 2.3224 | 1.6882 | 1.06 | 0.53089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Taxable income before losses and deferred depreciation | USD m |  | 1168.3805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1936 | 4.9068 | 5.4738 | 6.6871 | 7.5467 | -3.7885 | 9.9158 | 11.0577 | 12.1113 | 13.8287 | 15.0085 | 16.6818 | 18.2035 | 17.2238 | 21.7925 | 23.5862 | 26.145 | 28.5331 | 30.8027 | 32.8471 | 33.5146 | 18.6312 | 33.9261 | 33.8217 | 33.9914 | 34.1828 | 34.3111 | 34.4134 | 34.6511 | 31.3971 | 41.7672 | 55.1877 | 55.373 | 55.5806 | 55.7198 | 55.8284 | 56.1444 | 38.548 | 56.6346 | 56.4951 | 18.5041
| Tax losses used | USD m |  | 3.7885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 236.6435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1936 | 4.9068 | 5.4738 | 6.6871 | 7.5467 | 0 | 6.1273 | 11.0577 | 12.1113 | 13.8287 | 15.0085 | 16.6818 | 18.2035 | 17.2238 | 21.7925 | 23.5862 | 26.145 | 28.5331 | 0.53606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7.8881 | 31.5525 | 55.2168 | 78.8812 | 102.5455 | 126.2099 | 149.8742 | 173.5386 | 197.2029 | 220.8673 | 235.4499 | 230.543 | 225.0692 | 218.3821 | 210.8354 | 210.8354 | 204.7081 | 193.6504 | 181.5391 | 167.7104 | 152.7018 | 136.0201 | 117.8166 | 100.5927 | 78.8003 | 55.2141 | 29.0691 | 0.53606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 931.737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.2666 | 32.8471 | 33.5146 | 18.6312 | 33.9261 | 33.8217 | 33.9914 | 34.1828 | 34.3111 | 34.4134 | 34.6511 | 31.3971 | 41.7672 | 55.1877 | 55.373 | 55.5806 | 55.7198 | 55.8284 | 56.1444 | 38.548 | 56.6346 | 56.4951 | 18.5041
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Corporate income tax | USD m |  | 279.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.08 | 9.8541 | 10.0544 | 5.5894 | 10.1778 | 10.1465 | 10.1974 | 10.2548 | 10.2933 | 10.324 | 10.3953 | 9.4191 | 12.5302 | 16.5563 | 16.6119 | 16.6742 | 16.7159 | 16.7485 | 16.8433 | 11.5644 | 16.9904 | 16.9485 | 5.5512
| Minimum turnover tax | USD m |  | 15.7219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1186 | 0.35716 | 0.35896 | 0.36091 | 0.36181 | 0.35729 | 0.36443 | 0.36781 | 0.36943 | 0.37092 | 0.37288 | 0.375 | 0.37631 | 0.37708 | 0.3795 | 0.38251 | 0.38428 | 0.38591 | 0.38804 | 0.39035 | 0.39143 | 0.38662 | 0.39454 | 0.39853 | 0.40046 | 0.40223 | 0.40455 | 0.40707 | 0.40862 | 0.40954 | 0.41241 | 0.41598 | 0.41808 | 0.42001 | 0.42253 | 0.42527 | 0.42656 | 0.42141 | 0.43026 | 0.43498 | 0.29165
| Tax paid = max(CIT, MTT) | USD m |  | 285.9419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1186 | 0.35716 | 0.35896 | 0.36091 | 0.36181 | 0.35729 | 0.36443 | 0.36781 | 0.36943 | 0.37092 | 0.37288 | 0.375 | 0.37631 | 0.37708 | 0.3795 | 0.38251 | 0.38428 | 0.38591 | 9.08 | 9.8541 | 10.0544 | 5.5894 | 10.1778 | 10.1465 | 10.1974 | 10.2548 | 10.2933 | 10.324 | 10.3953 | 9.4191 | 12.5302 | 16.5563 | 16.6119 | 16.6742 | 16.7159 | 16.7485 | 16.8433 | 11.5644 | 16.9904 | 16.9485 | 5.5512
| Thin-cap disallowance | USD m |  | 6.3586 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 2.5744 | 1.7217 | 0.80297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.74057
|  | Gearing used in the closed-form gross-up | fraction | 0.74057
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97589
|  | First installment share of remaining profile | fraction | 0.026135
|  | DSRA coefficient per USD of E balance | factor | 0.048559
|  | DSRA coefficient per USD of A balance | factor | 0.060123
|  | DSRA coefficient per USD of B balance | factor | 0.058866
|  | DSRA coefficient per USD of C balance | factor | 0.071545
|  | DSRA coefficient per USD of standby balance | factor | 0.065238
|  | DSRA constant (swap net payment) | USD m | -0.44548
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0054193 | 0.0052445 | 0.0054193 | 0.0052445 | 0.0054193 | 0.0056617 | 0.0051138 | 0.0056617 | 0.005479 | 0.0056617 | 0.005479 | 0.0057963 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0058681 | 0.0054895 | 0.0058681 | 0.0056788 | 0.0058681 | 0.0056788 | 0.005904 | 0.005904 | 0.0057135 | 0.005904 | 0.0057135 | 0.005904 | 0.0059309 | 0.0053569 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0057396 | 0.0059309 | 0.0059488 | 0.0053731 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 108.1566 | 1.4969 | 2.1275 | 3.4343 | 5.3209 | 7.6664 | 10.394 | 13.3126 | 16.3512 | 19.3591 | 22.2359 | 24.8744 | 27.2288 | 29.2132 | 30.7343 | 31.797 | 32.3157 | 33.4452 | 31.8149 | 30.7328 | 29.2279 | 27.2364 | 24.9112 | 22.2102 | 19.323 | 16.3384 | 13.2722 | 10.3666 | 7.6158 | 5.2343 | 3.4443 | 2.0269 | 1.4226 | 1.3064 | 1.3382 | 1.3953 | 1.3919 | 1.3885 | 49.6256 | -0.38806 | 0.058015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 82.0763 | 83.4866 | 85.3894 | 88.281 | 92.6237 | 98.7784 | 106.9906 | 117.4823 | 130.3042 | 145.4691 | 162.8553 | 182.3407 | 203.6856 | 226.5917 | 250.7623 | 275.7995 | 301.3542 | 327.8781 | 353.1851 | 377.8472 | 401.4146 | 423.6065 | 444.0661 | 462.6177 | 479.0491 | 493.2194 | 505.1761 | 514.9112 | 522.6583 | 528.6384 | 533.0867 | 536.6729 | 539.7478 | 542.8128 | 545.8465 | 549.0025 | 552.168 | 555.2746 | 595.0671 | 596.9851 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227 | 599.3227
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0093225 | 0.0098258 | 0.010348 | 0.010854 | 0.01138 | 0.011909 | 0.012389 | 0.012922 | 0.01344 | 0.013976 | 0.014498 | 0.01504 | 0.015584 | 0.016113 | 0.016661 | 0.017193 | 0.017745 | 0.018301 | 0.018822 | 0.019381 | 0.019925 | 0.020488 | 0.021036 | 0.021604 | 0.022174 | 0.022729 | 0.023303 | 0.023862 | 0.024441 | 0.025023 | 0.02555 | 0.026136 | 0.026705 | 0.027296 | 0.02787 | 0.028465 | 0.029062 | 0.029642 | 0.030244 | 0.065036 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774 | 0.065774
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 888.1507
|  | Senior debt (committed tranches) | USD m | 657.74
|  | Debt share of monthly funding | fraction | 0.74057
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 27.1068 | 27.664 | 28.3739 | 29.3764 | 30.8192 | 32.8066 | 35.3982 | 38.6877 | 42.6722 | 47.3647 | 52.7194 | 58.7095 | 65.258 | 72.2706 | 79.6679 | 87.3209 | 95.1344 | 103.2395 | 110.9706 | 118.5182 | 125.7332 | 132.5409 | 138.8247 | 144.5416 | 149.623 | 154.0217 | 157.7619 | 160.8312 | 163.3096 | 165.2587 | 166.7337 | 167.9657 | 169.0399 | 170.1167 | 171.1797 | 172.285 | 173.3938 | 174.4804 | 186.5785 | 196.4241 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 19.8783 | 20.2869 | 20.8075 | 21.5427 | 22.6008 | 24.0582 | 25.9586 | 28.3709 | 31.2929 | 34.7341 | 38.6609 | 43.0536 | 47.8558 | 52.9984 | 58.4231 | 64.0353 | 69.7653 | 75.709 | 81.3784 | 86.9134 | 92.2044 | 97.1967 | 101.8048 | 105.9971 | 109.7235 | 112.9493 | 115.692 | 117.9429 | 119.7604 | 121.1897 | 122.2714 | 123.1749 | 123.9626 | 124.7523 | 125.5318 | 126.3423 | 127.1555 | 127.9523 | 136.8242 | 144.0444 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 9.0356 | 9.2213 | 9.458 | 9.7921 | 10.2731 | 10.9355 | 11.7994 | 12.8959 | 14.2241 | 15.7882 | 17.5731 | 19.5698 | 21.7527 | 24.0902 | 26.556 | 29.107 | 31.7115 | 34.4132 | 36.9902 | 39.5061 | 41.9111 | 44.1803 | 46.2749 | 48.1805 | 49.8743 | 51.3406 | 52.5873 | 53.6104 | 54.4365 | 55.0862 | 55.5779 | 55.9886 | 56.3466 | 56.7056 | 57.0599 | 57.4283 | 57.7979 | 58.1601 | 62.1928 | 65.4747 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 34.3353 | 35.0411 | 35.9403 | 37.2101 | 39.0377 | 41.5551 | 44.8377 | 49.0044 | 54.0514 | 59.9953 | 66.778 | 74.3654 | 82.6601 | 91.5428 | 100.9126 | 110.6065 | 120.5036 | 130.7701 | 140.5627 | 150.1231 | 159.2621 | 167.8852 | 175.8446 | 183.086 | 189.5224 | 195.0942 | 199.8317 | 203.7195 | 206.8588 | 209.3276 | 211.196 | 212.7566 | 214.1172 | 215.4812 | 216.8276 | 218.2277 | 219.6321 | 221.0085 | 236.3327 | 248.8039 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13
|  | ECA-covered tranche: interest | USD m |  | 16.3998 | 0 | 0.08742 | 0.09219 | 0.091506 | 0.097897 | 0.10987 | 0.10564 | 0.12619 | 0.13347 | 0.15213 | 0.16341 | 0.19475 | 0.21688 | 0.2333 | 0.26698 | 0.28481 | 0.32258 | 0.358 | 0.36343 | 0.41759 | 0.4316 | 0.47314 | 0.48267 | 0.52719 | 0.5489 | 0.54986 | 0.5849 | 0.57977 | 0.61076 | 0.62439 | 0.57069 | 0.63748 | 0.62147 | 0.6463 | 0.62943 | 0.65448 | 0.6587 | 0.64156 | 0.6671 | 0.69034 | 0.75099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 18.3432 | 0 | 0.10221 | 0.10779 | 0.10699 | 0.11446 | 0.12533 | 0.1205 | 0.14396 | 0.15226 | 0.17354 | 0.18641 | 0.21939 | 0.24432 | 0.26281 | 0.30075 | 0.32084 | 0.36338 | 0.4007 | 0.40679 | 0.46741 | 0.48309 | 0.52959 | 0.54025 | 0.58823 | 0.61246 | 0.61354 | 0.65263 | 0.64691 | 0.68148 | 0.69508 | 0.6353 | 0.70965 | 0.69183 | 0.71947 | 0.70069 | 0.72857 | 0.73328 | 0.71419 | 0.74262 | 0.7685 | 0.83602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 8.0257 | 0 | 0.044576 | 0.047008 | 0.046659 | 0.049918 | 0.054758 | 0.052649 | 0.062894 | 0.066521 | 0.075818 | 0.081441 | 0.09594 | 0.10684 | 0.11493 | 0.13152 | 0.1403 | 0.15891 | 0.17531 | 0.17797 | 0.20449 | 0.21136 | 0.2317 | 0.23636 | 0.25742 | 0.26802 | 0.26849 | 0.2856 | 0.28309 | 0.29822 | 0.30422 | 0.27806 | 0.3106 | 0.3028 | 0.3149 | 0.30668 | 0.31889 | 0.32094 | 0.31259 | 0.32503 | 0.33636 | 0.36591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 37.576 | 0 | 0.21046 | 0.22195 | 0.2203 | 0.23569 | 0.25735 | 0.24743 | 0.29558 | 0.31263 | 0.35632 | 0.38275 | 0.4498 | 0.50091 | 0.53882 | 0.61661 | 0.6578 | 0.74502 | 0.82091 | 0.83338 | 0.95756 | 0.9897 | 1.0849 | 1.1068 | 1.2046 | 1.2543 | 1.2565 | 1.3365 | 1.3248 | 1.3956 | 1.423 | 1.3007 | 1.4529 | 1.4164 | 1.473 | 1.4345 | 1.4916 | 1.5013 | 1.4622 | 1.5204 | 1.5734 | 1.7116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 4.8425 | 0 | 0.029209 | 0.030803 | 0.030574 | 0.032709 | 0.034316 | 0.032994 | 0.039414 | 0.041687 | 0.047513 | 0.051037 | 0.058701 | 0.06537 | 0.070318 | 0.08047 | 0.085845 | 0.097228 | 0.10593 | 0.10754 | 0.12356 | 0.12771 | 0.14 | 0.14282 | 0.15457 | 0.16094 | 0.16122 | 0.1715 | 0.16999 | 0.17908 | 0.18184 | 0.1662 | 0.18565 | 0.18099 | 0.18822 | 0.18331 | 0.1906 | 0.19183 | 0.18684 | 0.19428 | 0.20104 | 0.21871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | -0.78015 | 0 | 0.025634 | 0.021014 | 0.026832 | 0.022316 | 0.0043689 | 0.024928 | 0.0050195 | 0.01346 | 0.0060535 | 0.016486 | -0.010638 | -0.011849 | 0.0010133 | -0.014591 | 0.0012374 | -0.017633 | -0.036666 | 0.0063394 | -0.042776 | -0.019205 | -0.048472 | -0.021479 | -0.066261 | -0.068991 | -0.037536 | -0.073518 | -0.039578 | -0.076769 | -0.089192 | 0.023114 | -0.091062 | -0.053325 | -0.098323 | -0.060108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 10.4211 | 0.57103 | 0.4767 | 0.49097 | 0.47315 | 0.48602 | 0.48184 | 0.43002 | 0.46859 | 0.44426 | 0.44754 | 0.41996 | 0.41847 | 0.40113 | 0.36985 | 0.36189 | 0.3295 | 0.31833 | 0.29572 | 0.2547 | 0.24989 | 0.22069 | 0.20717 | 0.18142 | 0.16929 | 0.15274 | 0.13358 | 0.12531 | 0.11079 | 0.1056 | 0.098429 | 0.083809 | 0.08852 | 0.082214 | 0.081846 | 0.07619 | 0.075653 | 0.072455 | 0.067012 | 0.066101 | 0.030088 | 0.0025983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.95757 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 10.3397 | 10.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.87125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 39.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 119.0673 | 2.4475 | 3.1182 | 4.4035 | 6.3376 | 8.7299 | 11.3832 | 14.4492 | 17.502 | 20.612 | 23.5209 | 26.3115 | 28.7642 | 30.8033 | 32.4925 | 33.6161 | 34.3212 | 35.6018 | 33.9587 | 33.1533 | 31.6921 | 29.9029 | 27.6015 | 25.1116 | 22.3203 | 19.3216 | 16.4287 | 13.4819 | 10.8866 | 8.5613 | 6.4791 | 5.4117 | 4.7183 | 4.7301 | 4.6691 | 4.8551 | 4.8704 | 4.7729 | 53.1412 | 43.2473 | 3.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 657.74 | 567.3839 | 565.5266 | 563.1604 | 559.8187 | 555.0093 | 548.3845 | 539.7462 | 528.7811 | 515.4995 | 499.8578 | 482.0085 | 462.0417 | 440.2135 | 416.838 | 392.1805 | 366.6704 | 340.6252 | 313.6082 | 287.8381 | 262.6793 | 238.6292 | 215.9369 | 194.9911 | 175.9348 | 158.9967 | 144.3342 | 131.8671 | 121.6361 | 113.3746 | 106.8778 | 101.961 | 97.8543 | 94.2737 | 90.6842 | 87.141 | 83.4566 | 79.7607 | 76.1387 | 35.8117 | 2.9929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior tranche drawdown (pro rata) | USD m |  | 657.74 | 90.3561 | 1.8573 | 2.3663 | 3.3417 | 4.8094 | 6.6248 | 8.6384 | 10.965 | 13.2817 | 15.6417 | 17.8492 | 19.9669 | 21.8282 | 23.3755 | 24.6575 | 25.5101 | 26.0452 | 27.017 | 25.7701 | 25.1589 | 24.05 | 22.6923 | 20.9458 | 19.0563 | 16.9381 | 14.6625 | 12.4672 | 10.231 | 8.2614 | 6.4969 | 4.9168 | 4.1067 | 3.5806 | 3.5895 | 3.5432 | 3.6844 | 3.696 | 3.622 | 40.327 | 32.8189 | 2.9929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 21.4094 | 2.9411 | 0.060455 | 0.077022 | 0.10877 | 0.15655 | 0.21564 | 0.28118 | 0.35691 | 0.43232 | 0.50914 | 0.58099 | 0.64992 | 0.71051 | 0.76087 | 0.8026 | 0.83035 | 0.84777 | 0.8794 | 0.83882 | 0.81892 | 0.78283 | 0.73863 | 0.68179 | 0.62028 | 0.55134 | 0.47726 | 0.40581 | 0.33302 | 0.26891 | 0.21147 | 0.16004 | 0.13367 | 0.11655 | 0.11684 | 0.11533 | 0.11993 | 0.1203 | 0.1179 | 1.3126 | 1.0683 | 0.097417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 888.1507 | 122.0084 | 2.5079 | 3.1952 | 4.5123 | 6.4942 | 8.9455 | 11.6644 | 14.8061 | 17.9343 | 21.1211 | 24.1019 | 26.9614 | 29.4748 | 31.5641 | 33.2951 | 34.4465 | 35.169 | 36.4812 | 34.7975 | 33.9722 | 32.4749 | 30.6416 | 28.2833 | 25.7319 | 22.8716 | 19.7988 | 16.8345 | 13.815 | 11.1555 | 8.7728 | 6.6391 | 5.5454 | 4.8349 | 4.8469 | 4.7844 | 4.975 | 4.9907 | 4.8908 | 54.4538 | 44.3155 | 4.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 888.1507 | 122.0084 | 2.5079 | 3.1952 | 4.5123 | 6.4942 | 8.9455 | 11.6644 | 14.8061 | 17.9343 | 21.1211 | 24.1019 | 26.9614 | 29.4748 | 31.5641 | 33.2951 | 34.4465 | 35.169 | 36.4812 | 34.7975 | 33.9722 | 32.4749 | 30.6416 | 28.2833 | 25.7319 | 22.8716 | 19.7988 | 16.8345 | 13.815 | 11.1555 | 8.7728 | 6.6391 | 5.5454 | 4.8349 | 4.8469 | 4.7844 | 4.975 | 4.9907 | 4.8908 | 54.4538 | 44.3155 | 4.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6645e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility drawdown (75%) | USD m |  | 1.9984e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9984e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 6.6613e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6613e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 197.322 | 27.1068 | 0.55719 | 0.70988 | 1.0025 | 1.4428 | 1.9874 | 2.5915 | 3.2895 | 3.9845 | 4.6925 | 5.3548 | 5.9901 | 6.5485 | 7.0127 | 7.3972 | 7.653 | 7.8136 | 8.1051 | 7.731 | 7.5477 | 7.215 | 6.8077 | 6.2837 | 5.7169 | 5.0814 | 4.3987 | 3.7401 | 3.0693 | 2.4784 | 1.9491 | 1.475 | 1.232 | 1.0742 | 1.0768 | 1.063 | 1.1053 | 1.1088 | 1.0866 | 12.0981 | 9.8457 | 0.89786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 144.7028 | 19.8783 | 0.4086 | 0.52058 | 0.73517 | 1.0581 | 1.4575 | 1.9004 | 2.4123 | 2.922 | 3.4412 | 3.9268 | 4.3927 | 4.8022 | 5.1426 | 5.4246 | 5.6122 | 5.7299 | 5.9437 | 5.6694 | 5.535 | 5.291 | 4.9923 | 4.6081 | 4.1924 | 3.7264 | 3.2257 | 2.7428 | 2.2508 | 1.8175 | 1.4293 | 1.0817 | 0.90348 | 0.78772 | 0.78969 | 0.77951 | 0.81056 | 0.81311 | 0.79683 | 8.8719 | 7.2201 | 0.65843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 65.774 | 9.0356 | 0.18573 | 0.23663 | 0.33417 | 0.48094 | 0.66248 | 0.86384 | 1.0965 | 1.3282 | 1.5642 | 1.7849 | 1.9967 | 2.1828 | 2.3376 | 2.4657 | 2.551 | 2.6045 | 2.7017 | 2.577 | 2.5159 | 2.405 | 2.2692 | 2.0946 | 1.9056 | 1.6938 | 1.4662 | 1.2467 | 1.0231 | 0.82614 | 0.64969 | 0.49168 | 0.41067 | 0.35806 | 0.35895 | 0.35432 | 0.36844 | 0.3696 | 0.3622 | 4.0327 | 3.2819 | 0.29929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 249.9412 | 34.3353 | 0.70577 | 0.89918 | 1.2698 | 1.8276 | 2.5174 | 3.2826 | 4.1667 | 5.047 | 5.9439 | 6.7827 | 7.5874 | 8.2947 | 8.8827 | 9.3698 | 9.6939 | 9.8972 | 10.2664 | 9.7926 | 9.5604 | 9.139 | 8.6231 | 7.9594 | 7.2414 | 6.4365 | 5.5717 | 4.7375 | 3.8878 | 3.1393 | 2.4688 | 1.8684 | 1.5606 | 1.3606 | 1.364 | 1.3464 | 1.4001 | 1.4045 | 1.3763 | 15.3243 | 12.4712 | 1.1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 27.1068 | 27.664 | 28.3739 | 29.3764 | 30.8192 | 32.8066 | 35.3982 | 38.6877 | 42.6722 | 47.3647 | 52.7194 | 58.7095 | 65.258 | 72.2706 | 79.6679 | 87.3209 | 95.1344 | 103.2395 | 110.9706 | 118.5182 | 125.7332 | 132.5409 | 138.8247 | 144.5416 | 149.623 | 154.0217 | 157.7619 | 160.8312 | 163.3096 | 165.2587 | 166.7337 | 167.9657 | 169.0399 | 170.1167 | 171.1797 | 172.285 | 173.3938 | 174.4804 | 186.5785 | 196.4241 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322 | 197.322
|  | ABDB A-loan: closing balance | USD m |  |  | 19.8783 | 20.2869 | 20.8075 | 21.5427 | 22.6008 | 24.0582 | 25.9586 | 28.3709 | 31.2929 | 34.7341 | 38.6609 | 43.0536 | 47.8558 | 52.9984 | 58.4231 | 64.0353 | 69.7653 | 75.709 | 81.3784 | 86.9134 | 92.2044 | 97.1967 | 101.8048 | 105.9971 | 109.7235 | 112.9493 | 115.692 | 117.9429 | 119.7604 | 121.1897 | 122.2714 | 123.1749 | 123.9626 | 124.7523 | 125.5318 | 126.3423 | 127.1555 | 127.9523 | 136.8242 | 144.0444 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028 | 144.7028
|  | ABDB B-loan: closing balance | USD m |  |  | 9.0356 | 9.2213 | 9.458 | 9.7921 | 10.2731 | 10.9355 | 11.7994 | 12.8959 | 14.2241 | 15.7882 | 17.5731 | 19.5698 | 21.7527 | 24.0902 | 26.556 | 29.107 | 31.7115 | 34.4132 | 36.9902 | 39.5061 | 41.9111 | 44.1803 | 46.2749 | 48.1805 | 49.8743 | 51.3406 | 52.5873 | 53.6104 | 54.4365 | 55.0862 | 55.5779 | 55.9886 | 56.3466 | 56.7056 | 57.0599 | 57.4283 | 57.7979 | 58.1601 | 62.1928 | 65.4747 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774 | 65.774
|  | Commercial tranche: closing balance | USD m |  |  | 34.3353 | 35.0411 | 35.9403 | 37.2101 | 39.0377 | 41.5551 | 44.8377 | 49.0044 | 54.0514 | 59.9953 | 66.778 | 74.3654 | 82.6601 | 91.5428 | 100.9126 | 110.6065 | 120.5036 | 130.7701 | 140.5627 | 150.1231 | 159.2621 | 167.8852 | 175.8446 | 183.086 | 189.5224 | 195.0942 | 199.8317 | 203.7195 | 206.8588 | 209.3276 | 211.196 | 212.7566 | 214.1172 | 215.4812 | 216.8276 | 218.2277 | 219.6321 | 221.0085 | 236.3327 | 248.8039 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412 | 249.9412
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13 | 1.9984e-13
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 230.4107 | 31.6523 | 0.65062 | 0.82892 | 1.1706 | 1.6848 | 2.3207 | 3.0261 | 3.8411 | 4.6527 | 5.4794 | 6.2527 | 6.9945 | 7.6466 | 8.1886 | 8.6377 | 8.9364 | 9.1238 | 9.4642 | 9.0274 | 8.8133 | 8.4249 | 7.9493 | 7.3375 | 6.6755 | 5.9335 | 5.1364 | 4.3673 | 3.584 | 2.894 | 2.2759 | 1.7224 | 1.4386 | 1.2543 | 1.2574 | 1.2412 | 1.2907 | 1.2947 | 1.2688 | 14.1268 | 11.4967 | 1.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 216.2107 | 17.4523 | 0.65062 | 0.82892 | 1.1706 | 1.6848 | 2.3207 | 3.0261 | 3.8411 | 4.6527 | 5.4794 | 6.2527 | 6.9945 | 7.6466 | 8.1886 | 8.6377 | 8.9364 | 9.1238 | 9.4642 | 9.0274 | 8.8133 | 8.4249 | 7.9493 | 7.3375 | 6.6755 | 5.9335 | 5.1364 | 4.3673 | 3.584 | 2.894 | 2.2759 | 1.7224 | 1.4386 | 1.2543 | 1.2574 | 1.2412 | 1.2907 | 1.2947 | 1.2688 | 14.1268 | 11.4967 | 1.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 46.0821 | 6.3305 | 0.13012 | 0.16578 | 0.23412 | 0.33695 | 0.46414 | 0.60521 | 0.76822 | 0.93053 | 1.0959 | 1.2505 | 1.3989 | 1.5293 | 1.6377 | 1.7275 | 1.7873 | 1.8248 | 1.8928 | 1.8055 | 1.7627 | 1.685 | 1.5899 | 1.4675 | 1.3351 | 1.1867 | 1.0273 | 0.87347 | 0.7168 | 0.57881 | 0.45518 | 0.34447 | 0.28772 | 0.25086 | 0.25148 | 0.24824 | 0.25813 | 0.25894 | 0.25376 | 2.8254 | 2.2993 | 0.20968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 184.3285 | 25.3219 | 0.5205 | 0.66314 | 0.93648 | 1.3478 | 1.8566 | 2.4209 | 3.0729 | 3.7221 | 4.3835 | 5.0022 | 5.5956 | 6.1172 | 6.5509 | 6.9101 | 7.1491 | 7.299 | 7.5714 | 7.2219 | 7.0507 | 6.7399 | 6.3594 | 5.87 | 5.3404 | 4.7468 | 4.1091 | 3.4939 | 2.8672 | 2.3152 | 1.8207 | 1.3779 | 1.1509 | 1.0034 | 1.0059 | 0.99297 | 1.0325 | 1.0358 | 1.015 | 11.3014 | 9.1973 | 0.83873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 33.2469 | 0 | 0.19772 | 0.2101 | 0.21015 | 0.2264 | 0.2391 | 0.23124 | 0.27741 | 0.29462 | 0.33685 | 0.36284 | 0.41823 | 0.46675 | 0.5031 | 0.57679 | 0.61664 | 0.69985 | 0.76439 | 0.77799 | 0.8962 | 0.92934 | 1.0222 | 1.0469 | 1.1376 | 1.1898 | 1.1978 | 1.2805 | 1.2765 | 1.3525 | 1.3821 | 1.2717 | 1.4293 | 1.4034 | 1.4696 | 1.4415 | 1.5092 | 1.5297 | 1.5004 | 1.5707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 25.3219 | 26.0401 | 26.9133 | 28.06 | 29.6342 | 31.7298 | 34.3819 | 37.7322 | 41.749 | 46.4694 | 51.8344 | 57.8482 | 64.4322 | 71.4862 | 78.9731 | 86.7388 | 94.7377 | 103.0735 | 111.0734 | 119.0203 | 126.6895 | 134.0711 | 140.988 | 147.466 | 153.4026 | 158.7095 | 163.4839 | 167.6276 | 171.2953 | 174.4982 | 177.1477 | 179.7279 | 182.1347 | 184.6102 | 187.0447 | 189.5864 | 192.1518 | 194.6672 | 207.5394 | 216.7367 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754 | 217.5754
|  | Total debt drawdowns (incl. standby) | USD m |  | 657.74 | 90.3561 | 1.8573 | 2.3663 | 3.3417 | 4.8094 | 6.6248 | 8.6384 | 10.965 | 13.2817 | 15.6417 | 17.8492 | 19.9669 | 21.8282 | 23.3755 | 24.6575 | 25.5101 | 26.0452 | 27.017 | 25.7701 | 25.1589 | 24.05 | 22.6923 | 20.9458 | 19.0563 | 16.9381 | 14.6625 | 12.4672 | 10.231 | 8.2614 | 6.4969 | 4.9168 | 4.1067 | 3.5806 | 3.5895 | 3.5432 | 3.6844 | 3.696 | 3.622 | 40.327 | 32.8189 | 2.9929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 129.9508 | 13.8968 | 1.1004 | 1.1538 | 1.1685 | 1.2613 | 1.3504 | 1.3595 | 1.5701 | 1.6701 | 1.8478 | 1.9469 | 2.1486 | 2.3133 | 2.4362 | 2.6398 | 2.7486 | 2.9423 | 3.1116 | 3.0996 | 3.3169 | 3.347 | 3.4801 | 3.4704 | 3.5769 | 3.5983 | 3.5346 | 3.5985 | 3.5101 | 3.5604 | 3.5399 | 3.2954 | 3.504 | 3.4273 | 3.5062 | 3.4436 | 3.6343 | 3.6499 | 3.55 | 4.875 | 4.7254 | 4.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 888.1507
|  | Capitalized cost (book and tax) | USD m | 876.4574

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01978 | 0.020815 | 0.021927 | 0.022093 | 0.02254 | 0.022323 | 0.022693 | 0.022424 | 0.022796 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847
|  | ABDB A-loan: rate per period | factor |  |  | 0.031536 | 0.032379 | 0.033682 | 0.033721 | 0.034296 | 0.033887 | 0.034449 | 0.033988 | 0.034551 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602
|  | ABDB B-loan: rate per period | factor |  |  | 0.030258 | 0.031122 | 0.032404 | 0.032457 | 0.033018 | 0.03263 | 0.033171 | 0.032731 | 0.033273 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324
|  | Commercial tranche: rate per period | factor |  |  | 0.037595 | 0.03849 | 0.03998 | 0.039995 | 0.040662 | 0.040166 | 0.040832 | 0.040278 | 0.040946 | 0.040334 | 0.041002 | 0.040557 | 0.041002 | 0.040334 | 0.041002 | 0.043127 | 0.043842 | 0.043127 | 0.043842 | 0.043365 | 0.043842 | 0.043127 | 0.043842 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037387 | 0.038824 | 0.038833 | 0.039478 | 0.038995 | 0.039642 | 0.039103 | 0.039751 | 0.039156 | 0.039805 | 0.039373 | 0.039805 | 0.039156 | 0.039805 | 0.040832 | 0.041509 | 0.040832 | 0.041509 | 0.041058 | 0.041509 | 0.040832 | 0.041509 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97554 | 0.95004 | 0.92329 | 0.89575 | 0.86695 | 0.83722 | 0.80555 | 0.77292 | 0.74119 | 0.70944 | 0.67638 | 0.64236 | 0.60671 | 0.56988 | 0.52966 | 0.48772 | 0.4443 | 0.40007 | 0.35363 | 0.30582 | 0.2557 | 0.20396 | 0.14909 | 0.093089 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.026135 | 0.028158 | 0.029828 | 0.032159 | 0.034287 | 0.037824 | 0.040513 | 0.041052 | 0.042829 | 0.046599 | 0.050303 | 0.055498 | 0.060706 | 0.07057 | 0.079192 | 0.08902 | 0.099542 | 0.1161 | 0.1352 | 0.16389 | 0.20235 | 0.269 | 0.37563 | 0.49632 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197.322 | 192.165 | 186.754 | 181.1835 | 175.3568 | 169.3443 | 162.9389 | 156.3378 | 149.9199 | 143.499 | 136.812 | 129.9299 | 122.7191 | 115.2693 | 107.1348 | 98.6506 | 89.8687 | 80.923 | 71.5281 | 61.8574 | 51.7199 | 41.2542 | 30.157 | 18.8291 | 9.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 65.2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4247 | 4.3805 | 4.1971 | 4.1394 | 3.9628 | 3.869 | 3.6619 | 3.5718 | 3.3693 | 3.2785 | 3.0747 | 2.9685 | 2.7732 | 2.6335 | 2.4078 | 2.2538 | 2.0197 | 1.8488 | 1.6075 | 1.4132 | 1.1688 | 0.94252 | 0.67775 | 0.43018 | 0.21314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 197.322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.157 | 5.411 | 5.5705 | 5.8267 | 6.0125 | 6.4053 | 6.6011 | 6.4179 | 6.4209 | 6.6869 | 6.8821 | 7.2109 | 7.4497 | 8.1346 | 8.4842 | 8.7818 | 8.9457 | 9.3948 | 9.6707 | 10.1376 | 10.4657 | 11.0972 | 11.3278 | 9.3453 | 9.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 197.322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.157 | 5.411 | 5.5705 | 5.8267 | 6.0125 | 6.4053 | 6.6011 | 6.4179 | 6.4209 | 6.6869 | 6.8821 | 7.2109 | 7.4497 | 8.1346 | 8.4842 | 8.7818 | 8.9457 | 9.3948 | 9.6707 | 10.1376 | 10.4657 | 11.0972 | 11.3278 | 9.3453 | 9.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.165 | 186.754 | 181.1835 | 175.3568 | 169.3443 | 162.9389 | 156.3378 | 149.9199 | 143.499 | 136.812 | 129.9299 | 122.7191 | 115.2693 | 107.1348 | 98.6506 | 89.8687 | 80.923 | 71.5281 | 61.8574 | 51.7199 | 41.2542 | 30.157 | 18.8291 | 9.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 197.322 | 192.165 | 186.754 | 181.1835 | 175.3568 | 169.3443 | 162.9389 | 156.3378 | 149.9199 | 143.499 | 136.812 | 129.9299 | 122.7191 | 115.2693 | 107.1348 | 98.6506 | 89.8687 | 80.923 | 71.5281 | 61.8574 | 51.7199 | 41.2542 | 30.157 | 18.8291 | 9.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.7028 | 140.921 | 136.9529 | 132.8679 | 128.595 | 124.1858 | 119.4885 | 114.6477 | 109.9412 | 105.2326 | 100.3288 | 95.282 | 89.994 | 84.5309 | 78.5655 | 72.3437 | 65.9037 | 59.3435 | 52.454 | 45.3621 | 37.9279 | 30.2531 | 22.1151 | 13.808 | 6.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 72.5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9181 | 4.869 | 4.6616 | 4.5975 | 4.4013 | 4.2971 | 4.0672 | 3.9671 | 3.7422 | 3.6413 | 3.415 | 3.297 | 3.0801 | 2.925 | 2.6742 | 2.5033 | 2.2432 | 2.0534 | 1.7854 | 1.5696 | 1.2981 | 1.0468 | 0.75276 | 0.47779 | 0.23673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 144.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7818 | 3.9681 | 4.085 | 4.2729 | 4.4092 | 4.6972 | 4.8408 | 4.7065 | 4.7087 | 4.9038 | 5.0469 | 5.288 | 5.4631 | 5.9654 | 6.2218 | 6.44 | 6.5602 | 6.8895 | 7.0918 | 7.4342 | 7.6749 | 8.1379 | 8.3071 | 6.8532 | 6.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 144.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7818 | 3.9681 | 4.085 | 4.2729 | 4.4092 | 4.6972 | 4.8408 | 4.7065 | 4.7087 | 4.9038 | 5.0469 | 5.288 | 5.4631 | 5.9654 | 6.2218 | 6.44 | 6.5602 | 6.8895 | 7.0918 | 7.4342 | 7.6749 | 8.1379 | 8.3071 | 6.8532 | 6.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.921 | 136.9529 | 132.8679 | 128.595 | 124.1858 | 119.4885 | 114.6477 | 109.9412 | 105.2326 | 100.3288 | 95.282 | 89.994 | 84.5309 | 78.5655 | 72.3437 | 65.9037 | 59.3435 | 52.454 | 45.3621 | 37.9279 | 30.2531 | 22.1151 | 13.808 | 6.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 144.7028 | 140.921 | 136.9529 | 132.8679 | 128.595 | 124.1858 | 119.4885 | 114.6477 | 109.9412 | 105.2326 | 100.3288 | 95.282 | 89.994 | 84.5309 | 78.5655 | 72.3437 | 65.9037 | 59.3435 | 52.454 | 45.3621 | 37.9279 | 30.2531 | 22.1151 | 13.808 | 6.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.774 | 64.055 | 62.2513 | 60.3945 | 58.4523 | 56.4481 | 54.313 | 52.1126 | 49.9733 | 47.833 | 45.604 | 43.31 | 40.9064 | 38.4231 | 35.7116 | 32.8835 | 29.9562 | 26.9743 | 23.8427 | 20.6191 | 17.24 | 13.7514 | 10.0523 | 6.2764 | 3.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 31.7465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1528 | 2.1313 | 2.0407 | 2.0126 | 1.9267 | 1.8811 | 1.7804 | 1.7366 | 1.6382 | 1.594 | 1.495 | 1.4433 | 1.3484 | 1.2804 | 1.1707 | 1.0958 | 0.982 | 0.8989 | 0.78159 | 0.68712 | 0.56827 | 0.45826 | 0.32953 | 0.20916 | 0.10363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 65.774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.719 | 1.8037 | 1.8568 | 1.9422 | 2.0042 | 2.1351 | 2.2004 | 2.1393 | 2.1403 | 2.229 | 2.294 | 2.4036 | 2.4832 | 2.7115 | 2.8281 | 2.9273 | 2.9819 | 3.1316 | 3.2236 | 3.3792 | 3.4886 | 3.6991 | 3.7759 | 3.1151 | 3.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 65.774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.719 | 1.8037 | 1.8568 | 1.9422 | 2.0042 | 2.1351 | 2.2004 | 2.1393 | 2.1403 | 2.229 | 2.294 | 2.4036 | 2.4832 | 2.7115 | 2.8281 | 2.9273 | 2.9819 | 3.1316 | 3.2236 | 3.3792 | 3.4886 | 3.6991 | 3.7759 | 3.1151 | 3.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.055 | 62.2513 | 60.3945 | 58.4523 | 56.4481 | 54.313 | 52.1126 | 49.9733 | 47.833 | 45.604 | 43.31 | 40.9064 | 38.4231 | 35.7116 | 32.8835 | 29.9562 | 26.9743 | 23.8427 | 20.6191 | 17.24 | 13.7514 | 10.0523 | 6.2764 | 3.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 65.774 | 64.055 | 62.2513 | 60.3945 | 58.4523 | 56.4481 | 54.313 | 52.1126 | 49.9733 | 47.833 | 45.604 | 43.31 | 40.9064 | 38.4231 | 35.7116 | 32.8835 | 29.9562 | 26.9743 | 23.8427 | 20.6191 | 17.24 | 13.7514 | 10.0523 | 6.2764 | 3.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.9412 | 243.409 | 236.5551 | 229.4991 | 222.1186 | 214.5027 | 206.3893 | 198.0279 | 189.8985 | 181.7653 | 173.2952 | 159.5982 | 144.8617 | 130.7137 | 115.5758 | 99.5574 | 82.6177 | 66.2566 | 49.2397 | 32.6106 | 15.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 136.6188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0672 | 9.9665 | 9.5412 | 9.41 | 9.0084 | 8.7951 | 8.3245 | 8.1196 | 8.1898 | 7.969 | 7.4737 | 6.9971 | 6.282 | 5.7307 | 4.9845 | 4.3648 | 3.7938 | 3.093 | 2.2611 | 1.5223 | 0.72443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 161.3469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5322 | 6.854 | 7.0559 | 7.3805 | 7.6159 | 8.1134 | 8.3614 | 8.1293 | 8.1332 | 8.4701 | 8.7173 | 8.8574 | 8.7939 | 9.2245 | 9.1527 | 8.8626 | 8.224 | 7.6921 | 6.6573 | 5.3444 | 3.1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 161.3469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5322 | 6.854 | 7.0559 | 7.3805 | 7.6159 | 8.1134 | 8.3614 | 8.1293 | 8.1332 | 8.4701 | 8.7173 | 8.8574 | 8.7939 | 9.2245 | 9.1527 | 8.8626 | 8.224 | 7.6921 | 6.6573 | 5.3444 | 3.1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243.409 | 236.5551 | 229.4991 | 222.1186 | 214.5027 | 206.3893 | 198.0279 | 189.8985 | 181.7653 | 173.2952 | 164.5779 | 150.7409 | 136.0678 | 121.4892 | 106.4231 | 90.6949 | 74.3937 | 58.5645 | 42.5824 | 27.2662 | 12.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 88.5943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 12.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 249.9412 | 243.409 | 236.5551 | 229.4991 | 222.1186 | 214.5027 | 206.3893 | 198.0279 | 189.8985 | 181.7653 | 173.2952 | 159.5982 | 144.8617 | 130.7137 | 115.5758 | 99.5574 | 82.6177 | 66.2566 | 49.2397 | 32.6106 | 15.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9984e-13 | 1.9462e-13 | 1.8914e-13 | 1.835e-13 | 1.7759e-13 | 1.7151e-13 | 1.6502e-13 | 1.5833e-13 | 1.5183e-13 | 1.4533e-13 | 1.3856e-13 | 1.3159e-13 | 1.2429e-13 | 1.1674e-13 | 1.085e-13 | 9.9909e-14 | 9.1016e-14 | 8.1956e-14 | 7.2441e-14 | 6.2647e-14 | 5.238e-14 | 4.1781e-14 | 3.0542e-14 | 1.9069e-14 | 9.6048e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 1.1849e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8143e-15 | 7.7362e-15 | 7.4059e-15 | 7.3041e-15 | 6.9924e-15 | 6.8268e-15 | 6.4615e-15 | 6.3025e-15 | 6.1997e-15 | 6.0325e-15 | 5.6576e-15 | 5.4621e-15 | 5.1029e-15 | 4.8458e-15 | 4.4304e-15 | 4.1471e-15 | 3.8689e-15 | 3.5415e-15 | 3.0793e-15 | 2.7071e-15 | 2.2389e-15 | 1.8055e-15 | 1.2983e-15 | 8.2404e-16 | 4.0828e-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 1.9984e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2228e-15 | 5.4801e-15 | 5.6416e-15 | 5.9011e-15 | 6.0893e-15 | 6.4871e-15 | 6.6854e-15 | 6.4998e-15 | 6.5029e-15 | 6.7723e-15 | 6.9699e-15 | 7.3029e-15 | 7.5448e-15 | 8.2384e-15 | 8.5925e-15 | 8.8939e-15 | 9.0599e-15 | 9.5147e-15 | 9.7941e-15 | 1.0267e-14 | 1.0599e-14 | 1.1239e-14 | 1.1472e-14 | 9.4646e-15 | 9.6048e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 1.9984e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2228e-15 | 5.4801e-15 | 5.6416e-15 | 5.9011e-15 | 6.0893e-15 | 6.4871e-15 | 6.6854e-15 | 6.4998e-15 | 6.5029e-15 | 6.7723e-15 | 6.9699e-15 | 7.3029e-15 | 7.5448e-15 | 8.2384e-15 | 8.5925e-15 | 8.8939e-15 | 9.0599e-15 | 9.5147e-15 | 9.7941e-15 | 1.0267e-14 | 1.0599e-14 | 1.1239e-14 | 1.1472e-14 | 9.4646e-15 | 9.6048e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9462e-13 | 1.8914e-13 | 1.835e-13 | 1.7759e-13 | 1.7151e-13 | 1.6502e-13 | 1.5833e-13 | 1.5183e-13 | 1.4533e-13 | 1.3856e-13 | 1.3159e-13 | 1.2429e-13 | 1.1674e-13 | 1.085e-13 | 9.9909e-14 | 9.1016e-14 | 8.1956e-14 | 7.2441e-14 | 6.2647e-14 | 5.238e-14 | 4.1781e-14 | 3.0542e-14 | 1.9069e-14 | 9.6048e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.9984e-13 | 1.9462e-13 | 1.8914e-13 | 1.835e-13 | 1.7759e-13 | 1.7151e-13 | 1.6502e-13 | 1.5833e-13 | 1.5183e-13 | 1.4533e-13 | 1.3856e-13 | 1.3159e-13 | 1.2429e-13 | 1.1674e-13 | 1.085e-13 | 9.9909e-14 | 9.1016e-14 | 8.1956e-14 | 7.2441e-14 | 6.2647e-14 | 5.238e-14 | 4.1781e-14 | 3.0542e-14 | 1.9069e-14 | 9.6048e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 0
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 0
|  | Bond face amount | USD m | 0
|  | Swap unwind receipt | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | -7.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.44548 | -0.55857 | -0.44514 | -0.54985 | -0.45603 | -0.51392 | -0.38837 | -0.47444 | -0.35734 | -0.43548 | -0.3261 | -0.3943 | -0.31914 | -0.34981 | -0.25536 | -0.29938 | -0.21421 | -0.24558 | -0.17049 | -0.18772 | -0.1345 | -0.1252 | -0.071881 | -0.057142 | -0.022605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 16.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2828 | 1.27 | 1.2141 | 1.1974 | 1.1463 | 1.1192 | 1.0593 | 1.0332 | 0.97465 | 0.94837 | 0.88943 | 0.83271 | 0.74761 | 0.682 | 0.59319 | 0.51944 | 0.42403 | 0.3457 | 0.25272 | 0.17015 | 0.080969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 306.1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.5628 | 21.3474 | 20.4406 | 20.1596 | 19.2992 | 18.8423 | 17.834 | 17.3951 | 16.9395 | 16.4827 | 15.4584 | 14.7058 | 13.4837 | 12.5697 | 11.2371 | 10.2177 | 9.0388 | 7.8941 | 6.4357 | 5.1923 | 3.7596 | 2.4476 | 1.76 | 1.1171 | 0.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 315.1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.4002 | 22.0588 | 21.2096 | 20.8072 | 19.9895 | 19.4476 | 18.5049 | 17.9539 | 17.5568 | 16.9956 | 16.0217 | 15.1442 | 13.9122 | 12.9018 | 11.5749 | 10.4378 | 9.2486 | 7.9942 | 6.5179 | 5.1747 | 3.7061 | 2.3224 | 1.6882 | 1.06 | 0.53089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 569.1457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.19 | 18.0367 | 18.5682 | 19.4224 | 20.0418 | 21.3511 | 22.0038 | 21.393 | 21.4031 | 22.2898 | 22.9402 | 23.7598 | 24.1901 | 26.0359 | 26.6867 | 27.0117 | 26.7118 | 27.1081 | 26.6434 | 26.2954 | 24.8039 | 22.9342 | 23.4109 | 19.3137 | 19.5998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 884.3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 40.0955 | 39.7778 | 40.2296 | 40.0313 | 40.7987 | 40.5087 | 39.3469 | 38.9599 | 39.2854 | 38.962 | 38.9041 | 38.1023 | 38.9378 | 38.2616 | 37.4495 | 35.9605 | 35.1023 | 33.1613 | 31.4701 | 28.51 | 25.2566 | 25.099 | 20.3737 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657.74 | 640.55 | 622.5133 | 603.945 | 584.5227 | 564.4809 | 543.1298 | 521.126 | 499.7329 | 478.3299 | 456.0401 | 428.1201 | 398.4812 | 368.937 | 336.9877 | 303.4353 | 268.3464 | 233.4974 | 197.0645 | 160.4493 | 122.5769 | 85.2586 | 62.3244 | 38.9135 | 19.5998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 657.74 | 640.55 | 622.5133 | 603.945 | 584.5227 | 564.4809 | 543.1298 | 521.126 | 499.7329 | 478.3299 | 456.0401 | 428.1201 | 398.4812 | 368.937 | 336.9877 | 303.4353 | 268.3464 | 233.4974 | 197.0645 | 160.4493 | 122.5769 | 85.2586 | 62.3244 | 38.9135 | 19.5998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 249.9412 | 243.409 | 236.5551 | 229.4991 | 222.1186 | 214.5027 | 206.3893 | 198.0279 | 189.8985 | 181.7653 | 173.2952 | 164.5779 | 150.7409 | 136.0678 | 121.4892 | 106.4231 | 90.6949 | 74.3937 | 58.5645 | 42.5824 | 27.2662 | 12.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.5817 | 9.7915 | 9.7676 | 9.9662 | 9.9753 | 10.2743 | 10.2631 | 9.9897 | 9.7903 | 9.9654 | 9.9568 | 10.1793 | 10.223 | 10.7681 | 10.892 | 11.0357 | 10.9655 | 11.2437 | 11.2782 | 11.5508 | 11.6345 | 12.0397 | 12.0056 | 9.7755 | 9.6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8.6999 | 8.8371 | 8.7466 | 8.8704 | 8.8105 | 8.9943 | 8.908 | 8.6735 | 8.4509 | 8.545 | 8.4619 | 8.5849 | 8.5433 | 8.8903 | 8.896 | 8.9433 | 8.8034 | 8.943 | 8.8773 | 9.0038 | 8.973 | 9.1848 | 9.0598 | 7.331 | 7.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.8718 | 3.935 | 3.8975 | 3.9549 | 3.9309 | 4.0162 | 3.9808 | 3.8759 | 3.7785 | 3.823 | 3.789 | 3.8469 | 3.8316 | 3.992 | 3.9987 | 4.0231 | 3.9639 | 4.0305 | 4.0052 | 4.0663 | 4.0568 | 4.1573 | 4.1055 | 3.3243 | 3.2649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.5993 | 16.8205 | 16.5971 | 16.7905 | 16.6243 | 16.9086 | 16.6859 | 16.249 | 16.323 | 16.4391 | 16.191 | 16.3492 | 15.6878 | 15.5678 | 14.8604 | 14.1396 | 13.1927 | 12.1096 | 10.6073 | 8.9665 | 6.7764 | 3.9505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3037e-14 | 1.3216e-14 | 1.3047e-14 | 1.3205e-14 | 1.3082e-14 | 1.3314e-14 | 1.3147e-14 | 1.2802e-14 | 1.2703e-14 | 1.2805e-14 | 1.2628e-14 | 1.2765e-14 | 1.2648e-14 | 1.3084e-14 | 1.3023e-14 | 1.3041e-14 | 1.2929e-14 | 1.3056e-14 | 1.2873e-14 | 1.2974e-14 | 1.2838e-14 | 1.3044e-14 | 1.2771e-14 | 1.0289e-14 | 1.0013e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 40.0955 | 39.7778 | 40.2296 | 40.0313 | 40.7987 | 40.5087 | 39.3469 | 38.9599 | 39.2854 | 38.962 | 39.4247 | 38.7445 | 39.5783 | 39.0153 | 38.3975 | 37.1768 | 36.4693 | 34.898 | 33.6219 | 31.4469 | 29.2724 | 25.099 | 20.3737 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034039 | 0.034415 | 0.034053 | 0.034429 | 0.034178 | 0.034429 | 0.034053 | 0.034429 | 0.035114 | 0.035508 | 0.035114 | 0.035508 | 0.035246 | 0.035508 | 0.035114 | 0.035508 | 0.036176 | 0.036587 | 0.036176 | 0.036587 | 0.036313 | 0.036587 | 0.036176 | 0.036587 | 0.036176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842.8285 | 821.3484 | 798.8564 | 775.6365 | 751.3389 | 726.3461 | 700.1844 | 672.6253 | 643.833 | 616.9798 | 588.9159 | 560.2112 | 530.1214 | 499.1615 | 466.6843 | 431.6964 | 394.642 | 357.3913 | 318.2867 | 277.9722 | 235.6934 | 192.1471 | 146.5258 | 98.8419 | 48.891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.2814
|  | Debt capacity at the 1.35x target | USD m | 624.3174
|  | Debt at the 75% gearing cap (closed form) | USD m | 666.113
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.152 | 39.6121 | 39.3502 | 39.802 | 39.5445 | 39.9324 | 40.1143 | 40.5418 | 38.5992 | 38.9978 | 38.5392 | 39.0058 | 38.7423 | 39.1771 | 40.093 | 40.8796 | 40.2117 | 40.7215 | 40.447 | 40.9311 | 40.6625 | 41.089 | 41.349 | 41.8037 | 39.5346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657.74 | 640.977 | 623.4244 | 605.3037 | 586.3419 | 566.8376 | 546.4211 | 524.9141 | 502.4447 | 481.4886 | 459.5876 | 437.1866 | 413.7046 | 389.5436 | 364.1986 | 336.8942 | 307.9771 | 278.9067 | 248.3897 | 216.9284 | 183.9342 | 149.9509 | 114.3482 | 77.1358 | 38.1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.763 | 17.5526 | 18.1207 | 18.9618 | 19.5042 | 20.4165 | 21.507 | 22.4694 | 20.9561 | 21.9009 | 22.401 | 23.482 | 24.161 | 25.3451 | 27.3044 | 28.9171 | 29.0703 | 30.517 | 31.4613 | 32.9942 | 33.9833 | 35.6027 | 37.2123 | 38.9815 | 38.1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 52.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42082 | 0.42082 | 0.42082 | 0.42082 | 0.42082 | 0.42082 | 0 | 0 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 0 | 0 | 0.50085 | 0.50085 | 0.50085 | 0.50085 | 0.50085 | 0.50085 | 0 | 0 | 2.3736 | 2.3736 | 2.3736 | 2.3736 | 2.3736 | 2.3736 | 0 | 0 | 0.59609 | 0.59609 | 0.59609 | 0.59609 | 0.59609 | 0.59609 | 0 | 0 | 2.8249 | 2.8249 | 2.8249 | 2.8249 | 2.8249 | 2.8249 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42082 | 0.84164 | 1.2625 | 1.6833 | 2.1041 | 2.5249 | 0 | 0 | 1.9943 | 3.9886 | 5.983 | 7.9773 | 9.9716 | 11.9659 | 0 | 0 | 0.50085 | 1.0017 | 1.5025 | 2.0034 | 2.5042 | 3.0051 | 0 | 0 | 2.3736 | 4.7472 | 7.1207 | 9.4943 | 11.8679 | 14.2415 | 0 | 0 | 0.59609 | 1.1922 | 1.7883 | 2.3844 | 2.9805 | 3.5766 | 0 | 0 | 2.8249 | 5.6499 | 8.4748 | 11.2998 | 14.1247 | 16.9497 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 39.5902 | 40.0955 | 39.7778 | 40.2296 | 40.0313 | 40.7987 | 40.5087 | 39.3469 | 38.9599 | 39.2854 | 38.962 | 39.4247 | 38.7445 | 39.5783 | 39.0153 | 38.3975 | 37.1768 | 36.4693 | 34.898 | 33.6219 | 31.4469 | 29.2724 | 25.099 | 20.3737 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 3.3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50535 | 0 | 0.45172 | 0 | 0.76738 | 0 | 0 | 0 | 0.3255 | 0 | 0.46273 | 0 | 0.83384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 42.9367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31767 | 0 | 0.19828 | 0 | 0.28994 | 1.1618 | 0.38704 | 0 | 0.32338 | 0 | 0.68026 | 0 | 0.563 | 0.61778 | 1.2207 | 0.70751 | 1.5713 | 1.2761 | 2.175 | 2.1745 | 4.1734 | 4.7254 | 0.24298 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 40.0955 | 39.7778 | 40.2296 | 40.0313 | 40.7987 | 40.5087 | 39.3469 | 38.9599 | 39.2854 | 38.962 | 39.4247 | 38.7445 | 39.5783 | 39.0153 | 38.3975 | 37.1768 | 36.4693 | 34.898 | 33.6219 | 31.4469 | 29.2724 | 25.099 | 20.3737 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 19.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50038 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.692 | 1.1404
| Handback reserve release at expiry | USD m |  | 19.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2778
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50038 | 2.018 | 3.5521 | 5.1031 | 6.671 | 8.2561 | 9.8585 | 11.4785 | 13.1161 | 14.7717 | 16.4454 | 18.1375 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2344.0437 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 50.1694 | 50.759 | 50.4233 | 51.0022 | 50.6723 | 51.1694 | 51.4024 | 51.9503 | 49.461 | 49.9718 | 49.3841 | 49.982 | 49.6444 | 50.2016 | 51.3752 | 52.3832 | 51.5272 | 52.1805 | 51.8288 | 52.4491 | 52.105 | 52.6515 | 52.9846 | 53.5672 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.8093 | 46.2402 | 43.7578 | 36.3323 | 37.018 | 36.602 | 37.262 | 36.8645 | 37.4664 | 44.7157 | 40.4575 | 40.0599 | 37.2317
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 52.0366 | 50.759 | 50.4233 | 51.0022 | 50.6723 | 51.1694 | 51.4024 | 51.9503 | 49.461 | 49.9718 | 49.3841 | 49.982 | 49.6444 | 50.2016 | 51.3752 | 52.3832 | 51.5272 | 52.1805 | 51.8288 | 52.4491 | 52.105 | 52.6515 | 52.9846 | 53.5672 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.8093 | 46.2402 | 43.7578 | 36.3323 | 37.018 | 36.602 | 37.262 | 36.8645 | 37.4664 | 44.7157 | 40.4575 | 40.0599 | 37.2317
|  | Senior debt service and fees due | USD m |  | 884.3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.5902 | 40.0955 | 39.7778 | 40.2296 | 40.0313 | 40.7987 | 40.5087 | 39.3469 | 38.9599 | 39.2854 | 38.962 | 38.9041 | 38.1023 | 38.9378 | 38.2616 | 37.4495 | 35.9605 | 35.1023 | 33.1613 | 31.4701 | 28.51 | 25.2566 | 25.099 | 20.3737 | 20.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 12.4465 | 10.6635 | 10.6455 | 10.7727 | 10.641 | 10.3707 | 10.8937 | 12.6034 | 10.5011 | 10.6864 | 10.4221 | 11.078 | 11.5421 | 11.2638 | 13.1136 | 14.9337 | 15.5668 | 17.0782 | 18.6676 | 20.979 | 23.595 | 27.3948 | 27.8856 | 33.1935 | 30.529 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.8093 | 46.2402 | 43.7578 | 36.3323 | 37.018 | 36.602 | 37.262 | 36.8645 | 37.4664 | 44.7157 | 40.4575 | 40.0599 | 37.2317
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 11.9411 | 10.9811 | 10.1938 | 10.971 | 9.8736 | 10.6606 | 12.0555 | 12.9904 | 10.1756 | 11.0098 | 9.9594 | 11.7582 | 10.7083 | 11.8268 | 13.7314 | 16.1544 | 16.2743 | 18.6495 | 19.9437 | 23.154 | 25.7695 | 31.5682 | 32.6109 | 33.4365 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.8093 | 46.2402 | 43.7578 | 36.3323 | 37.018 | 36.602 | 37.262 | 36.8645 | 37.4664 | 44.7157 | 40.4575 | 40.0599 | 37.2317
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 11.9411 | 10.9811 | 10.1938 | 10.971 | 9.8736 | 10.6606 | 12.0555 | 12.9904 | 10.1756 | 11.0098 | 9.9594 | 11.7582 | 10.7083 | 11.8268 | 13.7314 | 16.1544 | 16.2743 | 18.6495 | 19.9437 | 23.154 | 25.7695 | 31.5682 | 32.6109 | 33.4365 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 55.3692
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2672 | 1.266 | 1.2676 | 1.2678 | 1.2658 | 1.2542 | 1.2689 | 1.3203 | 1.2695 | 1.272 | 1.2675 | 1.2848 | 1.3029 | 1.2893 | 1.3427 | 1.3988 | 1.4329 | 1.4865 | 1.5629 | 1.6666 | 1.8276 | 2.0847 | 2.111 | 2.6292 | 2.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2672 | 1.2666 | 1.2668 | 1.2677 | 1.2668 | 1.2599 | 1.2615 | 1.2942 | 1.2951 | 1.2708 | 1.2698 | 1.2761 | 1.2937 | 1.296 | 1.3158 | 1.3705 | 1.4155 | 1.4594 | 1.5236 | 1.6134 | 1.7431 | 1.9484 | 2.0978 | 2.3432 | 2.5732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 88.5943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 12.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1410.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9411 | 10.9811 | 10.1938 | 10.971 | 9.8736 | 10.6606 | 12.0555 | 12.9904 | 10.1756 | 11.0098 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 13.2551 | 31.5682 | 32.6109 | 33.4365 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 55.3692
|  | Share capital contributed | USD m | 46.0821
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 217.5754 | 221.0298 | 219.5013 | 219.0322 | 219.1569 | 218.6815 | 219.1667 | 219.0021 | 217.2636 | 214.6781 | 214.6158 | 213.8841 | 218.9804 | 223.5883 | 228.8256 | 233.8707 | 238.0226 | 241.3444 | 244.5769 | 246.965 | 248.6276 | 248.9575 | 247.4955 | 227.78 | 205.8997 | 182.3238 | 140.2532 | 95.6312 | 49.1506 | 8.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 245.9846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4126 | 10.512 | 10.1938 | 10.4955 | 9.8736 | 10.496 | 10.3171 | 10.4048 | 10.1134 | 10.278 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 11.7931 | 11.8527 | 10.7306 | 9.8606 | 8.5892 | 6.7168 | 4.5051 | 2.3538 | 0.40577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 256.7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5285 | 0.46912 | 0 | 0.47545 | 0 | 0.16465 | 1.7384 | 2.5856 | 0.062225 | 0.73176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.462 | 19.7156 | 21.8803 | 23.5759 | 42.0705 | 44.622 | 46.4807 | 40.5845 | 8.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 221.0298 | 219.5013 | 219.0322 | 219.1569 | 218.6815 | 219.1667 | 219.0021 | 217.2636 | 214.6781 | 214.6158 | 213.8841 | 218.9804 | 223.5883 | 228.8256 | 233.8707 | 238.0226 | 241.3444 | 244.5769 | 246.965 | 248.6276 | 248.9575 | 247.4955 | 227.78 | 205.8997 | 182.3238 | 140.2532 | 95.6312 | 49.1506 | 8.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.3785 | 15.1015 | 21.247 | 28.586 | 36.2431 | 44.935 | 54.1961 | 62.2782 | 73.4062 | 85.2247 | 94.99 | 100.5217 | 106.4485 | 113.2227 | 120.5976 | 118.906 | 129.0732 | 138.8999 | 149.4624 | 161.2257 | 173.8129 | 187.5692 | 202.3894 | 216.5231 | 233.8524 | 252.4343 | 272.8056 | 294.8469 | 318.8628 | 344.3099 | 337.3807 | 310.6401 | 288.6064 | 270.003 | 252.4745 | 234.421 | 216.8674 | 198.7508 | 181.1879 | 161.311 | 143.5758 | 128.3268 | 120.6496 | 112.449 | 104.7791 | 96.5425 | 88.9422 | 68.4402 | 53.3674 | 42.4733 | 9.287
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.8435 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 9.287
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.0821
|  | Liquidation distribution at PPA expiry | USD m |  | 46.0821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.0821
|  | Dividends | USD m |  | 908.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.8435 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 55.3692
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.3785 | 15.1015 | 21.247 | 28.586 | 36.2431 | 44.935 | 54.1961 | 62.2782 | 73.4062 | 85.2247 | 94.99 | 100.5217 | 106.4485 | 113.2227 | 120.5976 | 118.906 | 129.0732 | 138.8999 | 149.4624 | 161.2257 | 173.8129 | 187.5692 | 202.3894 | 216.5231 | 233.8524 | 252.4343 | 272.8056 | 294.8469 | 318.8628 | 311.4664 | 295.1442 | 262.4041 | 243.8738 | 226.2264 | 208.039 | 190.3956 | 172.2073 | 154.478 | 136.8789 | 116.5883 | 101.3522 | 93.5454 | 85.1995 | 77.4321 | 69.1195 | 61.298 | 53.1135 | 25.3801 | 14.5836 | 4.1054 | -46.0821
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1410.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9411 | 10.9811 | 10.1938 | 10.971 | 9.8736 | 10.6606 | 12.0555 | 12.9904 | 10.1756 | 11.0098 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 13.2551 | 31.5682 | 32.6109 | 33.4365 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 55.3692

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 876.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 5.843 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 17.5291 | 11.6861
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 600.282 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4544 | 32.8128 | 32.5708 | 31.5281 | 31.3027 | 30.3484 | 29.9435 | 28.822 | 28.3587 | 27.6702 | 27.2736 | 26.0977 | 25.6313 | 24.5036 | 23.8604 | 22.5925 | 21.8368 | 20.6183 | 19.7071 | 18.1523 | 17.0816 | 15.4992 | 14.1751 | 12.4188 | 10.9206 | 9.1201 | 6.7168 | 4.5051 | 2.3538 | 0.40577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 868.5693 | 844.9049 | 821.2406 | 797.5762 | 773.9119 | 750.2475 | 726.5832 | 702.9188 | 679.2545 | 655.5901 | 632.8022 | 611.7673 | 590.7323 | 569.6973 | 548.6623 | 527.6274 | 506.5924 | 485.5574 | 464.5224 | 443.4874 | 422.4525 | 401.4175 | 380.3825 | 359.3475 | 338.3126 | 317.2776 | 296.2426 | 275.2076 | 254.1726 | 233.1377 | 212.1027 | 191.0677 | 170.0327 | 148.9978 | 127.9628 | 106.9278 | 85.8928 | 64.8578 | 43.8229 | 22.7879 | 8.4724 | 7.596 | 6.7195 | 5.843 | 4.9666 | 4.0901 | 3.2137 | 2.3372 | 1.4608 | 0.5843 | 0
|  | Book value of plant (from COD) | USD m |  |  | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 876.4574 | 870.6143 | 853.0852 | 835.556 | 818.0269 | 800.4978 | 782.9686 | 765.4395 | 747.9103 | 730.3812 | 712.852 | 695.3229 | 677.7937 | 660.2646 | 642.7354 | 625.2063 | 607.6771 | 590.148 | 572.6188 | 555.0897 | 537.5605 | 520.0314 | 502.5022 | 484.9731 | 467.4439 | 449.9148 | 432.3856 | 414.8565 | 397.3274 | 379.7982 | 362.2691 | 344.7399 | 327.2108 | 309.6816 | 292.1525 | 274.6233 | 257.0942 | 239.565 | 222.0359 | 204.5067 | 186.9776 | 169.4484 | 151.9193 | 134.3901 | 116.861 | 99.3318 | 81.8027 | 64.2735 | 46.7444 | 29.2152 | 11.6861 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -1.7529 | -7.0117 | -12.2704 | -17.5291 | -22.7879 | -28.0466 | -33.3054 | -38.5641 | -43.8229 | -49.0816 | -51.8788 | -49.355 | -46.6611 | -43.6032 | -40.2874 | -39.2357 | -36.3457 | -31.9767 | -27.2916 | -22.0912 | -16.5369 | -10.4806 | -3.9678 | 2.2511 | 9.8406 | 17.9682 | 26.8634 | 36.4751 | 37.6877 | 38.7394 | 39.7912 | 40.8429 | 41.8947 | 42.9464 | 43.9982 | 45.0499 | 46.1017 | 47.1534 | 48.2052 | 49.2569 | 48.2928 | 43.297 | 38.3012 | 33.3054 | 28.3096 | 23.3138 | 18.318 | 13.3222 | 8.3263 | 3.3305 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7529 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -5.2587 | -2.7972 | 2.5238 | 2.6939 | 3.0579 | 3.3158 | 1.0517 | 2.8899 | 4.3691 | 4.6851 | 5.2004 | 5.5543 | 6.0563 | 6.5128 | 6.2189 | 7.5895 | 8.1276 | 8.8952 | 9.6117 | 1.2126 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | 1.0517 | -0.9641 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -4.9958 | -3.3305
|  | Net income | USD m |  | 861.9542 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3785 | 5.7229 | 6.1456 | 7.339 | 7.6571 | 8.6919 | 9.261 | 8.0821 | 11.128 | 11.8185 | 9.7653 | 5.5317 | 5.9268 | 6.7741 | 7.375 | -1.6917 | 10.1672 | 9.8267 | 10.5625 | 11.7633 | 12.5872 | 13.7563 | 14.8202 | 14.1337 | 17.3293 | 18.5819 | 20.3713 | 22.0413 | 24.0159 | 25.4471 | 25.9143 | 15.4959 | 26.2023 | 26.1292 | 26.248 | 26.382 | 26.4718 | 26.5435 | 26.7099 | 24.4321 | 26.9875 | 26.9745 | 27.1042 | 27.2495 | 27.347 | 27.423 | 27.6442 | 15.3267 | 27.9873 | 27.8897 | 5.1816
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 139.5623 | 239.8778 | 434.07 | 636.1576 | 753.7997 | 797.6206 | 870.6143 | 853.0852 | 835.556 | 818.0269 | 800.4978 | 782.9686 | 765.4395 | 747.9103 | 730.3812 | 712.852 | 695.3229 | 677.7937 | 660.2646 | 642.7354 | 625.2063 | 607.6771 | 590.148 | 572.6188 | 555.0897 | 537.5605 | 520.0314 | 502.5022 | 484.9731 | 467.4439 | 449.9148 | 432.3856 | 414.8565 | 397.3274 | 379.7982 | 362.2691 | 344.7399 | 327.2108 | 309.6816 | 292.1525 | 274.6233 | 257.0942 | 239.565 | 222.0359 | 204.5067 | 186.9776 | 169.4484 | 151.9193 | 134.3901 | 116.861 | 99.3318 | 81.8027 | 64.2735 | 46.7444 | 29.2152 | 11.6861 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 41.4574 | 40.5163 | 40.6195 | 41.492 | 41.7146 | 42.9028 | 43.0337 | 39.3469 | 38.9599 | 41.2797 | 42.9506 | 45.4077 | 46.7218 | 49.5499 | 50.9812 | 38.3975 | 37.1768 | 36.9702 | 35.8997 | 35.1244 | 33.4503 | 31.7767 | 28.1041 | 20.3737 | 20.1307 | 2.3736 | 4.7472 | 7.1207 | 9.4943 | 11.8679 | 14.2415 | 0 | 0 | 0.59609 | 1.1922 | 1.7883 | 2.3844 | 2.9805 | 4.0769 | 2.018 | 3.5521 | 7.928 | 12.3209 | 16.7309 | 21.1583 | 25.6032 | 30.0658 | 14.7717 | 16.4454 | 18.1375 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.181 | 40.0893 | 39.4807 | 40.4561 | 39.9842 | 41.0569 | 40.456 | 41.0733 | 40.787 | 42.4919 | 41.8473 | 42.8882 | 42.3913 | 43.5414 | 42.7358 | 42.8121 | 42.9218 | 45.0875 | 44.4041 | 45.5156 | 44.9918 | 46.2253 | 45.5424 | 46.2364 | 45.9289 | 47.8915 | 47.1661 | 48.3541 | 47.8011 | 49.1248 | 48.2033 | 48.2886 | 48.4208 | 50.9206 | 50.15 | 51.4205 | 50.836 | 52.2572 | 51.4787 | 52.2624 | 51.9301 | 54.1931 | 53.3735 | 54.7333 | 54.1147 | 55.6412 | 54.5845 | 54.6803 | 54.8389 | 57.7285 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.7529 | 7.0117 | 12.2704 | 17.5291 | 22.7879 | 28.0466 | 33.3054 | 38.5641 | 43.8229 | 49.0816 | 51.8788 | 49.355 | 46.6611 | 43.6032 | 40.2874 | 39.2357 | 36.3457 | 31.9767 | 27.2916 | 22.0912 | 16.5369 | 10.4806 | 3.9678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 139.5623 | 239.8778 | 434.07 | 636.1576 | 753.7997 | 797.6206 | 958.3556 | 946.0525 | 933.2766 | 922.8541 | 910.3344 | 900.3249 | 887.5845 | 872.2446 | 859.3009 | 851.0553 | 837.3496 | 820.7946 | 801.3887 | 784.7799 | 764.5607 | 733.4724 | 711.9424 | 692.0032 | 668.035 | 645.6418 | 620.3603 | 596.3348 | 567.9374 | 539.404 | 521.3244 | 488.0007 | 472.1197 | 458.1521 | 442.4436 | 428.6118 | 412.5346 | 380.8493 | 363.4524 | 349.0192 | 331.3155 | 315.653 | 298.1354 | 282.6235 | 265.4124 | 246.6079 | 230.2807 | 219.3905 | 205.4346 | 193.6752 | 179.9548 | 168.3971 | 154.2738 | 121.5464 | 105.8496 | 92.9021 | 0
|  | Senior debt | USD m |  |  | 102.7307 | 175.7315 | 317.1148 | 462.7489 | 544.3654 | 570.599 | 657.74 | 640.55 | 622.5133 | 603.945 | 584.5227 | 564.4809 | 543.1298 | 521.126 | 499.7329 | 478.3299 | 456.0401 | 428.1201 | 398.4812 | 368.937 | 336.9877 | 303.4353 | 268.3464 | 233.4974 | 197.0645 | 160.4493 | 122.5769 | 85.2586 | 62.3244 | 38.9135 | 19.5998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 29.6342 | 51.8344 | 94.7377 | 140.988 | 171.2953 | 187.0447 | 221.0298 | 219.5013 | 219.0322 | 219.1569 | 218.6815 | 219.1667 | 219.0021 | 217.2636 | 214.6781 | 214.6158 | 213.8841 | 218.9804 | 223.5883 | 228.8256 | 233.8707 | 238.0226 | 241.3444 | 244.5769 | 246.965 | 248.6276 | 248.9575 | 247.4955 | 227.78 | 205.8997 | 182.3238 | 140.2532 | 95.6312 | 49.1506 | 8.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24.1251 | 24.8176 | 24.402 | 25.084 | 24.805 | 25.6601 | 25.1744 | 25.4947 | 25.4015 | 26.8027 | 26.3533 | 27.0902 | 26.7885 | 27.7125 | 27.0226 | 27.0264 | 27.0963 | 28.9469 | 28.4609 | 29.257 | 28.9309 | 29.9294 | 29.3615 | 29.7345 | 29.6257 | 31.2628 | 30.7374 | 31.5975 | 31.2449 | 32.3238 | 31.5172 | 31.5202 | 31.6018 | 33.7642 | 33.1962 | 34.1254 | 33.7442 | 34.91 | 34.2462 | 34.6805 | 34.5535 | 36.466 | 35.8518 | 36.8556 | 36.4436 | 37.7032 | 36.7602 | 36.7621 | 36.8575 | 39.384 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2511 | 9.8406 | 17.9682 | 26.8634 | 36.4751 | 37.6877 | 38.7394 | 39.7912 | 40.8429 | 41.8947 | 42.9464 | 43.9982 | 45.0499 | 46.1017 | 47.1534 | 48.2052 | 49.2569 | 48.2928 | 43.297 | 38.3012 | 33.3054 | 28.3096 | 23.3138 | 18.318 | 13.3222 | 8.3263 | 3.3305 | 0
|  | Share capital | USD m |  |  | 7.1974 | 12.312 | 22.2175 | 32.4208 | 38.139 | 39.9769 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821 | 46.0821
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.3785 | 15.1015 | 21.247 | 28.586 | 36.2431 | 44.935 | 54.1961 | 62.2782 | 73.4062 | 85.2247 | 94.99 | 100.5217 | 106.4485 | 113.2227 | 120.5976 | 118.906 | 129.0732 | 138.8999 | 149.4624 | 161.2257 | 173.8129 | 187.5692 | 202.3894 | 216.5231 | 233.8524 | 252.4343 | 272.8056 | 294.8469 | 318.8628 | 311.4664 | 295.1442 | 262.4041 | 243.8738 | 226.2264 | 208.039 | 190.3956 | 172.2073 | 154.478 | 136.8789 | 116.5883 | 101.3522 | 93.5454 | 85.1995 | 77.4321 | 69.1195 | 61.298 | 53.1135 | 25.3801 | 14.5836 | 4.1054 | -46.0821
|  | Total liabilities and equity | USD m |  |  | 139.5623 | 239.8778 | 434.07 | 636.1576 | 753.7997 | 797.6206 | 958.3556 | 946.0525 | 933.2766 | 922.8541 | 910.3344 | 900.3249 | 887.5845 | 872.2446 | 859.3009 | 851.0553 | 837.3496 | 820.7946 | 801.3887 | 784.7799 | 764.5607 | 733.4724 | 711.9424 | 692.0032 | 668.035 | 645.6418 | 620.3603 | 596.3348 | 567.9374 | 539.404 | 521.3244 | 488.0007 | 472.1197 | 458.1521 | 442.4436 | 428.6118 | 412.5346 | 380.8493 | 363.4524 | 349.0192 | 331.3155 | 315.653 | 298.1354 | 282.6235 | 265.4124 | 246.6079 | 230.2807 | 219.3905 | 205.4346 | 193.6752 | 179.9548 | 168.3971 | 154.2738 | 121.5464 | 105.8496 | 92.9021 | 0
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034056 | 0.034437 | 0.034071 | 0.034452 | 0.034198 | 0.034452 | 0.034071 | 0.034452 | 0.035132 | 0.035531 | 0.035132 | 0.035374 | 0.034913 | 0.03497 | 0.034348 | 0.034399 | 0.034465 | 0.034237 | 0.033075 | 0.032251 | 0.030235 | 0.02724 | 0.027087 | 0.02724 | 0.027087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 32
| Rate in final maturity period | factor | 0.027087
| Discount rate used | factor |  |  | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.034056 | 0.034437 | 0.034071 | 0.034452 | 0.034198 | 0.034452 | 0.034071 | 0.034452 | 0.035132 | 0.035531 | 0.035132 | 0.035374 | 0.034913 | 0.03497 | 0.034348 | 0.034399 | 0.034465 | 0.034237 | 0.033075 | 0.032251 | 0.030235 | 0.02724 | 0.027087 | 0.02724 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087 | 0.027087
| PV of CFADS to final maturity | USD m |  |  | 705.1018 | 724.2006 | 743.8167 | 763.9641 | 784.6573 | 805.911 | 827.7403 | 848.2937 | 827.014 | 804.7352 | 781.7299 | 757.6599 | 732.898 | 706.9785 | 679.6635 | 651.129 | 624.5437 | 596.7627 | 568.3442 | 538.4667 | 507.6219 | 475.172 | 440.1181 | 402.8744 | 365.2323 | 325.5562 | 284.4951 | 241.2214 | 196.4097 | 149.1083 | 100.1625 | 49.3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 990.0408 | 1016.8576 | 1044.4008 | 1072.69 | 1101.7455 | 1131.588 | 1162.2388 | 1191.8527 | 1182.2733 | 1172.2286 | 1161.7442 | 1150.7665 | 1139.448 | 1127.5351 | 1114.5488 | 1100.997 | 1090.2166 | 1078.9814 | 1067.5045 | 1055.2841 | 1042.483 | 1028.7374 | 1012.6974 | 995.1497 | 977.9205 | 959.2209 | 939.1182 | 916.9571 | 892.576 | 864.2379 | 834.6626 | 803.8311 | 774.9445 | 744.5962 | 713.779 | 690.1744 | 667.0536 | 642.8853 | 612.0629 | 583.9089 | 555.9484 | 526.5717 | 496.8092 | 465.606 | 433.9449 | 400.8896 | 365.5081 | 331.6507 | 304.3016 | 275.5261 | 246.3871 | 215.7989 | 184.7797 | 152.3184 | 111.7284 | 74.2973 | 36.2498
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3499 | 1.3537 | 1.3566 | 1.361 | 1.3647 | 1.3706 | 1.3763 | 1.3797 | 1.3809 | 1.3878 | 1.394 | 1.4196 | 1.4485 | 1.4832 | 1.5258 | 1.577 | 1.6399 | 1.7204 | 1.8291 | 1.9827 | 2.2245 | 2.647 | 2.7952 | 3.0975 | 3.5436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2897 | 1.2911 | 1.2927 | 1.2944 | 1.2962 | 1.2984 | 1.3017 | 1.3042 | 1.303 | 1.3057 | 1.3086 | 1.3275 | 1.3513 | 1.3759 | 1.4101 | 1.4505 | 1.5013 | 1.5642 | 1.652 | 1.7731 | 1.9679 | 2.3037 | 2.3925 | 2.574 | 2.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.812 | 1.8457 | 1.8831 | 1.9236 | 1.9687 | 2.0186 | 2.076 | 2.1387 | 2.2032 | 2.2792 | 2.366 | 2.4935 | 2.6483 | 2.8256 | 3.0527 | 3.3374 | 3.7085 | 4.1881 | 4.8675 | 5.8531 | 7.4807 | 10.469 | 13.8668 | 21.4492 | 41.0122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR (debt-service weighted) | x | #VALUE!
| LLCR at first debt service period | x | 1.3499
| PLCR at first debt service period | x | 1.812

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1180.3235 | -14.2 | -17.4523 | -0.65062 | -0.82892 | -1.1706 | -1.6848 | -2.3207 | -3.0261 | -3.8411 | -4.6527 | -5.4794 | -6.2527 | -6.9945 | -7.6466 | -8.1886 | -8.6377 | -8.9364 | -9.1238 | -9.4642 | -9.0274 | -8.8133 | -8.4249 | -7.9493 | -7.3375 | -6.6755 | -5.9335 | -5.1364 | -4.3673 | -3.584 | -2.894 | -2.2759 | -1.7224 | -1.4386 | -1.2543 | -1.2574 | -1.2412 | -1.2907 | -1.2947 | -1.2688 | -14.1268 | -11.4967 | -1.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9411 | 10.9811 | 10.1938 | 10.971 | 9.8736 | 10.6606 | 12.0555 | 12.9904 | 10.1756 | 11.0098 | 4.9797 | 5.8791 | 5.3541 | 5.9134 | 6.8657 | 8.0772 | 8.1371 | 9.3248 | 9.9718 | 11.577 | 13.2551 | 31.5682 | 32.6109 | 33.4365 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.309 | 44.7226 | 42.2236 | 34.7814 | 35.4501 | 35.0169 | 35.6595 | 35.2446 | 35.8287 | 43.0601 | 38.7838 | 38.3679 | 55.3692
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1625.434 | 0 | -108.1116 | -1.4076 | -2.0414 | -3.3437 | -5.2329 | -7.5951 | -10.3049 | -13.236 | -16.2643 | -19.2733 | -22.155 | -24.8128 | -27.1615 | -29.1279 | -30.6553 | -31.6979 | -32.2266 | -33.3696 | -31.6979 | -30.6553 | -29.1279 | -27.1615 | -24.8128 | -22.155 | -19.2733 | -16.2643 | -13.236 | -10.3049 | -7.5951 | -5.2329 | -3.3437 | -2.0414 | -1.4076 | -1.3408 | -1.3408 | -1.3408 | -1.3408 | -1.3408 | -49.5788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 50.1694 | 50.759 | 50.4233 | 51.0022 | 50.6723 | 51.1694 | 51.4024 | 51.9503 | 49.461 | 49.9718 | 49.3841 | 49.982 | 49.6444 | 50.2016 | 51.3752 | 52.3832 | 51.5272 | 52.1805 | 51.8288 | 52.4491 | 52.105 | 52.6515 | 52.9846 | 53.5672 | 50.6597 | 51.3388 | 50.9858 | 42.9384 | 41.8153 | 42.2365 | 48.236 | 44.7326 | 43.7766 | 44.4354 | 44.0255 | 44.6601 | 44.2728 | 44.8093 | 46.2402 | 43.7578 | 36.3323 | 37.018 | 36.602 | 37.262 | 36.8645 | 37.4664 | 44.7157 | 40.4575 | 40.0599 | 37.2317
| Project cash flow, pre-tax | USD m |  | 1911.3759 | 0 | -108.1116 | -1.4076 | -2.0414 | -3.3437 | -5.2329 | -7.5951 | -10.3049 | -13.236 | -16.2643 | -19.2733 | -22.155 | -24.8128 | -27.1615 | -29.1279 | -30.6553 | -31.6979 | -32.2266 | -33.3696 | -31.6979 | -30.6553 | -29.1279 | -27.1615 | -24.8128 | -22.155 | -19.2733 | -16.2643 | -13.236 | -10.3049 | -7.5951 | -5.2329 | -3.3437 | -2.0414 | -1.4076 | -1.3408 | -1.3408 | -1.3408 | -1.3408 | -1.3408 | -49.5788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8672 | 50.1694 | 50.759 | 50.4233 | 51.0022 | 50.6723 | 51.1694 | 51.4024 | 51.9503 | 49.461 | 50.0904 | 49.7413 | 50.341 | 50.0053 | 50.5634 | 51.7325 | 52.7476 | 51.895 | 52.55 | 52.1997 | 52.822 | 52.48 | 53.0278 | 53.3617 | 53.9467 | 51.0422 | 51.7231 | 51.3717 | 52.0184 | 51.6694 | 52.2909 | 53.8253 | 54.9105 | 53.9231 | 54.6328 | 54.2803 | 54.9534 | 54.5968 | 55.2047 | 55.6594 | 56.2879 | 52.8887 | 53.6299 | 53.2762 | 53.9779 | 53.613 | 54.3097 | 56.2801 | 57.4479 | 57.0085 | 42.7829
| Cumulative equity cash flow | USD m |  |  | -14.2 | -31.6523 | -32.303 | -33.1319 | -34.3025 | -35.9872 | -38.308 | -41.334 | -45.1751 | -49.8278 | -55.3072 | -61.5599 | -68.5544 | -76.201 | -84.3896 | -93.0273 | -101.9636 | -111.0874 | -120.5516 | -129.5791 | -138.3924 | -146.8173 | -154.7665 | -162.104 | -168.7796 | -174.7131 | -179.8494 | -184.2168 | -187.8008 | -190.6948 | -192.9707 | -194.6931 | -196.1317 | -197.386 | -198.6434 | -199.8846 | -201.1753 | -202.47 | -203.7388 | -217.8656 | -229.3623 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -230.4107 | -218.4695 | -207.4884 | -197.2947 | -186.3237 | -176.45 | -165.7894 | -153.7339 | -140.7435 | -130.5678 | -119.558 | -114.5783 | -108.6992 | -103.3451 | -97.4317 | -90.566 | -82.4889 | -74.3517 | -65.027 | -55.0551 | -43.4781 | -30.2231 | 1.3452 | 33.9561 | 67.3926 | 118.0523 | 169.3911 | 220.3769 | 263.3153 | 305.1306 | 347.3671 | 395.6031 | 440.3357 | 484.1123 | 528.5478 | 572.5732 | 617.2333 | 661.5061 | 705.8151 | 750.5377 | 792.7613 | 827.5427 | 862.9928 | 898.0097 | 933.6693 | 968.9138 | 1004.7425 | 1047.8026 | 1086.5864 | 1124.9543 | 1180.3235
| Equity IRR (XIRR) | % | 12.07%
| Project IRR, post-tax (XIRR) | % | 10.44%
| Project IRR, pre-tax (XIRR) | % | 10.94%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -66.2147

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 0
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 0

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 888.1507
| Senior debt (four tranches) | USD m | 657.74
| Equity (incl. LNTP) | USD m | 230.4107
| Gearing (debt incl. standby / total funding) | % | 74.06%
| Interest during construction incl. swap and PRI | USD m | 84.407
| Commitment, upfront and agency fees | USD m | 22.5896
| ECA premium | USD m | 21.4094
| DSRA initial funding | USD m | 39.5902
| Standby drawn | USD m | 1.9984e-13
| Contingent equity drawn | USD m | 6.6613e-14
| Minimum DSCR | x | #VALUE!
| Average DSCR | x | #VALUE!
| LLCR at first debt service period (incl. DSRA) | x | 1.3499
| PLCR at first debt service period | x | 1.812
| Equity IRR | % | 12.07%
| Project IRR, post-tax | % | 10.44%
| Equity NPV at 16.0% (at FC) | USD m | -66.2147
| All checks | check | 0