## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 6
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code
|  | Construction case (1 FC budget, 2 actual) | code
|  | COD delay (sensitivity) | months
|  | Capex factor | factor
|  | Availability adjustment | points
|  | Dispatch factor when available | %
|  | Plant heat rate factor | factor
|  | Fixed opex factor | factor
|  | Gas price factor | factor
|  | Base rate shift from 2022H1 | %
|  | KCR devaluation from 2022H1 | fraction
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days
|  | Offtaker crisis events (1 = on) | flag
|  | Insurance market step-up from 2022H2 (1 = on) | flag
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code
|  | Performance LD prepayment June 2022 (1 = on) | flag
|  | Waiver and amendment 2023 (1 = on) | flag
|  | 2025 bond refinancing (1 = on) | flag
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code
|  | Soft mini-perm sweep (1 = on) | flag
|  | Shareholder loan share of equity | fraction
|  | Capital charge factor | factor
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date
|  | PPA expiry | date
|  | Construction months (NTP to COD) | months
|  | Period containing COD (period number) | index
|  | First debt service period | index
|  | Last month of the funding period (month number) | index
|  | Last operating period (period number) | index
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor
Semiannual timeline
|  | Period number | index
|  | Period start | date
|  | Period end | date
|  | Days in period | days
|  | Calendar year | year
|  | Half (1 = Jan-Jun) | index
|  | Operations start in period | date
|  | Operations end in period | date
|  | Operating months in period | months
|  | Operating days in period | days
|  | Operating months elapsed at period start | months
|  | Operating months elapsed at period end | months
|  | Flag_CODPeriod | flag
|  | Flag_DebtService (after COD period) | flag
|  | Flag_Operations | flag
|  | Flag_LastOperatingPeriod | flag
|  | Flag_ShockPeriods (2022H1-2022H2) | flag
|  | Flag from 2022H1 | flag

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index
|  | Month start | date
|  | Month end | date
|  | Days | days
|  | Semiannual period number | index
|  | Flag_Construction (before COD) | flag
|  | Flag_FundingPeriod (to end of COD period) | flag
|  | Flag_CODMonth | flag
|  | KCR per USD | KCR/USD
|  | Base rate (6M fixing for the half-year) | %
|  | Kessara policy rate | %
Uses before financing costs (USD m)
|  | EPC payment profile, selected | %
|  | EPC progress payments for contingency (FC) | %
|  | EPC payments | USD m
|  | Owner's costs | USD m
|  | Insurance during construction | USD m
|  | Development costs and fee | USD m
|  | Lenders' advisors and legal | USD m
|  | Contingency (FC: pro rata with EPC progress payments) | USD m
|  | Initial working capital | USD m
|  | Overrun items (actual) | USD m
|  | Uses before financing costs | USD m
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m
|  | VAT paid (drawn on the VAT facility) | KCR m
|  | VAT refunds (9-month lag) repaying the facility | KCR m
|  | VAT facility balance | KCR m
|  | VAT facility interest | USD m

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | %
|  | Base rate (6M LIBOR / Term SOFR + CAS) | %
|  | KCR per USD before devaluation sensitivity | KCR/USD
|  | KCR per USD, period average | KCR/USD
|  | US CPI change, current year | %
|  | Kessara CPI change, current year | %
|  | US CPI change, prior year | %
|  | Kessara CPI change, prior year | %
|  | US index, June 2018 (2018 price base) | index
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index
|  | US CPI index, tariff reading (3-month lag) | index
|  | US cost indexation factor vs 2018 prices | factor
|  | KC index, June 2018 (2018 price base) | index
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index
|  | Kessara CPI index, tariff reading (3-month lag) | index
|  | Kessara cost indexation factor vs 2018 prices | factor
Plant
|  | Operating year at period start | OY
|  | Months in that operating year | months
|  | Availability, profile (month-weighted) | %
|  | Availability | %
|  | Years since COD (period mid-point) | years
|  | Contracted capacity | MW
|  | Plant net heat rate, new and clean | kJ/kWh
|  | Output degradation factor | factor
|  | Net energy delivered | MWh
|  | Plant net heat rate | kJ/kWh
|  | Contracted heat rate at dispatched load | kJ/kWh
|  | Gas price (GCV) | USD/MMBtu
|  | Gas burned | MMBtu
|  | Take-or-pay quantity | MMBtu
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month
|  | Fixed O&M charge, indexed | USD/kW-month
|  | Availability factor min(1, A/90%) | factor
|  | Capacity payment | USD m
|  | VOM charge, indexed | USD/MWh
|  | Variable O&M payment | USD m
|  | Fuel charge (pass-through) | USD m
|  | GTA reservation charge (pass-through) | USD m
|  | GTA commodity charge (pass-through) | USD m
|  | Take-or-pay payment (pass-through) | USD m
|  | Non-fuel revenue | USD m
|  | Total revenue | USD m
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m
|  | Late payment interest received (60%, with settlement installments) | USD m
Operating costs (USD m)
|  | O&M fixed fee | USD m
|  | O&M availability incentive | USD m
|  | LTSA fixed fee | USD m
|  | Equivalent operating hours (2 GTs) | EOH
|  | LTSA variable fee | USD m
|  | Operational insurance | USD m
|  | G&A | USD m
|  | Land lease and permits | USD m
|  | Community fund and OREK levy | USD m
|  | Variable consumables | USD m
|  | Agency and account fees | USD m
|  | ABDB PRG fee | USD m
|  | Operating costs before pass-through items | USD m
|  | Gas purchases | USD m
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m
|  | VAT facility interest after the funding period | USD m
|  | FX conversion losses | USD m
|  | OY whose month 7 could fall in the period | OY
|  | Major maintenance outside LTSA (2018 prices) | USD m
|  | Major maintenance spend | USD m
|  | Months in period from OY20 | months
|  | Handback reserve contribution required | USD m
|  | Handback works at PPA expiry | USD m
|  | Total operating costs | USD m
|  | EBITDA | USD m
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag
|  | Extra receivable days on capacity and VOM (sensitivities) | days
|  | Trade receivables (normal terms) | USD m
|  | SEKA overdue receivables | USD m
|  | Gas payables | USD m
|  | GTA payables | USD m
|  | O&M and LTSA payables | USD m
|  | Other payables | USD m
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m
|  | Net working capital (excl. spares inventory) | USD m
|  | Increase in net working capital | USD m
|  | Release of spares inventory at expiry | USD m

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months
| Reduced-rate months (OY6-OY8) | months
| Full-rate months (OY9+) | months
| Tax depreciation (straight line from COD) | USD m
| Depreciation of holiday months (deemed deferred) | USD m
| Depreciation deducted currently | USD m
| Shareholder loan interest accrued | USD m
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction
| Shareholder loan interest deductible | USD m
| Senior financing costs deductible (all grandfathered) | USD m
| Non-holiday share of operating months | fraction
| Taxable income before losses and deferred depreciation | USD m
| Tax losses used | USD m
| Deferred depreciation used | USD m
| Deferred depreciation pool, closing | USD m
| Tax losses carried forward, closing | USD m
| Taxable income | USD m
| Applicable CIT rate (month-weighted) | %
| Corporate income tax | USD m
| Minimum turnover tax | USD m
| Tax paid = max(CIT, MTT) | USD m
| Thin-cap disallowance | USD m

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction
|  | Gearing used in the closed-form gross-up | fraction
|  | ECA premium gross-up denominator 1 - prem x share x g | factor
|  | First installment share of remaining profile | fraction
|  | DSRA coefficient per USD of E balance | factor
|  | DSRA coefficient per USD of A balance | factor
|  | DSRA coefficient per USD of B balance | factor
|  | DSRA coefficient per USD of C balance | factor
|  | DSRA coefficient per USD of standby balance | factor
|  | DSRA constant (swap net payment) | USD m
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor
|  | Blended commitment fee per month (kappa) | factor
|  | Costs independent of facility size | USD m
|  | Balance, constant part (alpha) | USD m
|  | Balance per USD of total funding (beta) | factor
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m
|  | Senior debt (committed tranches) | USD m
|  | Debt share of monthly funding | fraction
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m
|  | ABDB A-loan: opening balance | USD m
|  | ABDB B-loan: opening balance | USD m
|  | Commercial tranche: opening balance | USD m
|  | Standby facility: opening balance | USD m
|  | ECA-covered tranche: interest | USD m
|  | ABDB A-loan: interest | USD m
|  | ABDB B-loan: interest | USD m
|  | Commercial tranche: interest | USD m
|  | Standby facility: interest | USD m
|  | PRI premium on commercial tranche | USD m
|  | Swap net payment | USD m
|  | Commitment fees, senior tranches | USD m
|  | Commitment fee, standby facility | USD m
|  | Upfront and arrangement fees | USD m
|  | Agency fees during construction | USD m
|  | DSRA initial funding (COD month) | USD m
|  | Uses before ECA premium | USD m
|  | Headroom on committed senior tranches | USD m
|  | Senior tranche drawdown (pro rata) | USD m
|  | ECA premium (financed) | USD m
|  | Total uses of funds | USD m
|  | Funded pro rata from committed debt and equity | USD m
|  | Remaining uses after committed facilities | USD m
|  | Delay LDs and DSU proceeds received | USD m
|  | LD and DSU proceeds applied | USD m
|  | LD and DSU proceeds held (Proceeds Account) | USD m
|  | Standby facility drawdown (75%) | USD m
|  | Contingent equity (25%) | USD m
|  | ECA-covered tranche: drawdown | USD m
|  | ABDB A-loan: drawdown | USD m
|  | ABDB B-loan: drawdown | USD m
|  | Commercial tranche: drawdown | USD m
|  | ECA-covered tranche: closing balance | USD m
|  | ABDB A-loan: closing balance | USD m
|  | ABDB B-loan: closing balance | USD m
|  | Commercial tranche: closing balance | USD m
|  | Standby facility: closing balance | USD m
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m
|  | Equity contributed in cash | USD m
|  | Share capital | USD m
|  | Shareholder loans advanced | USD m
|  | Shareholder loan interest capitalized (to COD) | USD m
|  | Shareholder loan balance | USD m
|  | Total debt drawdowns (incl. standby) | USD m
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m
|  | Total funding requirement (sum of uses) | USD m
|  | Capitalized cost (book and tax) | USD m

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | %
|  | Waiver margin uplift | %
|  | ECA-covered tranche: rate per period | factor
|  | ABDB A-loan: rate per period | factor
|  | ABDB B-loan: rate per period | factor
|  | Commercial tranche: rate per period | factor
|  | Standby facility: rate per period | factor
|  | 2025 project bond: rate per period | factor
Contract repayment profile
|  | Repayment profile, selected | fraction
|  | Remaining profile (this and later installments) | fraction
|  | Installment share of remaining balance | fraction
|  | Flag_Refinancing (2025H1) | flag
|  | Flag_Waiver deferral (2023H2) | flag
|  | Flag_Deferred repayment (2024H1-2025H2) | flag
|  | Flag_LD prepayment (2022H1) | flag
ECA-covered tranche
|  | Opening balance | USD m
|  | Deferred principal, opening | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Scheduled principal per profile | USD m
|  | Principal deferred under the waiver | USD m
|  | Deferred amount at 2023-12-31 | USD m
|  | Deferred principal repaid | USD m
|  | Principal paid | USD m
|  | Performance LD prepayment | USD m
|  | Refinanced (prepaid from bond proceeds) | USD m
|  | Deferred principal, closing | USD m
|  | Balance after scheduled payment, LDs and refinancing | USD m
|  | Cash sweep prepayment | USD m
|  | Closing balance | USD m
ABDB A-loan
|  | Opening balance | USD m
|  | Deferred principal, opening | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Scheduled principal per profile | USD m
|  | Principal deferred under the waiver | USD m
|  | Deferred amount at 2023-12-31 | USD m
|  | Deferred principal repaid | USD m
|  | Principal paid | USD m
|  | Performance LD prepayment | USD m
|  | Refinanced (prepaid from bond proceeds) | USD m
|  | Deferred principal, closing | USD m
|  | Balance after scheduled payment, LDs and refinancing | USD m
|  | Cash sweep prepayment | USD m
|  | Closing balance | USD m
ABDB B-loan
|  | Opening balance | USD m
|  | Deferred principal, opening | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Scheduled principal per profile | USD m
|  | Principal deferred under the waiver | USD m
|  | Deferred amount at 2023-12-31 | USD m
|  | Deferred principal repaid | USD m
|  | Principal paid | USD m
|  | Performance LD prepayment | USD m
|  | Refinanced (prepaid from bond proceeds) | USD m
|  | Deferred principal, closing | USD m
|  | Balance after scheduled payment, LDs and refinancing | USD m
|  | Cash sweep prepayment | USD m
|  | Closing balance | USD m
Commercial tranche
|  | Opening balance | USD m
|  | Deferred principal, opening | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Scheduled principal per profile | USD m
|  | Principal deferred under the waiver | USD m
|  | Deferred amount at 2023-12-31 | USD m
|  | Deferred principal repaid | USD m
|  | Principal paid | USD m
|  | Performance LD prepayment | USD m
|  | Refinanced (prepaid from bond proceeds) | USD m
|  | Deferred principal, closing | USD m
|  | Balance after scheduled payment, LDs and refinancing | USD m
|  | Cash sweep prepayment | USD m
|  | Closing balance | USD m
Standby facility
|  | Opening balance | USD m
|  | Deferred principal, opening | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Scheduled principal per profile | USD m
|  | Principal deferred under the waiver | USD m
|  | Deferred amount at 2023-12-31 | USD m
|  | Deferred principal repaid | USD m
|  | Principal paid | USD m
|  | Performance LD prepayment | USD m
|  | Refinanced (prepaid from bond proceeds) | USD m
|  | Deferred principal, closing | USD m
|  | Balance after scheduled payment, LDs and refinancing | USD m
|  | Cash sweep prepayment | USD m
|  | Closing balance | USD m
2025 project bond
|  | Opening balance | USD m
|  | Interest (incl. WHT gross-up where applicable) | USD m
|  | Principal paid | USD m
|  | Balance after scheduled payment | USD m
|  | Closing balance | USD m
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m
|  | Principal prepaid (B-loan, commercial, standby) | USD m
|  | Bond face amount | USD m
|  | Swap unwind receipt | USD m
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m
|  | PRI premium (commercial tranche) | USD m
|  | ABDB PCG fee (bond) | USD m
|  | Waiver fee | USD m
|  | Interest, all tranches | USD m
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m
|  | Principal paid, all tranches | USD m
|  | Senior debt service | USD m
|  | Senior debt outstanding, opening | USD m
|  | Senior debt outstanding, closing | USD m
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m
|  | ECA-covered tranche: next period debt service | USD m
|  | ABDB A-loan: next period debt service | USD m
|  | ABDB B-loan: next period debt service | USD m
|  | Commercial tranche: next period debt service | USD m
|  | Standby facility: next period debt service | USD m
|  | Bond: next period debt service | USD m
|  | DSRA target (six months of next debt service) | USD m
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag
|  | Sculpting rate on scheduled balance | factor
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m
|  | Sculpted DSCR = PV(CFADS) / debt | x
|  | Debt capacity at the 1.35x target | USD m
|  | Debt at the 75% gearing cap (closed form) | USD m
|  | Sculpted debt service | USD m
|  | Sculpted balance, opening | USD m
|  | Sculpted principal | USD m
|  | Sculpted principal less contract principal (FC base) | USD m

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m
| MMRA balance | USD m
| DSRA opening | USD m
| DSRA drawing | USD m
| DSRA top-up | USD m
| DSRA release of excess | USD m
| DSRA closing | USD m
| Handback reserve contribution | USD m
| Handback reserve release at expiry | USD m
| Handback reserve balance | USD m
| Compensation Account (performance LDs held) | USD m

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m
|  | Cash brought forward (lock-up and trapped cash) | USD m
|  | Cash available for debt service | USD m
|  | Senior debt service and fees due | USD m
|  | Shortfall before DSRA | USD m
|  | Shortfall after DSRA (must be zero) | USD m
|  | Cash after debt service | USD m
|  | Cash after DSRA movements | USD m
|  | Cash available for distribution tests | USD m
Ratios and tests
|  | DSCR, period | x
|  | DSCR, historic 12 months (cash basis) | x
|  | First repayment made | flag
|  | Event of default (historic DSCR < 1.10x) | flag
|  | Tests waived (2023H1, 2023H2) | flag
|  | Waiver regime (from 2023H1) | flag
|  | Lock-up released under the waiver | flag
|  | Distributions permitted | flag
|  | Lock-up | flag
|  | Consecutive lock-ups | count
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m
|  | Lock-up account, closing | USD m
|  | Cash available for distribution | USD m
|  | Share capital contributed | USD m
|  | Shareholder loan balance, opening | USD m
|  | Shareholder loan interest paid | USD m
|  | Shareholder loan principal repaid | USD m
|  | Shareholder loan balance, closing | USD m
|  | Distributable reserves (retained earnings + current profit) | USD m
|  | Dividends within distributable reserves | USD m
|  | Cash trapped by the dividend restriction | USD m
|  | Liquidation distribution at PPA expiry | USD m
|  | Dividends | USD m
|  | Trapped cash, closing | USD m
|  | Retained earnings, closing | USD m
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m
|  | Tax written-down value | USD m
|  | Book value of plant (from COD) | USD m
|  | Deferred tax liability (asset if negative) | USD m
|  | Deferred tax expense | USD m
|  | Net income | USD m
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m
|  | Receivables (incl. overdue) | USD m
|  | Spares inventory | USD m
|  | Deferred tax asset | USD m
|  | Total assets | USD m
|  | Senior debt | USD m
|  | Shareholder loans (incl. capitalized interest) | USD m
|  | Payables (incl. deferred SNHK/GCK payables) | USD m
|  | Deferred tax liability | USD m
|  | Share capital | USD m
|  | Retained earnings | USD m
|  | Total liabilities and equity | USD m
|  | Balance check (assets less liabilities and equity) | USD m

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor
| Final maturity period | index
| Rate in final maturity period | factor
| Discount rate used | factor
| PV of CFADS to final maturity | USD m
| PV of CFADS to PPA expiry | USD m
| LLCR = (PV CFADS + DSRA) / debt | x
| LLCR excluding DSRA | x
| PLCR = PV CFADS to expiry / debt | x
| Minimum DSCR | x
| Average DSCR (debt-service weighted) | x
| LLCR at first debt service period | x
| PLCR at first debt service period | x

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date
| Equity cash flow (contributions negative) | USD m
| Project cash flow, post-tax (uses before financing; CFADS) | USD m
| Project cash flow, pre-tax | USD m
| Cumulative equity cash flow | USD m
| Equity IRR (XIRR) | %
| Project IRR, post-tax (XIRR) | %
| Project IRR, pre-tax (XIRR) | %
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check
| Committed debt drawn in full (FC-type), USD m | check
| Closed-form T less live T (re-grossed cases), USD m | check
| Balance sheet balances (max abs difference) | check
| No unpaid debt service after DSRA | check
| Debt repaid by final maturity | check
| FC base: live sculpting equals contract profile (max abs, USD m) | check
| FC base: debt not above DSCR capacity or gearing cap | check
| VAT facility within limit | check
| Standby and contingent equity within commitments | check
| ECA tranche within cap (USD 224.1m) | check
| MMRA never negative | check
| Sum of checks (0 = all pass) | check

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m
| Senior debt (four tranches) | USD m
| Equity (incl. LNTP) | USD m
| Gearing (debt incl. standby / total funding) | %
| Interest during construction incl. swap and PRI | USD m
| Commitment, upfront and agency fees | USD m
| ECA premium | USD m
| DSRA initial funding | USD m
| Standby drawn | USD m
| Contingent equity drawn | USD m
| Minimum DSCR | x
| Average DSCR | x
| LLCR at first debt service period (incl. DSRA) | x
| PLCR at first debt service period | x
| Equity IRR | %
| Project IRR, post-tax | %
| Equity NPV at 16.0% (at FC) | USD m
| All checks | check