## Inputs
Quebracho Alto (fictional; Illustrative): Chapter 13 practice files
Inputs: every number the workbook uses, with units (Examples 13.2 to 13.9)
Column D label, E unit, F value or scalar, G row total; first period in column J. Inputs: blue on yellow. Links: green. Checks: 0 when passing.
Check and macro settings
|  | Check tolerance | USD m | 0.001
Scenario control (Example 13.4)
|  | Scenario (1 Base, 2 Low, 3 High; cell named Scenario) | index | 1
Escalation factors by operating year (columns F to Y = years 1 to 20; Example 13.5)
|  | Escalation factor (tariff escalation 2.4% a year) |  | 1 | 1.024 | 1.0486 | 1.0737 | 1.0995 | 1.1259 | 1.1529 | 1.1806 | 1.2089 | 1.2379 | 1.2677 | 1.2981 | 1.3292 | 1.3611 | 1.3938 | 1.4272 | 1.4615 | 1.4966 | 1.5325 | 1.5693
Timing (Example 13.2)
|  | Notice to proceed | date | 2027-03-01
|  | Construction months | months | 26
|  | Commercial operation date | date | 2029-05-01
|  | Operating years | years | 20
|  | Months per operating period | months | 6
Operations and revenue (Examples 13.5 to 13.7)
|  | Annual energy (no degradation in these examples) | GWh | 551.4
|  | Base tariff (year 1) | USD/MWh | 63.4
|  | Tariff escalation (Example 13.5; factors in row 10) | % pa | 2.4%
|  | Operating cost | USD m pa | 7.94
|  | Discount rate (base) | % pa | 8.75%
Delay LDs (Example 13.3)
|  | Delay LD rate | USD/day | 39500
|  | Delay LD cap | USD | 9620000
|  | Days in each delay month (columns J to Q = delay months 1 to 8) | days |  |  |  |  | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Funding (Example 13.8)
|  | Gearing (debt share of total funding) | % | 72%
|  | IDC as a share of total debt (whole construction period; simplification) | % | 8.74% |  | Base | Low | High
|  | Costs before financing: scenario table H30:J30 (Base, Low, High); live value in F30 | USD m |  |  | 248.6 | 231.7 | 271.9
|  | Macro tolerance (optional Converge macro, ssec:13.8.5) | USD m | 0.001
|  | Macro pass limit | passes | 50
Goal seek (Example 13.7)
|  | Breakeven tariff at the base rate, pasted from Goal Seek (NPV = 0 by changing the tariff) | USD/MWh | 62.9122
|  | Breakeven test rate, low (Example 13.7) | % pa | 7.75%
|  | Breakeven test rate, high (Example 13.7) | % pa | 9.75%

## Time
Quebracho Alto (fictional; Illustrative): Chapter 13 practice files
Time: monthly construction timeline (rows 4 to 12) and semiannual operations timeline (rows 18 to 24)
Column D label, E unit, F value or scalar, G row total; first period in column J. Inputs: blue on yellow. Links: green. Checks: 0 when passing.
|  | Month counter | index
|  |  |  | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11 | 2027-12 | 2028-01 | 2028-02 | 2028-03 | 2028-04 | 2028-05 | 2028-06 | 2028-07 | 2028-08 | 2028-09 | 2028-10 | 2028-11 | 2028-12 | 2029-01 | 2029-02 | 2029-03 | 2029-04 | 2029-05 | 2029-06 | 2029-07 | 2029-08
|  | Days in month | days
|  | Month start | date
|  | Month end | date
|  | Flag_Construction | flag
Key dates (column F)
|  | Start of construction (notice to proceed) | date
|  | End of construction (last day of the last construction month) | date
|  | Commercial operation date | date
|  | End of operations | date
|  | Half-year counter (operations timeline) | index
|  | Half-year start | date
|  | Half-year end | date
|  | Days in half-year | days
|  | Flag_Operations | flag
|  | Flag_FirstOperationsPeriod | flag
|  | Operations fraction of the period (actual days) | fraction
|  | Operations fraction in the first operating period | fraction

## Calc
Quebracho Alto (fictional; Illustrative): Chapter 13 practice files
Calc: LD cap (Ex 13.3), revenue and NPV rows (Ex 13.5, 13.6), data table, goal seek (Ex 13.7), IDC closed form and iteration (Ex 13.8), sources and uses (Ex 13.9)
Column D label, E unit, F value or scalar, G row total; first period in column J. Inputs: blue on yellow. Links: green. Checks: 0 when passing.
|  | Operating year counter (revenue and NPV rows, columns J to AC) | index
Example 13.3: delay LDs with a cumulative cap (columns J to Q = delay months 1 to 8)
|  | Days in the delay month | days
|  | Delay LD rate | USD/day
|  | Delay LD cap | USD
|  | Delay LD accrual (capped) | USD
|  | Delay LDs, cumulative | USD
|  | Days to reach the cap | days
Examples 13.5 and 13.6: 20-year revenue and NPV rows (columns J to AC = operating years 1 to 20)
|  | Escalation factor (INDEX on the Inputs factor row; Example 13.5 replacement for OFFSET) | factor
|  | Revenue with escalation (Example 13.5) | USD m
|  | Discount factor at the base rate (end of year) | factor
|  | PV of revenue with escalation at the base rate | USD m
|  | Data-table input cell: flat tariff (row input; must sit on this sheet) | USD/MWh | 62
|  | Data-table input cell: discount rate (column input; must sit on this sheet) | % pa | 8.75%
|  | Revenue at the flat tariff (Example 13.6: no escalation) | USD m
|  | Operating cost | USD m
|  | Net cash flow | USD m
|  | Discount factor at the data-table rate | factor
|  | Present value of net cash flow | USD m
|  | NPV = -capex + sum of present values (feeds the data table) | USD m
|  | NPV, annuity form (Example 13.6 Excel form) | USD m
Example 13.8: IDC circularity (C, g, r_c from Inputs)
|  | Senior debt, closed form D = gC / (1 - g r_c) | USD m
|  | Pasted debt (written by the optional Converge macro; 0 = not run) | USD m | 0
|  | Debt computed from the pasted debt: g x (C + r_c x pasted) | USD m
|  | Convergence residual (computed less pasted) | USD m
|  | Iteration D0 = g x C | USD m
|  | Iteration D1 = g x (C + r_c x D0) | USD m
|  | Iteration D2 = g x (C + r_c x D1) | USD m
|  | Iteration D3 = g x (C + r_c x D2) | USD m
|  | Iteration D4 = g x (C + r_c x D3) | USD m
|  | Iteration D5 = g x (C + r_c x D4) | USD m
|  | NPV at the pasted goal-seek tariff and the base rate (Example 13.7; must be 0) | USD m
|  | Breakeven tariff, closed form, at the low test rate | USD/MWh
|  | Breakeven tariff, closed form, at the base rate | USD/MWh
|  | Breakeven tariff, closed form, at the high test rate | USD/MWh
|  | Annuity factor at the base rate | factor
|  | Interest during construction = r_c x D | USD m
|  | Total funding = C + IDC | USD m
|  | Equity = total funding - debt | USD m
Example 13.9: sources and uses
|  | Sources: debt + equity | USD m
|  | Uses: costs before financing + IDC | USD m
Example 13.6: two-way data table of NPV (USD m). Corner E64 = output; tariffs across (row input F30); rates down (column input F31)
|  | Data table (Data, What-If Analysis, Data Table; computed by Excel) |  | 58 | 62 | 66
7.75%
8.75%
9.75%
Closed-form grid: the same NPVs computed directly (live check on the data table)
Rate \ tariff

## Checks
Quebracho Alto (fictional; Illustrative): Chapter 13 practice files
Checks: each check 0 when passing; master check (Example 13.9)
Column D label, E unit, F value or scalar, G row total; first period in column J. Inputs: blue on yellow. Links: green. Checks: 0 when passing.
| Sources less uses (Example 13.9) | check
| Construction flags sum to the construction months | check
| Operations fraction between 0 and 1 in every period | check
| Revenue positive in every operating period (catches the Example 13.5 OFFSET failure) | check
| Goal-seek tariff still gives NPV = 0 (Example 13.7) | check
| Closed-form debt solves D = g(C + r_c D) | check
| Iteration D5 within tolerance of the closed form | check
| Delay LDs never exceed the cap | check
| NPV row equals the annuity form | check
| Data table equals the closed-form grid (Excel computes the table on open; blank table = not yet computed) | check
| Master check (sum of the checks above; 0 = all pass) | check
Stress test (Section 13.10 step 5): insert a column on Inputs and a row on Calc, change Scenario, and confirm F18 stays 0; then replace Calc row 26 with =OFFSET(Inputs!$E$10,0,J$4) and insert a column at Inputs F: F10 fires (1).