## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 1
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 1
|  | Construction case (1 FC budget, 2 actual) | code | 1
|  | COD delay (sensitivity) | months | 0
|  | Capex factor | factor | 1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 0
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 0
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 1
|  | Performance LD prepayment June 2022 (1 = on) | flag | 0
|  | Waiver and amendment 2023 (1 = on) | flag | 0
|  | 2025 bond refinancing (1 = on) | flag | 0
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 1
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 654.6336
|  | Equity commitment (base, incl. LNTP) | USD m | 205.2822
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.023923 | 0.024546 | 0.025557 | 0.026244 | 0.02802 | 0.02843 | 0.029025 | 0.030095 | 0.030851 | 0.031178 | 0.03252 | 0.033518 | 0.035684 | 0.036033 | 0.037826 | 0.039302 | 0.042889 | 0.044172 | 0.046129 | 0.047596 | 0.050445 | 0.051645 | 0.053343 | 0.055238 | 0.05689 | 0.058903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 523.7069 | 511.1784 | 498.3234 | 484.9392 | 471.1951 | 456.5209 | 441.632 | 426.4316 | 410.6706 | 394.5137 | 378.1858 | 361.155 | 343.6014 | 324.9137 | 306.043 | 286.2334 | 265.6505 | 243.189 | 220.056 | 195.8979 | 170.9715 | 144.553 | 117.5064 | 89.5703 | 60.6417 | 30.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 73.1964 | 74.6795 | 76.5714 | 79.256 | 83.1258 | 88.4884 | 95.4917 | 104.3699 | 115.128 | 127.7934 | 142.2506 | 158.4392 | 176.1365 | 195.094 | 215.0845 | 235.7736 | 256.8891 | 278.8136 | 299.7483 | 320.1711 | 339.7079 | 358.1355 | 375.1615 | 390.6614 | 404.4469 | 416.4035 | 426.5694 | 434.9386 | 441.699 | 447.0442 | 451.1534 | 454.5639 | 487.2305 | 521.3236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-05-01
|  | PPA expiry | date | 2046-04-30
|  | Construction months (NTP to COD) | months | 33
|  | Period containing COD (period number) | index | 6
|  | First debt service period | index | 7
|  | Last month of the funding period (month number) | index | 35
|  | Last operating period (period number) | index | 56
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-05-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-04-30
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 120 | 0
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 14 | 20 | 26 | 32 | 38 | 44 | 50 | 56 | 62 | 68 | 74 | 80 | 86 | 92 | 98 | 104 | 110 | 116 | 122 | 128 | 134 | 140 | 146 | 152 | 158 | 164 | 170 | 176 | 182 | 188 | 194 | 200 | 206 | 212 | 218 | 224 | 230 | 236 | 242 | 248 | 254 | 260 | 266 | 272 | 278 | 284 | 290 | 296 | 300 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 520.4953 | 522.6929 | 524.8998 | 527.116 | 529.3416 | 531.5766 | 533.821 | 536.0748 | 538.3382 | 540.6112 | 542.8937 | 545.1859 | 547.4878 | 549.7993 | 552.1207 | 554.4518 | 556.7928 | 559.1437 | 561.5044 | 563.8752 | 566.256 | 568.6468 | 571.0477 | 573.4587 | 575.88 | 578.3114 | 580.7532 | 583.2052 | 585.6676 | 588.1403 | 590.6236 | 593.1173 | 595.6215 | 598.1363 | 600.6617 | 603.1978 | 605.7446 | 608.3021 | 610.8705 | 613.4497 | 616.0398 | 618.6408 | 621.2528 | 623.8758 | 626.5099 | 629.1551 | 631.8115 | 634.4791 | 637.158 | 639.8481 | 642.5497 | 645.2626 | 647.987
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.06 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 571.84 | 57.184 | 0.061759 | 0.64789 | 1.8522 | 3.5992 | 5.7836 | 8.2894 | 10.9999 | 13.8002 | 16.5828 | 19.2476 | 21.7053 | 23.8772 | 25.6956 | 27.1081 | 28.0722 | 28.5611 | 28.5611 | 28.0722 | 27.1081 | 25.6956 | 23.8772 | 21.7053 | 19.2476 | 16.5828 | 13.8002 | 10.9999 | 8.2894 | 5.7836 | 3.5992 | 1.8522 | 0.64789 | 42.9498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 46.18 | 5.5416 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 7.62 | 6.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 8.97 | 6.279 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0.084094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 38.4 | 0 | 0.0050269 | 0.052736 | 0.15076 | 0.29296 | 0.47076 | 0.67472 | 0.89535 | 1.1233 | 1.3498 | 1.5667 | 1.7667 | 1.9435 | 2.0915 | 2.2065 | 2.285 | 2.3248 | 2.3248 | 2.285 | 2.2065 | 2.0915 | 1.9435 | 1.7667 | 1.5667 | 1.3498 | 1.1233 | 0.89535 | 0.67472 | 0.47076 | 0.29296 | 0.15076 | 0.052736 | 0.0050269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 710.99 | 108.1116 | 1.4208 | 2.0547 | 3.357 | 5.2462 | 7.6084 | 10.3182 | 13.2493 | 16.2775 | 19.2866 | 22.1683 | 24.8261 | 27.1747 | 29.1412 | 30.6686 | 31.7112 | 32.2399 | 33.3829 | 31.7112 | 30.6686 | 29.1412 | 27.1747 | 24.8261 | 22.1683 | 19.2866 | 16.2775 | 13.2493 | 10.3182 | 7.6084 | 5.2462 | 3.357 | 2.0547 | 49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 42938.798 | 4293.8798 | 4.6374 | 48.6497 | 139.0788 | 270.2568 | 434.283 | 622.4408 | 825.9707 | 1036.242 | 1245.1822 | 1445.277 | 1629.828 | 1792.9095 | 1929.4549 | 2035.5137 | 2107.9085 | 2144.6212 | 2144.6212 | 2107.9085 | 2035.5137 | 1929.4549 | 1792.9095 | 1629.828 | 1445.277 | 1245.1822 | 1036.242 | 825.9707 | 622.4408 | 434.283 | 270.2568 | 139.0788 | 48.6497 | 3225.0472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 7728.9836 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 7728.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.8984 | 0.83473 | 8.7569 | 25.0342 | 48.6462 | 78.1709 | 112.0393 | 148.6747 | 186.5236 | 224.1328 | 260.1499 | 293.369 | 322.7237 | 347.3019 | 366.3925 | 379.4235 | 386.0318 | 386.0318 | 379.4235 | 366.3925 | 347.3019 | 322.7237 | 293.369 | 260.1499 | 224.1328 | 186.5236 | 148.6747 | 112.0393 | 78.1709 | 48.6462 | 25.0342 | 8.7569 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 772.8984 | 773.7331 | 782.49 | 807.5242 | 856.1704 | 934.3414 | 1046.3807 | 1195.0555 | 1381.579 | 832.8134 | 1092.1286 | 1376.7407 | 1674.4302 | 1973.0859 | 2261.3074 | 2528.6916 | 2766.0487 | 2965.5569 | 3120.8477 | 3227.0903 | 3281.0231 | 3281.0231 | 3227.0903 | 3120.8477 | 2965.5569 | 2766.0487 | 2528.6916 | 2261.3074 | 1973.0859 | 1674.4302 | 1376.7407 | 1092.1286 | 1412.4872 | 1188.3544 | 1001.8309 | 853.1561 | 741.1168 | 662.9458 | 614.2996 | 589.2654 | 580.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.6349 | 0 | 0.019446 | 0.020031 | 0.019522 | 0.02073 | 0.021887 | 0.021483 | 0.026525 | 0.029193 | 0.034728 | 0.020174 | 0.027222 | 0.034172 | 0.040051 | 0.048562 | 0.053634 | 0.061715 | 0.067224 | 0.06714 | 0.07521 | 0.074946 | 0.078407 | 0.075559 | 0.076471 | 0.073643 | 0.067436 | 0.064723 | 0.057019 | 0.052468 | 0.045588 | 0.034797 | 0.031543 | 0.024113 | 0.03209 | 0.026017 | 0.02257 | 0.019139 | 0.016022 | 0.014747 | 0.013169 | 0.012998 | 0.012751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | KCR per USD, period average | KCR/USD |  |  | 526.0068 | 539.4735 | 553.285 | 567.4501 | 581.9779 | 596.8776 | 612.1587 | 627.8311 | 643.9047 | 660.3899 | 677.297 | 694.6371 | 712.4211 | 730.6603 | 749.3666 | 768.5517 | 788.228 | 808.4081 | 829.1048 | 850.3314 | 872.1015 | 894.4289 | 917.3279 | 940.8131 | 964.8997 | 989.6029 | 1014.9385 | 1040.9228 | 1067.5723 | 1094.9041 | 1122.9356 | 1151.6848 | 1181.1701 | 1211.4102 | 1242.4245 | 1274.2328 | 1306.8555 | 1340.3134 | 1374.6278 | 1409.8208 | 1445.9148 | 1482.9329 | 1520.8987 | 1559.8364 | 1599.7711 | 1640.7281 | 1682.7338 | 1725.8148 | 1769.9988 | 1815.314 | 1861.7894 | 1909.4546 | 1958.3401 | 2008.4772 | 2059.8979 | 2112.635 | 2166.7223
|  | US CPI change, current year | % |  |  | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, current year | % |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI change, prior year | % |  |  | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US index, June 2018 (2018 price base) | index | 103.3281
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 103.8918 | 105.0284 | 106.1774 | 107.339 | 108.5133 | 109.7005 | 110.9006 | 112.1139 | 113.3405 | 114.5804 | 115.8339 | 117.1012 | 118.3823 | 119.6774 | 120.9867 | 122.3103 | 123.6484 | 125.0011 | 126.3687 | 127.7512 | 129.1488 | 130.5617 | 131.9901 | 133.4341 | 134.8938 | 136.3696 | 137.8615 | 139.3697 | 140.8945 | 142.4359 | 143.9941 | 145.5695 | 147.162 | 148.772 | 150.3996 | 152.045 | 153.7084 | 155.39 | 157.0899 | 158.8085 | 160.5459 | 162.3023 | 164.0779 | 165.873 | 167.6876 | 169.5222 | 171.3768 | 173.2517 | 175.1471 | 177.0632 | 179.0003 | 180.9586 | 182.9383 | 184.9397 | 186.963 | 189.0084 | 191.0761
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 104.4586 | 105.6014 | 106.7567 | 107.9246 | 109.1053 | 110.2989 | 111.5056 | 112.7255 | 113.9587 | 115.2055 | 116.4658 | 117.74 | 119.0281 | 120.3303 | 121.6467 | 122.9775 | 124.3229 | 125.683 | 127.058 | 128.4481 | 129.8533 | 131.2739 | 132.7101 | 134.162 | 135.6297 | 137.1135 | 138.6136 | 140.13 | 141.6631 | 143.2129 | 144.7797 | 146.3636 | 147.9648 | 149.5836 | 151.22 | 152.8744 | 154.5469 | 156.2376 | 157.9469 | 159.6749 | 161.4217 | 163.1877 | 164.973 | 166.7778 | 168.6024 | 170.447 | 172.3117 | 174.1968 | 176.1025 | 178.0291 | 179.9768 | 181.9458 | 183.9363 | 185.9486 | 187.9829 | 190.0394 | 192.1185
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0055 | 1.0165 | 1.0276 | 1.0388 | 1.0502 | 1.0617 | 1.0733 | 1.085 | 1.0969 | 1.1089 | 1.121 | 1.1333 | 1.1457 | 1.1582 | 1.1709 | 1.1837 | 1.1967 | 1.2097 | 1.223 | 1.2364 | 1.2499 | 1.2636 | 1.2774 | 1.2914 | 1.3055 | 1.3198 | 1.3342 | 1.3488 | 1.3636 | 1.3785 | 1.3936 | 1.4088 | 1.4242 | 1.4398 | 1.4556 | 1.4715 | 1.4876 | 1.5038 | 1.5203 | 1.5369 | 1.5537 | 1.5707 | 1.5879 | 1.6053 | 1.6229 | 1.6406 | 1.6586 | 1.6767 | 1.6951 | 1.7136 | 1.7323 | 1.7513 | 1.7705 | 1.7898 | 1.8094 | 1.8292 | 1.8492
|  | KC index, June 2018 (2018 price base) | index | 112.9227
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 114.983 | 119.2169 | 123.6067 | 128.1581 | 132.8772 | 137.77 | 142.843 | 148.1027 | 153.5562 | 159.2105 | 165.0729 | 171.1512 | 177.4534 | 183.9876 | 190.7624 | 197.7866 | 205.0696 | 212.6206 | 220.4498 | 228.5672 | 236.9835 | 245.7097 | 254.7573 | 264.138 | 273.8641 | 283.9483 | 294.4039 | 305.2444 | 316.4842 | 328.1378 | 340.2205 | 352.7481 | 365.737 | 379.2042 | 393.1673 | 407.6445 | 422.6548 | 438.2179 | 454.3539 | 471.0842 | 488.4305 | 506.4155 | 525.0628 | 544.3967 | 564.4425 | 585.2264 | 606.7757 | 629.1184 | 652.2839 | 676.3023 | 701.2051 | 727.025 | 753.7955 | 781.5518 | 810.3302 | 840.1682 | 871.105
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 117.0808 | 121.3919 | 125.8618 | 130.4963 | 135.3015 | 140.2836 | 145.4491 | 150.8048 | 156.3578 | 162.1152 | 168.0846 | 174.2738 | 180.6909 | 187.3444 | 194.2428 | 201.3952 | 208.811 | 216.4998 | 224.4718 | 232.7373 | 241.3072 | 250.1926 | 259.4052 | 268.9571 | 278.8606 | 289.1288 | 299.7752 | 310.8135 | 322.2583 | 334.1245 | 346.4277 | 359.1838 | 372.4097 | 386.1226 | 400.3405 | 415.0818 | 430.366 | 446.213 | 462.6435 | 479.6789 | 497.3417 | 515.6549 | 534.6423 | 554.329 | 574.7405 | 595.9037 | 617.8461 | 640.5964 | 664.1845 | 688.6412 | 713.9983 | 740.2892 | 767.5482 | 795.8109 | 825.1143 | 855.4968 | 886.9979
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0182 | 1.0557 | 1.0946 | 1.1349 | 1.1767 | 1.22 | 1.265 | 1.3115 | 1.3598 | 1.4099 | 1.4618 | 1.5156 | 1.5715 | 1.6293 | 1.6893 | 1.7515 | 1.816 | 1.8829 | 1.9522 | 2.0241 | 2.0986 | 2.1759 | 2.256 | 2.3391 | 2.4252 | 2.5145 | 2.6071 | 2.7031 | 2.8027 | 2.9059 | 3.0129 | 3.1238 | 3.2388 | 3.3581 | 3.4817 | 3.6099 | 3.7429 | 3.8807 | 4.0236 | 4.1717 | 4.3254 | 4.4846 | 4.6498 | 4.821 | 4.9985 | 5.1825 | 5.3734 | 5.5712 | 5.7764 | 5.9891 | 6.2096 | 6.4383 | 6.6753 | 6.9211 | 7.176 | 7.4402 | 7.7142
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 26
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 0
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.7333 | 90.6 | 91.6667 | 93.8 | 93.5 | 92.9 | 93.2 | 93.8 | 92.1 | 88.7 | 90.4 | 93.8 | 93.8 | 0
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.41667 | 0.91667 | 1.4167 | 1.9167 | 2.4167 | 2.9167 | 3.4167 | 3.9167 | 4.4167 | 4.9167 | 5.4167 | 5.9167 | 6.4167 | 6.9167 | 7.4167 | 7.9167 | 8.4167 | 8.9167 | 9.4167 | 9.9167 | 10.4167 | 10.9167 | 11.4167 | 11.9167 | 12.4167 | 12.9167 | 13.4167 | 13.9167 | 14.4167 | 14.9167 | 15.4167 | 15.9167 | 16.4167 | 16.9167 | 17.4167 | 17.9167 | 18.4167 | 18.9167 | 19.4167 | 19.9167 | 20.4167 | 20.9167 | 21.4167 | 21.9167 | 22.4167 | 22.9167 | 23.4167 | 23.9167 | 24.4167 | 24.8333 | 0
|  | Contracted capacity | MW | 588.4
|  | Plant net heat rate, new and clean | kJ/kWh | 6261
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98988 | 0.98938 | 0.98864 | 0.9879 | 0.98715 | 0.98641 | 0.98567 | 0.98493 | 0.98418 | 0.98344 | 0.9827 | 0.98196 | 0.98121 | 0.98047 | 0.97973 | 0.97899 | 0.97824 | 0.9775 | 0.97676 | 0.97602 | 0.97527 | 0.97453 | 0.97379 | 0.97305 | 0.9723 | 0.97156 | 0.97082 | 0.97008 | 0.96933 | 0.96859 | 0.96785 | 0.96711 | 0.96636 | 0.96562 | 0.96488 | 0.96414 | 0.96339 | 0.96265 | 0.96191 | 0.96117 | 0.96042 | 0.95968 | 0.95894 | 0.9582 | 0.95745 | 0.95671 | 0.95597 | 0.95523 | 0.95448 | 0.95374 | 0.95312 | 0.99
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 610197.8847 | 1829678.2427 | 1822457.6681 | 1809402.8106 | 1813881.5431 | 1824185.7752 | 1802084.1562 | 1759300.8791 | 1778671.879 | 1818693.3077 | 1811507.8661 | 1798523.2747 | 1802966.8742 | 1813200.8402 | 1778990.7603 | 1712018.3752 | 1743507.1072 | 1807708.3727 | 1800558.0641 | 1787643.7388 | 1792052.2052 | 1802215.9051 | 1780364.1212 | 1738080.5141 | 1757201.6791 | 1796723.4376 | 1789608.2621 | 1776764.203 | 1781137.5363 | 1791230.9701 | 1757419.0648 | 1691243.0289 | 1722333.5863 | 1785738.5026 | 1778658.4602 | 1765884.6671 | 1770222.8674 | 1780246.0351 | 1758644.0861 | 1716860.1492 | 1735731.4791 | 1774753.5675 | 1767708.6582 | 1755005.1312 | 1759308.1984 | 1769261.1 | 1735847.3694 | 1670467.6827 | 1701160.0655 | 1763768.6325 | 1175082.9123 | 0
|  | Plant net heat rate | kJ/kWh |  |  | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.243 | 6456.8886 | 6459.4711 | 6463.3449 | 6467.2186 | 6471.0924 | 6474.9661 | 6478.8399 | 6482.7136 | 6486.5874 | 6490.4611 | 6494.3349 | 6498.2086 | 6502.0823 | 6505.9561 | 6509.8298 | 6513.7036 | 6517.5773 | 6521.4511 | 6525.3248 | 6529.1986 | 6533.0723 | 6536.9461 | 6540.8198 | 6544.6936 | 6548.5673 | 6552.441 | 6556.3148 | 6560.1885 | 6564.0623 | 6567.936 | 6571.8098 | 6575.6835 | 6579.5573 | 6583.431 | 6587.3048 | 6591.1785 | 6595.0522 | 6598.926 | 6602.7997 | 6606.6735 | 6610.5472 | 6614.421 | 6618.2947 | 6622.1685 | 6626.0422 | 6629.916 | 6633.7897 | 6637.6635 | 6641.5372 | 6645.4109 | 6648.6391 | 6456.243
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.968 | 6471.1242 | 6474.3584 | 6477.5926 | 6480.8268 | 6484.061 | 6487.2953 | 6490.5295 | 6493.7637 | 6496.9979 | 6500.2321 | 6503.4663 | 6506.7005 | 6509.9348 | 6513.169 | 6516.4032 | 6519.6374 | 6522.8716 | 6526.1058 | 6529.34 | 6532.5743 | 6535.8085 | 6539.0427 | 6542.2769 | 6545.5111 | 6548.7453 | 6551.9795 | 6555.2138 | 6558.448 | 6561.6822 | 6564.9164 | 6568.1506 | 6571.3848 | 6574.619 | 6577.8533 | 6581.0875 | 6584.3217 | 6587.5559 | 6590.7901 | 6594.0243 | 6597.2585 | 6600.4928 | 6603.727 | 6606.9612 | 6610.1954 | 6613.4296 | 6616.6638 | 6619.898 | 6623.1323 | 6626.3665 | 6629.0617 | 6468.429
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 4137692.7979 | 12411833.3307 | 12370265.7341 | 12289014.3891 | 12326811.9429 | 12404258.6808 | 12261301.272 | 11977362.8114 | 12116476.9239 | 12396505.2781 | 12354897.6145 | 12273656.3697 | 12311315.5234 | 12388573.1226 | 12162072.2212 | 11711180.1611 | 11933673.834 | 12380462.2143 | 12338816.7706 | 12257590.1995 | 12295108.6664 | 12372172.5532 | 12229403.2985 | 11946025.9973 | 12084596.4827 | 12363704.1393 | 12322023.2024 | 12240815.8786 | 12278191.3719 | 12355056.9726 | 12128987.9936 | 11679148.2501 | 11900855.7346 | 12346231.0531 | 12304516.9097 | 12223333.4069 | 12260563.6397 | 12337226.3808 | 12194677.8039 | 11911926.7092 | 12049921.0439 | 12328042.9557 | 12286297.8926 | 12205142.7845 | 12242225.47 | 12318680.7778 | 12093095.5557 | 11644411.7978 | 11865281.2595 | 12309139.8471 | 8204753.1026 | 0
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 3533120 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 6950400 | 0
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4881 | 14.5209 | 14.5541 | 14.5876 | 14.6215 | 14.6558 | 14.6904 | 14.7255 | 14.7609 | 14.7967 | 14.8329 | 14.8695 | 14.9065 | 14.9439 | 14.9817 | 15.0199 | 15.0586 | 15.0976 | 15.1371 | 15.177 | 15.2174 | 15.2582 | 15.2994 | 15.3411 | 15.3833 | 15.4259 | 15.469 | 15.5125 | 15.5566 | 15.6011 | 15.6461 | 15.6916 | 15.7375 | 15.784 | 15.831 | 15.8786 | 15.9266 | 15.9751 | 16.0242 | 16.0739 | 16.124 | 16.1748 | 16.226 | 16.2779 | 16.3303 | 16.3832 | 16.4368 | 16.4909 | 16.5457 | 16.601 | 16.6569 | 16.7135 | 16.7706 | 16.8284 | 16.8869 | 16.9459 | 17.0056
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3994 | 2.4257 | 2.4522 | 2.479 | 2.5062 | 2.5336 | 2.5613 | 2.5893 | 2.6176 | 2.6463 | 2.6752 | 2.7045 | 2.7341 | 2.764 | 2.7942 | 2.8248 | 2.8557 | 2.8869 | 2.9185 | 2.9505 | 2.9827 | 3.0154 | 3.0484 | 3.0817 | 3.1154 | 3.1495 | 3.184 | 3.2188 | 3.254 | 3.2896 | 3.3256 | 3.362 | 3.3988 | 3.4359 | 3.4735 | 3.5115 | 3.5499 | 3.5888 | 3.628 | 3.6677 | 3.7079 | 3.7484 | 3.7894 | 3.8309 | 3.8728 | 3.9152 | 3.958 | 4.0013 | 4.0451 | 4.0893 | 4.1341 | 4.1793 | 4.225 | 4.2712 | 4.318 | 4.3652 | 4.413
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 1.0422 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0304 | 1.0067 | 1.0185 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0233 | 0.98556 | 1.0044 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0304 | 1.0067 | 1.0185 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0233 | 0.98556 | 1.0044 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0304 | 1.0067 | 1.0185 | 1.0422 | 1.0389 | 1.0322 | 1.0356 | 1.0422 | 1.0233 | 0.98556 | 1.0044 | 1.0422 | 1.0422 | 0
|  | Capacity payment | USD m |  | 3464.1225 | 0 | 0 | 0 | 0 | 0 | 21.0825 | 63.4771 | 63.5053 | 63.3301 | 63.7702 | 64.4205 | 63.9275 | 62.6934 | 63.6736 | 65.4058 | 65.4489 | 65.2824 | 65.7502 | 66.435 | 65.4905 | 63.3256 | 64.7997 | 67.51 | 67.5693 | 67.4122 | 67.9103 | 68.6328 | 68.1374 | 66.8515 | 67.9267 | 69.8055 | 69.8825 | 69.7357 | 70.2668 | 71.0304 | 70.052 | 67.7667 | 69.3755 | 72.3098 | 72.4061 | 72.2705 | 72.8376 | 73.6461 | 73.148 | 71.8004 | 72.9886 | 75.0419 | 75.1592 | 75.0359 | 75.6423 | 76.4997 | 75.4809 | 73.0524 | 74.8214 | 78.0224 | 52.2757 | 0
|  | VOM charge, indexed | USD/MWh |  |  | 4.0142 | 4.0581 | 4.1025 | 4.1474 | 4.1928 | 4.2386 | 4.285 | 4.3319 | 4.3793 | 4.4272 | 4.4756 | 4.5246 | 4.5741 | 4.6241 | 4.6747 | 4.7258 | 4.7775 | 4.8298 | 4.8827 | 4.9361 | 4.9901 | 5.0447 | 5.0999 | 5.1556 | 5.2121 | 5.2691 | 5.3267 | 5.385 | 5.4439 | 5.5035 | 5.5637 | 5.6245 | 5.6861 | 5.7483 | 5.8112 | 5.8747 | 5.939 | 6.004 | 6.0697 | 6.1361 | 6.2032 | 6.2711 | 6.3397 | 6.409 | 6.4791 | 6.55 | 6.6217 | 6.6941 | 6.7674 | 6.8414 | 6.9162 | 6.9919 | 7.0684 | 7.1457 | 7.2239 | 7.3029 | 7.3828
|  | Variable O&M payment | USD m |  | 499.3216 | 0 | 0 | 0 | 0 | 0 | 2.5864 | 7.8402 | 7.8947 | 7.9239 | 8.0304 | 8.1643 | 8.1537 | 8.0472 | 8.2248 | 8.5019 | 8.5609 | 8.5925 | 8.708 | 8.8532 | 8.7812 | 8.5431 | 8.7954 | 9.219 | 9.283 | 9.3173 | 9.4424 | 9.5999 | 9.5872 | 9.4619 | 9.6707 | 9.9964 | 10.0657 | 10.1028 | 10.2385 | 10.4091 | 10.3244 | 10.0443 | 10.3409 | 10.8388 | 10.914 | 10.9541 | 11.1012 | 11.2862 | 11.2712 | 11.1238 | 11.3691 | 11.7519 | 11.8333 | 11.8768 | 12.0361 | 12.2366 | 12.1369 | 11.8075 | 12.156 | 12.7413 | 8.5816 | 0
|  | Fuel charge (pass-through) | USD m |  | 4886.8261 | 0 | 0 | 0 | 0 | 0 | 25.7791 | 77.3244 | 78.5989 | 78.0749 | 79.8734 | 80.3672 | 81.0218 | 79.1376 | 81.6498 | 83.5286 | 84.9048 | 84.3382 | 86.2804 | 86.8132 | 86.922 | 83.6912 | 86.9783 | 90.2258 | 91.7118 | 91.0991 | 93.1964 | 93.7714 | 94.5338 | 92.3343 | 95.2642 | 97.4549 | 99.0593 | 98.3969 | 100.6615 | 101.2818 | 101.4074 | 97.6369 | 101.4704 | 105.2576 | 106.9897 | 106.2736 | 108.7188 | 109.388 | 110.276 | 107.7088 | 111.125 | 113.679 | 115.5489 | 114.7747 | 117.4147 | 118.1367 | 118.2815 | 113.8822 | 118.3519 | 122.7675 | 83.4617 | 0
|  | GTA reservation charge (pass-through) | USD m |  | 690.3467 | 0 | 0 | 0 | 0 | 0 | 3.8163 | 11.5116 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 10.893 | 0
|  | GTA commodity charge (pass-through) | USD m |  | 146.4295 | 0 | 0 | 0 | 0 | 0 | 0.82207 | 2.466 | 2.4946 | 2.4782 | 2.5231 | 2.539 | 2.5473 | 2.4883 | 2.555 | 2.6141 | 2.6444 | 2.627 | 2.6746 | 2.6913 | 2.6818 | 2.5823 | 2.6709 | 2.7709 | 2.803 | 2.7845 | 2.8349 | 2.8527 | 2.8621 | 2.7958 | 2.8706 | 2.9369 | 2.9709 | 2.9513 | 3.0048 | 3.0236 | 3.0128 | 2.901 | 3.0005 | 3.1127 | 3.1488 | 3.128 | 3.1846 | 3.2045 | 3.215 | 3.1404 | 3.2245 | 3.2989 | 3.337 | 3.315 | 3.3749 | 3.396 | 3.3838 | 3.2583 | 3.3699 | 3.4959 | 2.3652 | 0
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 3963.4441 | 0 | 0 | 0 | 0 | 0 | 23.6689 | 71.3172 | 71.4 | 71.254 | 71.8006 | 72.5848 | 72.0811 | 70.7406 | 71.8984 | 73.9077 | 74.0098 | 73.8749 | 74.4582 | 75.2882 | 74.2718 | 71.8687 | 73.5951 | 76.729 | 76.8523 | 76.7295 | 77.3527 | 78.2327 | 77.7247 | 76.3135 | 77.5974 | 79.8019 | 79.9482 | 79.8385 | 80.5053 | 81.4395 | 80.3764 | 77.8111 | 79.7163 | 83.1486 | 83.3201 | 83.2247 | 83.9388 | 84.9323 | 84.4192 | 82.9242 | 84.3576 | 86.7937 | 86.9925 | 86.9127 | 87.6784 | 88.7363 | 87.6178 | 84.86 | 86.9774 | 90.7637 | 60.8572 | 0
|  | Total revenue | USD m |  | 9687.0465 | 0 | 0 | 0 | 0 | 0 | 54.0865 | 162.6192 | 163.9873 | 163.4913 | 165.8632 | 167.3505 | 167.5568 | 164.404 | 168.122 | 172.2683 | 173.7581 | 173.2413 | 175.7952 | 177.3801 | 176.5127 | 170.9183 | 176.0005 | 182.6934 | 184.3147 | 183.7753 | 186.5259 | 188.2164 | 188.5333 | 185.0036 | 189.2712 | 193.9572 | 195.7206 | 195.1566 | 198.1198 | 199.9244 | 199.0322 | 192.7412 | 198.557 | 206.127 | 208.044 | 207.4534 | 210.6463 | 212.5743 | 213.0194 | 209.0487 | 213.9588 | 219.276 | 221.3588 | 220.7393 | 224.1806 | 226.2421 | 225.3196 | 218.2131 | 224.8867 | 233.483 | 157.5772 | 0
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 279.3596 | 0 | 0 | 0 | 0 | 0 | 1.399 | 4.2428 | 4.2892 | 4.3361 | 4.3835 | 4.4315 | 4.48 | 4.529 | 4.5785 | 4.6286 | 4.6793 | 4.7305 | 4.7822 | 4.8345 | 4.8874 | 4.9409 | 4.9949 | 5.0496 | 5.1048 | 5.1607 | 5.2171 | 5.2742 | 5.3319 | 5.3902 | 5.4492 | 5.5088 | 5.5691 | 5.63 | 5.6916 | 5.7539 | 5.8168 | 5.8805 | 5.9448 | 6.0098 | 6.0756 | 6.1421 | 6.2093 | 6.2772 | 6.3459 | 6.4153 | 6.4855 | 6.5564 | 6.6282 | 6.7007 | 6.774 | 6.8481 | 6.923 | 6.9987 | 7.0753 | 7.1527 | 4.8206 | 0
|  | O&M availability incentive | USD m |  | 4.108 | 0 | 0 | 0 | 0 | 0 | 0.0637 | 0.19319 | 0.16275 | 0.098721 | 0.13307 | 0.20179 | 0.083108 | -0.1604 | -0.038608 | 0.21076 | 0.17756 | 0.1077 | 0.14517 | 0.22014 | 0.012364 | -0.37497 | -0.20217 | 0.22993 | 0.1937 | 0.11749 | 0.15837 | 0.24016 | 0.098913 | -0.1909 | -0.045949 | 0.25084 | 0.21132 | 0.12818 | 0.17278 | 0.262 | 0.014715 | -0.44627 | -0.24062 | 0.27365 | 0.23054 | 0.13984 | 0.18849 | 0.28583 | 0.11772 | -0.2272 | -0.054687 | 0.29854 | 0.25151 | 0.15256 | 0.20563 | 0.31182 | 0.017513 | -0.53114 | -0.28637 | 0.32569 | 0.2195 | 0
|  | LTSA fixed fee | USD m |  | 93.2833 | 0 | 0 | 0 | 0 | 0 | 0.46714 | 1.4167 | 1.4322 | 1.4479 | 1.4637 | 1.4798 | 1.4959 | 1.5123 | 1.5289 | 1.5456 | 1.5625 | 1.5796 | 1.5969 | 1.6143 | 1.632 | 1.6499 | 1.6679 | 1.6862 | 1.7046 | 1.7232 | 1.7421 | 1.7612 | 1.7804 | 1.7999 | 1.8196 | 1.8395 | 1.8596 | 1.88 | 1.9005 | 1.9213 | 1.9423 | 1.9636 | 1.9851 | 2.0068 | 2.0288 | 2.0509 | 2.0734 | 2.0961 | 2.119 | 2.1422 | 2.1656 | 2.1893 | 2.2133 | 2.2375 | 2.262 | 2.2867 | 2.3117 | 2.337 | 2.3626 | 2.3884 | 1.6097 | 0
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 1406.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 4219.5 | 2813 | 0
|  | LTSA variable fee | USD m |  | 144.9197 | 0 | 0 | 0 | 0 | 0 | 0.72571 | 2.201 | 2.225 | 2.2494 | 2.274 | 2.2989 | 2.324 | 2.3494 | 2.3751 | 2.4011 | 2.4274 | 2.454 | 2.4808 | 2.5079 | 2.5354 | 2.5631 | 2.5912 | 2.6195 | 2.6482 | 2.6771 | 2.7064 | 2.736 | 2.766 | 2.7962 | 2.8268 | 2.8577 | 2.889 | 2.9206 | 2.9526 | 2.9849 | 3.0175 | 3.0505 | 3.0839 | 3.1176 | 3.1518 | 3.1862 | 3.2211 | 3.2563 | 3.292 | 3.328 | 3.3644 | 3.4012 | 3.4384 | 3.476 | 3.514 | 3.5525 | 3.5914 | 3.6306 | 3.6704 | 3.7105 | 2.5007 | 0
|  | Operational insurance | USD m |  | 154.4122 | 0 | 0 | 0 | 0 | 0 | 0.77325 | 2.3451 | 2.3708 | 2.3967 | 2.4229 | 2.4495 | 2.4762 | 2.5033 | 2.5307 | 2.5584 | 2.5864 | 2.6147 | 2.6433 | 2.6722 | 2.7015 | 2.731 | 2.7609 | 2.7911 | 2.8216 | 2.8525 | 2.8837 | 2.9153 | 2.9471 | 2.9794 | 3.012 | 3.0449 | 3.0782 | 3.1119 | 3.146 | 3.1804 | 3.2152 | 3.2504 | 3.2859 | 3.3219 | 3.3582 | 3.3949 | 3.4321 | 3.4696 | 3.5076 | 3.546 | 3.5848 | 3.624 | 3.6636 | 3.7037 | 3.7442 | 3.7852 | 3.8266 | 3.8685 | 3.9108 | 3.9536 | 2.6645 | 0
|  | G&A | USD m |  | 112.0828 | 0 | 0 | 0 | 0 | 0 | 0.56128 | 1.7023 | 1.7209 | 1.7397 | 1.7587 | 1.778 | 1.7974 | 1.8171 | 1.837 | 1.8571 | 1.8774 | 1.8979 | 1.9187 | 1.9397 | 1.9609 | 1.9824 | 2.004 | 2.026 | 2.0481 | 2.0705 | 2.0932 | 2.1161 | 2.1392 | 2.1626 | 2.1863 | 2.2102 | 2.2344 | 2.2588 | 2.2836 | 2.3085 | 2.3338 | 2.3593 | 2.3851 | 2.4112 | 2.4376 | 2.4643 | 2.4912 | 2.5185 | 2.546 | 2.5739 | 2.6021 | 2.6305 | 2.6593 | 2.6884 | 2.7178 | 2.7475 | 2.7776 | 2.808 | 2.8387 | 2.8698 | 1.9341 | 0
|  | Land lease and permits | USD m |  | 25.0349 | 0 | 0 | 0 | 0 | 0 | 0.12537 | 0.38022 | 0.38438 | 0.38858 | 0.39283 | 0.39713 | 0.40148 | 0.40587 | 0.41031 | 0.4148 | 0.41933 | 0.42392 | 0.42856 | 0.43325 | 0.43799 | 0.44278 | 0.44762 | 0.45252 | 0.45747 | 0.46248 | 0.46754 | 0.47265 | 0.47782 | 0.48305 | 0.48833 | 0.49368 | 0.49908 | 0.50454 | 0.51006 | 0.51564 | 0.52128 | 0.52698 | 0.53275 | 0.53857 | 0.54447 | 0.55042 | 0.55644 | 0.56253 | 0.56869 | 0.57491 | 0.5812 | 0.58756 | 0.59398 | 0.60048 | 0.60705 | 0.61369 | 0.62041 | 0.62719 | 0.63406 | 0.64099 | 0.432 | 0
|  | Community fund and OREK levy | USD m |  | 21.7989 | 0 | 0 | 0 | 0 | 0 | 0.13018 | 0.39224 | 0.3927 | 0.3919 | 0.3949 | 0.39922 | 0.39645 | 0.38907 | 0.39544 | 0.40649 | 0.40705 | 0.40631 | 0.40952 | 0.41409 | 0.40849 | 0.39528 | 0.40477 | 0.42201 | 0.42269 | 0.42201 | 0.42544 | 0.43028 | 0.42749 | 0.41972 | 0.42679 | 0.43891 | 0.43972 | 0.43911 | 0.44278 | 0.44792 | 0.44207 | 0.42796 | 0.43844 | 0.45732 | 0.45826 | 0.45774 | 0.46166 | 0.46713 | 0.46431 | 0.45608 | 0.46397 | 0.47737 | 0.47846 | 0.47802 | 0.48223 | 0.48805 | 0.4819 | 0.46673 | 0.47838 | 0.4992 | 0.33471 | 0
|  | Variable consumables | USD m |  | 134.8703 | 0 | 0 | 0 | 0 | 0 | 0.69861 | 2.1177 | 2.1324 | 2.1403 | 2.1691 | 2.2052 | 2.2024 | 2.1736 | 2.2216 | 2.2964 | 2.3124 | 2.3209 | 2.3521 | 2.3913 | 2.3719 | 2.3076 | 2.3757 | 2.4901 | 2.5074 | 2.5167 | 2.5505 | 2.593 | 2.5896 | 2.5557 | 2.6121 | 2.7001 | 2.7188 | 2.7288 | 2.7655 | 2.8116 | 2.7887 | 2.713 | 2.7931 | 2.9276 | 2.9479 | 2.9588 | 2.9985 | 3.0485 | 3.0444 | 3.0046 | 3.0709 | 3.1743 | 3.1962 | 3.208 | 3.251 | 3.3052 | 3.2783 | 3.1893 | 3.2834 | 3.4415 | 2.3179 | 0
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0.0425 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.085 | 0
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0.051875 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.10375 | 0
|  | Operating costs before pass-through items | USD m |  | 984.0259 | 0 | 0 | 0 | 0 | 0 | 5.0386 | 15.2743 | 15.3935 | 15.4724 | 15.676 | 15.9241 | 15.9401 | 15.8025 | 16.1221 | 16.6024 | 16.7324 | 16.8186 | 17.0403 | 17.3106 | 17.231 | 16.921 | 17.328 | 18.05 | 18.1918 | 18.2859 | 18.5275 | 18.822 | 18.8416 | 18.6791 | 19.0583 | 19.6279 | 19.7824 | 19.8852 | 20.1485 | 20.4693 | 20.3756 | 20.0091 | 20.4917 | 21.3477 | 21.5162 | 21.6284 | 21.9153 | 22.2648 | 22.2887 | 22.0968 | 22.5468 | 23.2223 | 23.4061 | 23.5284 | 23.8411 | 24.2219 | 24.1115 | 23.678 | 24.2503 | 25.2655 | 17.0226 | 0
|  | Gas purchases | USD m |  | 4890.5537 | 0 | 0 | 0 | 0 | 0 | 25.731 | 77.1852 | 78.4652 | 77.9499 | 79.7534 | 80.2545 | 80.9161 | 79.0424 | 81.5596 | 83.4446 | 84.8278 | 84.27 | 86.2191 | 86.7602 | 86.8774 | 83.6566 | 86.9508 | 90.2062 | 91.7008 | 91.0971 | 93.2035 | 93.7877 | 94.5595 | 92.3684 | 95.3087 | 97.5099 | 99.1248 | 98.4715 | 100.7477 | 101.3784 | 101.5138 | 97.7489 | 101.5966 | 105.3987 | 107.1434 | 106.4365 | 108.8959 | 109.5768 | 110.477 | 107.9154 | 111.3489 | 113.9189 | 115.8038 | 115.0389 | 117.6962 | 118.4312 | 118.5877 | 114.1878 | 118.6808 | 123.1204 | 83.7082 | 0
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5727.3299 | 0 | 0 | 0 | 0 | 0 | 30.3694 | 91.1628 | 92.4536 | 92.1123 | 93.9427 | 94.653 | 95.3701 | 93.5681 | 96.1334 | 98.2766 | 99.6712 | 99.2982 | 101.2757 | 102.0388 | 102.1964 | 99.015 | 102.378 | 105.9448 | 107.4514 | 107.0439 | 109.1803 | 110.0001 | 110.8343 | 108.7242 | 111.7183 | 114.2103 | 115.8379 | 115.3928 | 117.7007 | 118.5814 | 118.7623 | 115.0421 | 118.9669 | 123.1195 | 124.8776 | 124.3917 | 126.8847 | 127.8309 | 128.8012 | 126.3311 | 129.825 | 132.7222 | 134.6212 | 134.0908 | 136.7837 | 137.8003 | 138.0079 | 133.6587 | 138.2382 | 143.0722 | 96.9664 | 0
|  | VAT facility interest after the funding period | USD m |  | 0.1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0.098646 | 0.012751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7663 | 0 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Handback reserve contribution required | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
|  | Handback works at PPA expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
|  | Total operating costs | USD m |  | 6782.2345 | 0 | 0 | 0 | 0 | 0 | 35.4079 | 106.5357 | 107.8598 | 107.5847 | 109.6186 | 110.577 | 111.3102 | 111.8682 | 112.2555 | 114.879 | 116.4036 | 116.1168 | 118.3161 | 119.3494 | 119.4274 | 127.7724 | 119.706 | 123.9948 | 125.6432 | 125.3298 | 127.7078 | 128.822 | 129.6759 | 130.3759 | 130.7767 | 133.8382 | 135.6203 | 135.278 | 137.8492 | 139.0507 | 139.1379 | 149.1385 | 139.4586 | 144.4672 | 146.3939 | 146.02 | 148.8 | 150.0957 | 151.0899 | 151.9658 | 152.3717 | 155.9445 | 158.0273 | 157.6193 | 160.6248 | 162.0221 | 162.1194 | 174.103 | 162.4885 | 168.3377 | 133.0583 | 0
|  | EBITDA | USD m |  | 2904.8121 | 0 | 0 | 0 | 0 | 0 | 18.6785 | 56.0835 | 56.1274 | 55.9066 | 56.2446 | 56.7735 | 56.2466 | 52.5358 | 55.8665 | 57.3893 | 57.3545 | 57.1245 | 57.4791 | 58.0307 | 57.0853 | 43.1459 | 56.2946 | 58.6987 | 58.6716 | 58.4456 | 58.8181 | 59.3944 | 58.8574 | 54.6277 | 58.4946 | 60.119 | 60.1003 | 59.8787 | 60.2706 | 60.8737 | 59.8944 | 43.6026 | 59.0984 | 61.6599 | 61.6501 | 61.4333 | 61.8464 | 62.4787 | 61.9295 | 57.0829 | 61.5871 | 63.3316 | 63.3315 | 63.1201 | 63.5559 | 64.22 | 63.2002 | 44.1101 | 62.3982 | 65.1453 | 24.5189 | 0
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.8998 | 39.771 | 40.7703 | 39.9843 | 41.2367 | 40.9281 | 41.4289 | 40.2075 | 41.7983 | 42.1308 | 43.1995 | 42.3688 | 43.706 | 43.381 | 43.6433 | 41.8007 | 43.757 | 44.6805 | 45.8241 | 44.9451 | 46.3738 | 46.0312 | 46.6154 | 45.2455 | 47.0564 | 47.4352 | 48.6598 | 47.7285 | 49.2563 | 48.8946 | 49.2113 | 47.1378 | 49.365 | 50.4115 | 51.7236 | 50.7359 | 52.3706 | 51.9883 | 52.6696 | 51.126 | 53.1942 | 53.6273 | 55.034 | 53.9852 | 55.7355 | 55.3309 | 55.7109 | 53.3673 | 55.9111 | 57.1018 | 0 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 18.9819 | 18.8768 | 19.5079 | 19.0638 | 19.8282 | 19.6275 | 20.0067 | 19.331 | 20.2773 | 20.4076 | 21.0898 | 20.6095 | 21.4357 | 21.2185 | 21.4807 | 20.4595 | 21.6176 | 22.0613 | 22.7985 | 22.2792 | 23.1721 | 22.9372 | 23.3801 | 22.5901 | 23.6955 | 23.8475 | 24.6443 | 24.0827 | 25.0478 | 24.7936 | 25.0996 | 23.906 | 25.2588 | 25.7769 | 26.6379 | 26.0307 | 27.0736 | 26.7987 | 27.3157 | 26.3924 | 27.6834 | 27.8606 | 28.791 | 28.1345 | 29.2615 | 28.9642 | 29.3211 | 27.9264 | 29.5063 | 30.111 | 0 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.2812 | 2.2789 | 2.3185 | 2.3091 | 2.3518 | 2.3476 | 2.3825 | 2.3683 | 2.4155 | 2.4183 | 2.4602 | 2.4503 | 2.4956 | 2.4911 | 2.5251 | 2.5041 | 2.557 | 2.5661 | 2.6106 | 2.6 | 2.6481 | 2.6433 | 2.6827 | 2.6667 | 2.7198 | 2.7229 | 2.7701 | 2.7589 | 2.8099 | 2.8048 | 2.8432 | 2.8195 | 2.8791 | 2.8893 | 2.9394 | 2.9275 | 2.9816 | 2.9762 | 3.0205 | 3.0026 | 3.0623 | 3.0658 | 3.1189 | 3.1063 | 3.1637 | 3.158 | 3.2011 | 3.1746 | 3.2416 | 3.253 | 0 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.306 | 1.3131 | 1.3441 | 1.3259 | 1.3681 | 1.3715 | 1.3818 | 1.3419 | 1.3995 | 1.4325 | 1.4663 | 1.4465 | 1.4926 | 1.4962 | 1.4946 | 1.4313 | 1.5003 | 1.5628 | 1.5997 | 1.578 | 1.6283 | 1.6323 | 1.6446 | 1.5971 | 1.6657 | 1.7049 | 1.7451 | 1.7215 | 1.7764 | 1.7808 | 1.7788 | 1.7035 | 1.7856 | 1.86 | 1.9039 | 1.8781 | 1.9379 | 1.9427 | 1.9573 | 1.9008 | 1.9825 | 2.0292 | 2.077 | 2.0489 | 2.1142 | 2.1194 | 2.1171 | 2.0275 | 2.1252 | 2.2137 | 0 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 1.172 | 1.1773 | 1.2073 | 1.1968 | 1.2301 | 1.2248 | 1.2457 | 1.2346 | 1.2726 | 1.2744 | 1.307 | 1.2957 | 1.3318 | 1.3261 | 1.3457 | 1.3275 | 1.3717 | 1.3801 | 1.4155 | 1.4034 | 1.4426 | 1.4365 | 1.4612 | 1.4484 | 1.4931 | 1.4953 | 1.5337 | 1.5206 | 1.5631 | 1.5566 | 1.5798 | 1.5588 | 1.6108 | 1.6206 | 1.6624 | 1.6483 | 1.6944 | 1.6874 | 1.7166 | 1.7019 | 1.7546 | 1.7571 | 1.8024 | 1.7872 | 1.8374 | 1.8298 | 1.8573 | 1.8331 | 1.8942 | 1.9057 | 0 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 16.1588 | 16.1249 | 16.3925 | 16.0887 | 16.4585 | 16.3568 | 16.4121 | 15.9317 | 16.4333 | 16.598 | 16.8762 | 16.5669 | 16.9504 | 16.849 | 16.7972 | 16.0782 | 16.7104 | 17.1102 | 17.3998 | 17.0845 | 17.4828 | 17.3819 | 17.4469 | 16.9431 | 17.4822 | 17.6646 | 17.9665 | 17.6448 | 18.0591 | 17.9587 | 17.9099 | 17.1499 | 17.8307 | 18.2648 | 18.5802 | 18.2514 | 18.6831 | 18.5833 | 18.6595 | 18.1284 | 18.7114 | 18.9147 | 19.2446 | 18.9082 | 19.3588 | 19.2596 | 19.2142 | 18.4058 | 19.1438 | 19.6185 | 0 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.1588 | -0.03394 | 0.2676 | -0.30378 | 0.3698 | -0.10172 | 0.055366 | -0.48045 | 0.50164 | 0.16469 | 0.27817 | -0.30931 | 0.38348 | -0.10134 | -0.051819 | -0.71894 | 0.63215 | 0.39975 | 0.2896 | -0.3153 | 0.3983 | -0.1009 | 0.064993 | -0.50372 | 0.53906 | 0.18238 | 0.30198 | -0.32178 | 0.41436 | -0.10041 | -0.048784 | -0.76002 | 0.68081 | 0.43407 | 0.31539 | -0.3288 | 0.43176 | -0.099854 | 0.076187 | -0.53109 | 0.58301 | 0.20331 | 0.3299 | -0.3364 | 0.4506 | -0.099227 | -0.045372 | -0.80839 | 0.73803 | 0.47463 | -19.6185 | 0
|  | Release of spares inventory at expiry | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| Tax depreciation (straight line from COD) | USD m |  | 839.1369 | 0 | 0 | 0 | 0 | 0 | 7.5522 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 21.8176 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 13.7059 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.55942 | 0
| Depreciation of holiday months (deemed deferred) | USD m |  | 347.4027 | 0 | 0 | 0 | 0 | 0 | 7.5522 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 22.6567 | 21.8176 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 13.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 491.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7131 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 20.1393 | 13.7059 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.83914 | 0.55942 | 0
| Shareholder loan interest accrued | USD m |  | 100.5186 | 0 | 0 | 0 | 0 | 0 | 2.9782 | 9.1261 | 8.4833 | 8.2355 | 7.6801 | 7.402 | 6.8375 | 6.4203 | 5.819 | 5.3853 | 4.7559 | 4.2731 | 3.6002 | 3.4488 | 3.1159 | 2.8386 | 2.4331 | 2.1422 | 1.8217 | 1.5337 | 1.1434 | 0.76574 | 0.27889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 0.65661 | 0.7962 | 0.93063 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 97.0475 | 0 | 0 | 0 | 0 | 0 | 1.9555 | 7.2662 | 7.8948 | 8.2355 | 7.6801 | 7.402 | 6.8375 | 6.4203 | 5.819 | 5.3853 | 4.7559 | 4.2731 | 3.6002 | 3.4488 | 3.1159 | 2.8386 | 2.4331 | 2.1422 | 1.8217 | 1.5337 | 1.1434 | 0.76574 | 0.27889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 341.7269 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1264 | 22.5389 | 22.1213 | 21.4379 | 20.9718 | 20.2273 | 19.6561 | 18.8514 | 18.278 | 17.961 | 17.3312 | 16.4422 | 15.361 | 13.9956 | 12.7803 | 11.3666 | 10.1765 | 9.0448 | 7.8162 | 6.4313 | 5.1807 | 3.8016 | 2.6999 | 2.0347 | 1.3933 | 0.70076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Taxable income before losses and deferred depreciation | USD m |  | 1461.9105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4519 | 26.2406 | 27.6659 | 28.9564 | 31.1041 | 33.3087 | 34.6376 | 31.7885 | 36.3205 | 38.5864 | 39.2602 | 39.7394 | 40.1313 | 40.7345 | 39.7551 | 23.4633 | 38.9592 | 41.5206 | 41.5108 | 41.2941 | 41.7071 | 42.3394 | 41.7902 | 36.9436 | 47.8812 | 62.4924 | 62.4924 | 62.2809 | 62.7167 | 63.3808 | 62.3611 | 43.2709 | 61.5591 | 64.3062 | 23.9595 | 0
| Tax losses used | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 1461.9105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4519 | 26.2406 | 27.6659 | 28.9564 | 31.1041 | 33.3087 | 34.6376 | 31.7885 | 36.3205 | 38.5864 | 39.2602 | 39.7394 | 40.1313 | 40.7345 | 39.7551 | 23.4633 | 38.9592 | 41.5206 | 41.5108 | 41.2941 | 41.7071 | 42.3394 | 41.7902 | 36.9436 | 47.8812 | 62.4924 | 62.4924 | 62.2809 | 62.7167 | 63.3808 | 62.3611 | 43.2709 | 61.5591 | 64.3062 | 23.9595 | 0
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| Corporate income tax | USD m |  | 438.5731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2356 | 7.8722 | 8.2998 | 8.6869 | 9.3312 | 9.9926 | 10.3913 | 9.5365 | 10.8962 | 11.5759 | 11.7781 | 11.9218 | 12.0394 | 12.2203 | 11.9265 | 7.039 | 11.6877 | 12.4562 | 12.4533 | 12.3882 | 12.5121 | 12.7018 | 12.5371 | 11.0831 | 14.3643 | 18.7477 | 18.7477 | 18.6843 | 18.815 | 19.0142 | 18.7083 | 12.9813 | 18.4677 | 19.2919 | 7.1879 | 0
| Minimum turnover tax | USD m |  | 13.9998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12266 | 0.38365 | 0.38426 | 0.38365 | 0.38676 | 0.39116 | 0.38862 | 0.38157 | 0.38799 | 0.39901 | 0.39974 | 0.39919 | 0.40253 | 0.4072 | 0.40188 | 0.38906 | 0.39858 | 0.41574 | 0.4166 | 0.41612 | 0.41969 | 0.42466 | 0.4221 | 0.41462 | 0.42179 | 0.43397 | 0.43496 | 0.43456 | 0.43839 | 0.44368 | 0.43809 | 0.4243 | 0.43489 | 0.45382 | 0.30429 | 0
| Tax paid = max(CIT, MTT) | USD m |  | 438.5731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2356 | 7.8722 | 8.2998 | 8.6869 | 9.3312 | 9.9926 | 10.3913 | 9.5365 | 10.8962 | 11.5759 | 11.7781 | 11.9218 | 12.0394 | 12.2203 | 11.9265 | 7.039 | 11.6877 | 12.4562 | 12.4533 | 12.3882 | 12.5121 | 12.7018 | 12.5371 | 11.0831 | 14.3643 | 18.7477 | 18.7477 | 18.6843 | 18.815 | 19.0142 | 18.7083 | 12.9813 | 18.4677 | 19.2919 | 7.1879 | 0
| Thin-cap disallowance | USD m |  | 3.4711 | 0 | 0 | 0 | 0 | 0 | 1.0227 | 1.8599 | 0.58846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.76128
|  | Gearing used in the closed-form gross-up | fraction | 0.75
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97559
|  | First installment share of remaining profile | fraction | 0.023923
|  | DSRA coefficient per USD of E balance | factor | 0.046123
|  | DSRA coefficient per USD of A balance | factor | 0.057623
|  | DSRA coefficient per USD of B balance | factor | 0.056373
|  | DSRA coefficient per USD of C balance | factor | 0.069085
|  | DSRA coefficient per USD of standby balance | factor | 0.063564
|  | DSRA constant (swap net payment) | USD m | 0.55426
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0052553 | 0.0052445 | 0.0052553 | 0.0052445 | 0.0052553 | 0.0054898 | 0.0054575 | 0.0054898 | 0.005479 | 0.0054898 | 0.005479 | 0.0056201 | 0.0056201 | 0.0056093 | 0.0056201 | 0.0056093 | 0.0056201 | 0.0056896 | 0.005668 | 0.0056896 | 0.0056788 | 0.0056896 | 0.0056788 | 0.0057243 | 0.0057243 | 0.0057135 | 0.0057243 | 0.0057135 | 0.0057243 | 0.0057504 | 0.005718 | 0.0057504 | 0.0057396 | 0.0057504 | 0.0057396 | 0.0057504 | 0.0057504 | 0.0057396 | 0.0057504 | 0.0057396 | 0.0057504 | 0.0057677 | 0.0057354 | 0.0057677 | 0.0057569 | 0.0057677 | 0.0057569 | 0.0057677 | 0.0057677 | 0.0057569 | 0.0057677 | 0.0057569 | 0.0057677
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 108.1566 | 1.4585 | 2.0984 | 3.3935 | 5.2893 | 7.6709 | 10.3571 | 13.3158 | 16.3373 | 19.3602 | 22.216 | 24.9091 | 27.2659 | 29.2245 | 30.777 | 31.8078 | 32.3645 | 33.5323 | 31.8154 | 30.8322 | 29.2799 | 27.3473 | 24.9677 | 22.357 | 19.4753 | 16.4273 | 13.4337 | 10.4596 | 7.7838 | 5.4273 | 3.411 | 2.2237 | 49.7814 | 0.73125 | 0.13239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 83.1473 | 84.5501 | 86.4484 | 89.3499 | 93.7175 | 99.9476 | 108.2688 | 118.8902 | 131.8738 | 147.2258 | 164.8298 | 184.5813 | 206.2167 | 229.4396 | 253.9381 | 279.322 | 305.2232 | 332.1331 | 357.8316 | 382.8607 | 406.7943 | 429.3258 | 450.1171 | 468.9848 | 485.7076 | 500.1561 | 512.3506 | 522.3111 | 530.245 | 536.4075 | 541.0644 | 544.8047 | 585.127 | 587.8852 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013 | 590.2013
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0095643 | 0.010081 | 0.010616 | 0.011136 | 0.011674 | 0.012216 | 0.012712 | 0.013258 | 0.01379 | 0.014339 | 0.014875 | 0.01543 | 0.015987 | 0.01653 | 0.017091 | 0.017638 | 0.018203 | 0.018771 | 0.019309 | 0.019881 | 0.02044 | 0.021016 | 0.021579 | 0.02216 | 0.022743 | 0.023313 | 0.0239 | 0.024474 | 0.025066 | 0.025661 | 0.02621 | 0.026809 | 0.027394 | 0.061672 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388 | 0.062388
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 858.3354
|  | Senior debt (committed tranches) | USD m | 654.6336
|  | Debt share of monthly funding | fraction | 0.75
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 27.4486 | 28.0048 | 28.7143 | 29.721 | 31.1722 | 33.1831 | 35.8094 | 39.1387 | 43.173 | 47.9225 | 53.344 | 59.4147 | 66.0512 | 73.1602 | 80.6567 | 88.4151 | 96.3334 | 104.5551 | 112.4056 | 120.0642 | 127.3905 | 134.3008 | 140.6855 | 146.498 | 151.6676 | 156.1513 | 159.9635 | 163.102 | 165.6371 | 167.6416 | 169.1825 | 170.4615 | 182.7114 | 195.4964 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 20.129 | 20.5369 | 21.0571 | 21.7954 | 22.8596 | 24.3343 | 26.2602 | 28.7017 | 31.6602 | 35.1432 | 39.1189 | 43.5708 | 48.4375 | 53.6508 | 59.1482 | 64.8377 | 70.6445 | 76.6737 | 82.4308 | 88.0471 | 93.4197 | 98.4873 | 103.1694 | 107.4319 | 111.2229 | 114.511 | 117.3066 | 119.6081 | 121.4672 | 122.9372 | 124.0672 | 125.0051 | 133.9884 | 143.364 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 9.1495 | 9.3349 | 9.5714 | 9.907 | 10.3907 | 11.061 | 11.9365 | 13.0462 | 14.391 | 15.9742 | 17.7813 | 19.8049 | 22.0171 | 24.3867 | 26.8856 | 29.4717 | 32.1111 | 34.8517 | 37.4685 | 40.0214 | 42.4635 | 44.7669 | 46.8952 | 48.8327 | 50.5559 | 52.0504 | 53.3212 | 54.3673 | 55.2124 | 55.8805 | 56.3942 | 56.8205 | 60.9038 | 65.1655 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 34.7683 | 35.4727 | 36.3714 | 37.6466 | 39.4847 | 42.032 | 45.3586 | 49.5757 | 54.6858 | 60.7019 | 67.569 | 75.2586 | 83.6648 | 92.6696 | 102.1651 | 111.9924 | 122.0223 | 132.4365 | 142.3805 | 152.0813 | 161.3612 | 170.1144 | 178.2017 | 185.5642 | 192.1123 | 197.7916 | 202.6205 | 206.5958 | 209.807 | 212.346 | 214.2979 | 215.9178 | 231.4345 | 247.6287 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: interest | USD m |  | 12.4616 | 0 | 0.088522 | 0.090315 | 0.092604 | 0.09585 | 0.10754 | 0.11448 | 0.12354 | 0.13503 | 0.14895 | 0.16533 | 0.1907 | 0.21241 | 0.23613 | 0.26155 | 0.28835 | 0.31608 | 0.35081 | 0.38075 | 0.40934 | 0.43723 | 0.46391 | 0.48908 | 0.51702 | 0.53838 | 0.55738 | 0.57386 | 0.58787 | 0.5994 | 0.61286 | 0.62027 | 0.62598 | 0.63071 | 0.67603 | 0.72334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 13.959 | 0 | 0.1035 | 0.10559 | 0.10827 | 0.11206 | 0.12268 | 0.13059 | 0.14093 | 0.15403 | 0.16991 | 0.1886 | 0.21483 | 0.23928 | 0.266 | 0.29463 | 0.32482 | 0.35607 | 0.39267 | 0.42618 | 0.45818 | 0.48939 | 0.51926 | 0.54743 | 0.57689 | 0.60072 | 0.62192 | 0.64031 | 0.65594 | 0.66881 | 0.68224 | 0.6905 | 0.69684 | 0.70211 | 0.75257 | 0.80523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 6.1068 | 0 | 0.045138 | 0.046052 | 0.047219 | 0.048875 | 0.053599 | 0.057057 | 0.061572 | 0.067297 | 0.074234 | 0.0824 | 0.093945 | 0.10464 | 0.11632 | 0.12884 | 0.14205 | 0.15571 | 0.17179 | 0.18646 | 0.20046 | 0.21411 | 0.22718 | 0.2395 | 0.25245 | 0.26288 | 0.27216 | 0.2802 | 0.28705 | 0.29268 | 0.29861 | 0.30222 | 0.305 | 0.3073 | 0.32939 | 0.35244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 28.6 | 0 | 0.21312 | 0.21743 | 0.22294 | 0.23076 | 0.2519 | 0.26815 | 0.28937 | 0.31627 | 0.34888 | 0.38726 | 0.44045 | 0.49057 | 0.54537 | 0.60407 | 0.66597 | 0.73002 | 0.80444 | 0.8731 | 0.93866 | 1.0026 | 1.0638 | 1.1215 | 1.1814 | 1.2302 | 1.2736 | 1.3113 | 1.3433 | 1.3697 | 1.3968 | 1.4137 | 1.4267 | 1.4375 | 1.5408 | 1.6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 3.7456 | 0 | 0.029577 | 0.031182 | 0.030941 | 0.033093 | 0.034709 | 0.033372 | 0.039872 | 0.042173 | 0.048071 | 0.051638 | 0.059396 | 0.066155 | 0.071172 | 0.08146 | 0.08691 | 0.098446 | 0.10726 | 0.10891 | 0.12516 | 0.12937 | 0.14184 | 0.14471 | 0.15665 | 0.16312 | 0.16343 | 0.17387 | 0.17237 | 0.18161 | 0.18443 | 0.1686 | 0.18838 | 0.18368 | 0.20344 | 0.21065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | 0.79286 | 0 | -0.026046 | -0.021346 | -0.027247 | -0.022654 | -0.0044334 | -0.025293 | -0.0050929 | -0.013655 | -0.0061402 | -0.01672 | 0.010787 | 0.012015 | -0.0010275 | 0.014795 | -0.0012547 | 0.017879 | 0.037178 | -0.0064282 | 0.04338 | 0.019477 | 0.049163 | 0.021787 | 0.067216 | 0.069994 | 0.038085 | 0.074606 | 0.040169 | 0.077927 | 0.090548 | -0.02347 | 0.092486 | 0.054169 | 0.099882 | 0.062124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 9.79 | 0.56833 | 0.47313 | 0.48729 | 0.46959 | 0.48232 | 0.47813 | 0.4266 | 0.46471 | 0.44039 | 0.4434 | 0.41579 | 0.41396 | 0.39639 | 0.36502 | 0.35662 | 0.32412 | 0.31247 | 0.28955 | 0.24862 | 0.24304 | 0.21375 | 0.19968 | 0.17388 | 0.1612 | 0.14438 | 0.12525 | 0.11645 | 0.10201 | 0.096333 | 0.088996 | 0.075144 | 0.078736 | 0.072615 | 0.039585 | 0.0025029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.8165 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 10.2908 | 10.2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.74375 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 38.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 119.0158 | 2.4115 | 3.0762 | 4.3651 | 6.2922 | 8.7194 | 11.3873 | 14.4357 | 17.4925 | 20.5936 | 23.507 | 26.3224 | 28.7754 | 30.8245 | 32.5041 | 33.64 | 34.3333 | 35.6489 | 34.0394 | 33.207 | 31.7663 | 29.963 | 27.6838 | 25.2026 | 22.415 | 19.4411 | 16.5296 | 13.6081 | 10.9923 | 8.6912 | 6.6814 | 5.5453 | 53.1152 | 42.5057 | 3.8751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 654.6336 | 563.1381 | 561.2842 | 558.9193 | 555.5636 | 550.7263 | 544.0231 | 535.2689 | 524.1712 | 510.7235 | 494.8918 | 476.8204 | 456.5845 | 434.463 | 410.7661 | 385.778 | 359.9166 | 333.5222 | 306.1165 | 279.9481 | 254.4196 | 229.9987 | 206.9641 | 185.6817 | 166.3068 | 149.0749 | 134.1292 | 121.4218 | 110.9603 | 102.5098 | 95.8283 | 90.6918 | 86.4287 | 45.5955 | 2.9791 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11 | 3.0042e-11
|  | Senior tranche drawdown (pro rata) | USD m |  | 654.6336 | 91.4955 | 1.8539 | 2.3649 | 3.3557 | 4.8373 | 6.7032 | 8.7542 | 11.0977 | 13.4477 | 15.8317 | 18.0714 | 20.2358 | 22.1216 | 23.6969 | 24.9881 | 25.8614 | 26.3944 | 27.4057 | 26.1684 | 25.5285 | 24.4209 | 23.0346 | 21.2824 | 19.3749 | 17.2319 | 14.9457 | 12.7074 | 10.4615 | 8.4505 | 6.6815 | 5.1365 | 4.2631 | 40.8333 | 42.6164 | 2.9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 21.3083 | 2.9782 | 0.060343 | 0.076978 | 0.10923 | 0.15745 | 0.21819 | 0.28495 | 0.36123 | 0.43772 | 0.51532 | 0.58822 | 0.65868 | 0.72006 | 0.77133 | 0.81336 | 0.84179 | 0.85914 | 0.89206 | 0.85178 | 0.83095 | 0.7949 | 0.74978 | 0.69274 | 0.63065 | 0.5609 | 0.48648 | 0.41363 | 0.34052 | 0.27506 | 0.21748 | 0.16719 | 0.13876 | 1.3291 | 1.3872 | 0.096968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 859.9158 | 121.994 | 2.4718 | 3.1532 | 4.4743 | 6.4497 | 8.9376 | 11.6723 | 14.797 | 17.9302 | 21.109 | 24.0952 | 26.9811 | 29.4954 | 31.5958 | 33.3175 | 34.4818 | 35.1925 | 36.5409 | 34.8912 | 34.038 | 32.5612 | 30.7128 | 28.3765 | 25.8333 | 22.9759 | 19.9276 | 16.9432 | 13.9486 | 11.2673 | 8.9087 | 6.8486 | 5.6841 | 54.4444 | 43.8929 | 3.9721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 859.9158 | 121.994 | 2.4718 | 3.1532 | 4.4743 | 6.4497 | 8.9376 | 11.6723 | 14.797 | 17.9302 | 21.109 | 24.0952 | 26.9811 | 29.4954 | 31.5958 | 33.3175 | 34.4818 | 35.1925 | 36.5409 | 34.8912 | 34.038 | 32.5612 | 30.7128 | 28.3765 | 25.8333 | 22.9759 | 19.9276 | 16.9432 | 13.9486 | 11.2673 | 8.9087 | 6.8486 | 5.6841 | 54.4444 | 43.8929 | 3.9721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility drawdown (75%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 196.3901 | 27.4486 | 0.55616 | 0.70948 | 1.0067 | 1.4512 | 2.011 | 2.6263 | 3.3293 | 4.0343 | 4.7495 | 5.4214 | 6.0707 | 6.6365 | 7.1091 | 7.4964 | 7.7584 | 7.9183 | 8.2217 | 7.8505 | 7.6586 | 7.3263 | 6.9104 | 6.3847 | 5.8125 | 5.1696 | 4.4837 | 3.8122 | 3.1384 | 2.5352 | 2.0045 | 1.5409 | 1.2789 | 12.25 | 12.7849 | 0.89372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 144.0194 | 20.129 | 0.40785 | 0.52028 | 0.73826 | 1.0642 | 1.4747 | 1.9259 | 2.4415 | 2.9585 | 3.483 | 3.9757 | 4.4519 | 4.8667 | 5.2133 | 5.4974 | 5.6895 | 5.8068 | 6.0293 | 5.757 | 5.6163 | 5.3726 | 5.0676 | 4.6821 | 4.2625 | 3.791 | 3.288 | 2.7956 | 2.3015 | 1.8591 | 1.4699 | 1.13 | 0.93787 | 8.9833 | 9.3756 | 0.65539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 65.4634 | 9.1495 | 0.18539 | 0.23649 | 0.33557 | 0.48373 | 0.67032 | 0.87542 | 1.1098 | 1.3448 | 1.5832 | 1.8071 | 2.0236 | 2.2122 | 2.3697 | 2.4988 | 2.5861 | 2.6394 | 2.7406 | 2.6168 | 2.5529 | 2.4421 | 2.3035 | 2.1282 | 1.9375 | 1.7232 | 1.4946 | 1.2707 | 1.0461 | 0.84505 | 0.66815 | 0.51365 | 0.42631 | 4.0833 | 4.2616 | 0.29791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 248.7608 | 34.7683 | 0.70446 | 0.89867 | 1.2752 | 1.8382 | 2.5472 | 3.3266 | 4.2171 | 5.1101 | 6.0161 | 6.8671 | 7.6896 | 8.4062 | 9.0048 | 9.4955 | 9.8273 | 10.0299 | 10.4142 | 9.944 | 9.7008 | 9.28 | 8.7531 | 8.0873 | 7.3625 | 6.5481 | 5.6794 | 4.8288 | 3.9754 | 3.2112 | 2.539 | 1.9519 | 1.62 | 15.5166 | 16.1942 | 1.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 27.4486 | 28.0048 | 28.7143 | 29.721 | 31.1722 | 33.1831 | 35.8094 | 39.1387 | 43.173 | 47.9225 | 53.344 | 59.4147 | 66.0512 | 73.1602 | 80.6567 | 88.4151 | 96.3334 | 104.5551 | 112.4056 | 120.0642 | 127.3905 | 134.3008 | 140.6855 | 146.498 | 151.6676 | 156.1513 | 159.9635 | 163.102 | 165.6371 | 167.6416 | 169.1825 | 170.4615 | 182.7114 | 195.4964 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901 | 196.3901
|  | ABDB A-loan: closing balance | USD m |  |  | 20.129 | 20.5369 | 21.0571 | 21.7954 | 22.8596 | 24.3343 | 26.2602 | 28.7017 | 31.6602 | 35.1432 | 39.1189 | 43.5708 | 48.4375 | 53.6508 | 59.1482 | 64.8377 | 70.6445 | 76.6737 | 82.4308 | 88.0471 | 93.4197 | 98.4873 | 103.1694 | 107.4319 | 111.2229 | 114.511 | 117.3066 | 119.6081 | 121.4672 | 122.9372 | 124.0672 | 125.0051 | 133.9884 | 143.364 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194 | 144.0194
|  | ABDB B-loan: closing balance | USD m |  |  | 9.1495 | 9.3349 | 9.5714 | 9.907 | 10.3907 | 11.061 | 11.9365 | 13.0462 | 14.391 | 15.9742 | 17.7813 | 19.8049 | 22.0171 | 24.3867 | 26.8856 | 29.4717 | 32.1111 | 34.8517 | 37.4685 | 40.0214 | 42.4635 | 44.7669 | 46.8952 | 48.8327 | 50.5559 | 52.0504 | 53.3212 | 54.3673 | 55.2124 | 55.8805 | 56.3942 | 56.8205 | 60.9038 | 65.1655 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634 | 65.4634
|  | Commercial tranche: closing balance | USD m |  |  | 34.7683 | 35.4727 | 36.3714 | 37.6466 | 39.4847 | 42.032 | 45.3586 | 49.5757 | 54.6858 | 60.7019 | 67.569 | 75.2586 | 83.6648 | 92.6696 | 102.1651 | 111.9924 | 122.0223 | 132.4365 | 142.3805 | 152.0813 | 161.3612 | 170.1144 | 178.2017 | 185.5642 | 192.1123 | 197.7916 | 202.6205 | 206.5958 | 209.807 | 212.346 | 214.2979 | 215.9178 | 231.4345 | 247.6287 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608 | 248.7608
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 205.2822 | 30.4985 | 0.61795 | 0.78831 | 1.1186 | 1.6124 | 2.2344 | 2.9181 | 3.6992 | 4.4826 | 5.2772 | 6.0238 | 6.7453 | 7.3739 | 7.899 | 8.3294 | 8.6205 | 8.7981 | 9.1352 | 8.7228 | 8.5095 | 8.1403 | 7.6782 | 7.0941 | 6.4583 | 5.744 | 4.9819 | 4.2358 | 3.4872 | 2.8168 | 2.2272 | 1.7122 | 1.421 | 13.6111 | 1.2765 | 0.99302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 191.0822 | 16.2985 | 0.61795 | 0.78831 | 1.1186 | 1.6124 | 2.2344 | 2.9181 | 3.6992 | 4.4826 | 5.2772 | 6.0238 | 6.7453 | 7.3739 | 7.899 | 8.3294 | 8.6205 | 8.7981 | 9.1352 | 8.7228 | 8.5095 | 8.1403 | 7.6782 | 7.0941 | 6.4583 | 5.744 | 4.9819 | 4.2358 | 3.4872 | 2.8168 | 2.2272 | 1.7122 | 1.421 | 13.6111 | 1.2765 | 0.99302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 41.0564 | 6.0997 | 0.12359 | 0.15766 | 0.22372 | 0.32248 | 0.44688 | 0.58361 | 0.73985 | 0.89651 | 1.0554 | 1.2048 | 1.3491 | 1.4748 | 1.5798 | 1.6659 | 1.7241 | 1.7596 | 1.827 | 1.7446 | 1.7019 | 1.6281 | 1.5356 | 1.4188 | 1.2917 | 1.1488 | 0.99638 | 0.84716 | 0.69743 | 0.56337 | 0.44544 | 0.34243 | 0.2842 | 2.7222 | 0.2553 | 0.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 164.2258 | 24.3988 | 0.49436 | 0.63064 | 0.89486 | 1.2899 | 1.7875 | 2.3345 | 2.9594 | 3.586 | 4.2218 | 4.819 | 5.3962 | 5.8991 | 6.3192 | 6.6635 | 6.8964 | 7.0385 | 7.3082 | 6.9782 | 6.8076 | 6.5122 | 6.1426 | 5.6753 | 5.1667 | 4.5952 | 3.9855 | 3.3886 | 2.7897 | 2.2535 | 1.7817 | 1.3697 | 1.1368 | 10.8889 | 1.0212 | 0.79442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 23.3581 | 0 | 0.19051 | 0.20239 | 0.20236 | 0.21796 | 0.23013 | 0.22256 | 0.26704 | 0.28362 | 0.32429 | 0.34933 | 0.40267 | 0.44946 | 0.48454 | 0.55558 | 0.59403 | 0.67427 | 0.7365 | 0.7497 | 0.86376 | 0.89579 | 0.98542 | 1.0093 | 1.0969 | 1.1474 | 1.1552 | 1.2352 | 1.2315 | 1.305 | 1.3337 | 1.2273 | 1.3798 | 1.3549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 24.3988 | 25.0837 | 25.9167 | 27.0139 | 28.5218 | 30.5395 | 33.0965 | 36.3229 | 40.1926 | 44.7387 | 49.907 | 55.7059 | 62.0545 | 68.8582 | 76.0773 | 83.5677 | 91.2804 | 99.3251 | 107.053 | 114.7244 | 122.1324 | 129.2604 | 135.945 | 142.2085 | 147.9511 | 153.0919 | 157.7157 | 161.737 | 165.2954 | 168.4108 | 171.0079 | 173.5245 | 185.7683 | 186.7894 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839 | 187.5839
|  | Total debt drawdowns (incl. standby) | USD m |  | 654.6336 | 91.4955 | 1.8539 | 2.3649 | 3.3557 | 4.8373 | 6.7032 | 8.7542 | 11.0977 | 13.4477 | 15.8317 | 18.0714 | 20.2358 | 22.1216 | 23.6969 | 24.9881 | 25.8614 | 26.3944 | 27.4057 | 26.1684 | 25.5285 | 24.4209 | 23.0346 | 21.2824 | 19.3749 | 17.2319 | 14.9457 | 12.7074 | 10.4615 | 8.4505 | 6.6815 | 5.1365 | 4.2631 | 40.8333 | 42.6164 | 2.9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 110.1388 | 13.8824 | 1.051 | 1.0985 | 1.1173 | 1.2035 | 1.3292 | 1.3541 | 1.5477 | 1.6527 | 1.8224 | 1.9269 | 2.155 | 2.3207 | 2.4546 | 2.6489 | 2.7706 | 2.9525 | 3.158 | 3.18 | 3.3694 | 3.4201 | 3.538 | 3.5504 | 3.665 | 3.6893 | 3.65 | 3.6939 | 3.6305 | 3.659 | 3.6625 | 3.4916 | 3.6294 | 4.7855 | 5.1059 | 3.9721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 859.9158
|  | Capitalized cost (book and tax) | USD m | 839.1369

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01935 | 0.0207 | 0.02145 | 0.02185 | 0.02205 | 0.0222 | 0.0222 | 0.0223 | 0.0223 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235 | 0.02235
|  | ABDB A-loan: rate per period | factor |  |  | 0.03085 | 0.0322 | 0.03295 | 0.03335 | 0.03355 | 0.0337 | 0.0337 | 0.0338 | 0.0338 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385 | 0.03385
|  | ABDB B-loan: rate per period | factor |  |  | 0.0296 | 0.03095 | 0.0317 | 0.0321 | 0.0323 | 0.03245 | 0.03245 | 0.03255 | 0.03255 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326 | 0.0326
|  | Commercial tranche: rate per period | factor |  |  | 0.036778 | 0.038278 | 0.039111 | 0.039556 | 0.039778 | 0.039944 | 0.039944 | 0.040056 | 0.040056 | 0.040111 | 0.040111 | 0.040111 | 0.040111 | 0.040111 | 0.040111 | 0.042889 | 0.042889 | 0.042889 | 0.042889 | 0.042889 | 0.042889 | 0.042889 | 0.042889 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667 | 0.045667
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037387 | 0.038824 | 0.038833 | 0.039478 | 0.038995 | 0.039642 | 0.039103 | 0.039751 | 0.039156 | 0.039805 | 0.039373 | 0.039805 | 0.039156 | 0.039805 | 0.040832 | 0.041509 | 0.040832 | 0.041509 | 0.041058 | 0.041509 | 0.040832 | 0.041509 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.023923 | 0.024546 | 0.025557 | 0.026244 | 0.02802 | 0.02843 | 0.029025 | 0.030095 | 0.030851 | 0.031178 | 0.03252 | 0.033518 | 0.035684 | 0.036033 | 0.037826 | 0.039302 | 0.042889 | 0.044172 | 0.046129 | 0.047596 | 0.050445 | 0.051645 | 0.053343 | 0.055238 | 0.05689 | 0.058903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97608 | 0.95153 | 0.92597 | 0.89973 | 0.87171 | 0.84328 | 0.81426 | 0.78416 | 0.75331 | 0.72213 | 0.68961 | 0.65609 | 0.62041 | 0.58438 | 0.54655 | 0.50725 | 0.46436 | 0.42019 | 0.37406 | 0.32646 | 0.27602 | 0.22437 | 0.17103 | 0.11579 | 0.058903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.023923 | 0.025148 | 0.026859 | 0.028342 | 0.031143 | 0.032614 | 0.034419 | 0.03696 | 0.039343 | 0.041387 | 0.045033 | 0.048604 | 0.054388 | 0.058079 | 0.064728 | 0.07191 | 0.084553 | 0.095123 | 0.10978 | 0.12724 | 0.15452 | 0.18711 | 0.23774 | 0.32297 | 0.49131 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 196.3901 | 191.6919 | 186.8713 | 181.8522 | 176.6982 | 171.1953 | 165.612 | 159.9119 | 154.0015 | 147.9427 | 141.8197 | 135.4331 | 128.8505 | 121.8426 | 114.7661 | 107.3375 | 99.6189 | 91.1959 | 82.521 | 73.4617 | 64.1143 | 54.2074 | 44.0649 | 33.5889 | 22.7407 | 11.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 68.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3599 | 4.2747 | 4.1672 | 4.0644 | 3.9492 | 3.8262 | 3.7014 | 3.574 | 3.4419 | 3.3065 | 3.1697 | 3.0269 | 2.8798 | 2.7232 | 2.565 | 2.399 | 2.2265 | 2.0382 | 1.8443 | 1.6419 | 1.433 | 1.2115 | 0.98485 | 0.75071 | 0.50825 | 0.25854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 196.3901 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6982 | 4.8206 | 5.0191 | 5.154 | 5.5028 | 5.5833 | 5.7001 | 5.9104 | 6.0588 | 6.123 | 6.3866 | 6.5826 | 7.0079 | 7.0765 | 7.4286 | 7.7186 | 8.4231 | 8.6749 | 9.0593 | 9.3474 | 9.907 | 10.1425 | 10.476 | 10.8482 | 11.1727 | 11.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 196.3901 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6982 | 4.8206 | 5.0191 | 5.154 | 5.5028 | 5.5833 | 5.7001 | 5.9104 | 6.0588 | 6.123 | 6.3866 | 6.5826 | 7.0079 | 7.0765 | 7.4286 | 7.7186 | 8.4231 | 8.6749 | 9.0593 | 9.3474 | 9.907 | 10.1425 | 10.476 | 10.8482 | 11.1727 | 11.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 191.6919 | 186.8713 | 181.8522 | 176.6982 | 171.1953 | 165.612 | 159.9119 | 154.0015 | 147.9427 | 141.8197 | 135.4331 | 128.8505 | 121.8426 | 114.7661 | 107.3375 | 99.6189 | 91.1959 | 82.521 | 73.4617 | 64.1143 | 54.2074 | 44.0649 | 33.5889 | 22.7407 | 11.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 196.3901 | 191.6919 | 186.8713 | 181.8522 | 176.6982 | 171.1953 | 165.612 | 159.9119 | 154.0015 | 147.9427 | 141.8197 | 135.4331 | 128.8505 | 121.8426 | 114.7661 | 107.3375 | 99.6189 | 91.1959 | 82.521 | 73.4617 | 64.1143 | 54.2074 | 44.0649 | 33.5889 | 22.7407 | 11.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 144.0194 | 140.5741 | 137.0389 | 133.3583 | 129.5786 | 125.5432 | 121.4488 | 117.2687 | 112.9344 | 108.4913 | 104.0011 | 99.3176 | 94.4904 | 89.3513 | 84.1618 | 78.7142 | 73.0539 | 66.877 | 60.5154 | 53.8719 | 47.0172 | 39.7521 | 32.3142 | 24.6318 | 16.6765 | 8.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 75.9065 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8535 | 4.7514 | 4.6319 | 4.5142 | 4.3862 | 4.2496 | 4.111 | 3.9695 | 3.8228 | 3.6724 | 3.5204 | 3.3619 | 3.1985 | 3.0245 | 2.8489 | 2.6645 | 2.4729 | 2.2638 | 2.0484 | 1.8236 | 1.5915 | 1.3456 | 1.0938 | 0.83379 | 0.5645 | 0.28716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 144.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4453 | 3.5351 | 3.6807 | 3.7796 | 4.0354 | 4.0944 | 4.1801 | 4.3343 | 4.4431 | 4.4902 | 4.6835 | 4.8272 | 5.1391 | 5.1894 | 5.4476 | 5.6603 | 6.1769 | 6.3616 | 6.6435 | 6.8548 | 7.2651 | 7.4378 | 7.6824 | 7.9554 | 8.1933 | 8.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 144.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4453 | 3.5351 | 3.6807 | 3.7796 | 4.0354 | 4.0944 | 4.1801 | 4.3343 | 4.4431 | 4.4902 | 4.6835 | 4.8272 | 5.1391 | 5.1894 | 5.4476 | 5.6603 | 6.1769 | 6.3616 | 6.6435 | 6.8548 | 7.2651 | 7.4378 | 7.6824 | 7.9554 | 8.1933 | 8.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 140.5741 | 137.0389 | 133.3583 | 129.5786 | 125.5432 | 121.4488 | 117.2687 | 112.9344 | 108.4913 | 104.0011 | 99.3176 | 94.4904 | 89.3513 | 84.1618 | 78.7142 | 73.0539 | 66.877 | 60.5154 | 53.8719 | 47.0172 | 39.7521 | 32.3142 | 24.6318 | 16.6765 | 8.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 144.0194 | 140.5741 | 137.0389 | 133.3583 | 129.5786 | 125.5432 | 121.4488 | 117.2687 | 112.9344 | 108.4913 | 104.0011 | 99.3176 | 94.4904 | 89.3513 | 84.1618 | 78.7142 | 73.0539 | 66.877 | 60.5154 | 53.8719 | 47.0172 | 39.7521 | 32.3142 | 24.6318 | 16.6765 | 8.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 65.4634 | 63.8973 | 62.2904 | 60.6174 | 58.8994 | 57.0651 | 55.204 | 53.304 | 51.3338 | 49.3142 | 47.2732 | 45.1444 | 42.9502 | 40.6142 | 38.2554 | 35.7792 | 33.2063 | 30.3986 | 27.507 | 24.4872 | 21.3714 | 18.0691 | 14.6883 | 11.1963 | 7.5802 | 3.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 33.2282 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1243 | 2.0799 | 2.0276 | 1.9761 | 1.9201 | 1.8603 | 1.7997 | 1.7377 | 1.6735 | 1.6076 | 1.5411 | 1.4717 | 1.4002 | 1.324 | 1.2471 | 1.1664 | 1.0825 | 0.991 | 0.89673 | 0.79828 | 0.69671 | 0.58905 | 0.47884 | 0.365 | 0.24712 | 0.12571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 65.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5661 | 1.6069 | 1.673 | 1.718 | 1.8343 | 1.8611 | 1.9 | 1.9701 | 2.0196 | 2.041 | 2.1289 | 2.1942 | 2.336 | 2.3588 | 2.4762 | 2.5729 | 2.8077 | 2.8916 | 3.0198 | 3.1158 | 3.3023 | 3.3808 | 3.492 | 3.6161 | 3.7242 | 3.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 65.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5661 | 1.6069 | 1.673 | 1.718 | 1.8343 | 1.8611 | 1.9 | 1.9701 | 2.0196 | 2.041 | 2.1289 | 2.1942 | 2.336 | 2.3588 | 2.4762 | 2.5729 | 2.8077 | 2.8916 | 3.0198 | 3.1158 | 3.3023 | 3.3808 | 3.492 | 3.6161 | 3.7242 | 3.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.8973 | 62.2904 | 60.6174 | 58.8994 | 57.0651 | 55.204 | 53.304 | 51.3338 | 49.3142 | 47.2732 | 45.1444 | 42.9502 | 40.6142 | 38.2554 | 35.7792 | 33.2063 | 30.3986 | 27.507 | 24.4872 | 21.3714 | 18.0691 | 14.6883 | 11.1963 | 7.5802 | 3.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 65.4634 | 63.8973 | 62.2904 | 60.6174 | 58.8994 | 57.0651 | 55.204 | 53.304 | 51.3338 | 49.3142 | 47.2732 | 45.1444 | 42.9502 | 40.6142 | 38.2554 | 35.7792 | 33.2063 | 30.3986 | 27.507 | 24.4872 | 21.3714 | 18.0691 | 14.6883 | 11.1963 | 7.5802 | 3.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 248.7608 | 242.8097 | 236.7036 | 230.3461 | 223.8177 | 216.8474 | 209.7752 | 202.555 | 195.0685 | 187.394 | 179.6383 | 171.5486 | 155.2022 | 137.0758 | 119.4948 | 101.2956 | 84.6619 | 69.2987 | 54.2416 | 39.0001 | 24.6115 | 9.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 138.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9366 | 9.7259 | 9.4813 | 9.2394 | 8.9776 | 8.698 | 8.4143 | 8.1247 | 7.8244 | 8.0371 | 7.7045 | 7.3575 | 6.6564 | 5.879 | 5.125 | 4.3445 | 3.6311 | 3.1646 | 2.477 | 1.781 | 1.1239 | 0.45397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 147.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 5.951 | 6.1061 | 6.3575 | 6.5284 | 6.9702 | 7.0722 | 7.2202 | 7.4865 | 7.6745 | 7.7558 | 8.0896 | 8.338 | 8.4411 | 7.9612 | 7.7347 | 7.2841 | 7.1584 | 6.5919 | 5.9547 | 4.9624 | 3.803 | 1.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 147.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 5.951 | 6.1061 | 6.3575 | 6.5284 | 6.9702 | 7.0722 | 7.2202 | 7.4865 | 7.6745 | 7.7558 | 8.0896 | 8.338 | 8.4411 | 7.9612 | 7.7347 | 7.2841 | 7.1584 | 6.5919 | 5.9547 | 4.9624 | 3.803 | 1.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 242.8097 | 236.7036 | 230.3461 | 223.8177 | 216.8474 | 209.7752 | 202.555 | 195.0685 | 187.394 | 179.6383 | 171.5486 | 163.2107 | 146.7611 | 129.1145 | 111.7602 | 94.0114 | 77.5035 | 62.7068 | 48.2868 | 34.0376 | 20.8085 | 8.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 101.4591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0085 | 9.6853 | 9.6197 | 10.4646 | 9.3495 | 8.2048 | 8.4653 | 9.2867 | 9.4262 | 10.8675 | 8.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 248.7608 | 242.8097 | 236.7036 | 230.3461 | 223.8177 | 216.8474 | 209.7752 | 202.555 | 195.0685 | 187.394 | 179.6383 | 171.5486 | 155.2022 | 137.0758 | 119.4948 | 101.2956 | 84.6619 | 69.2987 | 54.2416 | 39.0001 | 24.6115 | 9.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497 | 0.45657
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 0
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 0
|  | Bond face amount | USD m | 0
|  | Swap unwind receipt | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | 8.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55426 | 0.46077 | 0.57833 | 0.4615 | 0.57093 | 0.47402 | 0.53511 | 0.40582 | 0.4976 | 0.37545 | 0.45824 | 0.3437 | 0.41633 | 0.33737 | 0.37082 | 0.2724 | 0.32188 | 0.23143 | 0.26663 | 0.18643 | 0.20716 | 0.15009 | 0.14238 | 0.085241 | 0.073478 | 0.029357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 17.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2979 | 1.2462 | 1.235 | 1.1822 | 1.1678 | 1.1191 | 1.0945 | 1.0396 | 1.0178 | 0.96179 | 0.93727 | 0.88047 | 0.80977 | 0.70742 | 0.62347 | 0.5199 | 0.44173 | 0.35567 | 0.28301 | 0.20017 | 0.12841 | 0.051304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 315.6196 | 0 | 0 | 0 | 0 | 0 | 0 | 21.2742 | 20.8319 | 20.308 | 19.7941 | 19.2331 | 18.6342 | 18.0264 | 17.406 | 16.7627 | 16.6237 | 15.9357 | 15.2181 | 14.1349 | 12.9508 | 11.786 | 10.5743 | 9.4129 | 8.4577 | 7.2666 | 6.0447 | 4.8451 | 3.6002 | 2.5575 | 1.9495 | 1.3199 | 0.6714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 341.7269 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1264 | 22.5389 | 22.1213 | 21.4379 | 20.9718 | 20.2273 | 19.6561 | 18.8514 | 18.278 | 17.961 | 17.3312 | 16.4422 | 15.361 | 13.9956 | 12.7803 | 11.3666 | 10.1765 | 9.0448 | 7.8162 | 6.4313 | 5.1807 | 3.8016 | 2.6999 | 2.0347 | 1.3933 | 0.70076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 553.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6606 | 16.0687 | 16.7303 | 17.1801 | 18.3428 | 18.611 | 19.0005 | 19.7014 | 20.196 | 20.4099 | 21.2885 | 21.942 | 22.9241 | 22.586 | 23.0871 | 23.2359 | 24.566 | 24.52 | 24.6773 | 24.2804 | 24.2774 | 22.8211 | 21.6504 | 22.4196 | 23.0902 | 23.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 894.9014 | 0 | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 38.2851 | 36.5816 | 35.8674 | 34.6025 | 34.7426 | 33.5647 | 32.4935 | 30.7117 | 29.4581 | 26.6227 | 24.3504 | 24.4544 | 24.4836 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 654.6336 | 638.973 | 622.9043 | 606.174 | 588.9938 | 570.6511 | 552.04 | 533.0396 | 513.3382 | 493.1422 | 472.7323 | 451.4438 | 421.4933 | 388.8839 | 356.6781 | 323.1265 | 290.5411 | 257.7702 | 224.785 | 190.821 | 157.1144 | 121.9695 | 91.0674 | 69.417 | 46.9973 | 23.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 654.6336 | 638.973 | 622.9043 | 606.174 | 588.9938 | 570.6511 | 552.04 | 533.0396 | 513.3382 | 493.1422 | 472.7323 | 451.4438 | 421.4933 | 388.8839 | 356.6781 | 323.1265 | 290.5411 | 257.7702 | 224.785 | 190.821 | 157.1144 | 121.9695 | 91.0674 | 69.417 | 46.9973 | 23.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 248.7608 | 242.8097 | 236.7036 | 230.3461 | 223.8177 | 216.8474 | 209.7752 | 202.555 | 195.0685 | 187.394 | 179.6383 | 171.5486 | 163.2107 | 146.7611 | 129.1145 | 111.7602 | 94.0114 | 77.5035 | 62.7068 | 48.2868 | 34.0376 | 20.8085 | 8.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.058 | 9.0953 | 9.1863 | 9.2184 | 9.452 | 9.4095 | 9.4016 | 9.4844 | 9.5007 | 9.4295 | 9.5562 | 9.6095 | 9.8877 | 9.7997 | 9.9936 | 10.1176 | 10.6495 | 10.7131 | 10.9036 | 10.9893 | 11.3399 | 11.354 | 11.4609 | 11.5989 | 11.6809 | 11.8265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 8.2988 | 8.2865 | 8.3126 | 8.2938 | 8.4216 | 8.3441 | 8.2912 | 8.3038 | 8.266 | 8.1626 | 8.2039 | 8.1891 | 8.3376 | 8.214 | 8.2965 | 8.3248 | 8.6498 | 8.6254 | 8.6919 | 8.6783 | 8.8566 | 8.7834 | 8.7763 | 8.7891 | 8.7578 | 8.7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 3.6903 | 3.6867 | 3.7006 | 3.6941 | 3.7544 | 3.7214 | 3.6997 | 3.7078 | 3.6931 | 3.6486 | 3.67 | 3.6659 | 3.7361 | 3.6829 | 3.7233 | 3.7393 | 3.8902 | 3.8826 | 3.9165 | 3.9141 | 3.999 | 3.9699 | 3.9708 | 3.9811 | 3.9713 | 3.9817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 15.8876 | 15.832 | 15.8388 | 15.7679 | 15.9478 | 15.7702 | 15.6345 | 15.6112 | 15.4989 | 15.7929 | 15.7941 | 15.6955 | 15.8766 | 14.8182 | 13.8949 | 12.8299 | 11.981 | 10.9117 | 9.7477 | 8.3492 | 6.8139 | 4.8436 | 2.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 39.1059 | 37.6095 | 36.9528 | 35.8576 | 35.9829 | 34.762 | 33.8535 | 32.3651 | 31.3942 | 29.2084 | 26.6827 | 24.4544 | 24.4836 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.035327 | 0.035274 | 0.035513 | 0.035366 | 0.035606 | 0.035446 | 0.035606 | 0.035366 | 0.035606 | 0.036421 | 0.036662 | 0.036421 | 0.036662 | 0.036502 | 0.036662 | 0.036421 | 0.036662 | 0.037477 | 0.037717 | 0.037477 | 0.037717 | 0.037557 | 0.037717 | 0.037477 | 0.037717 | 0.037477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 940.1063 | 917.6164 | 894.5405 | 870.5144 | 845.8424 | 819.5007 | 792.7738 | 765.4875 | 737.1948 | 708.1917 | 678.8815 | 648.3094 | 616.7989 | 583.2526 | 549.3778 | 513.8177 | 476.8692 | 436.5486 | 395.0226 | 351.6564 | 306.911 | 259.487 | 210.9357 | 160.7877 | 108.858 | 55.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.4361
|  | Debt capacity at the 1.35x target | USD m | 696.375
|  | Debt at the 75% gearing cap (closed form) | USD m | 643.7515
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 39.1059 | 38.4132 | 38.7871 | 38.76 | 40.2509 | 40.3087 | 40.5726 | 40.3351 | 41.084 | 40.5945 | 40.4601 | 40.3567 | 40.1013 | 40.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 654.6336 | 638.973 | 622.9043 | 606.174 | 588.9938 | 570.6511 | 552.04 | 533.0396 | 513.3382 | 493.1422 | 472.7323 | 451.4438 | 429.5017 | 406.1421 | 382.5537 | 357.7918 | 332.0631 | 303.9863 | 275.0701 | 244.8724 | 213.7144 | 180.6912 | 146.8829 | 111.9629 | 75.8022 | 38.5599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.6606 | 16.0687 | 16.7303 | 17.1801 | 18.3428 | 18.611 | 19.0005 | 19.7014 | 20.196 | 20.4099 | 21.2885 | 21.942 | 23.3596 | 23.5884 | 24.762 | 25.7287 | 28.0768 | 28.9162 | 30.1977 | 31.158 | 33.0232 | 33.8083 | 34.9201 | 36.1607 | 37.2423 | 38.5599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -2.3124e-09 | -1.2138e-09 | -2.7393e-09 | -1.3619e-09 | -2.7329e-09 | -1.6412e-09 | -2.5097e-09 | -9.4546e-10 | -2.1728e-09 | -7.0625e-10 | -1.7703e-09 | -3.8645e-10 | -1.25e-09 | -3.6277e-10 | -7.6342e-10 | 4.7667e-10 | 3.7357e-11 | 1.191e-09 | 8.1057e-10 | 1.8482e-09 | 1.7393e-09 | 2.4808e-09 | 2.6543e-09 | 3.4793e-09 | 3.7273e-09 | 4.4245e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 51.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0.41627 | 0 | 0 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 1.9727 | 0 | 0 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0.49543 | 0 | 0 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 2.3479 | 0 | 0 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0.58964 | 0 | 0 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 2.7944 | 0 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.41627 | 0.83254 | 1.2488 | 1.6651 | 2.0813 | 2.4976 | 0 | 0 | 1.9727 | 3.9455 | 5.9182 | 7.891 | 9.8637 | 11.8365 | 0 | 0 | 0.49543 | 0.99086 | 1.4863 | 1.9817 | 2.4771 | 2.9726 | 0 | 0 | 2.3479 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 3.5378 | 0 | 0 | 2.7944 | 5.5888 | 8.3831 | 11.1775 | 13.9719 | 16.7663 | 0 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 39.1059 | 37.6095 | 36.9528 | 35.8576 | 35.9829 | 34.762 | 33.8535 | 32.3651 | 31.3942 | 29.2084 | 26.6827 | 24.4544 | 24.4836 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 2.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24406 | 0 | 0.6966 | 0 | 0 | 0 | 0 | 0 | 0.24893 | 0 | 0.72167 | 0 | 0 | 0 | 0.12533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02919 | 0.12433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 40.9771 | 0 | 0 | 0 | 0 | 0 | 1.7621e-12 | 0.17938 | 0 | 0.23364 | 0 | 0.47627 | 0.18178 | 0.10378 | 0.078698 | 0.10325 | 0 | 0.23549 | 0 | 1.4965 | 0.65664 | 1.0953 | 0 | 1.2209 | 0.90847 | 1.4884 | 0.97089 | 2.1858 | 2.5257 | 2.2284 | 0 | 0 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 39.1059 | 37.6095 | 36.9528 | 35.8576 | 35.9829 | 34.762 | 33.8535 | 32.3651 | 31.3942 | 29.2084 | 26.6827 | 24.4544 | 24.4836 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.5012 | 1.5176 | 1.5342 | 1.551 | 1.5679 | 1.5851 | 1.6024 | 1.62 | 1.6377 | 1.6556 | 1.6737 | 1.128 | 0
| Handback reserve release at expiry | USD m |  | 19.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0692 | 0
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49497 | 1.9961 | 3.5137 | 5.0479 | 6.5988 | 8.1668 | 9.7518 | 11.3543 | 12.9742 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2471.5889 | 0 | 0 | 0 | 0 | 0 | 2.5197 | 55.7012 | 55.4436 | 55.7941 | 55.4585 | 56.4589 | 55.775 | 55.5139 | 55.3649 | 55.2519 | 55.1036 | 55.4611 | 55.1229 | 56.1593 | 55.1644 | 55.7013 | 53.4269 | 49.9313 | 49.5868 | 49.5785 | 48.5932 | 49.0073 | 47.9057 | 48.5674 | 47.0593 | 46.0128 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.7266 | 50.0687 | 46.6397 | 41.5861 | 41.4595 | 41.9778 | 41.4959 | 42.5106 | 41.7429 | 48.7034 | 43.1925 | 45.3789 | 42.2996 | 0
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.5197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.5197 | 58.2209 | 55.4436 | 55.7941 | 55.4585 | 56.4589 | 55.775 | 55.5139 | 55.3649 | 55.2519 | 55.1036 | 55.4611 | 55.1229 | 56.1593 | 55.1644 | 55.7013 | 53.4269 | 49.9313 | 49.5868 | 49.5785 | 48.5932 | 49.0073 | 47.9057 | 48.5674 | 47.0593 | 46.0128 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.7266 | 50.0687 | 46.6397 | 41.5861 | 41.4595 | 41.9778 | 41.4959 | 42.5106 | 41.7429 | 48.7034 | 43.1925 | 45.3789 | 42.2996 | 0
|  | Senior debt service and fees due | USD m |  | 894.9014 | 0 | 0 | 0 | 0 | 0 | 0 | 38.787 | 38.6076 | 38.8516 | 38.618 | 39.3146 | 38.8383 | 38.6566 | 38.5528 | 38.4741 | 38.3708 | 38.6197 | 38.3843 | 38.2851 | 36.5816 | 35.8674 | 34.6025 | 34.7426 | 33.5647 | 32.4935 | 30.7117 | 29.4581 | 26.6227 | 24.3504 | 24.4544 | 24.4836 | 24.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.5197 | 19.4339 | 16.836 | 16.9424 | 16.8405 | 17.1443 | 16.9366 | 16.8574 | 16.8121 | 16.7778 | 16.7328 | 16.8413 | 16.7386 | 17.8741 | 18.5828 | 19.8339 | 18.8243 | 15.1887 | 16.022 | 17.0851 | 17.8815 | 19.5492 | 21.283 | 24.2171 | 22.605 | 21.5293 | 21.0644 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.7266 | 50.0687 | 46.6397 | 41.5861 | 41.4595 | 41.9778 | 41.4959 | 42.5106 | 41.7429 | 48.7034 | 43.1925 | 45.3789 | 42.2996 | 0
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.5197 | 19.6133 | 16.5919 | 17.1761 | 16.1439 | 17.6206 | 17.1184 | 16.9611 | 16.8908 | 16.881 | 16.4838 | 17.0768 | 16.0169 | 19.3706 | 19.2395 | 20.9292 | 18.699 | 16.4096 | 16.9305 | 18.5735 | 18.8524 | 21.735 | 23.8087 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.7266 | 50.0687 | 46.6397 | 41.5861 | 41.4595 | 41.9778 | 41.4959 | 42.5106 | 41.7429 | 48.7034 | 43.1925 | 45.3789 | 42.2996 | 0
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.5197 | 19.6133 | 16.5919 | 17.1761 | 16.1439 | 17.6206 | 17.1184 | 16.9611 | 16.8908 | 16.881 | 16.4838 | 17.0768 | 16.0169 | 19.3706 | 19.2395 | 20.9292 | 18.699 | 16.4096 | 16.9305 | 18.5735 | 18.8524 | 21.735 | 23.8087 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 60.2407 | 0
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4669 | 1.508 | 1.553 | 1.544 | 1.4372 | 1.4773 | 1.5258 | 1.5822 | 1.6636 | 1.7994 | 1.9945 | 1.9244 | 1.8793 | 1.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4361 | 1.4515 | 1.487 | 1.5303 | 1.5486 | 1.4905 | 1.4569 | 1.5012 | 1.5532 | 1.6221 | 1.7281 | 1.8926 | 1.9594 | 1.9018 | 1.8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 101.4591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0085 | 9.6853 | 9.6197 | 10.4646 | 9.3495 | 8.2048 | 8.4653 | 9.2867 | 9.4262 | 10.8675 | 8.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 2.5197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1514.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6133 | 16.5919 | 17.1761 | 16.1439 | 17.6206 | 17.1184 | 16.9611 | 16.8908 | 16.881 | 16.4838 | 17.0768 | 8.0085 | 9.6853 | 9.6197 | 10.4646 | 9.3495 | 8.2048 | 8.4653 | 9.2867 | 9.4262 | 10.8675 | 15.7277 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 60.2407 | 0
|  | Share capital contributed | USD m | 41.0564
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 187.5839 | 190.5621 | 180.0749 | 171.9662 | 163.0256 | 154.5618 | 144.3432 | 134.0623 | 123.5215 | 112.4497 | 100.9539 | 89.226 | 76.4223 | 72.0141 | 65.7775 | 59.2737 | 51.6477 | 44.7313 | 38.6687 | 32.0251 | 24.2721 | 15.9894 | 5.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 97.5403 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1261 | 8.4833 | 8.2355 | 7.6801 | 7.402 | 6.8375 | 6.4203 | 5.819 | 5.3853 | 4.7559 | 4.2731 | 3.6002 | 3.4488 | 3.1159 | 2.8386 | 2.4331 | 2.1422 | 1.8217 | 1.5337 | 1.1434 | 0.76574 | 0.27889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 190.5621 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4872 | 8.1087 | 8.9405 | 8.4639 | 10.2186 | 10.2809 | 10.5408 | 11.0718 | 11.4958 | 11.7279 | 12.8037 | 4.4082 | 6.2365 | 6.5039 | 7.626 | 6.9164 | 6.0626 | 6.6436 | 7.753 | 8.2827 | 10.1018 | 5.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 190.5621 | 180.0749 | 171.9662 | 163.0256 | 154.5618 | 144.3432 | 134.0623 | 123.5215 | 112.4497 | 100.9539 | 89.226 | 76.4223 | 72.0141 | 65.7775 | 59.2737 | 51.6477 | 44.7313 | 38.6687 | 32.0251 | 24.2721 | 15.9894 | 5.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.5186 | 14.8048 | 21.3652 | 28.3699 | 36.9517 | 46.8063 | 57.4432 | 65.3578 | 78.0089 | 93.1899 | 109.5344 | 127.2649 | 146.9118 | 168.343 | 190.5272 | 200.2644 | 222.734 | 243.452 | 265.1677 | 287.7868 | 311.9092 | 337.5749 | 364.1708 | 379.2111 | 380.5396 | 387.3239 | 395.7507 | 380.2455 | 364.7563 | 350.151 | 333.9232 | 307.0284 | 285.2385 | 269.9226 | 253.1497 | 236.1133 | 218.8736 | 202.5479 | 184.8636 | 164.842 | 147.6375 | 135.0995 | 127.6317 | 120.1592 | 112.4905 | 105.7858 | 97.3699 | 76.3761 | 61.2412 | 53.5581 | 19.1843 | 0
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5612 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 19.1843 | 0
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.0564 | 0
|  | Liquidation distribution at PPA expiry | USD m |  | 41.0564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.0564 | 0
|  | Dividends | USD m |  | 1225.9131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5612 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 60.2407 | 0
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.5186 | 14.8048 | 21.3652 | 28.3699 | 36.9517 | 46.8063 | 57.4432 | 65.3578 | 78.0089 | 93.1899 | 109.5344 | 127.2649 | 146.9118 | 168.343 | 190.5272 | 200.2644 | 222.734 | 243.452 | 265.1677 | 287.7868 | 311.9092 | 337.5749 | 354.6096 | 352.7657 | 357.9639 | 365.919 | 350.0784 | 334.3148 | 319.2873 | 303.7451 | 288.2545 | 255.6175 | 238.5086 | 221.7426 | 204.8579 | 187.329 | 170.5607 | 153.2608 | 136.6319 | 116.2744 | 102.5153 | 95.0475 | 87.7231 | 79.7494 | 72.5798 | 64.8777 | 57.247 | 29.3103 | 19.7043 | 9.853 | -41.0564 | -41.0564
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1514.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6133 | 16.5919 | 17.1761 | 16.1439 | 17.6206 | 17.1184 | 16.9611 | 16.8908 | 16.881 | 16.4838 | 17.0768 | 8.0085 | 9.6853 | 9.6197 | 10.4646 | 9.3495 | 8.2048 | 8.4653 | 9.2867 | 9.4262 | 10.8675 | 15.7277 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 60.2407 | 0

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 839.1369 | 0 | 0 | 0 | 0 | 0 | 5.5942 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 16.7827 | 11.1885 | 0
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 442.2454 | 0 | 0 | 0 | 0 | 0 | 2.9782 | 32.2525 | 31.0221 | 30.3569 | 29.118 | 28.3739 | 27.0648 | 26.0764 | 24.6705 | 23.6633 | 22.7169 | 21.6043 | 20.0425 | 18.8098 | 17.1114 | 15.619 | 13.7997 | 12.3187 | 10.8664 | 9.3499 | 7.5748 | 5.9464 | 4.0805 | 2.6999 | 2.0347 | 1.3933 | 0.70076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 839.1369 | 839.1369 | 839.1369 | 839.1369 | 839.1369 | 831.5847 | 808.928 | 786.2713 | 763.6146 | 740.9579 | 718.3012 | 695.6445 | 672.9878 | 650.3311 | 627.6744 | 605.8568 | 585.7176 | 565.5783 | 545.439 | 525.2997 | 505.1604 | 485.0211 | 464.8818 | 444.7426 | 424.6033 | 404.464 | 384.3247 | 364.1854 | 344.0461 | 323.9068 | 303.7676 | 283.6283 | 263.489 | 243.3497 | 223.2104 | 203.0711 | 182.9318 | 162.7926 | 142.6533 | 122.514 | 102.3747 | 82.2354 | 62.0961 | 41.9568 | 21.8176 | 8.1117 | 7.2725 | 6.4334 | 5.5942 | 4.7551 | 3.916 | 3.0768 | 2.2377 | 1.3986 | 0.55942 | 0 | 0
|  | Book value of plant (from COD) | USD m |  |  | 839.1369 | 839.1369 | 839.1369 | 839.1369 | 839.1369 | 833.5426 | 816.7599 | 799.9772 | 783.1944 | 766.4117 | 749.629 | 732.8462 | 716.0635 | 699.2807 | 682.498 | 665.7153 | 648.9325 | 632.1498 | 615.3671 | 598.5843 | 581.8016 | 565.0188 | 548.2361 | 531.4534 | 514.6706 | 497.8879 | 481.1052 | 464.3224 | 447.5397 | 430.7569 | 413.9742 | 397.1915 | 380.4087 | 363.626 | 346.8432 | 330.0605 | 313.2778 | 296.495 | 279.7123 | 262.9296 | 246.1468 | 229.3641 | 212.5813 | 195.7986 | 179.0159 | 162.2331 | 145.4504 | 128.6677 | 111.8849 | 95.1022 | 78.3194 | 61.5367 | 44.754 | 27.9712 | 11.1885 | 0 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0.5874 | 2.3496 | 4.1118 | 5.874 | 7.6361 | 9.3983 | 11.1605 | 12.9227 | 14.6849 | 16.4471 | 17.9575 | 18.9645 | 19.9715 | 20.9784 | 21.9854 | 22.9924 | 23.9993 | 25.0063 | 26.0132 | 27.0202 | 28.0272 | 29.0341 | 30.0411 | 31.0481 | 32.055 | 33.062 | 34.069 | 35.0759 | 36.0829 | 37.0899 | 38.0968 | 39.1038 | 40.1107 | 41.1177 | 42.1247 | 43.1316 | 44.1386 | 45.1456 | 46.1525 | 47.1595 | 46.2364 | 41.4534 | 36.6703 | 31.8872 | 27.1041 | 22.321 | 17.538 | 12.7549 | 7.9718 | 3.1887 | 0 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5874 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.7622 | 1.5104 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | 1.007 | -0.92305 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -4.7831 | -3.1887 | 0
|  | Net income | USD m |  | 1184.8566 | 0 | 0 | 0 | 0 | 0 | 9.5186 | 5.2861 | 6.5604 | 7.0048 | 8.5817 | 9.8547 | 10.6368 | 7.9146 | 12.6511 | 15.1811 | 16.3444 | 17.7305 | 19.6469 | 21.4311 | 22.1842 | 9.7373 | 22.4696 | 20.718 | 21.7157 | 22.6191 | 24.1224 | 25.6656 | 26.5959 | 24.6015 | 27.774 | 29.36 | 29.8317 | 30.1671 | 30.4415 | 30.8637 | 30.1781 | 18.7739 | 29.621 | 31.414 | 31.4072 | 31.2554 | 31.5445 | 31.9872 | 31.6027 | 28.2101 | 31.363 | 32.5842 | 32.5842 | 32.4361 | 32.7412 | 33.2061 | 32.4922 | 19.1291 | 31.9308 | 33.8538 | 9.3313 | 0
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 139.3562 | 239.5745 | 433.7992 | 636.1603 | 754.2274 | 833.5426 | 816.7599 | 799.9772 | 783.1944 | 766.4117 | 749.629 | 732.8462 | 716.0635 | 699.2807 | 682.498 | 665.7153 | 648.9325 | 632.1498 | 615.3671 | 598.5843 | 581.8016 | 565.0188 | 548.2361 | 531.4534 | 514.6706 | 497.8879 | 481.1052 | 464.3224 | 447.5397 | 430.7569 | 413.9742 | 397.1915 | 380.4087 | 363.626 | 346.8432 | 330.0605 | 313.2778 | 296.495 | 279.7123 | 262.9296 | 246.1468 | 229.3641 | 212.5813 | 195.7986 | 179.0159 | 162.2331 | 145.4504 | 128.6677 | 111.8849 | 95.1022 | 78.3194 | 61.5367 | 44.754 | 27.9712 | 11.1885 | 0 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 41.3067 | 39.0238 | 39.6842 | 39.8668 | 40.9797 | 40.9197 | 41.1542 | 38.5528 | 38.4741 | 40.3436 | 42.5652 | 44.3025 | 46.9969 | 47.4732 | 48.7893 | 35.8576 | 35.9829 | 35.2574 | 34.8444 | 33.8514 | 33.3759 | 31.6856 | 29.6553 | 24.4544 | 24.4836 | 26.9558 | 4.6958 | 7.0437 | 9.3916 | 11.7394 | 14.0873 | 0 | 0 | 0.58964 | 1.1793 | 1.7689 | 2.3586 | 2.9482 | 4.0328 | 1.9961 | 3.5137 | 7.8422 | 12.1876 | 16.5499 | 20.9293 | 25.3261 | 29.7405 | 14.6119 | 16.2675 | 17.9412 | 0 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 39.8998 | 39.771 | 40.7703 | 39.9843 | 41.2367 | 40.9281 | 41.4289 | 40.2075 | 41.7983 | 42.1308 | 43.1995 | 42.3688 | 43.706 | 43.381 | 43.6433 | 41.8007 | 43.757 | 44.6805 | 45.8241 | 44.9451 | 46.3738 | 46.0312 | 46.6154 | 45.2455 | 47.0564 | 47.4352 | 48.6598 | 47.7285 | 49.2563 | 48.8946 | 49.2113 | 47.1378 | 49.365 | 50.4115 | 51.7236 | 50.7359 | 52.3706 | 51.9883 | 52.6696 | 51.126 | 53.1942 | 53.6273 | 55.034 | 53.9852 | 55.7355 | 55.3309 | 55.7109 | 53.3673 | 55.9111 | 57.1018 | 0 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 0 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 139.3562 | 239.5745 | 433.7992 | 636.1603 | 754.2274 | 920.0992 | 900.9048 | 885.7817 | 868.3955 | 853.9781 | 836.8267 | 820.7793 | 800.1738 | 784.9031 | 770.3224 | 756.83 | 740.9538 | 728.2027 | 711.5712 | 696.3669 | 664.8098 | 650.1088 | 633.524 | 617.4719 | 598.8171 | 582.9877 | 564.1719 | 545.9431 | 522.5895 | 507.6469 | 493.7152 | 455.8971 | 440.5309 | 427.6238 | 412.8273 | 398.7091 | 365.7656 | 351.21 | 336.0634 | 321.1825 | 304.0016 | 289.4433 | 272.8678 | 257.8511 | 237.488 | 224.291 | 212.2699 | 201.2392 | 187.77 | 177.117 | 164.3265 | 152.3381 | 118.0832 | 105.4998 | 91.5815 | 0 | 0
|  | Senior debt | USD m |  |  | 103.9072 | 177.8132 | 321.1113 | 468.9518 | 552.1238 | 654.6336 | 638.973 | 622.9043 | 606.174 | 588.9938 | 570.6511 | 552.04 | 533.0396 | 513.3382 | 493.1422 | 472.7323 | 451.4438 | 421.4933 | 388.8839 | 356.6781 | 323.1265 | 290.5411 | 257.7702 | 224.785 | 190.821 | 157.1144 | 121.9695 | 91.0674 | 69.417 | 46.9973 | 23.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 28.5218 | 49.907 | 91.2804 | 135.945 | 165.2954 | 190.5621 | 180.0749 | 171.9662 | 163.0256 | 154.5618 | 144.3432 | 134.0623 | 123.5215 | 112.4497 | 100.9539 | 89.226 | 76.4223 | 72.0141 | 65.7775 | 59.2737 | 51.6477 | 44.7313 | 38.6687 | 32.0251 | 24.2721 | 15.9894 | 5.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 23.741 | 23.6461 | 24.3778 | 23.8956 | 24.7782 | 24.5713 | 25.0167 | 24.2758 | 25.365 | 25.5328 | 26.3233 | 25.8019 | 26.7556 | 26.532 | 26.8461 | 25.7224 | 27.0466 | 27.5703 | 28.4243 | 27.8606 | 28.8911 | 28.6493 | 29.1685 | 28.3023 | 29.5742 | 29.7706 | 30.6933 | 30.0838 | 31.1972 | 30.9358 | 31.3013 | 29.9879 | 31.5343 | 32.1467 | 33.1435 | 32.4845 | 33.6875 | 33.405 | 34.0102 | 32.9977 | 34.4828 | 34.7126 | 35.7894 | 35.077 | 36.3767 | 36.0714 | 36.4967 | 34.9615 | 36.7672 | 37.4833 | 0 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0.5874 | 2.3496 | 4.1118 | 5.874 | 7.6361 | 9.3983 | 11.1605 | 12.9227 | 14.6849 | 16.4471 | 17.9575 | 18.9645 | 19.9715 | 20.9784 | 21.9854 | 22.9924 | 23.9993 | 25.0063 | 26.0132 | 27.0202 | 28.0272 | 29.0341 | 30.0411 | 31.0481 | 32.055 | 33.062 | 34.069 | 35.0759 | 36.0829 | 37.0899 | 38.0968 | 39.1038 | 40.1107 | 41.1177 | 42.1247 | 43.1316 | 44.1386 | 45.1456 | 46.1525 | 47.1595 | 46.2364 | 41.4534 | 36.6703 | 31.8872 | 27.1041 | 22.321 | 17.538 | 12.7549 | 7.9718 | 3.1887 | 0 | 0
|  | Share capital | USD m |  |  | 6.9271 | 11.8542 | 21.4074 | 31.2635 | 36.8083 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564 | 41.0564
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 9.5186 | 14.8048 | 21.3652 | 28.3699 | 36.9517 | 46.8063 | 57.4432 | 65.3578 | 78.0089 | 93.1899 | 109.5344 | 127.2649 | 146.9118 | 168.343 | 190.5272 | 200.2644 | 222.734 | 243.452 | 265.1677 | 287.7868 | 311.9092 | 337.5749 | 354.6096 | 352.7657 | 357.9639 | 365.919 | 350.0784 | 334.3148 | 319.2873 | 303.7451 | 288.2545 | 255.6175 | 238.5086 | 221.7426 | 204.8579 | 187.329 | 170.5607 | 153.2608 | 136.6319 | 116.2744 | 102.5153 | 95.0475 | 87.7231 | 79.7494 | 72.5798 | 64.8777 | 57.247 | 29.3103 | 19.7043 | 9.853 | -41.0564 | -41.0564
|  | Total liabilities and equity | USD m |  |  | 139.3562 | 239.5745 | 433.7992 | 636.1603 | 754.2274 | 920.0992 | 900.9048 | 885.7817 | 868.3955 | 853.9781 | 836.8267 | 820.7793 | 800.1738 | 784.9031 | 770.3224 | 756.83 | 740.9538 | 728.2027 | 711.5712 | 696.3669 | 664.8098 | 650.1088 | 633.524 | 617.4719 | 598.8171 | 582.9877 | 564.1719 | 545.9431 | 522.5895 | 507.6469 | 493.7152 | 455.8971 | 440.5309 | 427.6238 | 412.8273 | 398.7091 | 365.7656 | 351.21 | 336.0634 | 321.1825 | 304.0016 | 289.4433 | 272.8678 | 257.8511 | 237.488 | 224.291 | 212.2699 | 201.2392 | 187.77 | 177.117 | 164.3265 | 152.3381 | 118.0832 | 105.4998 | 91.5815 | 0 | 0
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.035327 | 0.035274 | 0.035513 | 0.035366 | 0.035606 | 0.035446 | 0.035606 | 0.035366 | 0.035606 | 0.036421 | 0.036662 | 0.036421 | 0.036444 | 0.035989 | 0.035832 | 0.035177 | 0.035026 | 0.035088 | 0.034772 | 0.033703 | 0.032974 | 0.031168 | 0.029647 | 0.029312 | 0.029647 | 0.029312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 32
| Rate in final maturity period | factor | 0.029312
| Discount rate used | factor |  |  | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.035327 | 0.035274 | 0.035513 | 0.035366 | 0.035606 | 0.035446 | 0.035606 | 0.035366 | 0.035606 | 0.036421 | 0.036662 | 0.036421 | 0.036444 | 0.035989 | 0.035832 | 0.035177 | 0.035026 | 0.035088 | 0.034772 | 0.033703 | 0.032974 | 0.031168 | 0.029647 | 0.029312 | 0.029647 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312 | 0.029312
| PV of CFADS to final maturity | USD m |  |  | 757.928 | 780.1443 | 803.0117 | 826.5495 | 850.7772 | 875.715 | 898.8641 | 874.9173 | 850.3352 | 824.7392 | 798.4483 | 770.4191 | 741.9525 | 712.8567 | 682.7026 | 651.7592 | 620.3937 | 587.6773 | 553.9585 | 517.9879 | 481.4654 | 443.0157 | 405.1728 | 369.4332 | 332.8093 | 294.8031 | 256.1458 | 215.5847 | 174.3985 | 131.0015 | 87.782 | 44.3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 1033.1311 | 1063.414 | 1094.5846 | 1126.6689 | 1159.6937 | 1193.6864 | 1226.1558 | 1213.7713 | 1201.1418 | 1188.0041 | 1174.5604 | 1159.9231 | 1145.2628 | 1130.5274 | 1115.1446 | 1099.5988 | 1084.5443 | 1068.8445 | 1052.6505 | 1034.8544 | 1016.9334 | 997.6704 | 979.3386 | 963.7098 | 947.9381 | 931.3211 | 914.1167 | 895.2515 | 875.2492 | 852.6305 | 830.5633 | 809.1745 | 787.2206 | 764.3647 | 741.3006 | 716.6236 | 691.9604 | 660.832 | 633.4724 | 603.8606 | 573.269 | 541.2883 | 508.8416 | 474.4696 | 439.6506 | 402.4688 | 367.6262 | 336.8158 | 305.229 | 272.198 | 238.6807 | 203.1663 | 167.3786 | 123.5814 | 84.0113 | 41.095 | 0
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.4323 | 1.4297 | 1.4275 | 1.4243 | 1.4224 | 1.4181 | 1.414 | 1.4097 | 1.4049 | 1.3995 | 1.3941 | 1.3868 | 1.4071 | 1.4287 | 1.4535 | 1.482 | 1.5184 | 1.568 | 1.6312 | 1.7145 | 1.8301 | 2.007 | 2.208 | 2.2394 | 2.3888 | 2.8853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3731 | 1.3693 | 1.3651 | 1.3606 | 1.3556 | 1.3501 | 1.344 | 1.3373 | 1.3299 | 1.3216 | 1.3124 | 1.3018 | 1.3143 | 1.332 | 1.3499 | 1.371 | 1.3945 | 1.4332 | 1.4806 | 1.5449 | 1.6303 | 1.7675 | 1.915 | 1.8872 | 1.8678 | 1.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.873 | 1.8996 | 1.9283 | 1.9598 | 1.9942 | 2.0326 | 2.0746 | 2.1209 | 2.1723 | 2.2298 | 2.2942 | 2.3676 | 2.4974 | 2.6611 | 2.8511 | 3.0876 | 3.3707 | 3.7386 | 4.2171 | 4.8806 | 5.8182 | 7.34 | 9.611 | 12.2827 | 17.6726 | 33.8466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | 1.4361
| Average DSCR (debt-service weighted) | x | 1.5296
| LLCR at first debt service period | x | 1.4323
| PLCR at first debt service period | x | 1.873

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1308.7333 | -14.2 | -16.2985 | -0.61795 | -0.78831 | -1.1186 | -1.6124 | -2.2344 | -2.9181 | -3.6992 | -4.4826 | -5.2772 | -6.0238 | -6.7453 | -7.3739 | -7.899 | -8.3294 | -8.6205 | -8.7981 | -9.1352 | -8.7228 | -8.5095 | -8.1403 | -7.6782 | -7.0941 | -6.4583 | -5.744 | -4.9819 | -4.2358 | -3.4872 | -2.8168 | -2.2272 | -1.7122 | -1.421 | -13.6111 | -1.2765 | -0.99302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6133 | 16.5919 | 17.1761 | 16.1439 | 17.6206 | 17.1184 | 16.9611 | 16.8908 | 16.881 | 16.4838 | 17.0768 | 8.0085 | 9.6853 | 9.6197 | 10.4646 | 9.3495 | 8.2048 | 8.4653 | 9.2867 | 9.4262 | 10.8675 | 15.7277 | 26.4454 | 22.5758 | 21.4049 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.2317 | 48.5676 | 45.1221 | 40.052 | 39.9086 | 40.4099 | 39.9108 | 40.9081 | 40.1229 | 47.0658 | 41.5369 | 43.7051 | 60.2407 | 0
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1760.5989 | 0 | -108.1116 | -1.4208 | -2.0547 | -3.357 | -5.2462 | -7.6084 | -10.3182 | -13.2493 | -16.2775 | -19.2866 | -22.1683 | -24.8261 | -27.1747 | -29.1412 | -30.6686 | -31.7112 | -32.2399 | -33.3829 | -31.7112 | -30.6686 | -29.1412 | -27.1747 | -24.8261 | -22.1683 | -19.2866 | -16.2775 | -13.2493 | -10.3182 | -7.6084 | -5.2462 | -3.357 | -2.0547 | -49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5197 | 55.7012 | 55.4436 | 55.7941 | 55.4585 | 56.4589 | 55.775 | 55.5139 | 55.3649 | 55.2519 | 55.1036 | 55.4611 | 55.1229 | 56.1593 | 55.1644 | 55.7013 | 53.4269 | 49.9313 | 49.5868 | 49.5785 | 48.5932 | 49.0073 | 47.9057 | 48.5674 | 47.0593 | 46.0128 | 45.6723 | 45.9307 | 45.469 | 46.4059 | 45.6687 | 51.411 | 46.7299 | 48.18 | 48.2918 | 48.7843 | 48.3128 | 49.2871 | 48.7266 | 50.0687 | 46.6397 | 41.5861 | 41.4595 | 41.9778 | 41.4959 | 42.5106 | 41.7429 | 48.7034 | 43.1925 | 45.3789 | 42.2996 | 0
| Project cash flow, pre-tax | USD m |  | 2199.1721 | 0 | -108.1116 | -1.4208 | -2.0547 | -3.357 | -5.2462 | -7.6084 | -10.3182 | -13.2493 | -16.2775 | -19.2866 | -22.1683 | -24.8261 | -27.1747 | -29.1412 | -30.6686 | -31.7112 | -32.2399 | -33.3829 | -31.7112 | -30.6686 | -29.1412 | -27.1747 | -24.8261 | -22.1683 | -19.2866 | -16.2775 | -13.2493 | -10.3182 | -7.6084 | -5.2462 | -3.357 | -2.0547 | -49.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5197 | 55.7012 | 55.4436 | 55.7941 | 55.4585 | 56.4589 | 55.775 | 55.5139 | 55.3649 | 55.2519 | 55.1036 | 55.4611 | 55.1229 | 56.1593 | 55.1644 | 55.7013 | 55.6624 | 57.8035 | 57.8865 | 58.2654 | 57.9244 | 58.9999 | 58.2969 | 58.104 | 57.9555 | 57.5887 | 57.4504 | 57.8526 | 57.5084 | 58.6263 | 57.5953 | 58.45 | 58.4176 | 60.6362 | 60.7451 | 61.1725 | 60.825 | 61.9889 | 61.2637 | 61.1518 | 61.004 | 60.3339 | 60.2073 | 60.6621 | 60.3109 | 61.5248 | 60.4512 | 61.6847 | 61.6602 | 64.6707 | 49.4874 | 0
| Cumulative equity cash flow | USD m |  |  | -14.2 | -30.4985 | -31.1164 | -31.9047 | -33.0233 | -34.6357 | -36.8701 | -39.7882 | -43.4875 | -47.97 | -53.2473 | -59.2711 | -66.0163 | -73.3902 | -81.2892 | -89.6185 | -98.239 | -107.0371 | -116.1723 | -124.8951 | -133.4046 | -141.545 | -149.2231 | -156.3173 | -162.7756 | -168.5196 | -173.5014 | -177.7373 | -181.2244 | -184.0413 | -186.2684 | -187.9806 | -189.4016 | -203.0127 | -204.2892 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -205.2822 | -185.6689 | -169.0769 | -151.9009 | -135.7569 | -118.1363 | -101.0179 | -84.0568 | -67.166 | -50.285 | -33.8012 | -16.7244 | -8.7159 | 0.96941 | 10.5891 | 21.0537 | 30.4032 | 38.608 | 47.0733 | 56.36 | 65.7862 | 76.6537 | 92.3814 | 118.8268 | 141.4026 | 162.8075 | 208.4798 | 254.4106 | 299.8796 | 346.2855 | 391.9542 | 443.3652 | 490.0951 | 538.2751 | 586.5669 | 635.3512 | 683.664 | 732.9511 | 781.1828 | 829.7503 | 874.8725 | 914.9244 | 954.833 | 995.2429 | 1035.1537 | 1076.0618 | 1116.1848 | 1163.2505 | 1204.7874 | 1248.4925 | 1308.7333 | 1308.7333
| Equity IRR (XIRR) | % | 15.22%
| Project IRR, post-tax (XIRR) | % | 11.83%
| Project IRR, pre-tax (XIRR) | % | 12.78%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -11.5028

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 1
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 1

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 859.9158
| Senior debt (four tranches) | USD m | 654.6336
| Equity (incl. LNTP) | USD m | 205.2822
| Gearing (debt incl. standby / total funding) | % | 76.13%
| Interest during construction incl. swap and PRI | USD m | 65.6659
| Commitment, upfront and agency fees | USD m | 21.6411
| ECA premium | USD m | 21.3083
| DSRA initial funding | USD m | 38.787
| Standby drawn | USD m | 0
| Contingent equity drawn | USD m | 0
| Minimum DSCR | x | 1.4361
| Average DSCR | x | 1.5296
| LLCR at first debt service period (incl. DSRA) | x | 1.4323
| PLCR at first debt service period | x | 1.873
| Equity IRR | % | 15.22%
| Project IRR, post-tax | % | 11.83%
| Equity NPV at 16.0% (at FC) | USD m | -11.5028
| All checks | check | 1

## AuditKey
Audit exercise key (Chapter 44): sponsor model version 0.9 with ten seeded errors. Do not distribute with the exercise.
Contract terms on the Inputs sheet come from sizing this erroneous model. Effects (P-F17) are from case_p.py: each error alone, re-sized.
ID | Seeded error | Cells (sheet, row) | Senior debt (USD m) | Change vs correct | Min DSCR base | Min DSCR downside | Equity IRR | Binding
correct | correct model |  | 633.26 | 0 | 1.35 | 1.2 | 13.27 | DSCR
E1 | Capacity payment without the availability cap (A/90% not capped at 1) | Operations row 42 | 641.91 | 8.66 | 1.37 | 1.2 | 14.13 | downside
E2 | LTSA variable fee on one gas turbine instead of two | Operations row 58 | 643.12 | 9.86 | 1.378 | 1.228 | 14.39 | gearing
E3 | Tariff indexation reads the index at period end instead of the lagged (Sep/Mar) reading | Operations row 18; Operations row 22 | 640.09 | 6.83 | 1.35 | 1.201 | 13.63 | DSCR
E4 | Senior loan interest on 30/360 instead of ACT/360 | Funding row 19; Funding row 33; Funding row 34; Funding row 35; Funding row 36; Funding row 12 (col F); Funding row 13 (col F); Funding row 14 (col F); Funding row 15 (col F); Debt row 10; Debt row 11; Debt row 12; Debt row 13 | 636.01 | 2.75 | 1.35 | 1.2 | 13.39 | DSCR
E5 | Full tax exemption applied to OY1-OY8 (15% band ignored) | Tax row 7; Tax row 8; Tax row 11 | 639.86 | 6.6 | 1.35 | 1.2 | 13.73 | DSCR
E6 | Deferred holiday depreciation lost (pool never credited) | Tax row 21 | 614.18 | -19.08 | 1.35 | 1.2 | 12.51 | DSCR
E7 | DSRA initial funding drawn 100% from senior debt instead of pro rata | Funding row 26 (col F); Funding row 47; Funding row 50 | 633.33 | 0.07 | 1.35 | 1.2 | 13.23 | DSCR
E8 | Sculpting on CFADS before tax | Debt row 136; Debt row 140 | 641.24 | 7.98 | 1.34 | 1.2 | 13.4 | DSCR
E9 | Fuel-charge revenue uses a typed 76.5% dispatch instead of the live dispatch | Operations row 46 | 633.26 | 0 | 1.35 | 1.2 | 13.27 | DSCR
E10 | Swap net settlement with legs reversed | Funding row 21; Funding row 39; Funding row 17 (col F); Debt row 114; Debt row 132; Debt row 135 | 623.39 | -9.86 | 1.35 | 1.2 | 12.88 | DSCR
ALL | all ten errors together | all of the above | 654.63 | 21.38 | 1.436 | 1.262 | 15.22 | gearing