## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 14
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 3
|  | Construction case (1 FC budget, 2 actual) | code | 2
|  | COD delay (sensitivity) | months | 0
|  | Capex factor | factor | 1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 0
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 0
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 2
|  | Performance LD prepayment June 2022 (1 = on) | flag | 1
|  | Waiver and amendment 2023 (1 = on) | flag | 0
|  | 2025 bond refinancing (1 = on) | flag | 0
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 1
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-12-01
|  | PPA expiry | date | 2046-11-30
|  | Construction months (NTP to COD) | months | 40
|  | Period containing COD (period number) | index | 7
|  | First debt service period | index | 8
|  | Last month of the funding period (month number) | index | 41
|  | Last operating period (period number) | index | 57
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-12-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-11-30
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 153
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 13 | 19 | 25 | 31 | 37 | 43 | 49 | 55 | 61 | 67 | 73 | 79 | 85 | 91 | 97 | 103 | 109 | 115 | 121 | 127 | 133 | 139 | 145 | 151 | 157 | 163 | 169 | 175 | 181 | 187 | 193 | 199 | 205 | 211 | 217 | 223 | 229 | 235 | 241 | 247 | 253 | 259 | 265 | 271 | 277 | 283 | 289 | 295
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 13 | 19 | 25 | 31 | 37 | 43 | 49 | 55 | 61 | 67 | 73 | 79 | 85 | 91 | 97 | 103 | 109 | 115 | 121 | 127 | 133 | 139 | 145 | 151 | 157 | 163 | 169 | 175 | 181 | 187 | 193 | 199 | 205 | 211 | 217 | 223 | 229 | 235 | 241 | 247 | 253 | 259 | 265 | 271 | 277 | 283 | 289 | 295 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 524.6 | 524.6 | 524.6 | 524.6 | 524.6 | 539.1 | 539.1 | 539.1 | 539.1 | 539.1 | 539.1 | 551.3 | 551.3 | 551.3 | 551.3 | 551.3 | 551.3 | 566 | 566 | 566 | 566 | 566 | 566 | 579.8 | 579.8 | 579.8 | 579.8 | 579.8 | 579.8 | 597.4 | 597.4 | 597.4 | 597.4 | 597.4 | 597.4 | 609.6 | 609.6 | 609.6 | 609.6 | 609.6 | 609.6 | 625.2069 | 625.2069 | 625.2069 | 625.2069 | 625.2069 | 625.2069 | 641.2133 | 641.2133 | 641.2133 | 641.2133 | 641.2133 | 641.2133
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 0.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 565.1216 | 57.1021 | 0.058244 | 0.49565 | 1.3042 | 2.4183 | 3.761 | 5.2974 | 6.9635 | 8.7092 | 10.4873 | 12.2552 | 13.9297 | 15.5578 | 17.0684 | 18.4344 | 19.6309 | 20.6386 | 21.3628 | 21.9419 | 22.2934 | 22.4092 | 22.2934 | 21.9419 | 21.2945 | 20.4992 | 19.4984 | 18.31 | 16.9532 | 15.4527 | 13.7821 | 12.0877 | 10.344 | 8.5902 | 6.8683 | 5.225 | 3.7001 | 2.3699 | 1.2781 | 0.48574 | 42.0277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 53.11 | 5.5416 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 7.62 | 6.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 8.97 | 6.279 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 32.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 705.1416 | 108.0297 | 1.3972 | 1.8346 | 2.6432 | 3.7572 | 5.1 | 6.6364 | 8.3024 | 10.0481 | 11.8263 | 13.5942 | 15.2687 | 16.8967 | 18.4073 | 19.7734 | 20.9699 | 21.9775 | 23.8447 | 23.2809 | 23.6324 | 24.0907 | 23.9749 | 23.6234 | 22.976 | 22.1807 | 21.1798 | 21.5581 | 20.2013 | 18.7008 | 17.5752 | 15.8809 | 14.1371 | 10.4741 | 10.0152 | 6.9519 | 5.882 | 3.5518 | 5.1 | 2.3526 | 57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 42938.798 | 4293.8798 | 4.3798 | 37.2709 | 98.0722 | 181.8458 | 283.9113 | 399.889 | 525.6568 | 657.4359 | 791.6626 | 925.1164 | 1054.7916 | 1178.0689 | 1292.4578 | 1395.8974 | 1486.4982 | 1562.8005 | 1623.4301 | 1667.4423 | 1694.1503 | 1702.9527 | 1694.1503 | 1667.4423 | 1623.4301 | 1562.8005 | 1486.4982 | 1395.8974 | 1292.4578 | 1178.0689 | 1054.7916 | 925.1164 | 791.6626 | 657.4359 | 525.6568 | 399.889 | 283.9113 | 181.8458 | 98.0722 | 37.2709 | 3224.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 7728.9836 | 772.8984 | 0.78836 | 6.7088 | 17.653 | 32.7322 | 51.104 | 71.98 | 94.6182 | 118.3385 | 142.4993 | 166.521 | 189.8625 | 212.0524 | 232.6424 | 251.2615 | 267.5697 | 281.3041 | 292.2174 | 300.1396 | 304.947 | 306.5315 | 304.947 | 300.1396 | 292.2174 | 281.3041 | 267.5697 | 251.2615 | 232.6424 | 212.0524 | 189.8625 | 166.521 | 142.4993 | 118.3385 | 94.6182 | 71.98 | 51.104 | 32.7322 | 17.653 | 6.7088 | 580.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 7728.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.8984 | 0.78836 | 6.7088 | 17.653 | 32.7322 | 51.104 | 71.98 | 94.6182 | 118.3385 | 142.4993 | 166.521 | 189.8625 | 212.0524 | 232.6424 | 251.2615 | 267.5697 | 281.3041 | 292.2174 | 300.1396 | 304.947 | 306.5315 | 304.947 | 300.1396 | 292.2174 | 281.3041 | 267.5697 | 251.2615 | 232.6424 | 212.0524 | 189.8625 | 166.521 | 142.4993 | 118.3385 | 94.6182 | 71.98 | 51.104 | 32.7322 | 17.653 | 6.7088 | 580.4621 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 772.8984 | 773.6867 | 780.3955 | 798.0485 | 830.7807 | 881.8848 | 953.8648 | 1048.483 | 1166.8215 | 536.4224 | 702.155 | 885.3087 | 1079.7081 | 1279.6183 | 1479.7757 | 1675.3654 | 1862.0513 | 2035.9302 | 2193.5706 | 2331.9967 | 2448.6657 | 2541.5603 | 2609.0575 | 2650.0134 | 2663.7478 | 2650.0134 | 2609.0575 | 2541.5603 | 2448.6657 | 2331.9967 | 2193.5706 | 2035.9302 | 1862.0513 | 1675.3654 | 1479.7757 | 1279.6183 | 1079.7081 | 885.3087 | 702.155 | 1116.0962 | 973.5969 | 855.2584 | 760.6402 | 688.6602 | 637.5561 | 604.8239 | 587.1709 | 580.4621 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.6492 | 0 | 0.019375 | 0.020041 | 0.019563 | 0.020672 | 0.020941 | 0.020078 | 0.024044 | 0.025576 | 0.029412 | 0.013085 | 0.017307 | 0.021822 | 0.025755 | 0.031541 | 0.035299 | 0.041296 | 0.044706 | 0.045727 | 0.052665 | 0.054183 | 0.05879 | 0.059052 | 0.06115 | 0.06211 | 0.060418 | 0.06211 | 0.059177 | 0.059568 | 0.0557 | 0.047912 | 0.049897 | 0.044817 | 0.042356 | 0.03688 | 0.032987 | 0.028525 | 0.023292 | 0.019735 | 0.015147 | 0.02488 | 0.028436 | 0.022562 | 0.022216 | 0.019465 | 0.018621 | 0.017095 | 0.016721 | 0.01653 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 524.6 | 539.1 | 551.3 | 566 | 579.8 | 597.4 | 609.6 | 625.2069 | 641.2133 | 657.6295 | 674.4661 | 691.7336 | 709.4433 | 727.6063 | 746.2343 | 765.3393 | 784.9334 | 805.0291 | 825.6393 | 846.7772 | 868.4562 | 890.6903 | 913.4936 | 936.8807 | 960.8665 | 985.4665 | 1010.6962 | 1036.5719 | 1063.11 | 1090.3276 | 1118.2419 | 1146.871 | 1176.233 | 1206.3467 | 1237.2314 | 1268.9067 | 1301.3931 | 1334.7111 | 1368.8821 | 1403.928 | 1439.8711 | 1476.7344 | 1514.5415 | 1553.3166 | 1593.0843 | 1633.8702 | 1675.7002 | 1718.6012 | 1762.6005 | 1807.7263 | 1854.0074 | 1901.4734 | 1950.1546 | 2000.0821 | 2051.2878 | 2103.8045 | 2157.6658
|  | KCR per USD, period average | KCR/USD |  |  | 524.6 | 539.1 | 551.3 | 566 | 579.8 | 597.4 | 609.6 | 625.2069 | 641.2133 | 657.6295 | 674.4661 | 691.7336 | 709.4433 | 727.6063 | 746.2343 | 765.3393 | 784.9334 | 805.0291 | 825.6393 | 846.7772 | 868.4562 | 890.6903 | 913.4936 | 936.8807 | 960.8665 | 985.4665 | 1010.6962 | 1036.5719 | 1063.11 | 1090.3276 | 1118.2419 | 1146.871 | 1176.233 | 1206.3467 | 1237.2314 | 1268.9067 | 1301.3931 | 1334.7111 | 1368.8821 | 1403.928 | 1439.8711 | 1476.7344 | 1514.5415 | 1553.3166 | 1593.0843 | 1633.8702 | 1675.7002 | 1718.6012 | 1762.6005 | 1807.7263 | 1854.0074 | 1901.4734 | 1950.1546 | 2000.0821 | 2051.2878 | 2103.8045 | 2157.6658
|  | US CPI change, current year | % |  |  | 2.4 | 1.8 | 1.8 | 1.2 | 1.2 | 4.7 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, current year | % |  |  | 7.6 | 7.9 | 7.9 | 9.8 | 9.8 | 10.6 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI change, prior year | % |  |  | 2.1 | 2.4 | 2.4 | 1.8 | 1.8 | 1.2 | 1.2 | 4.7 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.6 | 7.6 | 7.9 | 7.9 | 9.8 | 9.8 | 10.6 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US index, June 2018 (2018 price base) | index | 103.4292
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 104.0443 | 105.1308 | 106.0728 | 106.8651 | 107.5044 | 109.0707 | 111.6044 | 113.5091 | 114.751 | 116.0063 | 117.2755 | 118.5585 | 119.8555 | 121.1668 | 122.4924 | 123.8324 | 125.1872 | 126.5568 | 127.9413 | 129.341 | 130.756 | 132.1865 | 133.6326 | 135.0946 | 136.5726 | 138.0667 | 139.5772 | 141.1042 | 142.6479 | 144.2084 | 145.7861 | 147.381 | 148.9934 | 150.6234 | 152.2713 | 153.9371 | 155.6212 | 157.3237 | 159.0449 | 160.7849 | 162.5439 | 164.3221 | 166.1198 | 167.9372 | 169.7745 | 171.6318 | 173.5095 | 175.4077 | 177.3267 | 179.2667 | 181.2279 | 183.2106 | 185.2149 | 187.2412 | 189.2897 | 191.3605 | 193.454
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 102.8178 | 104.0443 | 105.1308 | 106.0728 | 106.8651 | 107.5044 | 109.0707 | 111.6044 | 113.5091 | 114.751 | 116.0063 | 117.2755 | 118.5585 | 119.8555 | 121.1668 | 122.4924 | 123.8324 | 125.1872 | 126.5568 | 127.9413 | 129.341 | 130.756 | 132.1865 | 133.6326 | 135.0946 | 136.5726 | 138.0667 | 139.5772 | 141.1042 | 142.6479 | 144.2084 | 145.7861 | 147.381 | 148.9934 | 150.6234 | 152.2713 | 153.9371 | 155.6212 | 157.3237 | 159.0449 | 160.7849 | 162.5439 | 164.3221 | 166.1198 | 167.9372 | 169.7745 | 171.6318 | 173.5095 | 175.4077 | 177.3267 | 179.2667 | 181.2279 | 183.2106 | 185.2149 | 187.2412 | 189.2897 | 191.3605
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0059 | 1.0165 | 1.0256 | 1.0332 | 1.0394 | 1.0545 | 1.079 | 1.0975 | 1.1095 | 1.1216 | 1.1339 | 1.1463 | 1.1588 | 1.1715 | 1.1843 | 1.1973 | 1.2104 | 1.2236 | 1.237 | 1.2505 | 1.2642 | 1.278 | 1.292 | 1.3062 | 1.3204 | 1.3349 | 1.3495 | 1.3643 | 1.3792 | 1.3943 | 1.4095 | 1.4249 | 1.4405 | 1.4563 | 1.4722 | 1.4883 | 1.5046 | 1.5211 | 1.5377 | 1.5545 | 1.5715 | 1.5887 | 1.6061 | 1.6237 | 1.6415 | 1.6594 | 1.6776 | 1.6959 | 1.7145 | 1.7332 | 1.7522 | 1.7714 | 1.7907 | 1.8103 | 1.8301 | 1.8502 | 1.8704
|  | KC index, June 2018 (2018 price base) | index | 112.9752
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 115.0632 | 119.4386 | 124.0668 | 129.4379 | 135.6321 | 142.381 | 149.7371 | 156.3581 | 162.1155 | 168.085 | 174.2742 | 180.6914 | 187.3448 | 194.2432 | 201.3956 | 208.8114 | 216.5003 | 224.4723 | 232.7378 | 241.3077 | 250.1932 | 259.4058 | 268.9577 | 278.8612 | 289.1295 | 299.7758 | 310.8142 | 322.259 | 334.1253 | 346.4284 | 359.1847 | 372.4106 | 386.1235 | 400.3414 | 415.0828 | 430.367 | 446.214 | 462.6445 | 479.68 | 497.3428 | 515.656 | 534.6435 | 554.3302 | 574.7418 | 595.905 | 617.8474 | 640.5979 | 664.186 | 688.6427 | 714 | 740.2909 | 767.55 | 795.8127 | 825.1162 | 855.4987 | 886.9999 | 919.6611
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 110.9252 | 115.0632 | 119.4386 | 124.0668 | 129.4379 | 135.6321 | 142.381 | 149.7371 | 156.3581 | 162.1155 | 168.085 | 174.2742 | 180.6914 | 187.3448 | 194.2432 | 201.3956 | 208.8114 | 216.5003 | 224.4723 | 232.7378 | 241.3077 | 250.1932 | 259.4058 | 268.9577 | 278.8612 | 289.1295 | 299.7758 | 310.8142 | 322.259 | 334.1253 | 346.4284 | 359.1847 | 372.4106 | 386.1235 | 400.3414 | 415.0828 | 430.367 | 446.214 | 462.6445 | 479.68 | 497.3428 | 515.656 | 534.6435 | 554.3302 | 574.7418 | 595.905 | 617.8474 | 640.5979 | 664.186 | 688.6427 | 714 | 740.2909 | 767.55 | 795.8127 | 825.1162 | 855.4987 | 886.9999
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0185 | 1.0572 | 1.0982 | 1.1457 | 1.2005 | 1.2603 | 1.3254 | 1.384 | 1.435 | 1.4878 | 1.5426 | 1.5994 | 1.6583 | 1.7193 | 1.7827 | 1.8483 | 1.9164 | 1.9869 | 2.0601 | 2.1359 | 2.2146 | 2.2961 | 2.3807 | 2.4683 | 2.5592 | 2.6535 | 2.7512 | 2.8525 | 2.9575 | 3.0664 | 3.1793 | 3.2964 | 3.4178 | 3.5436 | 3.6741 | 3.8094 | 3.9497 | 4.0951 | 4.2459 | 4.4022 | 4.5643 | 4.7324 | 4.9067 | 5.0873 | 5.2747 | 5.4689 | 5.6703 | 5.879 | 6.0955 | 6.32 | 6.5527 | 6.794 | 7.0441 | 7.3035 | 7.5724 | 7.8513 | 8.1404
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.8
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.8
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 0.33333 | 0.83333 | 1.3333 | 1.8333 | 2.3333 | 2.8333 | 3.3333 | 3.8333 | 4.3333 | 4.8333 | 5.3333 | 5.8333 | 6.3333 | 6.8333 | 7.3333 | 7.8333 | 8.3333 | 8.8333 | 9.3333 | 9.8333 | 10.3333 | 10.8333 | 11.3333 | 11.8333 | 12.3333 | 12.8333 | 13.3333 | 13.8333 | 14.3333 | 14.8333 | 15.3333 | 15.8333 | 16.3333 | 16.8333 | 17.3333 | 17.8333 | 18.3333 | 18.8333 | 19.3333 | 19.8333 | 20.3333 | 20.8333 | 21.3333 | 21.8333 | 22.3333 | 22.8333 | 23.3333 | 23.8333 | 24.3333 | 24.7917
|  | Contracted capacity | MW | 581.9
|  | Plant net heat rate, new and clean | kJ/kWh | 6286
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98994 | 0.9895 | 0.98876 | 0.98802 | 0.98728 | 0.98654 | 0.98579 | 0.98505 | 0.98431 | 0.98357 | 0.98282 | 0.98208 | 0.98134 | 0.98059 | 0.97985 | 0.97911 | 0.97837 | 0.97762 | 0.97688 | 0.97614 | 0.9754 | 0.97466 | 0.97391 | 0.97317 | 0.97243 | 0.97169 | 0.97094 | 0.9702 | 0.96946 | 0.96871 | 0.96797 | 0.96723 | 0.96649 | 0.96574 | 0.965 | 0.96426 | 0.96352 | 0.96278 | 0.96203 | 0.96129 | 0.96055 | 0.95981 | 0.95906 | 0.95832 | 0.95758 | 0.95683 | 0.95609 | 0.95535 | 0.95461 | 0.95386 | 0.95318
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 301747.4031 | 1809692.2823 | 1805442.5415 | 1789638.6594 | 1791181.1901 | 1804260.4896 | 1792651.4964 | 1740084.6497 | 1749008.6309 | 1798828.6968 | 1794596.3284 | 1778879.3087 | 1780404.467 | 1793396.9041 | 1775799.7969 | 1693319.8868 | 1708250.3196 | 1787965.1113 | 1783750.1154 | 1768119.9581 | 1769627.7438 | 1782533.3186 | 1771047.863 | 1719098.7042 | 1727899.1478 | 1777101.5258 | 1772903.9024 | 1757360.6074 | 1758851.0207 | 1771669.7331 | 1754269.5139 | 1672774.0439 | 1687507.5887 | 1766237.9403 | 1762057.6894 | 1746601.2568 | 1748074.2976 | 1760806.1476 | 1749444.2296 | 1698112.7587 | 1706789.6647 | 1755374.3549 | 1751211.4764 | 1735841.9061 | 1737297.5745 | 1749942.5621 | 1732739.231 | 1652228.201 | 1666764.8578 | 1744510.7694 | 1452721.6529
|  | Plant net heat rate | kJ/kWh |  |  | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.3467 | 6484.6154 | 6488.5046 | 6492.3939 | 6496.2831 | 6500.1723 | 6504.0615 | 6507.9507 | 6511.8399 | 6515.7291 | 6519.6184 | 6523.5076 | 6527.3968 | 6531.286 | 6535.1752 | 6539.0644 | 6542.9536 | 6546.8429 | 6550.7321 | 6554.6213 | 6558.5105 | 6562.3997 | 6566.2889 | 6570.1781 | 6574.0673 | 6577.9566 | 6581.8458 | 6585.735 | 6589.6242 | 6593.5134 | 6597.4026 | 6601.2918 | 6605.1811 | 6609.0703 | 6612.9595 | 6616.8487 | 6620.7379 | 6624.6271 | 6628.5163 | 6632.4055 | 6636.2948 | 6640.184 | 6644.0732 | 6647.9624 | 6651.8516 | 6655.7408 | 6659.63 | 6663.5193 | 6667.4085 | 6671.2977 | 6674.8628
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.6985 | 6470.5851 | 6473.8194 | 6477.0536 | 6480.2878 | 6483.522 | 6486.7562 | 6489.9904 | 6493.2246 | 6496.4589 | 6499.6931 | 6502.9273 | 6506.1615 | 6509.3957 | 6512.6299 | 6515.8641 | 6519.0984 | 6522.3326 | 6525.5668 | 6528.801 | 6532.0352 | 6535.2694 | 6538.5036 | 6541.7379 | 6544.9721 | 6548.2063 | 6551.4405 | 6554.6747 | 6557.9089 | 6561.1431 | 6564.3774 | 6567.6116 | 6570.8458 | 6574.08 | 6577.3142 | 6580.5484 | 6583.7827 | 6587.0169 | 6590.2511 | 6593.4853 | 6596.7195 | 6599.9537 | 6603.1879 | 6606.4222 | 6609.6564 | 6612.8906 | 6616.1248 | 6619.359 | 6622.5932 | 6625.8274 | 6628.7921
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2054187.3321 | 12324043.104 | 12302476.3899 | 12202096.6291 | 12219929.7596 | 12316529.6145 | 12244604.3289 | 11892656.6309 | 11960791.4414 | 12308838.6409 | 12287207.6409 | 12186862.27 | 12204582.77 | 12300970.1834 | 12187524.0681 | 11628370.8488 | 11737878.2986 | 12292924.2419 | 12271230.0912 | 12170924.7866 | 12188531.521 | 12284700.8163 | 12212780.0299 | 11861570.8184 | 11929350.1984 | 12276299.9068 | 12254543.7408 | 12154284.179 | 12171776.0123 | 12267721.5132 | 12154400.8162 | 11596594.2741 | 11705627.771 | 12258965.6357 | 12237148.5896 | 12136940.4471 | 12154316.2441 | 12250032.2741 | 12178132.1332 | 11827742.14 | 11895149.9431 | 12240921.4285 | 12219044.6377 | 12118893.591 | 12136152.2164 | 12231633.0989 | 12118463.5534 | 11562132.355 | 11670666.1657 | 12222167.2854 | 10183310.866
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1795520 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 8861760
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4409 | 14.4762 | 14.5074 | 14.5344 | 14.5572 | 14.5755 | 14.6205 | 14.6933 | 14.748 | 14.7836 | 14.8197 | 14.8562 | 14.893 | 14.9303 | 14.9679 | 15.006 | 15.0445 | 15.0834 | 15.1227 | 15.1625 | 15.2027 | 15.2433 | 15.2844 | 15.3259 | 15.3679 | 15.4104 | 15.4533 | 15.4967 | 15.5405 | 15.5848 | 15.6297 | 15.675 | 15.7208 | 15.7671 | 15.8139 | 15.8612 | 15.9091 | 15.9574 | 16.0063 | 16.0558 | 16.1057 | 16.1563 | 16.2073 | 16.259 | 16.3112 | 16.3639 | 16.4173 | 16.4712 | 16.5257 | 16.5808 | 16.6365 | 16.6929 | 16.7498 | 16.8074 | 16.8656 | 16.9244 | 16.9839
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3307 | 2.3564 | 2.385 | 2.4088 | 2.4366 | 2.4611 | 2.51 | 2.5704 | 2.6153 | 2.6439 | 2.6729 | 2.7021 | 2.7317 | 2.7616 | 2.7918 | 2.8223 | 2.8532 | 2.8844 | 2.916 | 2.9479 | 2.9801 | 3.0127 | 3.0457 | 3.079 | 3.1127 | 3.1467 | 3.1812 | 3.216 | 3.2511 | 3.2867 | 3.3227 | 3.359 | 3.3958 | 3.4329 | 3.4705 | 3.5084 | 3.5468 | 3.5856 | 3.6249 | 3.6645 | 3.7046 | 3.7451 | 3.7861 | 3.8275 | 3.8694 | 3.9117 | 3.9545 | 3.9978 | 4.0415 | 4.0857 | 4.1304 | 4.1756 | 4.2213 | 4.2675 | 4.3142 | 4.3614 | 4.4091
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1
|  | Capacity payment | USD m |  | 3339.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9683 | 60.2745 | 60.6223 | 60.8467 | 61.0736 | 61.3029 | 61.5348 | 61.7692 | 62.0062 | 62.2457 | 62.4879 | 62.7327 | 62.9802 | 63.2304 | 63.4834 | 62.8184 | 63.6776 | 64.259 | 64.5232 | 64.7902 | 65.0603 | 65.3332 | 65.6092 | 65.8882 | 66.1702 | 66.4553 | 66.7435 | 67.0349 | 67.3295 | 67.6273 | 67.9283 | 67.2471 | 68.1976 | 68.8514 | 69.1658 | 69.4837 | 69.8051 | 70.13 | 70.4584 | 70.7904 | 71.1261 | 71.4654 | 71.8084 | 72.1552 | 72.5058 | 72.8602 | 73.2185 | 72.5179 | 73.5772 | 74.3171 | 62.2428
|  | VOM charge, indexed | USD/MWh |  |  | 3.9102 | 3.954 | 4.0006 | 4.0397 | 4.0828 | 4.1203 | 4.1976 | 4.2978 | 4.3726 | 4.4204 | 4.4688 | 4.5177 | 4.5671 | 4.6171 | 4.6676 | 4.7186 | 4.7703 | 4.8224 | 4.8752 | 4.9285 | 4.9825 | 5.037 | 5.0921 | 5.1478 | 5.2041 | 5.261 | 5.3186 | 5.3768 | 5.4356 | 5.4951 | 5.5552 | 5.6159 | 5.6774 | 5.7395 | 5.8023 | 5.8658 | 5.9299 | 5.9948 | 6.0604 | 6.1267 | 6.1937 | 6.2615 | 6.33 | 6.3992 | 6.4692 | 6.54 | 6.6116 | 6.6839 | 6.757 | 6.8309 | 6.9057 | 6.9812 | 7.0576 | 7.1348 | 7.2129 | 7.2918 | 7.3716
|  | Variable O&M payment | USD m |  | 499.2739 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2666 | 7.7778 | 7.8944 | 7.9109 | 8.0044 | 8.151 | 8.1872 | 8.0341 | 8.1636 | 8.488 | 8.5607 | 8.5785 | 8.6798 | 8.8388 | 8.8478 | 8.5292 | 8.6985 | 9.204 | 9.2828 | 9.3021 | 9.4119 | 9.5843 | 9.6267 | 9.4465 | 9.5988 | 9.9801 | 10.0655 | 10.0864 | 10.2054 | 10.3922 | 10.4027 | 10.028 | 10.227 | 10.8212 | 10.9137 | 10.9363 | 11.0653 | 11.2678 | 11.3176 | 11.1057 | 11.2846 | 11.7328 | 11.833 | 11.8574 | 11.9972 | 12.2167 | 12.229 | 11.7883 | 12.0222 | 12.7206 | 10.7088
|  | Fuel charge (pass-through) | USD m |  | 4888.8555 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7474 | 78.0029 | 77.8586 | 78.76 | 78.8672 | 81.0724 | 80.591 | 79.8321 | 80.2815 | 84.2616 | 84.1052 | 85.0783 | 85.1936 | 87.5751 | 86.7589 | 84.4257 | 85.2124 | 91.0177 | 90.8482 | 91.8987 | 92.0226 | 94.5944 | 94.0314 | 93.1448 | 93.6679 | 98.3103 | 98.1266 | 99.2606 | 99.3938 | 102.1709 | 101.2173 | 98.494 | 99.4105 | 106.1817 | 105.9825 | 107.2066 | 107.3497 | 110.3484 | 109.6902 | 108.6544 | 109.2632 | 114.6771 | 114.4612 | 115.7824 | 115.9363 | 119.174 | 118.0601 | 114.8821 | 115.9495 | 123.8456 | 103.1771
|  | GTA reservation charge (pass-through) | USD m |  | 696.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9395 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 16.4303 | 13.8886
|  | GTA commodity charge (pass-through) | USD m |  | 146.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40812 | 2.4853 | 2.4809 | 2.4976 | 2.5012 | 2.5588 | 2.5439 | 2.5078 | 2.5222 | 2.6345 | 2.6299 | 2.6475 | 2.6514 | 2.7124 | 2.6874 | 2.6025 | 2.6271 | 2.7926 | 2.7876 | 2.8063 | 2.8104 | 2.875 | 2.8582 | 2.8176 | 2.8337 | 2.9599 | 2.9547 | 2.9744 | 2.9787 | 3.0472 | 3.0191 | 2.9237 | 2.9512 | 3.1371 | 3.1315 | 3.1525 | 3.157 | 3.2296 | 3.2106 | 3.165 | 3.183 | 3.3247 | 3.3188 | 3.3409 | 3.3457 | 3.4226 | 3.3909 | 3.2838 | 3.3146 | 3.5233 | 2.9356
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 3839.0052 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2349 | 68.0522 | 68.5167 | 68.7576 | 69.078 | 69.454 | 69.722 | 69.8033 | 70.1698 | 70.7337 | 71.0486 | 71.3112 | 71.66 | 72.0692 | 72.3312 | 71.3476 | 72.3761 | 73.463 | 73.8059 | 74.0924 | 74.4722 | 74.9175 | 75.2359 | 75.3347 | 75.769 | 76.4354 | 76.809 | 77.1213 | 77.5348 | 78.0195 | 78.331 | 77.2751 | 78.4246 | 79.6726 | 80.0795 | 80.42 | 80.8704 | 81.3978 | 81.776 | 81.8961 | 82.4106 | 83.1981 | 83.6414 | 84.0127 | 84.503 | 85.077 | 85.4475 | 84.3063 | 85.5994 | 87.0377 | 72.9516
|  | Total revenue | USD m |  | 9570.9009 | 0 | 0 | 0 | 0 | 0 | 0 | 26.3299 | 160.0341 | 160.5405 | 161.6814 | 162.3059 | 164.9918 | 164.8942 | 164.1619 | 165.1914 | 169.8289 | 170.1849 | 171.4191 | 172.0923 | 174.9939 | 174.5536 | 171.1322 | 173.1833 | 180.2209 | 180.604 | 181.9392 | 182.6648 | 185.7996 | 185.6855 | 184.8361 | 186.034 | 191.4478 | 191.8601 | 193.3046 | 194.0868 | 197.4733 | 196.9596 | 193.0627 | 195.3943 | 203.5768 | 204.0207 | 205.5832 | 206.4266 | 210.085 | 209.9521 | 208.9672 | 210.3613 | 216.6803 | 217.1584 | 218.8487 | 219.758 | 223.71 | 223.1112 | 218.6597 | 221.3193 | 230.837 | 192.953
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 290.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72247 | 4.4105 | 4.4587 | 4.5075 | 4.5568 | 4.6067 | 4.6571 | 4.708 | 4.7595 | 4.8116 | 4.8642 | 4.9174 | 4.9712 | 5.0256 | 5.0806 | 5.1362 | 5.1924 | 5.2492 | 5.3066 | 5.3647 | 5.4234 | 5.4827 | 5.5427 | 5.6033 | 5.6646 | 5.7266 | 5.7892 | 5.8526 | 5.9166 | 5.9813 | 6.0468 | 6.1129 | 6.1798 | 6.2474 | 6.3158 | 6.3848 | 6.4547 | 6.5253 | 6.5967 | 6.6689 | 6.7418 | 6.8156 | 6.8902 | 6.9655 | 7.0417 | 7.1188 | 7.1967 | 7.2754 | 7.355 | 7.4354 | 6.264
|  | O&M availability incentive | USD m |  | 4.2077 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032371 | 0.19754 | 0.18306 | 0.10094 | 0.11906 | 0.20633 | 0.14678 | -0.16401 | -0.10264 | 0.21551 | 0.19971 | 0.11012 | 0.12988 | 0.22509 | 0.1201 | -0.38341 | -0.31655 | 0.23511 | 0.21787 | 0.12014 | 0.1417 | 0.24557 | 0.1747 | -0.1952 | -0.12216 | 0.25649 | 0.23769 | 0.13107 | 0.15458 | 0.2679 | 0.14294 | -0.45632 | -0.37674 | 0.27982 | 0.25931 | 0.14299 | 0.16864 | 0.29226 | 0.20792 | -0.23232 | -0.14539 | 0.30527 | 0.28289 | 0.15599 | 0.18398 | 0.31885 | 0.17012 | -0.5431 | -0.44838 | 0.33303 | 0.28056
|  | LTSA fixed fee | USD m |  | 95.5554 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23739 | 1.4486 | 1.4645 | 1.4805 | 1.4967 | 1.5131 | 1.5296 | 1.5464 | 1.5633 | 1.5804 | 1.5977 | 1.6152 | 1.6328 | 1.6507 | 1.6688 | 1.687 | 1.7055 | 1.7241 | 1.743 | 1.7621 | 1.7813 | 1.8008 | 1.8205 | 1.8404 | 1.8606 | 1.8809 | 1.9015 | 1.9223 | 1.9433 | 1.9646 | 1.9861 | 2.0078 | 2.0298 | 2.052 | 2.0744 | 2.0971 | 2.1201 | 2.1433 | 2.1667 | 2.1904 | 2.2144 | 2.2386 | 2.2631 | 2.2879 | 2.3129 | 2.3382 | 2.3638 | 2.3896 | 2.4158 | 2.4422 | 2.0574
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1406.5 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 7032.5
|  | LTSA variable fee | USD m |  | 296.8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73759 | 4.5011 | 4.5503 | 4.6001 | 4.6504 | 4.7013 | 4.7527 | 4.8047 | 4.8573 | 4.9104 | 4.9641 | 5.0184 | 5.0734 | 5.1289 | 5.185 | 5.2417 | 5.299 | 5.357 | 5.4156 | 5.4749 | 5.5348 | 5.5953 | 5.6565 | 5.7184 | 5.781 | 5.8442 | 5.9081 | 5.9728 | 6.0381 | 6.1042 | 6.171 | 6.2385 | 6.3067 | 6.3757 | 6.4455 | 6.516 | 6.5873 | 6.6593 | 6.7322 | 6.8058 | 6.8803 | 6.9556 | 7.0317 | 7.1086 | 7.1864 | 7.265 | 7.3445 | 7.4248 | 7.506 | 7.5882 | 6.3926
|  | Operational insurance | USD m |  | 158.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39295 | 2.3979 | 2.4242 | 2.4507 | 2.4775 | 2.5046 | 2.532 | 2.5597 | 2.5877 | 2.616 | 2.6446 | 2.6736 | 2.7028 | 2.7324 | 2.7623 | 2.7925 | 2.8231 | 2.8539 | 2.8852 | 2.9167 | 2.9486 | 2.9809 | 3.0135 | 3.0465 | 3.0798 | 3.1135 | 3.1476 | 3.182 | 3.2168 | 3.252 | 3.2876 | 3.3236 | 3.3599 | 3.3967 | 3.4338 | 3.4714 | 3.5094 | 3.5478 | 3.5866 | 3.6258 | 3.6655 | 3.7056 | 3.7461 | 3.7871 | 3.8285 | 3.8704 | 3.9128 | 3.9556 | 3.9989 | 4.0426 | 3.4057
|  | G&A | USD m |  | 117.5427 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29185 | 1.782 | 1.8015 | 1.8212 | 1.8411 | 1.8612 | 1.8816 | 1.9022 | 1.923 | 1.944 | 1.9653 | 1.9868 | 2.0085 | 2.0305 | 2.0527 | 2.0752 | 2.0979 | 2.1208 | 2.1441 | 2.1675 | 2.1912 | 2.2152 | 2.2394 | 2.2639 | 2.2887 | 2.3137 | 2.339 | 2.3646 | 2.3905 | 2.4167 | 2.4431 | 2.4698 | 2.4968 | 2.5242 | 2.5518 | 2.5797 | 2.6079 | 2.6364 | 2.6653 | 2.6944 | 2.7239 | 2.7537 | 2.7839 | 2.8143 | 2.8451 | 2.8762 | 2.9077 | 2.9395 | 2.9717 | 3.0042 | 2.5309
|  | Land lease and permits | USD m |  | 26.8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066676 | 0.40732 | 0.41177 | 0.41628 | 0.42083 | 0.42543 | 0.43009 | 0.43479 | 0.43955 | 0.44436 | 0.44922 | 0.45414 | 0.4591 | 0.46413 | 0.4692 | 0.47434 | 0.47953 | 0.48477 | 0.49008 | 0.49544 | 0.50086 | 0.50634 | 0.51188 | 0.51748 | 0.52314 | 0.52886 | 0.53465 | 0.5405 | 0.54641 | 0.55239 | 0.55843 | 0.56454 | 0.57072 | 0.57696 | 0.58327 | 0.58965 | 0.5961 | 0.60263 | 0.60922 | 0.61588 | 0.62262 | 0.62943 | 0.63632 | 0.64328 | 0.65032 | 0.65743 | 0.66462 | 0.6719 | 0.67925 | 0.68668 | 0.57849
|  | Community fund and OREK levy | USD m |  | 21.1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061792 | 0.37429 | 0.37684 | 0.37817 | 0.37993 | 0.382 | 0.38347 | 0.38392 | 0.38593 | 0.38904 | 0.39077 | 0.39221 | 0.39413 | 0.39638 | 0.39782 | 0.39241 | 0.39807 | 0.40405 | 0.40593 | 0.40751 | 0.4096 | 0.41205 | 0.4138 | 0.41434 | 0.41673 | 0.42039 | 0.42245 | 0.42417 | 0.42644 | 0.42911 | 0.43082 | 0.42501 | 0.43134 | 0.4382 | 0.44044 | 0.44231 | 0.44479 | 0.44769 | 0.44977 | 0.45043 | 0.45326 | 0.45759 | 0.46003 | 0.46207 | 0.46477 | 0.46792 | 0.46996 | 0.46368 | 0.4708 | 0.47871 | 0.40123
|  | Variable consumables | USD m |  | 138.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35601 | 2.1723 | 2.1909 | 2.1954 | 2.2214 | 2.2621 | 2.2721 | 2.2296 | 2.2656 | 2.3556 | 2.3758 | 2.3807 | 2.4088 | 2.4529 | 2.4554 | 2.367 | 2.414 | 2.5543 | 2.5762 | 2.5815 | 2.612 | 2.6598 | 2.6716 | 2.6216 | 2.6638 | 2.7697 | 2.7934 | 2.7992 | 2.8322 | 2.884 | 2.887 | 2.783 | 2.8382 | 3.0031 | 3.0288 | 3.035 | 3.0708 | 3.127 | 3.1408 | 3.082 | 3.1317 | 3.2561 | 3.2839 | 3.2907 | 3.3295 | 3.3904 | 3.3938 | 3.2715 | 3.3364 | 3.5302 | 2.9719
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02125 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.10625
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025937 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.12969
|  | Operating costs before pass-through items | USD m |  | 1164.0153 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9463 | 17.9746 | 18.1448 | 18.2339 | 18.4469 | 18.7459 | 18.8686 | 18.6885 | 18.9623 | 19.5501 | 19.7346 | 19.8318 | 20.0639 | 20.3898 | 20.4751 | 20.0661 | 20.376 | 21.2665 | 21.4676 | 21.5736 | 21.8266 | 22.1818 | 22.3278 | 22.1139 | 22.4393 | 23.1375 | 23.3568 | 23.4723 | 23.7481 | 24.1353 | 24.2368 | 23.7519 | 24.1197 | 25.1771 | 25.4162 | 25.5422 | 25.8428 | 26.2649 | 26.4384 | 26.1846 | 26.5712 | 27.4006 | 27.6611 | 27.7985 | 28.1263 | 28.5863 | 28.707 | 28.132 | 28.5685 | 29.8243 | 25.1188
|  | Gas purchases | USD m |  | 4912.1191 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7743 | 78.1721 | 78.0353 | 78.9465 | 79.0619 | 81.2806 | 80.806 | 80.053 | 80.5117 | 84.5116 | 84.363 | 85.3476 | 85.4717 | 87.8696 | 87.0592 | 84.7263 | 85.5242 | 91.3597 | 91.1985 | 92.2621 | 92.3956 | 94.9871 | 94.431 | 93.5497 | 94.0843 | 98.757 | 98.582 | 99.7309 | 99.8745 | 102.675 | 101.7265 | 98.9991 | 99.9299 | 106.7468 | 106.5568 | 107.7979 | 107.9523 | 110.9784 | 110.3271 | 109.2958 | 109.9187 | 115.3761 | 115.1699 | 116.5105 | 116.6764 | 119.9462 | 118.8364 | 115.6485 | 116.7341 | 124.6955 | 103.8942
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5755.1594 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1219 | 92.1511 | 92.2004 | 93.1102 | 93.4226 | 95.746 | 95.3872 | 94.5796 | 95.2518 | 99.3451 | 99.3942 | 100.3771 | 100.7103 | 103.2192 | 102.5227 | 100.0852 | 101.119 | 107.0999 | 107.1484 | 108.2103 | 108.5656 | 111.2748 | 110.8492 | 109.9064 | 110.6815 | 115.459 | 115.5065 | 116.6537 | 117.0326 | 119.9579 | 119.1378 | 116.2927 | 117.4892 | 124.4693 | 124.5155 | 125.7546 | 126.1588 | 129.3173 | 128.813 | 127.7124 | 128.6061 | 134.1812 | 134.2257 | 135.564 | 135.9951 | 139.4052 | 138.44 | 135.1199 | 136.5046 | 144.6491 | 120.7184
|  | VAT facility interest after the funding period | USD m |  | 0.16165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12839 | 0.033251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 52.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1438 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
|  | Handback reserve contribution required | USD m |  | 19.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25306 | 1.535 | 1.5518 | 1.5687 | 1.5859 | 1.6032 | 1.6208 | 1.6385 | 1.6564 | 1.6746 | 1.6929 | 1.7114 | 1.4418
|  | Handback works at PPA expiry | USD m |  | 19.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.5339
|  | Total operating costs | USD m |  | 6991.7326 | 0 | 0 | 0 | 0 | 0 | 0 | 18.0682 | 110.2541 | 110.3785 | 111.3442 | 111.8695 | 114.4919 | 114.2559 | 115.8219 | 114.2142 | 118.8952 | 119.1287 | 120.2089 | 120.7742 | 123.609 | 122.9977 | 132.2543 | 121.495 | 128.3664 | 128.616 | 129.7838 | 130.3922 | 133.4566 | 133.177 | 135.0598 | 133.1208 | 138.5965 | 138.8633 | 140.126 | 140.7808 | 144.0933 | 143.3745 | 154.4492 | 141.6089 | 149.6465 | 149.9317 | 151.2968 | 152.0016 | 155.5822 | 155.2513 | 157.5145 | 155.1774 | 161.5818 | 161.8868 | 163.3625 | 164.1214 | 167.9915 | 167.147 | 180.3957 | 165.0731 | 174.4734 | 165.3711
|  | EBITDA | USD m |  | 2579.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2617 | 49.7801 | 50.162 | 50.3372 | 50.4364 | 50.4999 | 50.6384 | 48.34 | 50.9773 | 50.9337 | 51.0561 | 51.2102 | 51.3181 | 51.385 | 51.5558 | 38.8779 | 51.6883 | 51.8545 | 51.988 | 52.1554 | 52.2726 | 52.343 | 52.5085 | 49.7763 | 52.9132 | 52.8512 | 52.9968 | 53.1786 | 53.306 | 53.3801 | 53.585 | 38.6135 | 53.7855 | 53.9303 | 54.089 | 54.2865 | 54.425 | 54.5028 | 54.7007 | 51.4526 | 55.1839 | 55.0986 | 55.2716 | 55.4861 | 55.6366 | 55.7185 | 55.9643 | 38.264 | 56.2463 | 56.3635 | 27.5819
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.2208 | 39.7875 | 39.2626 | 40.197 | 39.6944 | 40.7947 | 40.3274 | 40.8137 | 40.4001 | 42.2226 | 41.6213 | 42.618 | 42.0878 | 43.2677 | 42.6897 | 42.5467 | 42.3546 | 44.8063 | 44.1694 | 45.2335 | 44.6735 | 45.9395 | 45.4122 | 45.9537 | 45.4975 | 47.5975 | 46.9223 | 48.0591 | 47.4669 | 48.8258 | 48.1695 | 47.999 | 47.7867 | 50.613 | 49.8964 | 51.1119 | 50.4848 | 51.9441 | 51.347 | 51.9532 | 51.4471 | 53.8708 | 53.1094 | 54.4099 | 53.7452 | 55.3129 | 54.5652 | 54.3629 | 54.127 | 57.3904 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18.5434 | 19.435 | 19.0847 | 19.6276 | 19.3358 | 20.0969 | 19.7623 | 19.9027 | 19.6903 | 21.0112 | 20.6323 | 21.219 | 20.9034 | 21.726 | 21.2917 | 21.0646 | 20.9162 | 22.7137 | 22.304 | 22.9381 | 22.5967 | 23.4858 | 23.0945 | 23.2582 | 23.0097 | 24.5528 | 24.1097 | 24.795 | 24.4258 | 25.3867 | 24.8788 | 24.613 | 24.4394 | 26.5393 | 26.0601 | 26.8006 | 26.4014 | 27.4397 | 26.9822 | 27.173 | 26.8823 | 28.6847 | 28.1666 | 28.9667 | 28.535 | 29.657 | 29.0633 | 28.7524 | 28.5491 | 31.0016 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.2718 | 2.317 | 2.3095 | 2.3476 | 2.3414 | 2.3844 | 2.3774 | 2.4077 | 2.4033 | 2.4586 | 2.4507 | 2.4911 | 2.4846 | 2.5302 | 2.5212 | 2.5457 | 2.5426 | 2.6089 | 2.6005 | 2.6433 | 2.6364 | 2.6848 | 2.6769 | 2.7111 | 2.7061 | 2.7683 | 2.7594 | 2.8049 | 2.7975 | 2.8488 | 2.8388 | 2.8663 | 2.8629 | 2.9374 | 2.928 | 2.9762 | 2.9685 | 3.0229 | 3.014 | 3.0525 | 3.0469 | 3.1169 | 3.1069 | 3.158 | 3.1498 | 3.2075 | 3.1962 | 3.2273 | 3.2234 | 3.3072 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.674 | 1.7499 | 1.7375 | 1.7717 | 1.7646 | 1.8177 | 1.8075 | 1.8058 | 1.8061 | 1.909 | 1.8955 | 1.9328 | 1.9251 | 1.983 | 1.9654 | 1.9362 | 1.937 | 2.0827 | 2.0679 | 2.1086 | 2.1002 | 2.1634 | 2.1513 | 2.1492 | 2.1496 | 2.2721 | 2.256 | 2.3003 | 2.2912 | 2.3601 | 2.3391 | 2.3043 | 2.3054 | 2.4787 | 2.4611 | 2.5096 | 2.4996 | 2.5748 | 2.5604 | 2.5579 | 2.5583 | 2.7042 | 2.685 | 2.7378 | 2.7269 | 2.8089 | 2.784 | 2.7426 | 2.7438 | 2.9501 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.1772 | 1.2293 | 1.2209 | 1.2505 | 1.243 | 1.2723 | 1.2689 | 1.2917 | 1.2856 | 1.3313 | 1.3221 | 1.3542 | 1.3462 | 1.3779 | 1.3729 | 1.3897 | 1.3852 | 1.4422 | 1.4323 | 1.4672 | 1.4585 | 1.493 | 1.4891 | 1.5161 | 1.509 | 1.5629 | 1.5522 | 1.5901 | 1.5808 | 1.6182 | 1.6125 | 1.6324 | 1.6272 | 1.6943 | 1.6828 | 1.724 | 1.7139 | 1.7546 | 1.7502 | 1.7821 | 1.7739 | 1.8374 | 1.825 | 1.8697 | 1.8589 | 1.9031 | 1.8965 | 1.9202 | 1.9141 | 1.9932 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14.5543 | 15.0563 | 14.91 | 15.1997 | 15.0095 | 15.2234 | 15.1113 | 15.4058 | 15.2147 | 15.5125 | 15.3207 | 15.6209 | 15.4285 | 15.6506 | 15.5385 | 15.6106 | 15.5736 | 15.9588 | 15.7648 | 16.0763 | 15.8816 | 16.1125 | 16.0004 | 16.3192 | 16.1231 | 16.4414 | 16.245 | 16.5689 | 16.3716 | 16.612 | 16.5003 | 16.5828 | 16.5518 | 16.9633 | 16.7643 | 17.1015 | 16.9014 | 17.1521 | 17.0402 | 17.3877 | 17.1856 | 17.5277 | 17.3259 | 17.6777 | 17.4746 | 17.7363 | 17.6253 | 17.7205 | 17.6966 | 18.1383 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5543 | 0.50194 | -0.14629 | 0.28967 | -0.19013 | 0.2139 | -0.11215 | 0.29452 | -0.19105 | 0.29779 | -0.19183 | 0.30017 | -0.19234 | 0.22208 | -0.1121 | 0.072051 | -0.037019 | 0.38529 | -0.19406 | 0.31154 | -0.19473 | 0.2309 | -0.11211 | 0.31878 | -0.19612 | 0.31837 | -0.19645 | 0.32387 | -0.1973 | 0.24041 | -0.11171 | 0.082589 | -0.031049 | 0.41151 | -0.19903 | 0.33723 | -0.20008 | 0.25067 | -0.11191 | 0.34752 | -0.20208 | 0.34211 | -0.20179 | 0.35172 | -0.20307 | 0.26173 | -0.11105 | 0.095191 | -0.023905 | 0.44172 | -18.1383
|  | Release of spares inventory at expiry | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
| Tax depreciation (straight line from COD) | USD m |  | 801.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6065 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.2382 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 16.1624 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.66787
| Depreciation of holiday months (deemed deferred) | USD m |  | 216.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6065 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 21.639 | 18.0325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 585.0534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2058 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 19.2346 | 16.1624 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.80144 | 0.66787
| Shareholder loan interest accrued | USD m |  | 183.1829 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6608 | 9.7754 | 9.3976 | 9.0716 | 9.0635 | 8.7687 | 8.6852 | 8.3506 | 8.2838 | 7.8279 | 7.7514 | 7.3703 | 7.5562 | 7.4959 | 7.5928 | 7.4762 | 7.5604 | 7.3389 | 7.3387 | 7.0361 | 6.9108 | 6.5013 | 5.383 | 4.2121 | 2.9447 | 1.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.64155 | 0.70481 | 0.85853 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 178.3725 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0655 | 6.8898 | 8.0682 | 9.0716 | 9.0635 | 8.7687 | 8.6852 | 8.3506 | 8.2838 | 7.8279 | 7.7514 | 7.3703 | 7.5562 | 7.4959 | 7.5928 | 7.4762 | 7.5604 | 7.3389 | 7.3387 | 7.0361 | 6.9108 | 6.5013 | 5.383 | 4.2121 | 2.9447 | 1.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 288.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.3776 | 20.4082 | 19.6335 | 19.2539 | 18.5033 | 17.9999 | 17.1509 | 16.6344 | 16.2215 | 15.6947 | 14.7959 | 13.9088 | 12.6984 | 11.6621 | 10.405 | 9.2841 | 8.0942 | 6.8537 | 5.4355 | 4.1187 | 2.7152 | 2.1661 | 1.5922 | 1.0072 | 0.48837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Taxable income before losses and deferred depreciation | USD m |  | 1287.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3959 | 9.8094 | 10.6185 | 11.956 | 13.0663 | 1.762 | 15.6092 | 17.1867 | 18.561 | 20.4492 | 22.0084 | 23.8919 | 25.7248 | 24.7374 | 29.7268 | 31.2993 | 33.7622 | 33.944 | 34.0714 | 34.1454 | 34.3504 | 19.3788 | 34.5508 | 34.6957 | 34.8544 | 35.0518 | 35.1903 | 35.2682 | 35.4661 | 32.218 | 39.0215 | 54.2971 | 54.4701 | 54.6847 | 54.8352 | 54.917 | 55.1628 | 37.4626 | 55.4448 | 55.5621 | 26.914
| Tax losses used | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 216.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3959 | 9.8094 | 10.6185 | 11.956 | 13.0663 | 1.762 | 15.6092 | 17.1867 | 18.561 | 20.4492 | 22.0084 | 23.8919 | 25.7248 | 24.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.6065 | 25.2455 | 46.8844 | 68.5234 | 90.1623 | 111.8013 | 133.4403 | 155.0792 | 176.7182 | 198.3572 | 214.9937 | 205.1843 | 194.5658 | 182.6098 | 169.5435 | 167.7815 | 152.1723 | 134.9857 | 116.4247 | 95.9756 | 73.9671 | 50.0753 | 24.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 1071.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38701 | 29.7268 | 31.2993 | 33.7622 | 33.944 | 34.0714 | 34.1454 | 34.3504 | 19.3788 | 34.5508 | 34.6957 | 34.8544 | 35.0518 | 35.1903 | 35.2682 | 35.4661 | 32.218 | 39.0215 | 54.2971 | 54.4701 | 54.6847 | 54.8352 | 54.917 | 55.1628 | 37.4626 | 55.4448 | 55.5621 | 26.914
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.175 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Corporate income tax | USD m |  | 321.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1161 | 8.918 | 9.3898 | 10.1287 | 10.1832 | 10.2214 | 10.2436 | 10.3051 | 5.8136 | 10.3653 | 10.4087 | 10.4563 | 10.5156 | 10.5571 | 10.5805 | 10.6398 | 9.6654 | 11.7064 | 16.2891 | 16.341 | 16.4054 | 16.4506 | 16.4751 | 16.5488 | 11.2388 | 16.6334 | 16.6686 | 8.0742
| Minimum turnover tax | USD m |  | 15.7214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.059207 | 0.35656 | 0.3583 | 0.36035 | 0.36166 | 0.35674 | 0.36188 | 0.36731 | 0.36903 | 0.37046 | 0.37236 | 0.37459 | 0.37618 | 0.37667 | 0.37884 | 0.38218 | 0.38404 | 0.38561 | 0.38767 | 0.3901 | 0.39166 | 0.38638 | 0.39212 | 0.39836 | 0.4004 | 0.4021 | 0.40435 | 0.40699 | 0.40888 | 0.40948 | 0.41205 | 0.41599 | 0.41821 | 0.42006 | 0.42252 | 0.42538 | 0.42724 | 0.42153 | 0.428 | 0.43519 | 0.36476
| Tax paid = max(CIT, MTT) | USD m |  | 326.0449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.059207 | 0.35656 | 0.3583 | 0.36035 | 0.36166 | 0.35674 | 0.36188 | 0.36731 | 0.36903 | 0.37046 | 0.37236 | 0.37459 | 0.37618 | 0.37667 | 8.918 | 9.3898 | 10.1287 | 10.1832 | 10.2214 | 10.2436 | 10.3051 | 5.8136 | 10.3653 | 10.4087 | 10.4563 | 10.5156 | 10.5571 | 10.5805 | 10.6398 | 9.6654 | 11.7064 | 16.2891 | 16.341 | 16.4054 | 16.4506 | 16.4751 | 16.5488 | 11.2388 | 16.6334 | 16.6686 | 8.0742
| Thin-cap disallowance | USD m |  | 4.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59534 | 2.8856 | 1.3294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.74057
|  | Gearing used in the closed-form gross-up | fraction | 0.75
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97559
|  | First installment share of remaining profile | fraction | 0.025482
|  | DSRA coefficient per USD of E balance | factor | 0.047905
|  | DSRA coefficient per USD of A balance | factor | 0.059469
|  | DSRA coefficient per USD of B balance | factor | 0.058212
|  | DSRA coefficient per USD of C balance | factor | 0.070892
|  | DSRA coefficient per USD of standby balance | factor | 0.064584
|  | DSRA constant (swap net payment) | USD m | -0.44548
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0054193 | 0.0052445 | 0.0054193 | 0.0052445 | 0.0054193 | 0.0057335 | 0.0051786 | 0.0057335 | 0.0055485 | 0.0057335 | 0.0055485 | 0.0051321 | 0.0051321 | 0.0049666 | 0.0051321 | 0.0049666 | 0.0051321 | 0.0048719 | 0.0045576 | 0.0048719 | 0.0047147 | 0.0048719 | 0.0047147 | 0.0034898 | 0.0034898 | 0.0033772 | 0.0034898 | 0.0033772 | 0.0034898 | 0.0033821 | 0.0030548 | 0.0033821 | 0.003273 | 0.0033821 | 0.003273 | 0.0033013 | 0.0033013 | 0.0031948 | 0.0033013 | 0.0031948 | 0.0033013 | 0.0059488 | 0.0053731 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0059488 | 0.0057569 | 0.0059488 | 0.0057569 | 0.0059488
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 108.0747 | 1.4865 | 1.9207 | 2.7338 | 3.8452 | 5.1647 | 6.7187 | 8.37 | 10.1246 | 11.8989 | 13.6596 | 15.4098 | 17.0513 | 18.5855 | 19.958 | 21.1815 | 22.1944 | 24.14 | 23.6223 | 23.9698 | 24.4619 | 24.3503 | 24.0318 | 23.8725 | 23.1108 | 22.1405 | 22.5422 | 21.2073 | 19.7212 | 18.6508 | 16.9671 | 15.2273 | 11.5689 | 11.1772 | 8.1666 | 5.96 | 3.6253 | 5.1675 | 2.4173 | 57.5739 | -0.37558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 83.0843 | 84.5084 | 86.2806 | 88.6744 | 91.9407 | 96.255 | 101.7453 | 108.5605 | 116.7368 | 126.321 | 137.2792 | 149.5758 | 163.1746 | 177.9801 | 193.9066 | 210.8053 | 228.5586 | 247.8202 | 266.6938 | 285.9418 | 305.5991 | 325.2594 | 344.7031 | 363.7503 | 382.2502 | 400.0167 | 418.1526 | 435.2716 | 451.3099 | 466.5202 | 480.3783 | 493.0129 | 502.8288 | 512.3932 | 519.6298 | 525.1836 | 528.953 | 533.8832 | 536.7402 | 581.9727 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726 | 582.7726
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0095643 | 0.010081 | 0.010617 | 0.011137 | 0.011677 | 0.012221 | 0.012715 | 0.013263 | 0.013795 | 0.014347 | 0.014884 | 0.015433 | 0.015984 | 0.016519 | 0.017074 | 0.017613 | 0.018171 | 0.018727 | 0.01925 | 0.019809 | 0.020353 | 0.020916 | 0.021463 | 0.022007 | 0.022551 | 0.02308 | 0.023627 | 0.024157 | 0.024707 | 0.025255 | 0.025751 | 0.026302 | 0.026835 | 0.027388 | 0.027923 | 0.028476 | 0.02903 | 0.029567 | 0.030123 | 0.030662 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938 | 0.065938
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 851.9297
|  | Senior debt (committed tranches) | USD m | 633.256
|  | Debt share of monthly funding | fraction | 0.74057
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 26.9957 | 27.5455 | 28.203 | 29.0408 | 30.1416 | 31.5539 | 33.3017 | 35.4554 | 38.0081 | 40.9825 | 44.3598 | 48.1367 | 52.2995 | 56.8155 | 61.6682 | 66.8046 | 72.1987 | 78.0389 | 83.7556 | 89.5922 | 95.5458 | 101.5048 | 107.3954 | 113.1691 | 118.7808 | 124.1711 | 129.6752 | 134.8741 | 139.7573 | 144.3951 | 148.6197 | 152.495 | 155.5314 | 158.4979 | 160.7708 | 162.5497 | 163.8003 | 165.3906 | 166.3715 | 179.8971 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 19.7969 | 20.2 | 20.6822 | 21.2966 | 22.1039 | 23.1395 | 24.4213 | 26.0006 | 27.8726 | 30.0538 | 32.5305 | 35.3002 | 38.353 | 41.6647 | 45.2233 | 48.99 | 52.9457 | 57.2285 | 61.4208 | 65.701 | 70.0669 | 74.4368 | 78.7567 | 82.9907 | 87.1059 | 91.0588 | 95.0952 | 98.9076 | 102.4887 | 105.8897 | 108.9877 | 111.8297 | 114.0564 | 116.2318 | 117.8986 | 119.2031 | 120.1202 | 121.2864 | 122.0057 | 131.9246 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 8.9986 | 9.1818 | 9.401 | 9.6803 | 10.0472 | 10.518 | 11.1006 | 11.8185 | 12.6694 | 13.6608 | 14.7866 | 16.0456 | 17.4332 | 18.9385 | 20.5561 | 22.2682 | 24.0662 | 26.013 | 27.9185 | 29.8641 | 31.8486 | 33.8349 | 35.7985 | 37.723 | 39.5936 | 41.3904 | 43.2251 | 44.958 | 46.5858 | 48.1317 | 49.5399 | 50.8317 | 51.8438 | 52.8326 | 53.5903 | 54.1832 | 54.6001 | 55.1302 | 55.4572 | 59.9657 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 34.1946 | 34.8909 | 35.7238 | 36.785 | 38.1794 | 39.9682 | 42.1822 | 44.9101 | 48.1436 | 51.9112 | 56.1891 | 60.9731 | 66.246 | 71.9664 | 78.113 | 84.6191 | 91.4516 | 98.8493 | 106.0905 | 113.4835 | 121.0246 | 128.5727 | 136.0342 | 143.3475 | 150.4557 | 157.2834 | 164.2553 | 170.8405 | 177.0259 | 182.9004 | 188.2516 | 193.1603 | 197.0065 | 200.764 | 203.6431 | 205.8963 | 207.4804 | 209.4947 | 210.7372 | 227.8697 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: interest | USD m |  | 7.0928 | 0 | 0.087061 | 0.091795 | 0.090955 | 0.096778 | 0.10953 | 0.10357 | 0.12101 | 0.12468 | 0.13812 | 0.14412 | 0.13561 | 0.14715 | 0.15472 | 0.17368 | 0.18244 | 0.20422 | 0.20268 | 0.20494 | 0.23512 | 0.24339 | 0.26822 | 0.27575 | 0.15906 | 0.16762 | 0.17025 | 0.18391 | 0.18587 | 0.19976 | 0.19255 | 0.17969 | 0.20476 | 0.20333 | 0.21429 | 0.21133 | 0.20905 | 0.21136 | 0.20612 | 0.21505 | 0.20935 | 0.23392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 10.6236 | 0 | 0.10179 | 0.10732 | 0.10634 | 0.11315 | 0.1241 | 0.11734 | 0.13711 | 0.14127 | 0.15649 | 0.16329 | 0.16387 | 0.17782 | 0.18697 | 0.20989 | 0.22046 | 0.24679 | 0.25349 | 0.25632 | 0.29407 | 0.30441 | 0.33546 | 0.34489 | 0.27263 | 0.28729 | 0.2918 | 0.31522 | 0.31857 | 0.34239 | 0.34419 | 0.3212 | 0.36602 | 0.36345 | 0.38304 | 0.37775 | 0.38681 | 0.39109 | 0.38138 | 0.39792 | 0.38737 | 0.43282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 4.561 | 0 | 0.044393 | 0.046807 | 0.046378 | 0.049348 | 0.054247 | 0.051293 | 0.059934 | 0.061751 | 0.068404 | 0.071378 | 0.071304 | 0.077375 | 0.081355 | 0.091326 | 0.095928 | 0.10738 | 0.11004 | 0.11127 | 0.12766 | 0.13215 | 0.14563 | 0.14972 | 0.11622 | 0.12246 | 0.12439 | 0.13437 | 0.1358 | 0.14595 | 0.14642 | 0.13664 | 0.15571 | 0.15461 | 0.16295 | 0.1607 | 0.16428 | 0.1661 | 0.16198 | 0.169 | 0.16452 | 0.18383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 22.4247 | 0 | 0.2096 | 0.221 | 0.21897 | 0.23299 | 0.25461 | 0.24075 | 0.28131 | 0.28984 | 0.32106 | 0.33502 | 0.3387 | 0.36753 | 0.38644 | 0.4338 | 0.45566 | 0.51007 | 0.52588 | 0.53174 | 0.61005 | 0.63151 | 0.69593 | 0.71548 | 0.5818 | 0.61308 | 0.62272 | 0.67268 | 0.67983 | 0.73066 | 0.73679 | 0.68757 | 0.78351 | 0.77801 | 0.81995 | 0.80863 | 0.83003 | 0.83922 | 0.8184 | 0.85389 | 0.83124 | 0.92878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 4.1568 | 0 | 0.029089 | 0.030671 | 0.03039 | 0.032336 | 0.033561 | 0.031734 | 0.03708 | 0.038204 | 0.04232 | 0.04416 | 0.049393 | 0.053598 | 0.056354 | 0.063261 | 0.06645 | 0.074384 | 0.08039 | 0.081287 | 0.093258 | 0.096539 | 0.10639 | 0.10937 | 0.11958 | 0.12601 | 0.12799 | 0.13826 | 0.13973 | 0.15018 | 0.15561 | 0.14522 | 0.16548 | 0.16432 | 0.17318 | 0.17079 | 0.17901 | 0.18099 | 0.1765 | 0.18415 | 0.17927 | 0.20031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | 13.6621 | 0 | 0.025634 | 0.021014 | 0.026832 | 0.022316 | -0.0012742 | 0.019501 | -0.001464 | 0.0066016 | -0.0017656 | 0.0080856 | 0.078754 | 0.087718 | 0.10813 | 0.10801 | 0.13205 | 0.13054 | 0.2055 | 0.2522 | 0.23974 | 0.27281 | 0.27166 | 0.30512 | 0.7904 | 0.82297 | 0.85602 | 0.87698 | 0.9026 | 0.91576 | 0.97483 | 0.99563 | 0.99526 | 1.0057 | 1.0746 | 1.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 11.347 | 0.54978 | 0.45644 | 0.47006 | 0.45306 | 0.46573 | 0.46255 | 0.41409 | 0.4534 | 0.43275 | 0.43978 | 0.41727 | 0.4214 | 0.41047 | 0.38557 | 0.38536 | 0.35934 | 0.35645 | 0.34084 | 0.30304 | 0.30739 | 0.28113 | 0.27327 | 0.24777 | 0.23898 | 0.22227 | 0.19939 | 0.19044 | 0.16888 | 0.15946 | 0.14533 | 0.11914 | 0.11968 | 0.10497 | 0.099682 | 0.088158 | 0.084519 | 0.079371 | 0.073309 | 0.07115 | 0.066108 | 0.02917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.95757 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 9.9548 | 9.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.87125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 35.663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 118.5792 | 2.4148 | 2.8883 | 3.6799 | 4.8356 | 6.2033 | 7.6774 | 9.4599 | 11.2131 | 13.0651 | 14.8348 | 16.59 | 18.2852 | 19.8369 | 21.3153 | 22.5617 | 23.6937 | 25.6533 | 25.1109 | 25.6373 | 26.1511 | 26.1752 | 25.8748 | 25.3608 | 24.6495 | 23.6771 | 24.1771 | 22.836 | 21.4496 | 20.3717 | 18.5566 | 17.0225 | 13.3376 | 13.0303 | 9.984 | 7.8137 | 5.4935 | 6.9852 | 4.3085 | 59.4118 | 37.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 633.256 | 543.2703 | 541.4378 | 539.2459 | 536.4534 | 532.7838 | 528.0764 | 522.2502 | 515.0715 | 506.5623 | 496.6476 | 485.39 | 472.8004 | 458.9243 | 443.8708 | 427.6954 | 410.5741 | 392.5938 | 373.1264 | 354.0706 | 334.6153 | 314.7701 | 294.9067 | 275.2712 | 256.0257 | 237.3201 | 219.3523 | 201.0052 | 183.6758 | 167.3984 | 151.9391 | 137.8571 | 124.9394 | 114.8179 | 104.9297 | 97.3532 | 91.4237 | 87.2549 | 81.954 | 78.6844 | 33.5989 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958 | 4.958
|  | Senior tranche drawdown (pro rata) | USD m |  | 628.2979 | 89.9857 | 1.8325 | 2.1918 | 2.7925 | 3.6695 | 4.7074 | 5.8261 | 7.1788 | 8.5092 | 9.9147 | 11.2576 | 12.5896 | 13.876 | 15.0535 | 16.1754 | 17.1213 | 17.9803 | 19.4674 | 19.0558 | 19.4553 | 19.8451 | 19.8635 | 19.6355 | 19.2454 | 18.7057 | 17.9677 | 18.3471 | 17.3294 | 16.2773 | 15.4593 | 14.0819 | 12.9178 | 10.1214 | 9.8882 | 7.5765 | 5.9295 | 4.1688 | 5.3008 | 3.2696 | 45.0855 | 28.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 20.4511 | 2.929 | 0.059649 | 0.071345 | 0.090897 | 0.11944 | 0.15323 | 0.18964 | 0.23367 | 0.27697 | 0.32272 | 0.36644 | 0.40979 | 0.45166 | 0.48999 | 0.52651 | 0.5573 | 0.58526 | 0.63366 | 0.62027 | 0.63327 | 0.64596 | 0.64656 | 0.63914 | 0.62644 | 0.60887 | 0.58485 | 0.5972 | 0.56407 | 0.52983 | 0.5032 | 0.45837 | 0.42047 | 0.32945 | 0.32186 | 0.24662 | 0.19301 | 0.13569 | 0.17254 | 0.10642 | 1.4675 | 0.93226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 848.3949 | 121.5083 | 2.4745 | 2.9597 | 3.7708 | 4.955 | 6.3565 | 7.8671 | 9.6935 | 11.49 | 13.3878 | 15.2013 | 16.9998 | 18.7369 | 20.3269 | 21.8418 | 23.119 | 24.2789 | 26.2869 | 25.7312 | 26.2706 | 26.797 | 26.8218 | 26.5139 | 25.9873 | 25.2584 | 24.2619 | 24.7743 | 23.4001 | 21.9794 | 20.8749 | 19.0149 | 17.4429 | 13.667 | 13.3521 | 10.2306 | 8.0067 | 5.6292 | 7.1578 | 4.4149 | 60.8793 | 38.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 848.3949 | 121.5083 | 2.4745 | 2.9597 | 3.7708 | 4.955 | 6.3565 | 7.8671 | 9.6935 | 11.49 | 13.3878 | 15.2013 | 16.9998 | 18.7369 | 20.3269 | 21.8418 | 23.119 | 24.2789 | 26.2869 | 25.7312 | 26.2706 | 26.797 | 26.8218 | 26.5139 | 25.9873 | 25.2584 | 24.2619 | 24.7743 | 23.4001 | 21.9794 | 20.8749 | 19.0149 | 17.4429 | 13.667 | 13.3521 | 10.2306 | 8.0067 | 5.6292 | 7.1578 | 4.4149 | 60.8793 | 38.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 17.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197
|  | Standby facility drawdown (75%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 188.4894 | 26.9957 | 0.54976 | 0.65755 | 0.83776 | 1.1009 | 1.4122 | 1.7478 | 2.1536 | 2.5528 | 2.9744 | 3.3773 | 3.7769 | 4.1628 | 4.5161 | 4.8526 | 5.1364 | 5.3941 | 5.8402 | 5.7167 | 5.8366 | 5.9535 | 5.959 | 5.8907 | 5.7736 | 5.6117 | 5.3903 | 5.5041 | 5.1988 | 4.8832 | 4.6378 | 4.2246 | 3.8753 | 3.0364 | 2.9665 | 2.273 | 1.7789 | 1.2506 | 1.5903 | 0.98088 | 13.5257 | 8.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 138.2255 | 19.7969 | 0.40316 | 0.48221 | 0.61436 | 0.8073 | 1.0356 | 1.2818 | 1.5793 | 1.872 | 2.1812 | 2.4767 | 2.7697 | 3.0527 | 3.3118 | 3.5586 | 3.7667 | 3.9557 | 4.2828 | 4.1923 | 4.2802 | 4.3659 | 4.37 | 4.3198 | 4.234 | 4.1152 | 3.9529 | 4.0364 | 3.8125 | 3.581 | 3.4011 | 3.098 | 2.8419 | 2.2267 | 2.1754 | 1.6668 | 1.3045 | 0.91714 | 1.1662 | 0.71931 | 9.9188 | 6.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 62.8298 | 8.9986 | 0.18325 | 0.21918 | 0.27925 | 0.36695 | 0.47074 | 0.58261 | 0.71788 | 0.85092 | 0.99147 | 1.1258 | 1.259 | 1.3876 | 1.5054 | 1.6175 | 1.7121 | 1.798 | 1.9467 | 1.9056 | 1.9455 | 1.9845 | 1.9863 | 1.9636 | 1.9245 | 1.8706 | 1.7968 | 1.8347 | 1.7329 | 1.6277 | 1.5459 | 1.4082 | 1.2918 | 1.0121 | 0.98882 | 0.75765 | 0.59295 | 0.41688 | 0.53008 | 0.32696 | 4.5086 | 2.8641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 238.7532 | 34.1946 | 0.69636 | 0.8329 | 1.0612 | 1.3944 | 1.7888 | 2.2139 | 2.7279 | 3.2335 | 3.7676 | 4.2779 | 4.7841 | 5.2729 | 5.7203 | 6.1467 | 6.5061 | 6.8325 | 7.3976 | 7.2412 | 7.393 | 7.5412 | 7.5481 | 7.4615 | 7.3133 | 7.1082 | 6.8277 | 6.9719 | 6.5852 | 6.1854 | 5.8746 | 5.3511 | 4.9087 | 3.8461 | 3.7575 | 2.8791 | 2.2532 | 1.5841 | 2.0143 | 1.2424 | 17.1325 | 10.8835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 26.9957 | 27.5455 | 28.203 | 29.0408 | 30.1416 | 31.5539 | 33.3017 | 35.4554 | 38.0081 | 40.9825 | 44.3598 | 48.1367 | 52.2995 | 56.8155 | 61.6682 | 66.8046 | 72.1987 | 78.0389 | 83.7556 | 89.5922 | 95.5458 | 101.5048 | 107.3954 | 113.1691 | 118.7808 | 124.1711 | 129.6752 | 134.8741 | 139.7573 | 144.3951 | 148.6197 | 152.495 | 155.5314 | 158.4979 | 160.7708 | 162.5497 | 163.8003 | 165.3906 | 166.3715 | 179.8971 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894 | 188.4894
|  | ABDB A-loan: closing balance | USD m |  |  | 19.7969 | 20.2 | 20.6822 | 21.2966 | 22.1039 | 23.1395 | 24.4213 | 26.0006 | 27.8726 | 30.0538 | 32.5305 | 35.3002 | 38.353 | 41.6647 | 45.2233 | 48.99 | 52.9457 | 57.2285 | 61.4208 | 65.701 | 70.0669 | 74.4368 | 78.7567 | 82.9907 | 87.1059 | 91.0588 | 95.0952 | 98.9076 | 102.4887 | 105.8897 | 108.9877 | 111.8297 | 114.0564 | 116.2318 | 117.8986 | 119.2031 | 120.1202 | 121.2864 | 122.0057 | 131.9246 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255 | 138.2255
|  | ABDB B-loan: closing balance | USD m |  |  | 8.9986 | 9.1818 | 9.401 | 9.6803 | 10.0472 | 10.518 | 11.1006 | 11.8185 | 12.6694 | 13.6608 | 14.7866 | 16.0456 | 17.4332 | 18.9385 | 20.5561 | 22.2682 | 24.0662 | 26.013 | 27.9185 | 29.8641 | 31.8486 | 33.8349 | 35.7985 | 37.723 | 39.5936 | 41.3904 | 43.2251 | 44.958 | 46.5858 | 48.1317 | 49.5399 | 50.8317 | 51.8438 | 52.8326 | 53.5903 | 54.1832 | 54.6001 | 55.1302 | 55.4572 | 59.9657 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298 | 62.8298
|  | Commercial tranche: closing balance | USD m |  |  | 34.1946 | 34.8909 | 35.7238 | 36.785 | 38.1794 | 39.9682 | 42.1822 | 44.9101 | 48.1436 | 51.9112 | 56.1891 | 60.9731 | 66.246 | 71.9664 | 78.113 | 84.6191 | 91.4516 | 98.8493 | 106.0905 | 113.4835 | 121.0246 | 128.5727 | 136.0342 | 143.3475 | 150.4557 | 157.2834 | 164.2553 | 170.8405 | 177.0259 | 182.9004 | 188.2516 | 193.1603 | 197.0065 | 200.764 | 203.6431 | 205.8963 | 207.4804 | 209.4947 | 210.7372 | 227.8697 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532 | 238.7532
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 220.0969 | 31.5226 | 0.64195 | 0.76782 | 0.97825 | 1.2855 | 1.649 | 2.0409 | 2.5148 | 2.9808 | 3.4732 | 3.9436 | 4.4102 | 4.8609 | 5.2734 | 5.6664 | 5.9977 | 6.2986 | 6.8196 | 6.6754 | 6.8153 | 6.9519 | 6.9583 | 6.8784 | 6.7418 | 6.5527 | 6.2942 | 6.4271 | 6.0706 | 5.7021 | 5.4155 | 4.933 | 4.5252 | 3.5456 | 3.4639 | 2.6541 | 2.0772 | 1.4604 | 1.8569 | 1.1454 | 15.7938 | 10.0331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 205.8969 | 17.3226 | 0.64195 | 0.76782 | 0.97825 | 1.2855 | 1.649 | 2.0409 | 2.5148 | 2.9808 | 3.4732 | 3.9436 | 4.4102 | 4.8609 | 5.2734 | 5.6664 | 5.9977 | 6.2986 | 6.8196 | 6.6754 | 6.8153 | 6.9519 | 6.9583 | 6.8784 | 6.7418 | 6.5527 | 6.2942 | 6.4271 | 6.0706 | 5.7021 | 5.4155 | 4.933 | 4.5252 | 3.5456 | 3.4639 | 2.6541 | 2.0772 | 1.4604 | 1.8569 | 1.1454 | 15.7938 | 10.0331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 44.0194 | 6.3045 | 0.12839 | 0.15356 | 0.19565 | 0.25709 | 0.32981 | 0.40819 | 0.50295 | 0.59617 | 0.69463 | 0.78872 | 0.88204 | 0.97217 | 1.0547 | 1.1333 | 1.1995 | 1.2597 | 1.3639 | 1.3351 | 1.3631 | 1.3904 | 1.3917 | 1.3757 | 1.3484 | 1.3105 | 1.2588 | 1.2854 | 1.2141 | 1.1404 | 1.0831 | 0.9866 | 0.90504 | 0.70912 | 0.69278 | 0.53082 | 0.41543 | 0.29207 | 0.37138 | 0.22907 | 3.1588 | 2.0066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 176.0775 | 25.2181 | 0.51356 | 0.61426 | 0.7826 | 1.0284 | 1.3192 | 1.6327 | 2.0118 | 2.3847 | 2.7785 | 3.1549 | 3.5282 | 3.8887 | 4.2187 | 4.5331 | 4.7982 | 5.0389 | 5.4556 | 5.3403 | 5.4523 | 5.5615 | 5.5666 | 5.5028 | 5.3934 | 5.2422 | 5.0354 | 5.1417 | 4.8565 | 4.5616 | 4.3324 | 3.9464 | 3.6201 | 2.8365 | 2.7711 | 2.1233 | 1.6617 | 1.1683 | 1.4855 | 0.91629 | 12.635 | 8.0265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 29.7658 | 0 | 0.19691 | 0.2092 | 0.20889 | 0.22385 | 0.23395 | 0.22263 | 0.26145 | 0.27077 | 0.30122 | 0.31555 | 0.35407 | 0.3854 | 0.40634 | 0.4572 | 0.48141 | 0.54006 | 0.58507 | 0.59292 | 0.68169 | 0.70759 | 0.78176 | 0.80611 | 0.88388 | 0.93453 | 0.95262 | 1.0327 | 1.0476 | 1.1301 | 1.1761 | 1.1024 | 1.2612 | 1.2587 | 1.3337 | 1.3227 | 1.3946 | 1.4193 | 1.3937 | 1.4634 | 1.4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 25.2181 | 25.9285 | 26.752 | 27.7435 | 28.9957 | 30.5489 | 32.4043 | 34.6775 | 37.333 | 40.4127 | 43.8832 | 47.7654 | 52.0395 | 56.6645 | 61.6548 | 66.9344 | 72.5134 | 78.5541 | 84.4873 | 90.6212 | 96.8903 | 103.2387 | 109.5476 | 115.8249 | 122.0016 | 127.9896 | 134.164 | 140.0681 | 145.7599 | 151.2683 | 156.3171 | 161.1985 | 165.2937 | 169.3985 | 172.8445 | 175.9008 | 178.4883 | 181.3675 | 183.7472 | 197.8169 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434 | 205.8434
|  | Total debt drawdowns (incl. standby) | USD m |  | 628.2979 | 89.9857 | 1.8325 | 2.1918 | 2.7925 | 3.6695 | 4.7074 | 5.8261 | 7.1788 | 8.5092 | 9.9147 | 11.2576 | 12.5896 | 13.876 | 15.0535 | 16.1754 | 17.1213 | 17.9803 | 19.4674 | 19.0558 | 19.4553 | 19.8451 | 19.8635 | 19.6355 | 19.2454 | 18.7057 | 17.9677 | 18.3471 | 17.3294 | 16.2773 | 15.4593 | 14.0819 | 12.9178 | 10.1214 | 9.8882 | 7.5765 | 5.9295 | 4.1688 | 5.3008 | 3.2696 | 45.0855 | 28.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 107.5903 | 13.4786 | 1.0773 | 1.1251 | 1.1276 | 1.1978 | 1.2565 | 1.2307 | 1.3911 | 1.4419 | 1.5616 | 1.6071 | 1.7311 | 1.8402 | 1.9195 | 2.0684 | 2.1492 | 2.3014 | 2.4422 | 2.4503 | 2.6382 | 2.7063 | 2.8469 | 2.8905 | 3.0113 | 3.0777 | 3.0821 | 3.2162 | 3.1988 | 3.2786 | 3.2996 | 3.1341 | 3.3058 | 3.1929 | 3.3369 | 3.2787 | 2.1247 | 2.0774 | 2.0578 | 2.0623 | 3.3648 | 3.011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 848.3949
|  | Capitalized cost (book and tax) | USD m | 801.4431

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01978 | 0.021217 | 0.018144 | 0.016481 | 0.0087911 | 0.0080444 | 0.0077178 | 0.022424 | 0.022796 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847 | 0.022598 | 0.022847 | 0.022474 | 0.022847 | 0.022474 | 0.022847
|  | ABDB A-loan: rate per period | factor |  |  | 0.031536 | 0.032781 | 0.0299 | 0.028109 | 0.020547 | 0.019608 | 0.019473 | 0.033988 | 0.034551 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602 | 0.034226 | 0.034602 | 0.034038 | 0.034602 | 0.034038 | 0.034602
|  | ABDB B-loan: rate per period | factor |  |  | 0.030258 | 0.031524 | 0.028622 | 0.026845 | 0.019269 | 0.018351 | 0.018196 | 0.032731 | 0.033273 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324 | 0.032962 | 0.033324 | 0.032781 | 0.033324 | 0.032781 | 0.033324
|  | Commercial tranche: rate per period | factor |  |  | 0.037595 | 0.038937 | 0.035778 | 0.03376 | 0.025385 | 0.024301 | 0.024193 | 0.040278 | 0.040946 | 0.040334 | 0.041002 | 0.040557 | 0.041002 | 0.040334 | 0.041002 | 0.043127 | 0.043842 | 0.043127 | 0.043842 | 0.043365 | 0.043842 | 0.043127 | 0.043842 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681 | 0.046174 | 0.046681 | 0.04592 | 0.046681 | 0.04592 | 0.046681
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037816 | 0.03479 | 0.032848 | 0.024813 | 0.023765 | 0.023668 | 0.039103 | 0.039751 | 0.039156 | 0.039805 | 0.039373 | 0.039805 | 0.039156 | 0.039805 | 0.040832 | 0.041509 | 0.040832 | 0.041509 | 0.041058 | 0.041509 | 0.040832 | 0.041509 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213 | 0.042743 | 0.043213 | 0.042508 | 0.043213 | 0.042508 | 0.043213
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97452 | 0.94728 | 0.91908 | 0.88956 | 0.85921 | 0.82748 | 0.79401 | 0.75901 | 0.72642 | 0.69231 | 0.65749 | 0.62097 | 0.58342 | 0.54408 | 0.50161 | 0.45684 | 0.41173 | 0.3643 | 0.31539 | 0.26409 | 0.21127 | 0.15598 | 0.098133 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.027953 | 0.029769 | 0.032122 | 0.034112 | 0.036934 | 0.040445 | 0.044085 | 0.042927 | 0.046964 | 0.050299 | 0.055542 | 0.060469 | 0.06742 | 0.078074 | 0.089237 | 0.098739 | 0.11521 | 0.13425 | 0.16267 | 0.2 | 0.26172 | 0.37085 | 0.51193 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.4894 | 178.1409 | 173.1614 | 168.0065 | 162.6097 | 157.0628 | 151.2619 | 145.1441 | 138.7454 | 132.7895 | 126.5531 | 120.1876 | 113.5121 | 106.6482 | 99.458 | 91.6929 | 83.5104 | 75.2647 | 66.5932 | 57.653 | 48.2747 | 38.6199 | 28.5124 | 17.9386 | 8.7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 60.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2267 | 4.0608 | 3.8917 | 3.8384 | 3.6747 | 3.5884 | 3.3995 | 3.3161 | 3.1182 | 3.0338 | 2.8442 | 2.7459 | 2.5652 | 2.4366 | 2.2352 | 2.0949 | 1.8768 | 1.7195 | 1.4966 | 1.3172 | 1.0909 | 0.88234 | 0.64079 | 0.40984 | 0.19677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 182.9439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.803 | 4.9795 | 5.1549 | 5.3967 | 5.547 | 5.8009 | 6.1178 | 6.3987 | 5.9559 | 6.2364 | 6.3655 | 6.6755 | 6.864 | 7.1902 | 7.7651 | 8.1824 | 8.2458 | 8.6715 | 8.9402 | 9.3783 | 9.6548 | 10.1075 | 10.5738 | 9.1833 | 8.7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 182.9439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.803 | 4.9795 | 5.1549 | 5.3967 | 5.547 | 5.8009 | 6.1178 | 6.3987 | 5.9559 | 6.2364 | 6.3655 | 6.6755 | 6.864 | 7.1902 | 7.7651 | 8.1824 | 8.2458 | 8.6715 | 8.9402 | 9.3783 | 9.6548 | 10.1075 | 10.5738 | 9.1833 | 8.7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 5.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178.1409 | 173.1614 | 168.0065 | 162.6097 | 157.0628 | 151.2619 | 145.1441 | 138.7454 | 132.7895 | 126.5531 | 120.1876 | 113.5121 | 106.6482 | 99.458 | 91.6929 | 83.5104 | 75.2647 | 66.5932 | 57.653 | 48.2747 | 38.6199 | 28.5124 | 17.9386 | 8.7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 188.4894 | 178.1409 | 173.1614 | 168.0065 | 162.6097 | 157.0628 | 151.2619 | 145.1441 | 138.7454 | 132.7895 | 126.5531 | 120.1876 | 113.5121 | 106.6482 | 99.458 | 91.6929 | 83.5104 | 75.2647 | 66.5932 | 57.653 | 48.2747 | 38.6199 | 28.5124 | 17.9386 | 8.7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.2255 | 130.6366 | 126.985 | 123.2047 | 119.2471 | 115.1794 | 110.9254 | 106.439 | 101.7466 | 97.379 | 92.8056 | 88.1376 | 83.2422 | 78.2087 | 72.9358 | 67.2414 | 61.241 | 55.1941 | 48.835 | 42.2789 | 35.4015 | 28.3213 | 20.9091 | 13.155 | 6.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 67.4253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.698 | 4.5136 | 4.3223 | 4.2632 | 4.0814 | 3.9855 | 3.7757 | 3.683 | 3.4633 | 3.3695 | 3.1589 | 3.0498 | 2.8491 | 2.7062 | 2.4826 | 2.3267 | 2.0845 | 1.9098 | 1.6622 | 1.4629 | 1.2117 | 0.97998 | 0.71171 | 0.45519 | 0.21854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 134.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5222 | 3.6517 | 3.7803 | 3.9576 | 4.0678 | 4.254 | 4.4864 | 4.6924 | 4.3677 | 4.5733 | 4.6681 | 4.8953 | 5.0336 | 5.2728 | 5.6944 | 6.0004 | 6.0469 | 6.3591 | 6.5561 | 6.8774 | 7.0802 | 7.4122 | 7.7542 | 6.7345 | 6.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 134.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5222 | 3.6517 | 3.7803 | 3.9576 | 4.0678 | 4.254 | 4.4864 | 4.6924 | 4.3677 | 4.5733 | 4.6681 | 4.8953 | 5.0336 | 5.2728 | 5.6944 | 6.0004 | 6.0469 | 6.3591 | 6.5561 | 6.8774 | 7.0802 | 7.4122 | 7.7542 | 6.7345 | 6.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 4.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.6366 | 126.985 | 123.2047 | 119.2471 | 115.1794 | 110.9254 | 106.439 | 101.7466 | 97.379 | 92.8056 | 88.1376 | 83.2422 | 78.2087 | 72.9358 | 67.2414 | 61.241 | 55.1941 | 48.835 | 42.2789 | 35.4015 | 28.3213 | 20.9091 | 13.155 | 6.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 138.2255 | 130.6366 | 126.985 | 123.2047 | 119.2471 | 115.1794 | 110.9254 | 106.439 | 101.7466 | 97.379 | 92.8056 | 88.1376 | 83.2422 | 78.2087 | 72.9358 | 67.2414 | 61.241 | 55.1941 | 48.835 | 42.2789 | 35.4015 | 28.3213 | 20.9091 | 13.155 | 6.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.8298 | 59.3803 | 57.7205 | 56.0022 | 54.2032 | 52.3543 | 50.4206 | 48.3814 | 46.2485 | 44.2632 | 42.1844 | 40.0625 | 37.8374 | 35.5494 | 33.1527 | 30.5643 | 27.8368 | 25.0882 | 22.1977 | 19.2177 | 16.0916 | 12.8733 | 9.5041 | 5.9795 | 2.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 29.5159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0565 | 1.9758 | 1.8921 | 1.8662 | 1.7867 | 1.7447 | 1.6528 | 1.6123 | 1.5161 | 1.475 | 1.3829 | 1.3351 | 1.2472 | 1.1847 | 1.0868 | 1.0185 | 0.91252 | 0.83605 | 0.72767 | 0.64042 | 0.53041 | 0.429 | 0.31156 | 0.19926 | 0.095669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 60.9813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.601 | 1.6598 | 1.7183 | 1.7989 | 1.849 | 1.9336 | 2.0393 | 2.1329 | 1.9853 | 2.0788 | 2.1218 | 2.2252 | 2.288 | 2.3967 | 2.5884 | 2.7275 | 2.7486 | 2.8905 | 2.9801 | 3.1261 | 3.2183 | 3.3692 | 3.5246 | 3.0611 | 2.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 60.9813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.601 | 1.6598 | 1.7183 | 1.7989 | 1.849 | 1.9336 | 2.0393 | 2.1329 | 1.9853 | 2.0788 | 2.1218 | 2.2252 | 2.288 | 2.3967 | 2.5884 | 2.7275 | 2.7486 | 2.8905 | 2.9801 | 3.1261 | 3.2183 | 3.3692 | 3.5246 | 3.0611 | 2.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 1.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.3803 | 57.7205 | 56.0022 | 54.2032 | 52.3543 | 50.4206 | 48.3814 | 46.2485 | 44.2632 | 42.1844 | 40.0625 | 37.8374 | 35.5494 | 33.1527 | 30.5643 | 27.8368 | 25.0882 | 22.1977 | 19.2177 | 16.0916 | 12.8733 | 9.5041 | 5.9795 | 2.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 62.8298 | 59.3803 | 57.7205 | 56.0022 | 54.2032 | 52.3543 | 50.4206 | 48.3814 | 46.2485 | 44.2632 | 42.1844 | 40.0625 | 37.8374 | 35.5494 | 33.1527 | 30.5643 | 27.8368 | 25.0882 | 22.1977 | 19.2177 | 16.0916 | 12.8733 | 9.5041 | 5.9795 | 2.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.7532 | 225.6451 | 219.3377 | 212.8082 | 205.9723 | 198.9462 | 191.5984 | 183.8491 | 175.7442 | 168.2 | 160.3006 | 146.1978 | 130.9831 | 115.8692 | 100.618 | 84.4563 | 67.275 | 50.749 | 33.6794 | 17.0703 | 0.32451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 123.1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6165 | 9.2392 | 8.8468 | 8.7257 | 8.3536 | 8.1573 | 7.7279 | 7.5383 | 7.5793 | 7.3742 | 6.9133 | 6.4096 | 5.6801 | 5.0799 | 4.3394 | 3.7027 | 3.0893 | 2.369 | 1.5466 | 0.79686 | 0.014984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 138.5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0838 | 6.3074 | 6.5295 | 6.8359 | 7.0262 | 7.3478 | 7.7492 | 8.105 | 7.5441 | 7.8994 | 8.063 | 8.1201 | 7.9204 | 7.8119 | 7.8557 | 7.5366 | 6.6427 | 5.847 | 4.5215 | 2.7768 | 0.064901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 138.5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0838 | 6.3074 | 6.5295 | 6.8359 | 7.0262 | 7.3478 | 7.7492 | 8.105 | 7.5441 | 7.8994 | 8.063 | 8.1201 | 7.9204 | 7.8119 | 7.8557 | 7.5366 | 6.6427 | 5.847 | 4.5215 | 2.7768 | 0.064901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 7.0243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.6451 | 219.3377 | 212.8082 | 205.9723 | 198.9462 | 191.5984 | 183.8491 | 175.7442 | 168.2 | 160.3006 | 152.2376 | 138.0776 | 123.0627 | 108.0573 | 92.7623 | 76.9196 | 60.6323 | 44.902 | 29.158 | 14.2935 | 0.25961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 93.1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 8.3061 | 9.6446 | 9.8833 | 11.2226 | 12.0877 | 13.969 | 0.25961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 238.7532 | 225.6451 | 219.3377 | 212.8082 | 205.9723 | 198.9462 | 191.5984 | 183.8491 | 175.7442 | 168.2 | 160.3006 | 146.1978 | 130.9831 | 115.8692 | 100.618 | 84.4563 | 67.275 | 50.749 | 33.6794 | 17.0703 | 0.32451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 0
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 0
|  | Bond face amount | USD m | 0
|  | Swap unwind receipt | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | -7.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.44548 | -0.55857 | -0.44514 | -0.54985 | -0.45603 | -0.51392 | -0.38837 | -0.47444 | -0.35734 | -0.43548 | -0.3261 | -0.3943 | -0.31914 | -0.34981 | -0.25536 | -0.29938 | -0.21421 | -0.24558 | -0.17049 | -0.18772 | -0.1345 | -0.1252 | -0.071881 | -0.057142 | -0.022605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 15.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2254 | 1.1773 | 1.1257 | 1.1103 | 1.063 | 1.038 | 0.98337 | 0.95924 | 0.902 | 0.87759 | 0.82274 | 0.76279 | 0.67598 | 0.60455 | 0.51642 | 0.44065 | 0.34529 | 0.26478 | 0.17286 | 0.089065 | 0.0016748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 280.7426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5976 | 19.7894 | 18.9529 | 18.6934 | 17.8963 | 17.4758 | 16.5559 | 16.1496 | 15.6769 | 15.2526 | 14.2993 | 13.5403 | 12.3416 | 11.4073 | 10.144 | 9.1428 | 7.9632 | 6.8345 | 5.4331 | 4.2174 | 2.848 | 2.2913 | 1.6641 | 1.0643 | 0.51098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 288.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.3776 | 20.4082 | 19.6335 | 19.2539 | 18.5033 | 17.9999 | 17.1509 | 16.6344 | 16.2215 | 15.6947 | 14.7959 | 13.9088 | 12.6984 | 11.6621 | 10.405 | 9.2841 | 8.0942 | 6.8537 | 5.4355 | 4.1187 | 2.7152 | 2.1661 | 1.5922 | 1.0072 | 0.48837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 516.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.01 | 16.5984 | 17.183 | 17.9891 | 18.4899 | 19.3363 | 20.3927 | 21.3289 | 19.853 | 20.7878 | 21.2184 | 21.916 | 22.1059 | 22.6717 | 23.9035 | 24.447 | 23.6839 | 23.7682 | 22.9978 | 22.1586 | 20.0181 | 20.8888 | 21.8526 | 18.9789 | 18.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 804.7762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.3876 | 37.0066 | 36.8164 | 37.2431 | 36.9931 | 37.3362 | 37.5437 | 37.9633 | 36.0745 | 36.4825 | 36.0144 | 35.8248 | 34.8044 | 34.3338 | 34.3085 | 33.7311 | 31.7782 | 30.6218 | 28.4333 | 26.2773 | 22.7332 | 23.055 | 23.4448 | 19.9861 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628.2979 | 593.8029 | 577.2045 | 560.0215 | 542.0324 | 523.5425 | 504.2063 | 483.8135 | 462.4846 | 442.6316 | 421.8438 | 394.5855 | 365.5749 | 336.2754 | 306.1644 | 273.9549 | 239.8632 | 206.2961 | 171.3053 | 136.2198 | 100.0923 | 79.8146 | 58.9257 | 37.0731 | 18.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 628.2979 | 593.8029 | 577.2045 | 560.0215 | 542.0324 | 523.5425 | 504.2063 | 483.8135 | 462.4846 | 442.6316 | 421.8438 | 394.5855 | 365.5749 | 336.2754 | 306.1644 | 273.9549 | 239.8632 | 206.2961 | 171.3053 | 136.2198 | 100.0923 | 79.8146 | 58.9257 | 37.0731 | 18.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 238.7532 | 225.6451 | 219.3377 | 212.8082 | 205.9723 | 198.9462 | 191.5984 | 183.8491 | 175.7442 | 168.2 | 160.3006 | 152.2376 | 138.0776 | 123.0627 | 108.0573 | 92.7623 | 76.9196 | 60.6323 | 44.902 | 29.158 | 14.2935 | 0.25961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.0297 | 9.0403 | 9.0465 | 9.2351 | 9.2217 | 9.3892 | 9.5173 | 9.7147 | 9.0741 | 9.2701 | 9.2097 | 9.4213 | 9.4292 | 9.6268 | 10.0003 | 10.2773 | 10.1226 | 10.3911 | 10.4368 | 10.6955 | 10.7457 | 10.9898 | 11.2146 | 9.5932 | 8.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8.2202 | 8.1653 | 8.1026 | 8.2208 | 8.1491 | 8.2394 | 8.2621 | 8.3754 | 7.8309 | 7.9429 | 7.827 | 7.9451 | 7.8826 | 7.979 | 8.177 | 8.3271 | 8.1314 | 8.269 | 8.2184 | 8.3403 | 8.2918 | 8.3922 | 8.4659 | 7.1896 | 6.6391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.6575 | 3.6356 | 3.6104 | 3.6652 | 3.6356 | 3.6783 | 3.6921 | 3.7452 | 3.5014 | 3.5538 | 3.5047 | 3.5602 | 3.5352 | 3.5814 | 3.6751 | 3.746 | 3.6611 | 3.7266 | 3.7077 | 3.7665 | 3.7487 | 3.7982 | 3.8362 | 3.2604 | 3.0141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.7003 | 15.5466 | 15.3763 | 15.5615 | 15.3797 | 15.5051 | 15.4772 | 15.6433 | 15.1235 | 15.2736 | 14.9763 | 15.13 | 14.3372 | 13.6922 | 13.0967 | 12.3447 | 11.1272 | 9.8161 | 8.09 | 6.1042 | 3.5186 | 0.080064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37.3876 | 37.0066 | 36.8164 | 37.2431 | 36.9931 | 37.3362 | 37.5437 | 37.9633 | 36.0745 | 36.4825 | 36.0144 | 36.4566 | 35.5776 | 35.1717 | 35.2484 | 34.8798 | 33.2229 | 32.2735 | 30.5129 | 28.8709 | 26.2441 | 23.1364 | 23.4448 | 19.9861 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03403 | 0.034404 | 0.034044 | 0.034418 | 0.034169 | 0.034418 | 0.034045 | 0.034419 | 0.035104 | 0.035495 | 0.035104 | 0.035495 | 0.035234 | 0.035495 | 0.035106 | 0.035499 | 0.036168 | 0.036579 | 0.03617 | 0.036581 | 0.036308 | 0.036585 | 0.036181 | 0.036601 | 0.036164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820.9069 | 799.9899 | 777.6302 | 754.4819 | 730.2486 | 705.3398 | 679.2914 | 651.8184 | 623.085 | 596.339 | 568.3344 | 539.7486 | 509.7717 | 478.9476 | 446.6586 | 411.787 | 375.0416 | 338.011 | 299.0685 | 258.919 | 216.802 | 173.4429 | 128.0504 | 80.563 | 39.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.2963
|  | Debt capacity at the 1.35x target | USD m | 608.0791
|  | Debt at the 75% gearing cap (closed form) | USD m | 638.9473
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.6853 | 38.48 | 38.2788 | 38.7255 | 38.4628 | 38.8211 | 39.0329 | 39.4718 | 37.505 | 37.9315 | 37.4414 | 37.9032 | 37.6335 | 38.0221 | 38.9964 | 39.6223 | 39.0297 | 39.5783 | 39.3163 | 39.7958 | 39.52 | 39.9111 | 40.2062 | 34.0896 | 31.429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633.256 | 617.1204 | 599.8719 | 582.0151 | 563.3213 | 544.1064 | 524.0123 | 502.8194 | 480.6541 | 460.022 | 438.419 | 416.3676 | 393.2432 | 369.4651 | 344.5571 | 317.6567 | 289.311 | 260.7451 | 230.7045 | 199.7328 | 167.2433 | 133.7956 | 98.7794 | 62.1471 | 30.3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1355 | 17.2485 | 17.8568 | 18.6938 | 19.2149 | 20.0941 | 21.193 | 22.1652 | 20.6321 | 21.603 | 22.0514 | 23.1245 | 23.7781 | 24.908 | 26.9003 | 28.3458 | 28.5658 | 30.0406 | 30.9718 | 32.4895 | 33.4477 | 35.0162 | 36.6323 | 31.815 | 30.3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 52.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42564 | 0.42564 | 0.42564 | 0.42564 | 0.42564 | 0.42564 | 0 | 0 | 2.0172 | 2.0172 | 2.0172 | 2.0172 | 2.0172 | 2.0172 | 0 | 0 | 0.50659 | 0.50659 | 0.50659 | 0.50659 | 0.50659 | 0.50659 | 0 | 0 | 2.4008 | 2.4008 | 2.4008 | 2.4008 | 2.4008 | 2.4008 | 0 | 0 | 0.60292 | 0.60292 | 0.60292 | 0.60292 | 0.60292 | 0.60292 | 0 | 0 | 2.8573 | 2.8573 | 2.8573 | 2.8573 | 2.8573 | 2.8573 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42564 | 0.85129 | 1.2769 | 1.7026 | 2.1282 | 2.5539 | 0 | 0 | 2.0172 | 4.0343 | 6.0515 | 8.0687 | 10.0859 | 12.103 | 0 | 0 | 0.50659 | 1.0132 | 1.5198 | 2.0263 | 2.5329 | 3.0395 | 0 | 0 | 2.4008 | 4.8015 | 7.2023 | 9.6031 | 12.0038 | 14.4046 | 0 | 0 | 0.60292 | 1.2058 | 1.8088 | 2.4117 | 3.0146 | 3.6175 | 0 | 0 | 2.8573 | 5.7146 | 8.5719 | 11.4292 | 14.2865 | 17.1438 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 35.663 | 37.3876 | 37.0066 | 36.8164 | 37.2431 | 36.9931 | 37.3362 | 37.5437 | 37.9633 | 36.0745 | 36.4825 | 36.0144 | 36.4566 | 35.5776 | 35.1717 | 35.2484 | 34.8798 | 33.2229 | 32.2735 | 30.5129 | 28.8709 | 26.2441 | 23.1364 | 23.4448 | 19.9861 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 4.3568 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7246 | 0 | 0 | 0.42662 | 0 | 0.34302 | 0.20751 | 0.41969 | 0 | 0.40799 | 0 | 0.44226 | 0 | 0 | 0.076712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 40.0198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38098 | 0.19015 | 0 | 0.24993 | 0 | 0 | 0 | 1.8888 | 0 | 0.46818 | 0 | 0.87897 | 0.40598 | 0 | 0.36857 | 1.6569 | 0.9494 | 1.7606 | 1.6419 | 2.6269 | 3.1077 | 0 | 3.4587 | 1.4035 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37.3876 | 37.0066 | 36.8164 | 37.2431 | 36.9931 | 37.3362 | 37.5437 | 37.9633 | 36.0745 | 36.4825 | 36.0144 | 36.4566 | 35.5776 | 35.1717 | 35.2484 | 34.8798 | 33.2229 | 32.2735 | 30.5129 | 28.8709 | 26.2441 | 23.1364 | 23.4448 | 19.9861 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 19.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25306 | 1.535 | 1.5518 | 1.5687 | 1.5859 | 1.6032 | 1.6208 | 1.6385 | 1.6564 | 1.6746 | 1.6929 | 1.7114 | 1.4418
| Handback reserve release at expiry | USD m |  | 19.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.5339
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25306 | 1.788 | 3.3398 | 4.9085 | 6.4944 | 8.0976 | 9.7184 | 11.3569 | 13.0133 | 14.6879 | 16.3808 | 18.0922 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2258.4734 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 48.8525 | 49.8827 | 49.6219 | 50.2009 | 49.8604 | 50.3249 | 50.5993 | 51.1683 | 48.6187 | 49.1716 | 48.5363 | 49.135 | 48.7854 | 49.2891 | 50.5521 | 51.3634 | 50.5953 | 51.3064 | 50.9668 | 51.5884 | 51.2309 | 51.7379 | 52.1204 | 44.1913 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.5699 | 45.0572 | 43.6795 | 35.61 | 36.275 | 35.8717 | 36.5318 | 36.1243 | 36.6692 | 44.0739 | 39.6367 | 39.2532 | 42.9959
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 9.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.9271 | 58.0549 | 49.8827 | 49.6219 | 50.2009 | 49.8604 | 50.3249 | 50.5993 | 51.1683 | 48.6187 | 49.1716 | 48.5363 | 49.135 | 48.7854 | 49.2891 | 50.5521 | 51.3634 | 50.5953 | 51.3064 | 50.9668 | 51.5884 | 51.2309 | 51.7379 | 52.1204 | 44.1913 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.5699 | 45.0572 | 43.6795 | 35.61 | 36.275 | 35.8717 | 36.5318 | 36.1243 | 36.6692 | 44.0739 | 39.6367 | 39.2532 | 42.9959
|  | Senior debt service and fees due | USD m |  | 804.7762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.3876 | 37.0066 | 36.8164 | 37.2431 | 36.9931 | 37.3362 | 37.5437 | 37.9633 | 36.0745 | 36.4825 | 36.0144 | 35.8248 | 34.8044 | 34.3338 | 34.3085 | 33.7311 | 31.7782 | 30.6218 | 28.4333 | 26.2773 | 22.7332 | 23.055 | 23.4448 | 19.9861 | 18.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.9271 | 20.6674 | 12.8761 | 12.8054 | 12.9578 | 12.8672 | 12.9887 | 13.0557 | 13.205 | 12.5442 | 12.689 | 12.522 | 13.3101 | 13.981 | 14.9553 | 16.2436 | 17.6323 | 18.8171 | 20.6846 | 22.5335 | 25.3111 | 28.4977 | 28.6829 | 28.6756 | 24.2053 | 22.1598 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.5699 | 45.0572 | 43.6795 | 35.61 | 36.275 | 35.8717 | 36.5318 | 36.1243 | 36.6692 | 44.0739 | 39.6367 | 39.2532 | 42.9959
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.2025 | 21.0483 | 13.0662 | 12.3788 | 13.2078 | 12.5242 | 12.7812 | 12.636 | 15.0938 | 12.1362 | 13.1572 | 12.0797 | 14.1891 | 14.387 | 14.8786 | 16.6122 | 19.2893 | 19.7665 | 22.4452 | 24.1754 | 27.9379 | 31.6054 | 28.3745 | 32.1343 | 25.6088 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.5699 | 45.0572 | 43.6795 | 35.61 | 36.275 | 35.8717 | 36.5318 | 36.1243 | 36.6692 | 44.0739 | 39.6367 | 39.2532 | 42.9959
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.2025 | 21.0483 | 13.0662 | 12.3788 | 13.2078 | 12.5242 | 12.7812 | 12.636 | 15.0938 | 12.1362 | 13.1572 | 12.0797 | 14.1891 | 14.387 | 14.8786 | 16.6122 | 19.2893 | 19.7665 | 22.4452 | 24.1754 | 27.9379 | 31.6054 | 28.3745 | 32.1343 | 25.6088 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 61.0881
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3067 | 1.3479 | 1.3478 | 1.3479 | 1.3478 | 1.3479 | 1.3477 | 1.3478 | 1.3477 | 1.3478 | 1.3477 | 1.3715 | 1.4017 | 1.4356 | 1.4735 | 1.5227 | 1.5921 | 1.6755 | 1.7925 | 1.9632 | 2.2536 | 2.2441 | 2.2231 | 2.2111 | 2.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3067 | 1.3272 | 1.3479 | 1.3479 | 1.3479 | 1.3479 | 1.3478 | 1.3478 | 1.3478 | 1.3478 | 1.3478 | 1.3596 | 1.3864 | 1.4185 | 1.4545 | 1.4979 | 1.5564 | 1.633 | 1.7318 | 1.8745 | 2.0979 | 2.2488 | 2.2335 | 2.2176 | 2.2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 93.1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 8.3061 | 9.6446 | 9.8833 | 11.2226 | 12.0877 | 13.969 | 0.25961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1413.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.0483 | 13.0662 | 12.3788 | 13.2078 | 12.5242 | 12.7812 | 12.636 | 15.0938 | 12.1362 | 13.1572 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 8.3061 | 9.6446 | 9.8833 | 11.2226 | 12.0877 | 13.969 | 31.3458 | 28.3745 | 32.1343 | 25.6088 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 61.0881
|  | Share capital contributed | USD m | 44.0194
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 205.8434 | 207.5042 | 196.2313 | 192.5627 | 189.2555 | 185.1112 | 181.3557 | 177.2597 | 172.9743 | 166.1644 | 161.8561 | 156.4503 | 157.7807 | 158.2423 | 158.5448 | 158.6982 | 157.8684 | 155.7841 | 153.2398 | 149.3559 | 144.3043 | 137.2461 | 112.4017 | 89.4101 | 61.4879 | 38.8238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 179.2741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7754 | 9.3976 | 9.0716 | 9.0635 | 8.7687 | 8.6852 | 8.3506 | 8.2838 | 7.8279 | 7.7514 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 7.4762 | 7.5604 | 7.3389 | 7.3387 | 7.0361 | 6.9108 | 6.5013 | 5.383 | 4.2121 | 2.9447 | 1.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 209.7522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2729 | 3.6686 | 3.3072 | 4.1443 | 3.7555 | 4.096 | 4.2854 | 6.8099 | 4.3082 | 5.4059 | 0 | 0 | 0 | 0 | 0.82987 | 2.0843 | 2.5443 | 3.8839 | 5.0516 | 7.0582 | 24.8444 | 22.9915 | 27.9223 | 22.6641 | 38.8238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 207.5042 | 196.2313 | 192.5627 | 189.2555 | 185.1112 | 181.3557 | 177.2597 | 172.9743 | 166.1644 | 161.8561 | 156.4503 | 157.7807 | 158.2423 | 158.5448 | 158.6982 | 157.8684 | 155.7841 | 153.2398 | 149.3559 | 144.3043 | 137.2461 | 112.4017 | 89.4101 | 61.4879 | 38.8238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7308 | 12.1377 | 21.2737 | 31.6857 | 42.5844 | 54.5922 | 67.3253 | 78.9435 | 93.7823 | 109.4463 | 124.3965 | 133.1506 | 142.4692 | 152.7221 | 163.7509 | 166.8717 | 179.6802 | 193.5876 | 208.4553 | 224.6433 | 241.9209 | 260.5146 | 280.3899 | 299.6896 | 322.7423 | 346.8958 | 372.6839 | 358.0248 | 343.8481 | 329.1128 | 314.9068 | 289.7252 | 269.033 | 252.1128 | 236.2477 | 219.7992 | 203.8457 | 187.3125 | 171.314 | 152.7938 | 136.6801 | 121.9011 | 115.3297 | 108.2606 | 101.7176 | 94.5893 | 88.0582 | 68.6101 | 54.363 | 44.6534 | 17.0687
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089552 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 17.0687
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.0194
|  | Liquidation distribution at PPA expiry | USD m |  | 44.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.0194
|  | Dividends | USD m |  | 1024.4135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089552 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 61.0881
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7308 | 12.1377 | 21.2737 | 31.6857 | 42.5844 | 54.5922 | 67.3253 | 78.9435 | 93.7823 | 109.4463 | 124.3965 | 133.1506 | 142.4692 | 152.7221 | 163.7509 | 166.8717 | 179.6802 | 193.5876 | 208.4553 | 224.6433 | 241.9209 | 260.5146 | 280.3899 | 299.6896 | 322.7423 | 346.8063 | 332.02 | 317.7541 | 302.9669 | 288.6175 | 273.916 | 242.6034 | 225.5817 | 209.6056 | 193.0189 | 176.9684 | 160.3807 | 144.2437 | 127.9972 | 109.2715 | 94.5523 | 87.8598 | 80.6405 | 73.9922 | 66.8065 | 60.1035 | 53.0455 | 26.2108 | 16.4191 | 7.1116 | -44.0194
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1413.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.0483 | 13.0662 | 12.3788 | 13.2078 | 12.5242 | 12.7812 | 12.636 | 15.0938 | 12.1362 | 13.1572 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 8.3061 | 9.6446 | 9.8833 | 11.2226 | 12.0877 | 13.969 | 31.3458 | 28.3745 | 32.1343 | 25.6088 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 61.0881

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 801.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6715 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 16.0289 | 13.3574
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 471.2862 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6608 | 31.153 | 29.8058 | 28.705 | 28.3175 | 27.272 | 26.6851 | 25.5016 | 24.9182 | 24.0495 | 23.4461 | 22.1662 | 21.465 | 20.1943 | 19.2549 | 17.8812 | 16.8445 | 15.4332 | 14.1924 | 12.4716 | 11.0295 | 9.2165 | 7.5491 | 5.8042 | 3.9518 | 2.3173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 797.8366 | 776.1976 | 754.5586 | 732.9197 | 711.2807 | 689.6418 | 668.0028 | 646.3638 | 624.7249 | 603.0859 | 581.8477 | 562.613 | 543.3784 | 524.1438 | 504.9091 | 485.6745 | 466.4399 | 447.2052 | 427.9706 | 408.736 | 389.5013 | 370.2667 | 351.0321 | 331.7974 | 312.5628 | 293.3282 | 274.0935 | 254.8589 | 235.6243 | 216.3896 | 197.155 | 177.9204 | 158.6857 | 139.4511 | 120.2165 | 100.9818 | 81.7472 | 62.5126 | 43.2779 | 24.0433 | 7.8809 | 7.0794 | 6.278 | 5.4765 | 4.6751 | 3.8736 | 3.0722 | 2.2708 | 1.4693 | 0.66787 | 0
|  | Book value of plant (from COD) | USD m |  |  | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 801.4431 | 798.7716 | 782.7427 | 766.7139 | 750.685 | 734.6561 | 718.6273 | 702.5984 | 686.5696 | 670.5407 | 654.5118 | 638.483 | 622.4541 | 606.4253 | 590.3964 | 574.3675 | 558.3387 | 542.3098 | 526.2809 | 510.2521 | 494.2232 | 478.1944 | 462.1655 | 446.1366 | 430.1078 | 414.0789 | 398.0501 | 382.0212 | 365.9923 | 349.9635 | 333.9346 | 317.9057 | 301.8769 | 285.848 | 269.8192 | 253.7903 | 237.7614 | 221.7326 | 205.7037 | 189.6749 | 173.646 | 157.6171 | 141.5883 | 125.5594 | 109.5306 | 93.5017 | 77.4728 | 61.444 | 45.4151 | 29.3862 | 13.3574 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -0.80144 | -5.6101 | -10.4188 | -15.2274 | -20.0361 | -24.8447 | -29.6534 | -34.4621 | -39.2707 | -44.0794 | -47.5075 | -43.603 | -39.4557 | -34.9072 | -30.0255 | -28.5352 | -22.8907 | -16.773 | -10.243 | -3.1465 | 4.4178 | 12.5471 | 21.2262 | 29.4931 | 30.4548 | 31.4166 | 32.3783 | 33.34 | 34.3018 | 35.2635 | 36.2252 | 37.187 | 38.1487 | 39.1104 | 40.0722 | 41.0339 | 41.9956 | 42.9573 | 43.9191 | 44.8808 | 44.9209 | 40.3527 | 35.7844 | 31.2162 | 26.648 | 22.0798 | 17.5115 | 12.9433 | 8.3751 | 3.8069 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.80144 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -4.8087 | -3.4282 | 3.9045 | 4.1473 | 4.5485 | 4.8816 | 1.4903 | 5.6445 | 6.1177 | 6.53 | 7.0965 | 7.5643 | 8.1293 | 8.6792 | 8.2669 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.96173 | 0.040072 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -4.5682 | -3.8069
|  | Net income | USD m |  | 980.3941 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7308 | 7.4069 | 9.136 | 10.4119 | 10.8988 | 12.0077 | 12.7331 | 11.6182 | 14.8388 | 15.664 | 14.9502 | 8.7541 | 9.3187 | 10.2529 | 11.0288 | 3.1207 | 12.8086 | 13.9074 | 14.8677 | 16.188 | 17.2776 | 18.5938 | 19.8752 | 19.2997 | 23.0528 | 24.1535 | 25.8776 | 26.0048 | 26.094 | 26.1458 | 26.2893 | 15.8092 | 26.4296 | 26.531 | 26.6421 | 26.7803 | 26.8773 | 26.9318 | 27.0703 | 24.7966 | 27.4085 | 27.3488 | 27.4699 | 27.6201 | 27.7254 | 27.7827 | 27.9548 | 15.5646 | 28.1522 | 28.2343 | 9.9571
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 798.7716 | 782.7427 | 766.7139 | 750.685 | 734.6561 | 718.6273 | 702.5984 | 686.5696 | 670.5407 | 654.5118 | 638.483 | 622.4541 | 606.4253 | 590.3964 | 574.3675 | 558.3387 | 542.3098 | 526.2809 | 510.2521 | 494.2232 | 478.1944 | 462.1655 | 446.1366 | 430.1078 | 414.0789 | 398.0501 | 382.0212 | 365.9923 | 349.9635 | 333.9346 | 317.9057 | 301.8769 | 285.848 | 269.8192 | 253.7903 | 237.7614 | 221.7326 | 205.7037 | 189.6749 | 173.646 | 157.6171 | 141.5883 | 125.5594 | 109.5306 | 93.5017 | 77.4728 | 61.444 | 45.4151 | 29.3862 | 13.3574 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 65.075 | 37.4322 | 37.6677 | 38.52 | 38.6957 | 39.4644 | 40.0975 | 37.9633 | 36.0745 | 38.4997 | 40.0487 | 42.5081 | 43.6463 | 45.2575 | 47.3514 | 34.8798 | 33.2229 | 32.7801 | 31.526 | 30.3907 | 28.2704 | 25.6693 | 26.4843 | 19.9861 | 18.5826 | 2.4008 | 4.8015 | 7.2023 | 9.6031 | 12.0038 | 14.4046 | 0 | 0 | 0.60292 | 1.2058 | 1.8088 | 2.4117 | 3.0146 | 3.8706 | 1.788 | 3.3398 | 7.7658 | 12.209 | 16.6695 | 21.1476 | 25.6434 | 30.1572 | 14.6879 | 16.3808 | 18.0922 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.2208 | 39.7875 | 39.2626 | 40.197 | 39.6944 | 40.7947 | 40.3274 | 40.8137 | 40.4001 | 42.2226 | 41.6213 | 42.618 | 42.0878 | 43.2677 | 42.6897 | 42.5467 | 42.3546 | 44.8063 | 44.1694 | 45.2335 | 44.6735 | 45.9395 | 45.4122 | 45.9537 | 45.4975 | 47.5975 | 46.9223 | 48.0591 | 47.4669 | 48.8258 | 48.1695 | 47.999 | 47.7867 | 50.613 | 49.8964 | 51.1119 | 50.4848 | 51.9441 | 51.347 | 51.9532 | 51.4471 | 53.8708 | 53.1094 | 54.4099 | 53.7452 | 55.3129 | 54.5652 | 54.3629 | 54.127 | 57.3904 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.80144 | 5.6101 | 10.4188 | 15.2274 | 20.0361 | 24.8447 | 29.6534 | 34.4621 | 39.2707 | 44.0794 | 47.5075 | 43.603 | 39.4557 | 34.9072 | 30.0255 | 28.5352 | 22.8907 | 16.773 | 10.243 | 3.1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 908.2189 | 870.9226 | 859.413 | 849.9794 | 838.4323 | 829.081 | 818.0267 | 805.1587 | 791.636 | 784.6636 | 773.0105 | 756.5332 | 736.965 | 719.1788 | 699.7842 | 669.6503 | 646.128 | 625.9903 | 601.5405 | 578.3439 | 556.4882 | 539.1243 | 523.3832 | 501.3976 | 483.5089 | 453.3983 | 439.095 | 426.6038 | 412.3834 | 400.1143 | 385.8298 | 355.2259 | 338.9847 | 326.3851 | 310.2425 | 296.0321 | 279.979 | 266.0124 | 250.2424 | 232.7372 | 217.754 | 208.5749 | 196.2278 | 185.96 | 173.7445 | 163.7792 | 151.5164 | 119.8159 | 105.244 | 94.19 | 0
|  | Senior debt | USD m |  |  | 100.4722 | 147.866 | 240.6622 | 357.9848 | 465.8575 | 535.9028 | 628.2979 | 593.8029 | 577.2045 | 560.0215 | 542.0324 | 523.5425 | 504.2063 | 483.8135 | 462.4846 | 442.6316 | 421.8438 | 394.5855 | 365.5749 | 336.2754 | 306.1644 | 273.9549 | 239.8632 | 206.2961 | 171.3053 | 136.2198 | 100.0923 | 79.8146 | 58.9257 | 37.0731 | 18.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 28.9957 | 43.8832 | 72.5134 | 109.5476 | 145.7599 | 172.8445 | 207.5042 | 196.2313 | 192.5627 | 189.2555 | 185.1112 | 181.3557 | 177.2597 | 172.9743 | 166.1644 | 161.8561 | 156.4503 | 157.7807 | 158.2423 | 158.5448 | 158.6982 | 157.8684 | 155.7841 | 153.2398 | 149.3559 | 144.3043 | 137.2461 | 112.4017 | 89.4101 | 61.4879 | 38.8238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.6665 | 24.7312 | 24.3526 | 24.9974 | 24.6849 | 25.5712 | 25.2161 | 25.4079 | 25.1853 | 26.7101 | 26.3006 | 26.9971 | 26.6592 | 27.6171 | 27.1512 | 26.9361 | 26.7811 | 28.8474 | 28.4047 | 29.1572 | 28.7918 | 29.8269 | 29.4118 | 29.6346 | 29.3744 | 31.1561 | 30.6773 | 31.4903 | 31.0953 | 32.2139 | 31.6692 | 31.4162 | 31.2349 | 33.6497 | 33.1321 | 34.0103 | 33.5833 | 34.792 | 34.3068 | 34.5655 | 34.2614 | 36.3431 | 35.7834 | 36.7322 | 36.2706 | 37.5766 | 36.94 | 36.6425 | 36.4305 | 39.2521 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4178 | 12.5471 | 21.2262 | 29.4931 | 30.4548 | 31.4166 | 32.3783 | 33.34 | 34.3018 | 35.2635 | 36.2252 | 37.187 | 38.1487 | 39.1104 | 40.0722 | 41.0339 | 41.9956 | 42.9573 | 43.9191 | 44.8808 | 44.9209 | 40.3527 | 35.7844 | 31.2162 | 26.648 | 22.0798 | 17.5115 | 12.9433 | 8.3751 | 3.8069 | 0
|  | Share capital | USD m |  |  | 7.0392 | 10.3597 | 16.8611 | 25.0809 | 32.6386 | 37.5461 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194 | 44.0194
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7308 | 12.1377 | 21.2737 | 31.6857 | 42.5844 | 54.5922 | 67.3253 | 78.9435 | 93.7823 | 109.4463 | 124.3965 | 133.1506 | 142.4692 | 152.7221 | 163.7509 | 166.8717 | 179.6802 | 193.5876 | 208.4553 | 224.6433 | 241.9209 | 260.5146 | 280.3899 | 299.6896 | 322.7423 | 346.8063 | 332.02 | 317.7541 | 302.9669 | 288.6175 | 273.916 | 242.6034 | 225.5817 | 209.6056 | 193.0189 | 176.9684 | 160.3807 | 144.2437 | 127.9972 | 109.2715 | 94.5523 | 87.8598 | 80.6405 | 73.9922 | 66.8065 | 60.1035 | 53.0455 | 26.2108 | 16.4191 | 7.1116 | -44.0194
|  | Total liabilities and equity | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 908.2189 | 870.9226 | 859.413 | 849.9794 | 838.4323 | 829.081 | 818.0267 | 805.1587 | 791.636 | 784.6636 | 773.0105 | 756.5332 | 736.965 | 719.1788 | 699.7842 | 669.6503 | 646.128 | 625.9903 | 601.5405 | 578.3439 | 556.4882 | 539.1243 | 523.3832 | 501.3976 | 483.5089 | 453.3983 | 439.095 | 426.6038 | 412.3834 | 400.1143 | 385.8298 | 355.2259 | 338.9847 | 326.3851 | 310.2425 | 296.0321 | 279.979 | 266.0124 | 250.2424 | 232.7372 | 217.754 | 208.5749 | 196.2278 | 185.96 | 173.7445 | 163.7792 | 151.5164 | 119.8159 | 105.244 | 94.19 | 3.0155e-11
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034025 | 0.034369 | 0.034015 | 0.034381 | 0.034137 | 0.034381 | 0.034016 | 0.034382 | 0.035075 | 0.035458 | 0.035074 | 0.035249 | 0.034735 | 0.03468 | 0.033985 | 0.033889 | 0.033745 | 0.033223 | 0.03173 | 0.030236 | 0.027126 | 0.027139 | 0.02702 | 0.027167 | 0.026991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 32
| Rate in final maturity period | factor | 0.026991
| Discount rate used | factor |  |  | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.034025 | 0.034369 | 0.034015 | 0.034381 | 0.034137 | 0.034381 | 0.034016 | 0.034382 | 0.035075 | 0.035458 | 0.035074 | 0.035249 | 0.034735 | 0.03468 | 0.033985 | 0.033889 | 0.033745 | 0.033223 | 0.03173 | 0.030236 | 0.027126 | 0.027139 | 0.02702 | 0.027167 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991 | 0.026991
| PV of CFADS to final maturity | USD m |  |  | 681.7842 | 700.186 | 719.0844 | 738.4929 | 758.4253 | 778.8956 | 799.9185 | 827.8014 | 807.1145 | 784.9712 | 762.05 | 738.0489 | 713.3832 | 687.585 | 660.3744 | 631.911 | 605.4564 | 577.7529 | 549.4809 | 519.7146 | 488.9818 | 456.6507 | 421.6179 | 384.5428 | 346.924 | 307.1433 | 265.9221 | 222.3741 | 177.1754 | 130.246 | 81.6449 | 39.6716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 957.4854 | 983.3285 | 1009.8691 | 1037.1261 | 1065.1187 | 1093.8669 | 1123.391 | 1160.0046 | 1150.6208 | 1140.2833 | 1129.448 | 1118.0783 | 1106.3855 | 1094.0992 | 1080.7164 | 1066.7052 | 1055.5009 | 1043.755 | 1031.8277 | 1019.0637 | 1005.676 | 991.2639 | 974.4 | 956.0583 | 937.7254 | 917.5726 | 895.7202 | 871.2149 | 843.617 | 814.7743 | 784.6692 | 761.7947 | 741.6137 | 720.9664 | 700.155 | 678.1714 | 655.9804 | 632.6949 | 602.6498 | 575.4645 | 548.4894 | 520.0647 | 491.2708 | 461.0654 | 430.4411 | 398.489 | 364.1873 | 330.3373 | 303.6433 | 275.5638 | 247.1298 | 217.2681 | 187.008 | 155.3863 | 115.5064 | 78.9872 | 41.8659
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.377 | 1.4216 | 1.4237 | 1.4273 | 1.4299 | 1.4339 | 1.4382 | 1.4434 | 1.4443 | 1.4503 | 1.455 | 1.4849 | 1.519 | 1.5587 | 1.6066 | 1.6663 | 1.7417 | 1.8381 | 1.9711 | 2.1641 | 2.4839 | 2.5097 | 2.6082 | 2.7414 | 3.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3175 | 1.3592 | 1.36 | 1.3608 | 1.3616 | 1.3626 | 1.3637 | 1.3649 | 1.3663 | 1.3679 | 1.3696 | 1.3926 | 1.4216 | 1.4541 | 1.4915 | 1.539 | 1.6032 | 1.6817 | 1.793 | 1.9522 | 2.2217 | 2.2198 | 2.2103 | 2.2023 | 2.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8463 | 1.9377 | 1.9755 | 2.0168 | 2.0628 | 2.1133 | 2.1699 | 2.2337 | 2.3065 | 2.3846 | 2.4743 | 2.615 | 2.7876 | 2.9906 | 3.2377 | 3.5568 | 3.9858 | 4.5455 | 5.3564 | 6.5756 | 8.7041 | 10.5697 | 13.8271 | 21.1655 | 42.1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR (debt-service weighted) | x | #VALUE!
| LLCR at first debt service period | x | 1.377
| PLCR at first debt service period | x | 1.8463

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1193.3428 | -14.2 | -17.3226 | -0.64195 | -0.76782 | -0.97825 | -1.2855 | -1.649 | -2.0409 | -2.5148 | -2.9808 | -3.4732 | -3.9436 | -4.4102 | -4.8609 | -5.2734 | -5.6664 | -5.9977 | -6.2986 | -6.8196 | -6.6754 | -6.8153 | -6.9519 | -6.9583 | -6.8784 | -6.7418 | -6.5527 | -6.2942 | -6.4271 | -6.0706 | -5.7021 | -5.4155 | -4.933 | -4.5252 | -3.5456 | -3.4639 | -2.6541 | -2.0772 | -1.4604 | -1.8569 | -1.1454 | -15.7938 | -10.0331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.0483 | 13.0662 | 12.3788 | 13.2078 | 12.5242 | 12.7812 | 12.636 | 15.0938 | 12.1362 | 13.1572 | 6.0399 | 7.0946 | 7.1935 | 7.4393 | 8.3061 | 9.6446 | 9.8833 | 11.2226 | 12.0877 | 13.969 | 31.3458 | 28.3745 | 32.1343 | 25.6088 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.3168 | 43.5223 | 42.1278 | 34.0413 | 34.6891 | 34.2685 | 34.9111 | 34.4858 | 35.0127 | 42.3993 | 37.9439 | 37.5418 | 61.0881
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1553.3318 | 0 | -108.0297 | -1.3972 | -1.8346 | -2.6432 | -3.7572 | -5.1 | -6.6364 | -8.3024 | -10.0481 | -11.8263 | -13.5942 | -15.2687 | -16.8967 | -18.4073 | -19.7734 | -20.9699 | -21.9775 | -23.8447 | -23.2809 | -23.6324 | -24.0907 | -23.9749 | -23.6234 | -22.976 | -22.1807 | -21.1798 | -21.5581 | -20.2013 | -18.7008 | -17.5752 | -15.8809 | -14.1371 | -10.4741 | -10.0152 | -6.9519 | -5.882 | -3.5518 | -5.1 | -2.3526 | -57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 48.8525 | 49.8827 | 49.6219 | 50.2009 | 49.8604 | 50.3249 | 50.5993 | 51.1683 | 48.6187 | 49.1716 | 48.5363 | 49.135 | 48.7854 | 49.2891 | 50.5521 | 51.3634 | 50.5953 | 51.3064 | 50.9668 | 51.5884 | 51.2309 | 51.7379 | 52.1204 | 44.1913 | 40.7423 | 40.6638 | 40.2708 | 40.8811 | 40.4953 | 40.9909 | 47.1218 | 43.4513 | 42.5072 | 43.2288 | 42.8308 | 43.465 | 43.0688 | 43.5699 | 45.0572 | 43.6795 | 35.61 | 36.275 | 35.8717 | 36.5318 | 36.1243 | 36.6692 | 44.0739 | 39.6367 | 39.2532 | 42.9959
| Project cash flow, pre-tax | USD m |  | 1879.3767 | 0 | -108.0297 | -1.3972 | -1.8346 | -2.6432 | -3.7572 | -5.1 | -6.6364 | -8.3024 | -10.0481 | -11.8263 | -13.5942 | -15.2687 | -16.8967 | -18.4073 | -19.7734 | -20.9699 | -21.9775 | -23.8447 | -23.2809 | -23.6324 | -24.0907 | -23.9749 | -23.6234 | -22.976 | -22.1807 | -21.1798 | -21.5581 | -20.2013 | -18.7008 | -17.5752 | -15.8809 | -14.1371 | -10.4741 | -10.0152 | -6.9519 | -5.882 | -3.5518 | -5.1 | -2.3526 | -57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 48.8525 | 49.8827 | 49.6219 | 50.2009 | 49.8604 | 50.3249 | 50.5993 | 51.1683 | 48.6187 | 49.2308 | 48.8929 | 49.4933 | 49.1457 | 49.6507 | 50.9089 | 51.7253 | 50.9626 | 51.6755 | 51.3372 | 51.9607 | 51.6055 | 52.1141 | 52.4971 | 53.1093 | 50.1321 | 50.7925 | 50.454 | 51.1026 | 50.7389 | 51.296 | 52.9355 | 53.8165 | 52.9159 | 53.6851 | 53.3463 | 54.0221 | 53.6492 | 54.2097 | 54.7227 | 55.386 | 51.8992 | 52.6161 | 52.2771 | 52.9824 | 52.5994 | 53.218 | 55.3127 | 56.2702 | 55.9218 | 51.0701
| Cumulative equity cash flow | USD m |  |  | -14.2 | -31.5226 | -32.1645 | -32.9323 | -33.9106 | -35.1961 | -36.8451 | -38.886 | -41.4008 | -44.3816 | -47.8548 | -51.7984 | -56.2087 | -61.0695 | -66.3429 | -72.0092 | -78.007 | -84.3056 | -91.1251 | -97.8005 | -104.6158 | -111.5677 | -118.526 | -125.4045 | -132.1463 | -138.699 | -144.9932 | -151.4203 | -157.4909 | -163.193 | -168.6085 | -173.5415 | -178.0667 | -181.6123 | -185.0762 | -187.7303 | -189.8075 | -191.2678 | -193.1247 | -194.2701 | -210.0639 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -220.0969 | -199.0486 | -185.9824 | -173.6036 | -160.3958 | -147.8716 | -135.0904 | -122.4544 | -107.3606 | -95.2244 | -82.0672 | -76.0274 | -68.9328 | -61.7393 | -54.3 | -45.9939 | -36.3493 | -26.466 | -15.2434 | -3.1557 | 10.8132 | 42.159 | 70.5335 | 102.6678 | 128.2766 | 169.0189 | 209.6827 | 249.9535 | 290.8346 | 331.3299 | 372.3208 | 419.4426 | 462.8938 | 505.401 | 548.6298 | 591.4606 | 634.9256 | 677.9944 | 721.3112 | 764.8335 | 806.9613 | 841.0026 | 875.6917 | 909.9602 | 944.8712 | 979.357 | 1014.3698 | 1056.7691 | 1094.7129 | 1132.2547 | 1193.3428
| Equity IRR (XIRR) | % | 13.34%
| Project IRR, post-tax (XIRR) | % | 10.48%
| Project IRR, pre-tax (XIRR) | % | 11.15%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -40.4343

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 0
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 0

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 848.3949
| Senior debt (four tranches) | USD m | 633.256
| Equity (incl. LNTP) | USD m | 220.0969
| Gearing (debt incl. standby / total funding) | % | 74.06%
| Interest during construction incl. swap and PRI | USD m | 62.521
| Commitment, upfront and agency fees | USD m | 23.1306
| ECA premium | USD m | 20.4511
| DSRA initial funding | USD m | 35.663
| Standby drawn | USD m | 0
| Contingent equity drawn | USD m | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR | x | #VALUE!
| LLCR at first debt service period (incl. DSRA) | x | 1.377
| PLCR at first debt service period | x | 1.8463
| Equity IRR | % | 13.34%
| Project IRR, post-tax | % | 10.48%
| Equity NPV at 16.0% (at FC) | USD m | -40.4343
| All checks | check | 0