## Cover
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Case P companion model
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
Companion model for Chapters 39-45. Python mirror: model/case_p.py (source of truth).
Select the scenario on the Inputs sheet (cell named Scenario):
1: FC base
2: FC banking
3: FC downside
4: Sens: availability -3 points
5: Sens: heat rate +2%
6: Sens: fixed opex +10%
7: Sens: capex +10% funded pro rata
8: Sens: COD delay 6 months, no LDs
9: Sens: base rate +200 bps (unhedged)
10: Sens: KCR devaluation 40%, 90-day lag
11: Sens: SEKA pays 120 days late for 12 months
12: Sens: dispatch 50%
13: Sens: gas price +30%
14: COD re-forecast (2021 lenders case)
15: Actual history
Circularity: none. IDC/fee/premium/DSRA gross-up is solved in closed form on the Funding sheet
(balance = alpha + beta x T; T = alpha/(g - beta)). Sculpting with tax uses the contractual
repayment profile on Inputs; the Debt sheet recomputes the sculpted profile live and the
Checks sheet reports the difference (Python iterates the profile to convergence, tolerance USD 1,000).
Sheets: Cover, Inputs, Time, Construction, Operations, Tax, Funding, Debt, Reserves, Waterfall, Financials, Ratios, Returns, Checks, Outputs
Sign convention: costs stored positive and subtracted explicitly.

## Inputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Inputs: scenario selector, assumptions, contract terms
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Scenario table: columns J-X = scenarios 1-15; semiannual rows: columns = periods; annual rows: columns = years 2015+ |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Scenario control
|  | Scenario selector (1-15, see table below) | index | 15
Live scenario parameters (selected from the scenario table)
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
|  | Construction case (1 FC budget, 2 actual) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | COD delay (sensitivity) [table] | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capex factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Availability adjustment [table] | points |  |  | 0 | 0 | -6.5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dispatch factor when available [table] | % |  |  | 76.5 | 72 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 50 | 76.5 | 76.5 | 76.5
|  | Plant heat rate factor [table] | factor |  |  | 1 | 1 | 1.015 | 1 | 1.02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Fixed opex factor [table] | factor |  |  | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Gas price factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1
|  | Base rate shift from 2022H1 [table] | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR devaluation from 2022H1 [table] | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 [table] | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 0 | 0 | 0
|  | Offtaker crisis events (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Insurance market step-up from 2022H2 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
|  | Performance LD prepayment June 2022 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Waiver and amendment 2023 (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2025 bond refinancing (1 = on) [table] | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) [table] | code |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft mini-perm sweep (1 = on) [table] | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Shareholder loan share of equity [table] | fraction |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Capital charge factor [table] | factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Macro path (1 FC forward, 2 actual history, 3 COD re-forecast) | code | 2
|  | Construction case (1 FC budget, 2 actual) | code | 2
|  | COD delay (sensitivity) | months | 0
|  | Capex factor | factor | 1
|  | Availability adjustment | points | 0
|  | Dispatch factor when available | % | 76.5
|  | Plant heat rate factor | factor | 1
|  | Fixed opex factor | factor | 1
|  | Gas price factor | factor | 1
|  | Base rate shift from 2022H1 | % | 0
|  | KCR devaluation from 2022H1 | fraction | 0
|  | Extra days on SEKA capacity/VOM payments, 2022H1-2022H2 | days | 0
|  | Offtaker crisis events (1 = on) | flag | 1
|  | Insurance market step-up from 2022H2 (1 = on) | flag | 1
|  | Repayment profile (1 FC contract, 2 COD re-sculpted) | code | 2
|  | Performance LD prepayment June 2022 (1 = on) | flag | 1
|  | Waiver and amendment 2023 (1 = on) | flag | 1
|  | 2025 bond refinancing (1 = on) | flag | 1
|  | Funding mode (1 committed amounts, 2 re-grossed pro rata) | code | 1
|  | Soft mini-perm sweep (1 = on) | flag | 1
|  | Shareholder loan share of equity | fraction | 0.8
|  | Capital charge factor | factor | 1
Capital cost (USD m unless stated)
|  | EPC contract price | USD m | 571.84
|  | of which offshore portion | USD m | 489.17
|  | of which onshore portion | USD m | 82.67
|  | Onshore portion fixed in KCR at | KCR/USD | 519.4
|  | Owner's costs | USD m | 46.18
|  | Insurance during construction | USD m | 7.62
|  | Development costs reimbursed at FC | USD m | 21.43
|  | Development fee at FC | USD m | 11.2
|  | Lenders' advisors and legal | USD m | 8.97
|  | Contingency | USD m | 38.4
|  | Initial working capital (spares, fuel) | USD m | 5.35
|  | LNTP paid February 2018 (equity credit at FC) | USD m | 14.2
|  | Extended owner's costs (actual, months 34-40) | USD m | 6.93
|  | VAT on onshore EPC | % | 18
|  | VAT facility margin over policy rate | % | 2.5
|  | VAT facility limit | KCR m | 7900
|  | Policy rate, FC expectation | % | 13.5
Senior debt terms
|  | ECA-covered tranche share | fraction | 0.3
|  | ABDB A-loan share | fraction | 0.22
|  | ABDB B-loan share | fraction | 0.1
|  | Commercial tranche share | fraction | 0.38
|  | ECA margin | % | 1.35
|  | A-loan margin | % | 3.65
|  | B-loan margin | % | 3.4
|  | Commercial margin to 2025 | % | 4.1
|  | Commercial margin 2026-2029 | % | 4.6
|  | Commercial margin from 2030 | % | 5.1
|  | ECA commitment fee | % pa | 0.45
|  | A-loan commitment fee | % pa | 0.75
|  | B-loan commitment fee | % pa | 0.85
|  | Commercial commitment fee (% of margin) | % | 40
|  | ECA arrangement fee | % | 1.1
|  | A-loan front-end fee | % | 1.25
|  | B-loan upfront fee | % | 1.5
|  | Commercial upfront fee | % | 2.15
|  | Withholding tax on commercial interest (grossed up) | % | 10
|  | ECA premium (% of ECA drawdowns, financed) | % | 10.85
|  | PRI premium | % pa | 1.15
|  | PRI cover of commercial tranche | % | 90
|  | Swap fixed rate | % | 2.947
|  | ISDA 6M spread adjustment | % | 0.42826
|  | Standby facility | USD m | 46
|  | Standby commitment fee | % pa | 0.6
|  | Standby margin over tranche margin | % | 0.25
|  | Standby commercial share | fraction | 0.6
|  | Contingent equity | USD m | 15.4
|  | Shareholder loan rate | % pa | 9.5
|  | Gearing cap | fraction | 0.75
|  | Sizing DSCR target | x | 1.35
|  | Agency and account fees | USD m pa | 0.255
|  | Lock-up historic DSCR | x | 1.2
|  | Event of default DSCR | x | 1.1
|  | Waiver release DSCR (two consecutive tests) | x | 1.25
|  | Soft mini-perm sweep share (from 2027) | fraction | 0.5
Contract terms fixed at financial close (from the FC base sizing run)
|  | Senior debt commitment (total, 4 tranches) | USD m | 633.256
|  | Equity commitment (base, incl. LNTP) | USD m | 221.8338
Plant and PPA
|  | Contracted capacity (FC) | MW | 588.4
|  | Contracted capacity after tests | MW | 581.9
|  | Guaranteed net heat rate | kJ/kWh | 6261
|  | Tested net heat rate | kJ/kWh | 6286
|  | PPA contracted heat rate | kJ/kWh | 6323
|  | Contracted HR degradation allowance | % pa | 0.1
|  | Average part-load penalty | % | 2.3
|  | HHV/LHV ratio | factor | 1.108
|  | kJ per MMBtu | kJ | 1055056
|  | Output degradation, non-recoverable | % pa | 0.15
|  | Output degradation, recoverable average | % | 1
|  | Heat-rate degradation, non-recoverable | % pa | 0.12
|  | Heat-rate degradation, recoverable average | % | 0.8
|  | GT operating hours per year | h | 8059
|  | GT starts per year | starts | 38
|  | EOH per start | h | 10
|  | PPA availability target | % | 90
|  | Capital charge (Nov 2016 prices) | USD/kW-month | 14.36
|  | Capital charge indexed share | fraction | 0.2
|  | Fixed O&M charge | USD/kW-month | 2.31
|  | Fixed O&M US CPI share | fraction | 0.62
|  | Bid base FX rate | KCR/USD | 462.35
|  | Variable O&M charge | USD/MWh | 3.86
|  | VOM US CPI share | fraction | 0.7
Fuel and transport
|  | GSA gas price 2018 | USD/MMBtu | 5.86
|  | GSA escalation | % pa | 2
|  | Daily contract quantity | MMBtu/d | 72400
|  | Take-or-pay level | fraction | 0.8
|  | GTA reserved capacity | MMBtu/d | 96500
|  | GTA reservation charge 2018 | USD/MMBtu | 0.62
|  | GTA commodity charge 2018 | USD/MMBtu | 0.19
|  | GTA escalation | % pa | 1.5
Operating costs (2018 prices)
|  | O&M fixed fee | USD m pa | 7.92
|  | O&M USD share | fraction | 0.65
|  | KCR conversion rate for 2018-price local costs | KCR/USD | 516.8
|  | O&M availability incentive (max) | USD m pa | 0.6
|  | LTSA fixed fee | USD m pa | 2.64
|  | LTSA variable fee | USD/EOH/GT | 486
|  | Operational insurance | USD m pa | 4.37
|  | Insurance market step-up (actual, from 2022H2) | fraction | 0.18
|  | Project company G&A | USD m pa | 3.18
|  | Land lease and permits | KCR m pa | 368
|  | Community fund + OREK levy | % of non-fuel revenue | 0.55
|  | Variable consumables | USD/MWh | 1.08
|  | ABDB PRG fee (0.75% x USD 41.5m) | USD m pa | 0.31125
|  | Major maintenance outside LTSA (OY8, 16, 24) | USD m | 9.47
|  | HRSG/BOP works outside LTSA (OY4, 12, 20) | USD m | 2.18
|  | Handback reserve from OY20 | USD m pa | 1.85
Working capital
|  | Receivable days | days | 45
|  | Gas payable days | days | 45
|  | GTA payable days | days | 30
|  | O&M/LTSA payable days | days | 30
|  | Other payable days | days | 30
Tax
|  | Corporate income tax | % | 30
|  | Reduced rate OY6-OY8 | % | 15
|  | Minimum turnover tax (non-fuel revenue, from OY6) | % | 0.5
|  | Plant share of capitalized cost | fraction | 0.92
|  | Plant life | months | 240
|  | Buildings share | fraction | 0.05
|  | Buildings life | months | 300
|  | Intangibles share | fraction | 0.03
|  | Intangibles life | months | 60
|  | Thin capitalization ratio (SHL to equity) | x | 3
|  | Deferred tax rate | % | 30
Events (actual history)
|  | Share of SEKA arrears matched by deferred SNHK/GCK payables (calibration) | fraction | 0.8
|  | Late payment interest spread | % | 2
|  | Late payment interest received (1 - waived) | fraction | 0.6
|  | EPC delay LDs received Nov 2021 | USD m | 10.1393
|  | DSU insurance proceeds Nov 2021 | USD m | 7.0804
|  | Performance LDs (prepay June 2022) | USD m | 18.485
|  | Waiver fee | % of senior debt | 0.25
|  | Margin uplift 2023H2-2024H2 | % | 0.5
|  | Deferred share of 2023-12-31 principal | fraction | 0.6
|  | Bond coupon | % | 7.875
|  | Bond issue price | fraction | 0.99512
|  | Underwriting fee | fraction | 0.01
|  | Other transaction costs | USD m | 3.1
|  | ABDB partial credit guarantee | USD m | 95
|  | PCG fee | % pa | 1.1
|  | PCG upfront fee | % | 0.75
|  | Flat swap rate for unwind | % | 3.68
|  | Share of swap terminated | fraction | 0.48
|  | Share of swap remaining after refi | fraction | 0.52
Annual tables (columns J = 2015 ... ): CPI annual average change (%), policy rate (%)
|  | Calendar year | year |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049
|  | US CPI, FC expectation | % |  |  | 0.1 | 1.3 | 2.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, FC expectation | % |  |  | 8.7 | 9.4 | 8.1 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | US CPI, actual history + assumptions | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 8 | 4.1 | 2.9 | 2.7 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI, actual history + assumptions | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 26.3 | 34.8 | 19.2 | 12.4 | 9.6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI, COD re-forecast | % |  |  | 0.1 | 1.3 | 2.1 | 2.4 | 1.8 | 1.2 | 4.7 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
|  | Kessara CPI, COD re-forecast | % |  |  | 8.7 | 9.4 | 8.1 | 7.6 | 7.9 | 9.8 | 10.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  | Kessara policy rate (actual) | % |  |  | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 27 | 24.5 | 18 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Semiannual inputs (column J = 2018H2 ... BN = 2046H2)
|  | 6M LIBOR forward curve at FC | % |  |  | 2.52 | 2.79 | 2.94 | 3.02 | 3.06 | 3.09 | 3.09 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | 6M LIBOR to 2022H2; 6M Term SOFR + CAS from 2023H1 (actual) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate, COD re-forecast | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 3.11 | 3.11 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12
|  | KCR per USD, semiannual average (actual to 2026H2) | KCR/USD |  |  | 2015: 524.6; 2016: 539.1; 2017: 551.3; 2018: 566; 2019: 579.8; 2020: 597.4; 2021: 609.6; 2022: 654.9; 2023: 830.3; 2024: 1052.8; 2025: 1043.8; 2026: 1093.1; 2027: 1050.7; 2028: 1035.6; 2029: 1023.8; 2030: 1028.9; 2031: 1043.9
|  | SEKA overdue receivables at period end (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses (actual) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Settlement installment share of late payment interest | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contract repayment profile at FC (share of debt) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02446 | 0.025496 | 0.026752 | 0.02754 | 0.028807 | 0.029725 | 0.031667 | 0.032635 | 0.031729 | 0.031744 | 0.03306 | 0.034024 | 0.03565 | 0.036831 | 0.040217 | 0.041945 | 0.043417 | 0.044227 | 0.046447 | 0.047811 | 0.050119 | 0.051741 | 0.054863 | 0.056004 | 0.046202 | 0.046887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COD re-sculpted repayment profile (share of debt at COD) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond amortization profile (share of face) | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011242 | 0.016602 | 0.018131 | 0.018079 | 0.019418 | 0.019457 | 0.020589 | 0.022638 | 0.02415 | 0.024378 | 0.025773 | 0.02586 | 0.02714 | 0.027257 | 0.028388 | 0.025763 | 0.02351 | 0.020506 | 0.089087 | 0.091053 | 0.095849 | 0.098063 | 0.10279 | 0.12428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, semiannual (contract) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 506.6048 | 494.213 | 481.2968 | 467.7443 | 453.7925 | 439.1989 | 424.1399 | 408.0971 | 391.5639 | 375.4896 | 359.4077 | 342.6596 | 325.4228 | 307.3624 | 288.7038 | 268.3299 | 247.0804 | 225.0853 | 202.6798 | 179.1495 | 154.9282 | 129.5377 | 103.3252 | 75.5312 | 47.1595 | 23.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Availability profile by OY (8-year cycle, cols J-Q) | % |  |  | 2015: 93.8; 2016: 92.9; 2017: 93.8; 2018: 90.6; 2019: 93.8; 2020: 92.9; 2021: 93.8; 2022: 88.7
Monthly inputs (column J = Aug 2018 ... BJ = Dec 2022)
|  | EPC payment profile, FC (33 months) | % |  |  | 10 | 0.0108 | 0.1133 | 0.3239 | 0.6294 | 1.0114 | 1.4496 | 1.9236 | 2.4133 | 2.8999 | 3.3659 | 3.7957 | 4.1755 | 4.4935 | 4.7405 | 4.9091 | 4.9946 | 4.9946 | 4.9091 | 4.7405 | 4.4935 | 4.1755 | 3.7957 | 3.3659 | 2.8999 | 2.4133 | 1.9236 | 1.4496 | 1.0114 | 0.6294 | 0.3239 | 0.1133 | 7.5108
|  | EPC payment profile, actual (40 months) | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102
|  | Owner's cost profile, FC | % |  |  | 12 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Overrun items, actual (excl. extended owners) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap notional schedule, monthly (contract) | USD m |  |  | 0 | 72.0383 | 73.5189 | 75.4062 | 78.0742 | 81.916 | 87.21 | 94.1162 | 102.8823 | 113.5022 | 126.0097 | 140.2836 | 156.2511 | 173.7077 | 192.4026 | 212.1225 | 232.525 | 253.3551 | 274.9625 | 295.5733 | 315.6943 | 334.9286 | 353.0762 | 369.8271 | 385.0659 | 398.6101 | 410.3342 | 420.3016 | 428.4805 | 435.0833 | 440.2743 | 444.2027 | 447.4816 | 479.625 | 504.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Time: semiannual operating timeline (monthly timeline on the Construction sheet)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Key dates (scenario-dependent)
|  | Commercial operation date | date | 2021-12-01
|  | PPA expiry | date | 2046-11-30
|  | Construction months (NTP to COD) | months | 40
|  | Period containing COD (period number) | index | 7
|  | First debt service period | index | 8
|  | Last month of the funding period (month number) | index | 41
|  | Last operating period (period number) | index | 57
|  | FC FX drift (Kessara 7.5% / US 2.2%) | factor | 1.0519
Semiannual timeline
|  | Period number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Period start | date | time axis 2018-07-01 to 2046-07-01
|  | Period end | date | time axis 2018-12-31 to 2046-12-31
|  | Days in period | days |  |  | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184
|  | Calendar year | year |  |  | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | 2022 | 2023 | 2023 | 2024 | 2024 | 2025 | 2025 | 2026 | 2026 | 2027 | 2027 | 2028 | 2028 | 2029 | 2029 | 2030 | 2030 | 2031 | 2031 | 2032 | 2032 | 2033 | 2033 | 2034 | 2034 | 2035 | 2035 | 2036 | 2036 | 2037 | 2037 | 2038 | 2038 | 2039 | 2039 | 2040 | 2040 | 2041 | 2041 | 2042 | 2042 | 2043 | 2043 | 2044 | 2044 | 2045 | 2045 | 2046 | 2046
|  | Half (1 = Jan-Jun) | index |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
|  | Operations start in period | date | time axis 2021-12-01 to 2046-07-01
|  | Operations end in period | date | time axis 2018-12-31 to 2046-11-30
|  | Operating months in period | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
|  | Operating days in period | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 184 | 181 | 184 | 182 | 184 | 181 | 184 | 181 | 153
|  | Operating months elapsed at period start | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 13 | 19 | 25 | 31 | 37 | 43 | 49 | 55 | 61 | 67 | 73 | 79 | 85 | 91 | 97 | 103 | 109 | 115 | 121 | 127 | 133 | 139 | 145 | 151 | 157 | 163 | 169 | 175 | 181 | 187 | 193 | 199 | 205 | 211 | 217 | 223 | 229 | 235 | 241 | 247 | 253 | 259 | 265 | 271 | 277 | 283 | 289 | 295
|  | Operating months elapsed at period end | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 13 | 19 | 25 | 31 | 37 | 43 | 49 | 55 | 61 | 67 | 73 | 79 | 85 | 91 | 97 | 103 | 109 | 115 | 121 | 127 | 133 | 139 | 145 | 151 | 157 | 163 | 169 | 175 | 181 | 187 | 193 | 199 | 205 | 211 | 217 | 223 | 229 | 235 | 241 | 247 | 253 | 259 | 265 | 271 | 277 | 283 | 289 | 295 | 300
|  | Flag_CODPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_DebtService (after COD period) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_Operations | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Flag_LastOperatingPeriod | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Flag_ShockPeriods (2022H1-2022H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag from 2022H1 | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Construction
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Construction: monthly uses of funds before financing costs, VAT
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Monthly timeline (column J = August 2018)
|  | Month number | index |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
|  | Month start | date | time axis 2018-08-01 to 2022-12-01
|  | Month end | date | time axis 2018-08-31 to 2022-12-31
|  | Days | days |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
|  | Semiannual period number | index |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9
|  | Flag_Construction (before COD) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_FundingPeriod (to end of COD period) | flag |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_CODMonth | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | KCR per USD | KCR/USD |  |  | 524.6 | 524.6 | 524.6 | 524.6 | 524.6 | 539.1 | 539.1 | 539.1 | 539.1 | 539.1 | 539.1 | 551.3 | 551.3 | 551.3 | 551.3 | 551.3 | 551.3 | 566 | 566 | 566 | 566 | 566 | 566 | 579.8 | 579.8 | 579.8 | 579.8 | 579.8 | 579.8 | 597.4 | 597.4 | 597.4 | 597.4 | 597.4 | 597.4 | 609.6 | 609.6 | 609.6 | 609.6 | 609.6 | 609.6 | 654.9 | 654.9 | 654.9 | 654.9 | 654.9 | 654.9 | 830.3 | 830.3 | 830.3 | 830.3 | 830.3 | 830.3
|  | Base rate (6M fixing for the half-year) | % |  |  | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94
|  | Kessara policy rate | % |  |  | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Uses before financing costs (USD m)
|  | EPC payment profile, selected | % |  |  | 10 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 7.5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC progress payments for contingency (FC) | % |  |  | 0 | 0.0102 | 0.0868 | 0.2284 | 0.4235 | 0.6612 | 0.9313 | 1.2242 | 1.5311 | 1.8437 | 2.1545 | 2.4565 | 2.7436 | 3.01 | 3.2509 | 3.4619 | 3.6396 | 3.7808 | 3.8833 | 3.9455 | 3.966 | 3.9455 | 3.8833 | 3.7808 | 3.6396 | 3.4619 | 3.2509 | 3.01 | 2.7436 | 2.4565 | 2.1545 | 1.8437 | 1.5311 | 1.2242 | 0.9313 | 0.6612 | 0.4235 | 0.2284 | 0.0868 | 0.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EPC payments | USD m |  | 565.1216 | 57.1021 | 0.058244 | 0.49565 | 1.3042 | 2.4183 | 3.761 | 5.2974 | 6.9635 | 8.7092 | 10.4873 | 12.2552 | 13.9297 | 15.5578 | 17.0684 | 18.4344 | 19.6309 | 20.6386 | 21.3628 | 21.9419 | 22.2934 | 22.4092 | 22.2934 | 21.9419 | 21.2945 | 20.4992 | 19.4984 | 18.31 | 16.9532 | 15.4527 | 13.7821 | 12.0877 | 10.344 | 8.5902 | 6.8683 | 5.225 | 3.7001 | 2.3699 | 1.2781 | 0.48574 | 42.0277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner's costs | USD m |  | 53.11 | 5.5416 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 1.2699 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insurance during construction | USD m |  | 7.62 | 6.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Development costs and fee | USD m |  | 32.63 | 32.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lenders' advisors and legal | USD m |  | 8.97 | 6.279 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency (FC: pro rata with EPC progress payments) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Initial working capital | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overrun items (actual) | USD m |  | 32.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 0.3425 | 1.9092 | 1.9092 | 1.9092 | 2.4542 | 2.4542 | 2.4542 | 0.545 | 2.0879 | 0.66786 | 1.1229 | 0.12286 | 2.7629 | 0.80786 | 9.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before financing costs | USD m |  | 705.1416 | 108.0297 | 1.3972 | 1.8346 | 2.6432 | 3.7572 | 5.1 | 6.6364 | 8.3024 | 10.0481 | 11.8263 | 13.5942 | 15.2687 | 16.8967 | 18.4073 | 19.7734 | 20.9699 | 21.9775 | 23.8447 | 23.2809 | 23.6324 | 24.0907 | 23.9749 | 23.6234 | 22.976 | 22.1807 | 21.1798 | 21.5581 | 20.2013 | 18.7008 | 17.5752 | 15.8809 | 14.1371 | 10.4741 | 10.0152 | 6.9519 | 5.882 | 3.5518 | 5.1 | 2.3526 | 57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT on onshore EPC (KCR m) and UBK VAT facility
|  | Onshore EPC payments | KCR m |  | 42938.798 | 4293.8798 | 4.3798 | 37.2709 | 98.0722 | 181.8458 | 283.9113 | 399.889 | 525.6568 | 657.4359 | 791.6626 | 925.1164 | 1054.7916 | 1178.0689 | 1292.4578 | 1395.8974 | 1486.4982 | 1562.8005 | 1623.4301 | 1667.4423 | 1694.1503 | 1702.9527 | 1694.1503 | 1667.4423 | 1623.4301 | 1562.8005 | 1486.4982 | 1395.8974 | 1292.4578 | 1178.0689 | 1054.7916 | 925.1164 | 791.6626 | 657.4359 | 525.6568 | 399.889 | 283.9113 | 181.8458 | 98.0722 | 37.2709 | 3224.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT paid (drawn on the VAT facility) | KCR m |  | 7728.9836 | 772.8984 | 0.78836 | 6.7088 | 17.653 | 32.7322 | 51.104 | 71.98 | 94.6182 | 118.3385 | 142.4993 | 166.521 | 189.8625 | 212.0524 | 232.6424 | 251.2615 | 267.5697 | 281.3041 | 292.2174 | 300.1396 | 304.947 | 306.5315 | 304.947 | 300.1396 | 292.2174 | 281.3041 | 267.5697 | 251.2615 | 232.6424 | 212.0524 | 189.8625 | 166.521 | 142.4993 | 118.3385 | 94.6182 | 71.98 | 51.104 | 32.7322 | 17.653 | 6.7088 | 580.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VAT refunds (9-month lag) repaying the facility | KCR m |  | 7728.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.8984 | 0.78836 | 6.7088 | 17.653 | 32.7322 | 51.104 | 71.98 | 94.6182 | 118.3385 | 142.4993 | 166.521 | 189.8625 | 212.0524 | 232.6424 | 251.2615 | 267.5697 | 281.3041 | 292.2174 | 300.1396 | 304.947 | 306.5315 | 304.947 | 300.1396 | 292.2174 | 281.3041 | 267.5697 | 251.2615 | 232.6424 | 212.0524 | 189.8625 | 166.521 | 142.4993 | 118.3385 | 94.6182 | 71.98 | 51.104 | 32.7322 | 17.653 | 6.7088 | 580.4621 | 0 | 0 | 0 | 0
|  | VAT facility balance | KCR m |  |  | 772.8984 | 773.6867 | 780.3955 | 798.0485 | 830.7807 | 881.8848 | 953.8648 | 1048.483 | 1166.8215 | 536.4224 | 702.155 | 885.3087 | 1079.7081 | 1279.6183 | 1479.7757 | 1675.3654 | 1862.0513 | 2035.9302 | 2193.5706 | 2331.9967 | 2448.6657 | 2541.5603 | 2609.0575 | 2650.0134 | 2663.7478 | 2650.0134 | 2609.0575 | 2541.5603 | 2448.6657 | 2331.9967 | 2193.5706 | 2035.9302 | 1862.0513 | 1675.3654 | 1479.7757 | 1279.6183 | 1079.7081 | 885.3087 | 702.155 | 1116.0962 | 973.5969 | 855.2584 | 760.6402 | 688.6602 | 637.5561 | 604.8239 | 587.1709 | 580.4621 | 0 | 0 | 0 | 0 | 0
|  | VAT facility interest | USD m |  | 1.6358 | 0 | 0.019375 | 0.020041 | 0.019563 | 0.020672 | 0.020941 | 0.020078 | 0.024044 | 0.025576 | 0.029412 | 0.013085 | 0.017307 | 0.021822 | 0.025755 | 0.031541 | 0.035299 | 0.041296 | 0.044706 | 0.045727 | 0.052665 | 0.054183 | 0.05879 | 0.059052 | 0.06115 | 0.06211 | 0.060418 | 0.06211 | 0.059177 | 0.059568 | 0.0557 | 0.047912 | 0.049897 | 0.044817 | 0.042356 | 0.03688 | 0.032987 | 0.028525 | 0.023292 | 0.019735 | 0.015147 | 0.02488 | 0.027146 | 0.021539 | 0.021209 | 0.018582 | 0.017777 | 0.01632 | 0.012913 | 0.012766 | 0 | 0 | 0 | 0

## Operations
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Operations: macro paths, plant, revenue, operating costs, working capital
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Macro paths
|  | Base rate before sensitivity shift | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | Base rate (6M LIBOR / Term SOFR + CAS) | % |  |  | 2.52 | 2.87 | 2.2 | 1.91 | 0.37 | 0.25 | 0.16 | 0.34 | 2.94 | 5.2883 | 5.8983 | 5.5883 | 5.6483 | 4.6783 | 4.5983 | 4.0483 | 4.0083 | 3.8783 | 3.8783 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283 | 3.9283
|  | KCR per USD before devaluation sensitivity | KCR/USD |  |  | 524.6 | 539.1 | 551.3 | 566 | 579.8 | 597.4 | 609.6 | 654.9 | 830.3 | 1052.8 | 1043.8 | 1093.1 | 1050.7 | 1035.6 | 1023.8 | 1028.9 | 1043.9 | 1072.5881 | 1102.0645 | 1127.0965 | 1152.697 | 1178.879 | 1205.6557 | 1233.0406 | 1261.0475 | 1289.6906 | 1318.9842 | 1348.9432 | 1379.5827 | 1410.9181 | 1442.9653 | 1475.7404 | 1509.2599 | 1543.5407 | 1578.6003 | 1614.4561 | 1651.1264 | 1688.6296 | 1726.9846 | 1766.2108 | 1806.328 | 1847.3563 | 1889.3166 | 1932.23 | 1976.1181 | 2021.003 | 2066.9075 | 2113.8546 | 2161.868 | 2210.972 | 2261.1914 | 2312.5514 | 2365.078 | 2418.7977 | 2473.7375 | 2529.9252 | 2587.3892
|  | KCR per USD, period average | KCR/USD |  |  | 524.6 | 539.1 | 551.3 | 566 | 579.8 | 597.4 | 609.6 | 654.9 | 830.3 | 1052.8 | 1043.8 | 1093.1 | 1050.7 | 1035.6 | 1023.8 | 1028.9 | 1043.9 | 1072.5881 | 1102.0645 | 1127.0965 | 1152.697 | 1178.879 | 1205.6557 | 1233.0406 | 1261.0475 | 1289.6906 | 1318.9842 | 1348.9432 | 1379.5827 | 1410.9181 | 1442.9653 | 1475.7404 | 1509.2599 | 1543.5407 | 1578.6003 | 1614.4561 | 1651.1264 | 1688.6296 | 1726.9846 | 1766.2108 | 1806.328 | 1847.3563 | 1889.3166 | 1932.23 | 1976.1181 | 2021.003 | 2066.9075 | 2113.8546 | 2161.868 | 2210.972 | 2261.1914 | 2312.5514 | 2365.078 | 2418.7977 | 2473.7375 | 2529.9252 | 2587.3892
|  | US CPI change, current year | % |  |  | 2.4 | 1.8 | 1.8 | 1.2 | 1.2 | 4.7 | 4.7 | 8 | 8 | 4.1 | 4.1 | 2.9 | 2.9 | 2.7 | 2.7 | 2.6 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI change, current year | % |  |  | 7.6 | 7.9 | 7.9 | 9.8 | 9.8 | 10.6 | 10.6 | 26.3 | 26.3 | 34.8 | 34.8 | 19.2 | 19.2 | 12.4 | 12.4 | 9.6 | 9.6 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US CPI change, prior year | % |  |  | 2.1 | 2.4 | 2.4 | 1.8 | 1.8 | 1.2 | 1.2 | 4.7 | 4.7 | 8 | 8 | 4.1 | 4.1 | 2.9 | 2.9 | 2.7 | 2.7 | 2.6 | 2.6 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  | Kessara CPI change, prior year | % |  |  | 8.1 | 7.6 | 7.6 | 7.9 | 7.9 | 9.8 | 9.8 | 10.6 | 10.6 | 26.3 | 26.3 | 34.8 | 34.8 | 19.2 | 19.2 | 12.4 | 12.4 | 9.6 | 9.6 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | US index, June 2018 (2018 price base) | index | 103.4292
|  | US CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 104.0443 | 105.1308 | 106.0728 | 106.8651 | 107.5044 | 109.0707 | 111.6044 | 115.0864 | 119.6013 | 123.1557 | 125.655 | 127.834 | 129.6744 | 131.4772 | 133.2404 | 134.9942 | 136.7379 | 138.4027 | 139.9853 | 141.586 | 143.205 | 144.8425 | 146.4987 | 148.1739 | 149.8682 | 151.5819 | 153.3151 | 155.0682 | 156.8414 | 158.6348 | 160.4487 | 162.2834 | 164.1391 | 166.0159 | 167.9143 | 169.8343 | 171.7763 | 173.7405 | 175.7271 | 177.7365 | 179.7689 | 181.8245 | 183.9036 | 186.0064 | 188.1333 | 190.2846 | 192.4604 | 194.6611 | 196.887 | 199.1383 | 201.4154 | 203.7185 | 206.0479 | 208.404 | 210.787 | 213.1973 | 215.6351
|  | US CPI index, tariff reading (3-month lag) | index |  |  | 102.8178 | 104.0443 | 105.1308 | 106.0728 | 106.8651 | 107.5044 | 109.0707 | 111.6044 | 115.0864 | 119.6013 | 123.1557 | 125.655 | 127.834 | 129.6744 | 131.4772 | 133.2404 | 134.9942 | 136.7379 | 138.4027 | 139.9853 | 141.586 | 143.205 | 144.8425 | 146.4987 | 148.1739 | 149.8682 | 151.5819 | 153.3151 | 155.0682 | 156.8414 | 158.6348 | 160.4487 | 162.2834 | 164.1391 | 166.0159 | 167.9143 | 169.8343 | 171.7763 | 173.7405 | 175.7271 | 177.7365 | 179.7689 | 181.8245 | 183.9036 | 186.0064 | 188.1333 | 190.2846 | 192.4604 | 194.6611 | 196.887 | 199.1383 | 201.4154 | 203.7185 | 206.0479 | 208.404 | 210.787 | 213.1973
|  | US cost indexation factor vs 2018 prices | factor |  |  | 1.0059 | 1.0165 | 1.0256 | 1.0332 | 1.0394 | 1.0545 | 1.079 | 1.1127 | 1.1564 | 1.1907 | 1.2149 | 1.236 | 1.2538 | 1.2712 | 1.2882 | 1.3052 | 1.322 | 1.3381 | 1.3534 | 1.3689 | 1.3846 | 1.4004 | 1.4164 | 1.4326 | 1.449 | 1.4656 | 1.4823 | 1.4993 | 1.5164 | 1.5338 | 1.5513 | 1.569 | 1.587 | 1.6051 | 1.6235 | 1.642 | 1.6608 | 1.6798 | 1.699 | 1.7184 | 1.7381 | 1.758 | 1.7781 | 1.7984 | 1.819 | 1.8398 | 1.8608 | 1.8821 | 1.9036 | 1.9254 | 1.9474 | 1.9696 | 1.9922 | 2.0149 | 2.038 | 2.0613 | 2.0849
|  | KC index, June 2018 (2018 price base) | index | 112.9752
|  | Kessara CPI index, cost reading (Mar/Sep), Nov 2016 = 100 | index |  |  | 115.0632 | 119.4386 | 124.0668 | 129.4379 | 135.6321 | 142.381 | 149.7371 | 162.7868 | 182.9451 | 208.9749 | 242.627 | 273.1685 | 298.242 | 320.8702 | 340.183 | 358.3907 | 375.1993 | 391.3548 | 406.7078 | 421.6813 | 436.1906 | 451.199 | 466.7239 | 482.783 | 499.3946 | 516.5778 | 534.3522 | 552.7382 | 571.7569 | 591.4299 | 611.7798 | 632.83 | 654.6044 | 677.1281 | 700.4267 | 724.5271 | 749.4566 | 775.2439 | 801.9186 | 829.511 | 858.0529 | 887.5768 | 918.1166 | 949.7072 | 982.3847 | 1016.1867 | 1051.1517 | 1087.3197 | 1124.7323 | 1163.4321 | 1203.4635 | 1244.8724 | 1287.706 | 1332.0134 | 1377.8454 | 1425.2544 | 1474.2946
|  | Kessara CPI index, tariff reading (3-month lag) | index |  |  | 110.9252 | 115.0632 | 119.4386 | 124.0668 | 129.4379 | 135.6321 | 142.381 | 149.7371 | 162.7868 | 182.9451 | 208.9749 | 242.627 | 273.1685 | 298.242 | 320.8702 | 340.183 | 358.3907 | 375.1993 | 391.3548 | 406.7078 | 421.6813 | 436.1906 | 451.199 | 466.7239 | 482.783 | 499.3946 | 516.5778 | 534.3522 | 552.7382 | 571.7569 | 591.4299 | 611.7798 | 632.83 | 654.6044 | 677.1281 | 700.4267 | 724.5271 | 749.4566 | 775.2439 | 801.9186 | 829.511 | 858.0529 | 887.5768 | 918.1166 | 949.7072 | 982.3847 | 1016.1867 | 1051.1517 | 1087.3197 | 1124.7323 | 1163.4321 | 1203.4635 | 1244.8724 | 1287.706 | 1332.0134 | 1377.8454 | 1425.2544
|  | Kessara cost indexation factor vs 2018 prices | factor |  |  | 1.0185 | 1.0572 | 1.0982 | 1.1457 | 1.2005 | 1.2603 | 1.3254 | 1.4409 | 1.6193 | 1.8497 | 2.1476 | 2.418 | 2.6399 | 2.8402 | 3.0111 | 3.1723 | 3.3211 | 3.4641 | 3.6 | 3.7325 | 3.8609 | 3.9938 | 4.1312 | 4.2734 | 4.4204 | 4.5725 | 4.7298 | 4.8926 | 5.0609 | 5.235 | 5.4152 | 5.6015 | 5.7942 | 5.9936 | 6.1998 | 6.4131 | 6.6338 | 6.8621 | 7.0982 | 7.3424 | 7.5951 | 7.8564 | 8.1267 | 8.4063 | 8.6956 | 8.9948 | 9.3043 | 9.6244 | 9.9556 | 10.2981 | 10.6525 | 11.019 | 11.3981 | 11.7903 | 12.196 | 12.6156 | 13.0497
Plant
|  | Operating year at period start | OY |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Months in that operating year | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5
|  | Availability, profile (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.8
|  | Availability | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 93.8 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 93.2667 | 90.6 | 91.1333 | 93.8 | 93.65 | 92.9 | 93.05 | 93.8 | 92.95 | 88.7 | 89.55 | 93.8 | 93.8
|  | Years since COD (period mid-point) | years |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 0.33333 | 0.83333 | 1.3333 | 1.8333 | 2.3333 | 2.8333 | 3.3333 | 3.8333 | 4.3333 | 4.8333 | 5.3333 | 5.8333 | 6.3333 | 6.8333 | 7.3333 | 7.8333 | 8.3333 | 8.8333 | 9.3333 | 9.8333 | 10.3333 | 10.8333 | 11.3333 | 11.8333 | 12.3333 | 12.8333 | 13.3333 | 13.8333 | 14.3333 | 14.8333 | 15.3333 | 15.8333 | 16.3333 | 16.8333 | 17.3333 | 17.8333 | 18.3333 | 18.8333 | 19.3333 | 19.8333 | 20.3333 | 20.8333 | 21.3333 | 21.8333 | 22.3333 | 22.8333 | 23.3333 | 23.8333 | 24.3333 | 24.7917
|  | Contracted capacity | MW | 581.9
|  | Plant net heat rate, new and clean | kJ/kWh | 6286
|  | Output degradation factor | factor |  |  | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.98994 | 0.9895 | 0.98876 | 0.98802 | 0.98728 | 0.98654 | 0.98579 | 0.98505 | 0.98431 | 0.98357 | 0.98282 | 0.98208 | 0.98134 | 0.98059 | 0.97985 | 0.97911 | 0.97837 | 0.97762 | 0.97688 | 0.97614 | 0.9754 | 0.97466 | 0.97391 | 0.97317 | 0.97243 | 0.97169 | 0.97094 | 0.9702 | 0.96946 | 0.96871 | 0.96797 | 0.96723 | 0.96649 | 0.96574 | 0.965 | 0.96426 | 0.96352 | 0.96278 | 0.96203 | 0.96129 | 0.96055 | 0.95981 | 0.95906 | 0.95832 | 0.95758 | 0.95683 | 0.95609 | 0.95535 | 0.95461 | 0.95386 | 0.95318
|  | Net energy delivered | MWh |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 301747.4031 | 1809692.2823 | 1805442.5415 | 1789638.6594 | 1791181.1901 | 1804260.4896 | 1792651.4964 | 1740084.6497 | 1749008.6309 | 1798828.6968 | 1794596.3284 | 1778879.3087 | 1780404.467 | 1793396.9041 | 1775799.7969 | 1693319.8868 | 1708250.3196 | 1787965.1113 | 1783750.1154 | 1768119.9581 | 1769627.7438 | 1782533.3186 | 1771047.863 | 1719098.7042 | 1727899.1478 | 1777101.5258 | 1772903.9024 | 1757360.6074 | 1758851.0207 | 1771669.7331 | 1754269.5139 | 1672774.0439 | 1687507.5887 | 1766237.9403 | 1762057.6894 | 1746601.2568 | 1748074.2976 | 1760806.1476 | 1749444.2296 | 1698112.7587 | 1706789.6647 | 1755374.3549 | 1751211.4764 | 1735841.9061 | 1737297.5745 | 1749942.5621 | 1732739.231 | 1652228.201 | 1666764.8578 | 1744510.7694 | 1452721.6529
|  | Plant net heat rate | kJ/kWh |  |  | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.0226 | 6482.3467 | 6484.6154 | 6488.5046 | 6492.3939 | 6496.2831 | 6500.1723 | 6504.0615 | 6507.9507 | 6511.8399 | 6515.7291 | 6519.6184 | 6523.5076 | 6527.3968 | 6531.286 | 6535.1752 | 6539.0644 | 6542.9536 | 6546.8429 | 6550.7321 | 6554.6213 | 6558.5105 | 6562.3997 | 6566.2889 | 6570.1781 | 6574.0673 | 6577.9566 | 6581.8458 | 6585.735 | 6589.6242 | 6593.5134 | 6597.4026 | 6601.2918 | 6605.1811 | 6609.0703 | 6612.9595 | 6616.8487 | 6620.7379 | 6624.6271 | 6628.5163 | 6632.4055 | 6636.2948 | 6640.184 | 6644.0732 | 6647.9624 | 6651.8516 | 6655.7408 | 6659.63 | 6663.5193 | 6667.4085 | 6671.2977 | 6674.8628
|  | Contracted heat rate at dispatched load | kJ/kWh |  |  | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.429 | 6468.6985 | 6470.5851 | 6473.8194 | 6477.0536 | 6480.2878 | 6483.522 | 6486.7562 | 6489.9904 | 6493.2246 | 6496.4589 | 6499.6931 | 6502.9273 | 6506.1615 | 6509.3957 | 6512.6299 | 6515.8641 | 6519.0984 | 6522.3326 | 6525.5668 | 6528.801 | 6532.0352 | 6535.2694 | 6538.5036 | 6541.7379 | 6544.9721 | 6548.2063 | 6551.4405 | 6554.6747 | 6557.9089 | 6561.1431 | 6564.3774 | 6567.6116 | 6570.8458 | 6574.08 | 6577.3142 | 6580.5484 | 6583.7827 | 6587.0169 | 6590.2511 | 6593.4853 | 6596.7195 | 6599.9537 | 6603.1879 | 6606.4222 | 6609.6564 | 6612.8906 | 6616.1248 | 6619.359 | 6622.5932 | 6625.8274 | 6628.7921
|  | Gas price (GCV) | USD/MMBtu |  |  | 5.86 | 5.9772 | 5.9772 | 6.0967 | 6.0967 | 6.2187 | 6.2187 | 6.3431 | 6.3431 | 6.4699 | 6.4699 | 6.5993 | 6.5993 | 6.7313 | 6.7313 | 6.8659 | 6.8659 | 7.0032 | 7.0032 | 7.1433 | 7.1433 | 7.2862 | 7.2862 | 7.4319 | 7.4319 | 7.5805 | 7.5805 | 7.7321 | 7.7321 | 7.8868 | 7.8868 | 8.0445 | 8.0445 | 8.2054 | 8.2054 | 8.3695 | 8.3695 | 8.5369 | 8.5369 | 8.7077 | 8.7077 | 8.8818 | 8.8818 | 9.0594 | 9.0594 | 9.2406 | 9.2406 | 9.4254 | 9.4254 | 9.614 | 9.614 | 9.8062 | 9.8062 | 10.0024 | 10.0024 | 10.2024 | 10.2024
|  | Gas burned | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2054187.3321 | 12324043.104 | 12302476.3899 | 12202096.6291 | 12219929.7596 | 12316529.6145 | 12244604.3289 | 11892656.6309 | 11960791.4414 | 12308838.6409 | 12287207.6409 | 12186862.27 | 12204582.77 | 12300970.1834 | 12187524.0681 | 11628370.8488 | 11737878.2986 | 12292924.2419 | 12271230.0912 | 12170924.7866 | 12188531.521 | 12284700.8163 | 12212780.0299 | 11861570.8184 | 11929350.1984 | 12276299.9068 | 12254543.7408 | 12154284.179 | 12171776.0123 | 12267721.5132 | 12154400.8162 | 11596594.2741 | 11705627.771 | 12258965.6357 | 12237148.5896 | 12136940.4471 | 12154316.2441 | 12250032.2741 | 12178132.1332 | 11827742.14 | 11895149.9431 | 12240921.4285 | 12219044.6377 | 12118893.591 | 12136152.2164 | 12231633.0989 | 12118463.5534 | 11562132.355 | 11670666.1657 | 12222167.2854 | 10183310.866
|  | Take-or-pay quantity | MMBtu |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1795520 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10483520 | 10657280 | 10541440 | 10657280 | 10483520 | 10657280 | 10483520 | 8861760
Revenue (USD m)
|  | Capital charge, indexed | USD/kW-month |  |  | 14.4409 | 14.4762 | 14.5074 | 14.5344 | 14.5572 | 14.5755 | 14.6205 | 14.6933 | 14.7933 | 14.9229 | 15.025 | 15.0968 | 15.1594 | 15.2122 | 15.264 | 15.3147 | 15.365 | 15.4151 | 15.4629 | 15.5084 | 15.5544 | 15.6008 | 15.6479 | 15.6954 | 15.7436 | 15.7922 | 15.8414 | 15.8912 | 15.9416 | 15.9925 | 16.044 | 16.0961 | 16.1488 | 16.2021 | 16.256 | 16.3105 | 16.3656 | 16.4214 | 16.4778 | 16.5349 | 16.5926 | 16.651 | 16.71 | 16.7697 | 16.8301 | 16.8912 | 16.953 | 17.0155 | 17.0787 | 17.1426 | 17.2073 | 17.2727 | 17.3388 | 17.4057 | 17.4734 | 17.5418 | 17.611
|  | Fixed O&M charge, indexed | USD/kW-month |  |  | 2.3307 | 2.3564 | 2.385 | 2.4088 | 2.4366 | 2.4611 | 2.51 | 2.5263 | 2.444 | 2.4182 | 2.5764 | 2.7005 | 2.886 | 3.026 | 3.155 | 3.2501 | 3.3268 | 3.3781 | 3.4234 | 3.4694 | 3.5125 | 3.5526 | 3.5933 | 3.6344 | 3.6759 | 3.7179 | 3.7605 | 3.8035 | 3.847 | 3.8909 | 3.9354 | 3.9804 | 4.0259 | 4.072 | 4.1185 | 4.1656 | 4.2133 | 4.2614 | 4.3102 | 4.3595 | 4.4093 | 4.4597 | 4.5107 | 4.5623 | 4.6145 | 4.6672 | 4.7206 | 4.7746 | 4.8292 | 4.8844 | 4.9402 | 4.9967 | 5.0539 | 5.1117 | 5.1701 | 5.2292 | 5.289
|  | Availability factor min(1, A/90%) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.98556 | 0.995 | 1 | 1
|  | Capacity payment | USD m |  | 3510.0259 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9683 | 60.1206 | 60.1821 | 60.5448 | 61.4535 | 62.1374 | 63.0037 | 63.677 | 64.3082 | 64.8171 | 65.2605 | 65.6145 | 65.9398 | 66.2589 | 66.5699 | 65.9066 | 66.8427 | 67.4881 | 67.8011 | 68.1178 | 68.4381 | 68.762 | 69.0896 | 69.421 | 69.7562 | 70.0952 | 70.438 | 70.7848 | 71.1356 | 71.4904 | 71.8492 | 71.1691 | 72.2163 | 72.9505 | 73.326 | 73.7059 | 74.09 | 74.4786 | 74.8716 | 75.2691 | 75.6711 | 76.0778 | 76.4891 | 76.905 | 77.3258 | 77.7513 | 78.1818 | 77.4815 | 78.6622 | 79.5028 | 66.6277
|  | VOM charge, indexed | USD/MWh |  |  | 3.9102 | 3.954 | 4.0006 | 4.0397 | 4.0828 | 4.1203 | 4.1976 | 4.2397 | 4.1593 | 4.162 | 4.3996 | 4.5836 | 4.846 | 5.0457 | 5.2305 | 5.3703 | 5.4857 | 5.5675 | 5.6409 | 5.7144 | 5.7843 | 5.8504 | 5.9173 | 5.985 | 6.0534 | 6.1226 | 6.1926 | 6.2634 | 6.3351 | 6.4075 | 6.4808 | 6.5549 | 6.6298 | 6.7056 | 6.7823 | 6.8599 | 6.9383 | 7.0176 | 7.0979 | 7.179 | 7.2611 | 7.3442 | 7.4281 | 7.5131 | 7.599 | 7.6859 | 7.7738 | 7.8627 | 7.9526 | 8.0435 | 8.1355 | 8.2285 | 8.3226 | 8.4178 | 8.514 | 8.6114 | 8.7098
|  | Variable O&M payment | USD m |  | 574.2367 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2666 | 7.6726 | 7.5094 | 7.4485 | 7.8804 | 8.27 | 8.6873 | 8.7799 | 9.1482 | 9.6603 | 9.8446 | 9.904 | 10.0431 | 10.2481 | 10.2717 | 9.9066 | 10.1082 | 10.7009 | 10.7978 | 10.8255 | 10.9587 | 11.1648 | 11.2197 | 11.0151 | 11.1981 | 11.6487 | 11.754 | 11.7842 | 11.9291 | 12.1534 | 12.1717 | 11.7389 | 11.9777 | 12.6799 | 12.7945 | 12.8273 | 12.9849 | 13.2291 | 13.294 | 13.0515 | 13.2682 | 13.8019 | 13.9266 | 13.9622 | 14.1337 | 14.3994 | 14.4209 | 13.9081 | 14.1909 | 15.0226 | 12.653
|  | Fuel charge (pass-through) | USD m |  | 4888.8555 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7474 | 78.0029 | 77.8586 | 78.76 | 78.8672 | 81.0724 | 80.591 | 79.8321 | 80.2815 | 84.2616 | 84.1052 | 85.0783 | 85.1936 | 87.5751 | 86.7589 | 84.4257 | 85.2124 | 91.0177 | 90.8482 | 91.8987 | 92.0226 | 94.5944 | 94.0314 | 93.1448 | 93.6679 | 98.3103 | 98.1266 | 99.2606 | 99.3938 | 102.1709 | 101.2173 | 98.494 | 99.4105 | 106.1817 | 105.9825 | 107.2066 | 107.3497 | 110.3484 | 109.6902 | 108.6544 | 109.2632 | 114.6771 | 114.4612 | 115.7824 | 115.9363 | 119.174 | 118.0601 | 114.8821 | 115.9495 | 123.8456 | 103.1771
|  | GTA reservation charge (pass-through) | USD m |  | 696.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9395 | 11.4938 | 11.6843 | 11.6662 | 11.8595 | 11.9066 | 12.0374 | 12.0188 | 12.218 | 12.199 | 12.4012 | 12.382 | 12.5873 | 12.6372 | 12.7761 | 12.7563 | 12.9677 | 12.9476 | 13.1622 | 13.1418 | 13.3597 | 13.4127 | 13.5601 | 13.5391 | 13.7635 | 13.7421 | 13.9699 | 13.9483 | 14.1795 | 14.2357 | 14.3921 | 14.3699 | 14.608 | 14.5854 | 14.8271 | 14.8042 | 15.0496 | 15.1093 | 15.2753 | 15.2516 | 15.5044 | 15.4804 | 15.737 | 15.7126 | 15.9731 | 16.0364 | 16.2126 | 16.1875 | 16.4558 | 16.4303 | 13.8886
|  | GTA commodity charge (pass-through) | USD m |  | 146.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40812 | 2.4853 | 2.4809 | 2.4976 | 2.5012 | 2.5588 | 2.5439 | 2.5078 | 2.5222 | 2.6345 | 2.6299 | 2.6475 | 2.6514 | 2.7124 | 2.6874 | 2.6025 | 2.6271 | 2.7926 | 2.7876 | 2.8063 | 2.8104 | 2.875 | 2.8582 | 2.8176 | 2.8337 | 2.9599 | 2.9547 | 2.9744 | 2.9787 | 3.0472 | 3.0191 | 2.9237 | 2.9512 | 3.1371 | 3.1315 | 3.1525 | 3.157 | 3.2296 | 3.2106 | 3.165 | 3.183 | 3.3247 | 3.3188 | 3.3409 | 3.3457 | 3.4226 | 3.3909 | 3.2838 | 3.3146 | 3.5233 | 2.9356
|  | Take-or-pay payment (pass-through) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non-fuel revenue | USD m |  | 4084.2627 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2349 | 67.7931 | 67.6916 | 67.9933 | 69.334 | 70.4074 | 71.691 | 72.457 | 73.4564 | 74.4774 | 75.1051 | 75.5184 | 75.9829 | 76.507 | 76.8416 | 75.8132 | 76.9509 | 78.189 | 78.5989 | 78.9433 | 79.3967 | 79.9268 | 80.3093 | 80.4361 | 80.9543 | 81.7438 | 82.1921 | 82.5691 | 83.0647 | 83.6438 | 84.0209 | 82.908 | 84.1941 | 85.6304 | 86.1206 | 86.5332 | 87.075 | 87.7077 | 88.1656 | 88.3206 | 88.9393 | 89.8797 | 90.4157 | 90.8673 | 91.4595 | 92.1507 | 92.6026 | 91.3896 | 92.853 | 94.5254 | 79.2807
|  | Total revenue | USD m |  | 9816.1584 | 0 | 0 | 0 | 0 | 0 | 0 | 26.3299 | 159.7751 | 159.7154 | 160.917 | 162.5619 | 165.9452 | 166.8632 | 166.8156 | 168.4781 | 173.5726 | 174.2414 | 175.6263 | 176.4151 | 179.4317 | 179.064 | 175.5977 | 177.7581 | 184.9469 | 185.3969 | 186.7901 | 187.5893 | 190.8089 | 190.759 | 189.9376 | 191.2193 | 196.7562 | 197.2432 | 198.7524 | 199.6166 | 203.0977 | 202.6494 | 198.6956 | 201.1638 | 209.5346 | 210.0617 | 211.6964 | 212.6312 | 216.3949 | 216.3417 | 215.3916 | 216.89 | 223.3619 | 223.9326 | 225.7033 | 226.7145 | 230.7837 | 230.2663 | 225.743 | 228.573 | 238.3246 | 199.282
|  | Late payment interest accrued (to settlement 2024-03-21) | USD m |  | 8.707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10824 | 1.1021 | 3.13 | 3.5202 | 0.84647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Late payment interest received (60%, with settlement installments) | USD m |  | 5.2242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0448 | 2.0897 | 2.0897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs (USD m)
|  | O&M fixed fee | USD m |  | 338.8813 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72247 | 4.4401 | 4.3734 | 4.3234 | 4.6009 | 4.7658 | 5.0268 | 5.2365 | 5.4226 | 5.568 | 5.6817 | 5.7577 | 5.8236 | 5.8957 | 5.9631 | 6.0313 | 6.1002 | 6.17 | 6.2405 | 6.3119 | 6.3841 | 6.4571 | 6.5309 | 6.6056 | 6.6811 | 6.7575 | 6.8348 | 6.9129 | 6.992 | 7.0719 | 7.1528 | 7.2346 | 7.3173 | 7.401 | 7.4856 | 7.5712 | 7.6578 | 7.7453 | 7.8339 | 7.9235 | 8.0141 | 8.1057 | 8.1984 | 8.2921 | 8.387 | 8.4829 | 8.5799 | 8.678 | 8.7772 | 8.8776 | 7.4826
|  | O&M availability incentive | USD m |  | 4.5966 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032371 | 0.20029 | 0.1908 | 0.10717 | 0.12756 | 0.22247 | 0.15881 | -0.17797 | -0.11165 | 0.23493 | 0.21814 | 0.12043 | 0.14211 | 0.24641 | 0.13153 | -0.42012 | -0.34702 | 0.25787 | 0.23908 | 0.1319 | 0.15564 | 0.26987 | 0.19208 | -0.21473 | -0.13445 | 0.28243 | 0.26185 | 0.14446 | 0.17046 | 0.29557 | 0.15778 | -0.50394 | -0.41626 | 0.30932 | 0.28678 | 0.15822 | 0.1867 | 0.32371 | 0.2304 | -0.25757 | -0.16127 | 0.33877 | 0.31409 | 0.17328 | 0.20447 | 0.35454 | 0.18926 | -0.60448 | -0.49931 | 0.37103 | 0.31273
|  | LTSA fixed fee | USD m |  | 105.0343 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23739 | 1.4688 | 1.5264 | 1.5718 | 1.6037 | 1.6315 | 1.655 | 1.678 | 1.7005 | 1.7228 | 1.7451 | 1.7663 | 1.7865 | 1.807 | 1.8276 | 1.8485 | 1.8697 | 1.891 | 1.9127 | 1.9345 | 1.9567 | 1.979 | 2.0017 | 2.0246 | 2.0477 | 2.0711 | 2.0948 | 2.1188 | 2.143 | 2.1675 | 2.1923 | 2.2173 | 2.2427 | 2.2683 | 2.2943 | 2.3205 | 2.347 | 2.3739 | 2.401 | 2.4285 | 2.4562 | 2.4843 | 2.5127 | 2.5415 | 2.5705 | 2.5999 | 2.6297 | 2.6597 | 2.6901 | 2.7209 | 2.2933
|  | Equivalent operating hours (2 GTs) | EOH |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1406.5 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 7032.5
|  | LTSA variable fee | USD m |  | 326.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73759 | 4.5636 | 4.7426 | 4.8836 | 4.9827 | 5.0691 | 5.1421 | 5.2136 | 5.2835 | 5.353 | 5.4222 | 5.4882 | 5.5509 | 5.6144 | 5.6786 | 5.7435 | 5.8092 | 5.8756 | 5.9428 | 6.0108 | 6.0795 | 6.149 | 6.2193 | 6.2905 | 6.3624 | 6.4351 | 6.5087 | 6.5832 | 6.6584 | 6.7346 | 6.8116 | 6.8895 | 6.9682 | 7.0479 | 7.1285 | 7.21 | 7.2925 | 7.3758 | 7.4602 | 7.5455 | 7.6318 | 7.719 | 7.8073 | 7.8966 | 7.9869 | 8.0782 | 8.1706 | 8.264 | 8.3585 | 8.4541 | 7.1256
|  | Operational insurance | USD m |  | 204.6507 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39295 | 2.4313 | 2.9814 | 3.07 | 3.1323 | 3.1867 | 3.2325 | 3.2775 | 3.3214 | 3.3652 | 3.4086 | 3.4501 | 3.4896 | 3.5295 | 3.5698 | 3.6107 | 3.6519 | 3.6937 | 3.7359 | 3.7787 | 3.8219 | 3.8656 | 3.9098 | 3.9545 | 3.9997 | 4.0454 | 4.0917 | 4.1385 | 4.1858 | 4.2337 | 4.2821 | 4.331 | 4.3806 | 4.4306 | 4.4813 | 4.5325 | 4.5844 | 4.6368 | 4.6898 | 4.7434 | 4.7977 | 4.8525 | 4.908 | 4.9642 | 5.0209 | 5.0783 | 5.1364 | 5.1951 | 5.2545 | 5.3146 | 4.4795
|  | G&A | USD m |  | 140.1577 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29185 | 1.7886 | 1.7206 | 1.6685 | 1.8112 | 1.8914 | 2.029 | 2.1374 | 2.2325 | 2.3044 | 2.3581 | 2.3907 | 2.4181 | 2.4489 | 2.4769 | 2.5052 | 2.5339 | 2.5628 | 2.5921 | 2.6218 | 2.6518 | 2.6821 | 2.7127 | 2.7438 | 2.7751 | 2.8069 | 2.839 | 2.8714 | 2.9043 | 2.9375 | 2.9711 | 3.005 | 3.0394 | 3.0741 | 3.1093 | 3.1449 | 3.1808 | 3.2172 | 3.254 | 3.2912 | 3.3288 | 3.3669 | 3.4054 | 3.4443 | 3.4837 | 3.5235 | 3.5638 | 3.6046 | 3.6458 | 3.6875 | 3.108
|  | Land lease and permits | USD m |  | 34.4386 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066676 | 0.40484 | 0.35886 | 0.32328 | 0.37858 | 0.40701 | 0.4623 | 0.50463 | 0.54117 | 0.56731 | 0.58538 | 0.59425 | 0.60105 | 0.60934 | 0.6163 | 0.62335 | 0.63048 | 0.63769 | 0.64498 | 0.65236 | 0.65982 | 0.66736 | 0.67499 | 0.68271 | 0.69052 | 0.69841 | 0.7064 | 0.71448 | 0.72265 | 0.73091 | 0.73927 | 0.74772 | 0.75627 | 0.76492 | 0.77366 | 0.78251 | 0.79146 | 0.80051 | 0.80966 | 0.81892 | 0.82828 | 0.83775 | 0.84733 | 0.85702 | 0.86682 | 0.87673 | 0.88676 | 0.8969 | 0.90715 | 0.91753 | 0.77335
|  | Community fund and OREK levy | USD m |  | 22.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061792 | 0.37286 | 0.3723 | 0.37396 | 0.38134 | 0.38724 | 0.3943 | 0.39851 | 0.40401 | 0.40963 | 0.41308 | 0.41535 | 0.41791 | 0.42079 | 0.42263 | 0.41697 | 0.42323 | 0.43004 | 0.43229 | 0.43419 | 0.43668 | 0.4396 | 0.4417 | 0.4424 | 0.44525 | 0.44959 | 0.45206 | 0.45413 | 0.45686 | 0.46004 | 0.46211 | 0.45599 | 0.46307 | 0.47097 | 0.47366 | 0.47593 | 0.47891 | 0.48239 | 0.48491 | 0.48576 | 0.48917 | 0.49434 | 0.49729 | 0.49977 | 0.50303 | 0.50683 | 0.50931 | 0.50264 | 0.51069 | 0.51989 | 0.43604
|  | Variable consumables | USD m |  | 160.0707 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35601 | 2.189 | 2.1679 | 2.1375 | 2.2622 | 2.3541 | 2.4533 | 2.4713 | 2.5647 | 2.7036 | 2.7496 | 2.7616 | 2.7955 | 2.8504 | 2.8547 | 2.7533 | 2.8093 | 2.974 | 3.001 | 3.0087 | 3.0457 | 3.103 | 3.1182 | 3.0614 | 3.1122 | 3.2374 | 3.2667 | 3.2751 | 3.3154 | 3.3777 | 3.3828 | 3.2625 | 3.3289 | 3.524 | 3.5559 | 3.565 | 3.6088 | 3.6767 | 3.6947 | 3.6273 | 3.6875 | 3.8359 | 3.8705 | 3.8804 | 3.9281 | 4.0019 | 4.0079 | 3.8654 | 3.944 | 4.1751 | 3.5166
|  | Agency and account fees | USD m |  | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02125 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.1275 | 0.10625
|  | ABDB PRG fee | USD m |  | 7.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025937 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.15563 | 0.12969
|  | Operating costs before pass-through items | USD m |  | 1350.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9463 | 18.1424 | 18.7175 | 18.7423 | 19.5636 | 20.1984 | 20.8372 | 21.0225 | 21.6418 | 22.512 | 22.8651 | 23.0278 | 23.3084 | 23.7055 | 23.8244 | 23.3958 | 23.764 | 24.776 | 25.0245 | 25.1679 | 25.4748 | 25.8957 | 26.0845 | 25.8737 | 26.2627 | 27.067 | 27.3391 | 27.496 | 27.8319 | 28.2925 | 28.4348 | 27.9229 | 28.3633 | 29.5744 | 29.8721 | 30.0439 | 30.4115 | 30.9154 | 31.1417 | 30.8896 | 31.3554 | 32.3184 | 32.6442 | 32.8323 | 33.2345 | 33.786 | 33.9567 | 33.3449 | 33.8718 | 35.3213 | 29.7637
|  | Gas purchases | USD m |  | 4912.1191 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7743 | 78.1721 | 78.0353 | 78.9465 | 79.0619 | 81.2806 | 80.806 | 80.053 | 80.5117 | 84.5116 | 84.363 | 85.3476 | 85.4717 | 87.8696 | 87.0592 | 84.7263 | 85.5242 | 91.3597 | 91.1985 | 92.2621 | 92.3956 | 94.9871 | 94.431 | 93.5497 | 94.0843 | 98.757 | 98.582 | 99.7309 | 99.8745 | 102.675 | 101.7265 | 98.9991 | 99.9299 | 106.7468 | 106.5568 | 107.7979 | 107.9523 | 110.9784 | 110.3271 | 109.2958 | 109.9187 | 115.3761 | 115.1699 | 116.5105 | 116.6764 | 119.9462 | 118.8364 | 115.6485 | 116.7341 | 124.6955 | 103.8942
|  | Pass-through costs (gas, GTA, take-or-pay) | USD m |  | 5755.1594 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1219 | 92.1511 | 92.2004 | 93.1102 | 93.4226 | 95.746 | 95.3872 | 94.5796 | 95.2518 | 99.3451 | 99.3942 | 100.3771 | 100.7103 | 103.2192 | 102.5227 | 100.0852 | 101.119 | 107.0999 | 107.1484 | 108.2103 | 108.5656 | 111.2748 | 110.8492 | 109.9064 | 110.6815 | 115.459 | 115.5065 | 116.6537 | 117.0326 | 119.9579 | 119.1378 | 116.2927 | 117.4892 | 124.4693 | 124.5155 | 125.7546 | 126.1588 | 129.3173 | 128.813 | 127.7124 | 128.6061 | 134.1812 | 134.2257 | 135.564 | 135.9951 | 139.4052 | 138.44 | 135.1199 | 136.5046 | 144.6491 | 120.7184
|  | VAT facility interest after the funding period | USD m |  | 0.14825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12257 | 0.025679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FX conversion losses | USD m |  | 6.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.27 | 3.84 | 1.12 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OY whose month 7 could fall in the period | OY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 16 | 16 | 17 | 17 | 18 | 18 | 19 | 19 | 20 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 25 | 25
|  | Major maintenance outside LTSA (2018 prices) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.47 | 0 | 0 | 0
|  | Major maintenance spend | USD m |  | 58.3765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0815 | 0 | 0 | 0
|  | Months in period from OY20 | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
|  | Handback reserve contribution required | USD m |  | 21.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28042 | 1.7018 | 1.7212 | 1.7409 | 1.7608 | 1.781 | 1.8013 | 1.8219 | 1.8428 | 1.8638 | 1.8851 | 1.9067 | 1.6071
|  | Handback works at PPA expiry | USD m |  | 21.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7148
|  | Total operating costs | USD m |  | 7192.7391 | 0 | 0 | 0 | 0 | 0 | 0 | 18.0682 | 110.4161 | 112.2136 | 115.6926 | 114.1062 | 116.2544 | 116.2245 | 118.3733 | 116.8936 | 121.8571 | 122.2593 | 123.4049 | 124.0187 | 126.9247 | 126.3471 | 136.7428 | 124.883 | 131.8759 | 132.1729 | 133.3781 | 134.0404 | 137.1705 | 136.9338 | 139.1237 | 136.9442 | 142.5261 | 142.8456 | 144.1497 | 144.8645 | 148.2504 | 147.5726 | 160.1233 | 145.8525 | 154.0437 | 154.3876 | 155.7985 | 156.5703 | 160.2327 | 159.9547 | 162.6127 | 159.9616 | 166.4996 | 166.8699 | 168.3963 | 169.2296 | 173.1912 | 172.3967 | 187.5463 | 170.3764 | 179.9705 | 172.1969
|  | EBITDA | USD m |  | 2628.6435 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2617 | 49.359 | 47.5018 | 45.2244 | 48.4558 | 50.7356 | 52.7284 | 50.5321 | 51.5844 | 51.7155 | 51.9821 | 52.2214 | 52.3964 | 52.507 | 52.7169 | 38.855 | 52.875 | 53.071 | 53.224 | 53.412 | 53.5489 | 53.6384 | 53.8252 | 50.8139 | 54.2752 | 54.2301 | 54.3976 | 54.6027 | 54.7521 | 54.8473 | 55.0768 | 38.5723 | 55.3113 | 55.4909 | 55.6741 | 55.8979 | 56.061 | 56.1622 | 56.387 | 52.7789 | 56.9284 | 56.8623 | 57.0627 | 57.307 | 57.4849 | 57.5925 | 57.8697 | 38.1967 | 58.1966 | 58.3542 | 27.0851
Working capital (USD m, period-end balances)
|  | Flag: final operating period or later (working capital unwinds) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Extra receivable days on capacity and VOM (sensitivities) | days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade receivables (normal terms) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.2208 | 39.7231 | 39.0608 | 40.007 | 39.757 | 41.0304 | 40.8089 | 41.4735 | 41.2039 | 43.1534 | 42.6134 | 43.664 | 43.145 | 44.365 | 43.7928 | 43.6569 | 43.4734 | 45.9813 | 45.3416 | 46.4395 | 45.8778 | 47.178 | 46.653 | 47.222 | 46.7656 | 48.9173 | 48.2388 | 49.4136 | 48.8193 | 50.2165 | 49.561 | 49.3995 | 49.1977 | 52.0942 | 51.3738 | 52.6317 | 52.0022 | 53.5042 | 52.9097 | 53.5504 | 53.0437 | 55.532 | 54.7661 | 56.1141 | 55.4465 | 57.0619 | 56.3151 | 56.124 | 55.901 | 59.252 | 0
|  | SEKA overdue receivables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.4 | 68.9 | 112.6 | 71.8 | 34.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18.5434 | 19.435 | 19.0847 | 19.6276 | 19.3358 | 20.0969 | 19.7623 | 19.9027 | 19.6903 | 21.0112 | 20.6323 | 21.219 | 20.9034 | 21.726 | 21.2917 | 21.0646 | 20.9162 | 22.7137 | 22.304 | 22.9381 | 22.5967 | 23.4858 | 23.0945 | 23.2582 | 23.0097 | 24.5528 | 24.1097 | 24.795 | 24.4258 | 25.3867 | 24.8788 | 24.613 | 24.4394 | 26.5393 | 26.0601 | 26.8006 | 26.4014 | 27.4397 | 26.9822 | 27.173 | 26.8823 | 28.6847 | 28.1666 | 28.9667 | 28.535 | 29.657 | 29.0633 | 28.7524 | 28.5491 | 31.0016 | 0
|  | GTA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.2718 | 2.317 | 2.3095 | 2.3476 | 2.3414 | 2.3844 | 2.3774 | 2.4077 | 2.4033 | 2.4586 | 2.4507 | 2.4911 | 2.4846 | 2.5302 | 2.5212 | 2.5457 | 2.5426 | 2.6089 | 2.6005 | 2.6433 | 2.6364 | 2.6848 | 2.6769 | 2.7111 | 2.7061 | 2.7683 | 2.7594 | 2.8049 | 2.7975 | 2.8488 | 2.8388 | 2.8663 | 2.8629 | 2.9374 | 2.928 | 2.9762 | 2.9685 | 3.0229 | 3.014 | 3.0525 | 3.0469 | 3.1169 | 3.1069 | 3.158 | 3.1498 | 3.2075 | 3.1962 | 3.2273 | 3.2234 | 3.3072 | 0
|  | O&M and LTSA payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.674 | 1.769 | 1.7663 | 1.8043 | 1.8448 | 1.9267 | 1.9537 | 1.9807 | 2.0046 | 2.1346 | 2.1305 | 2.1767 | 2.169 | 2.2357 | 2.2175 | 2.1884 | 2.19 | 2.3527 | 2.3372 | 2.3849 | 2.3765 | 2.4486 | 2.4365 | 2.4374 | 2.4386 | 2.5767 | 2.5598 | 2.612 | 2.6028 | 2.6818 | 2.66 | 2.625 | 2.627 | 2.8221 | 2.8036 | 2.8608 | 2.8506 | 2.9372 | 2.9226 | 2.9237 | 2.9251 | 3.0908 | 3.0705 | 3.1332 | 3.1221 | 3.2168 | 3.1907 | 3.1487 | 3.1511 | 3.3851 | 0
|  | Other payables | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.1772 | 1.2381 | 1.2855 | 1.3022 | 1.3449 | 1.4027 | 1.4437 | 1.5037 | 1.524 | 1.5967 | 1.5975 | 1.6401 | 1.6313 | 1.6718 | 1.6669 | 1.6894 | 1.6846 | 1.7538 | 1.7428 | 1.7865 | 1.777 | 1.8199 | 1.8164 | 1.851 | 1.8434 | 1.9095 | 1.8977 | 1.9453 | 1.935 | 1.9818 | 1.9762 | 2.0031 | 1.9975 | 2.0798 | 2.0669 | 2.1189 | 2.1077 | 2.1588 | 2.1548 | 2.1961 | 2.1872 | 2.2658 | 2.2519 | 2.3086 | 2.2966 | 2.3523 | 2.3458 | 2.3781 | 2.3715 | 2.4692 | 0
|  | Deferred SNHK/GCK payables matching SEKA energy-charge arrears | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.72 | 55.12 | 90.08 | 57.44 | 27.68 | 9.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net working capital (excl. spares inventory) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14.5543 | 18.644 | 28.3948 | 37.4454 | 29.2501 | 22.1397 | 17.7318 | 15.6787 | 15.5817 | 15.9524 | 15.8024 | 16.1371 | 15.9568 | 16.2013 | 16.0955 | 16.1689 | 16.14 | 16.5521 | 16.357 | 16.6866 | 16.4912 | 16.7389 | 16.6287 | 16.9643 | 16.7678 | 17.1099 | 16.9122 | 17.2564 | 17.0581 | 17.3174 | 17.2073 | 17.292 | 17.2709 | 17.7157 | 17.5152 | 17.8752 | 17.674 | 17.9457 | 17.836 | 18.2051 | 18.0023 | 18.3738 | 18.1702 | 18.5475 | 18.343 | 18.6282 | 18.5192 | 18.6175 | 18.6059 | 19.0887 | 0
|  | Increase in net working capital | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5543 | 4.0897 | 9.7508 | 9.0505 | -8.1953 | -7.1103 | -4.4079 | -2.0531 | -0.097034 | 0.3707 | -0.14999 | 0.33475 | -0.18037 | 0.24457 | -0.1058 | 0.073381 | -0.028928 | 0.41214 | -0.19509 | 0.32958 | -0.19546 | 0.24773 | -0.11022 | 0.33565 | -0.19649 | 0.34207 | -0.1977 | 0.34415 | -0.19823 | 0.25922 | -0.11003 | 0.084659 | -0.02107 | 0.44479 | -0.20051 | 0.36002 | -0.20123 | 0.27169 | -0.10964 | 0.36909 | -0.20283 | 0.3715 | -0.20355 | 0.37729 | -0.20449 | 0.2852 | -0.109 | 0.098248 | -0.011611 | 0.48288 | -19.0887
|  | Release of spares inventory at expiry | USD m |  | 5.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.35

## Tax
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Tax: holiday, deferred depreciation, thin capitalization, minimum turnover tax
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Holiday months (OY1-OY5) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reduced-rate months (OY6-OY8) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full-rate months (OY9+) | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
| Tax depreciation (straight line from COD) | USD m |  | 801.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6063 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.237 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 16.1615 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.66783
| Depreciation of holiday months (deemed deferred) | USD m |  | 216.3775 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6063 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 21.6377 | 18.0315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation deducted currently | USD m |  | 585.0206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2056 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 19.2336 | 16.1615 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.8014 | 0.66783
| Shareholder loan interest accrued | USD m |  | 146.8275 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6577 | 9.757 | 9.5391 | 9.8329 | 10.4668 | 10.8488 | 11.4876 | 9.6624 | 9.1656 | 8.4454 | 8.1142 | 7.4522 | 7.0528 | 6.3982 | 5.8845 | 5.2054 | 4.623 | 3.7985 | 3.1216 | 2.2654 | 1.4791 | 0.56923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thin cap: deductible share = min(1, 3 x equity / SHL) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.64134 | 0.70478 | 0.87245 | 0.92601 | 0.92745 | 0.92239 | 0.96428 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Shareholder loan interest deductible | USD m |  | 139.3966 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0632 | 6.8766 | 8.3223 | 9.1054 | 9.7074 | 10.0069 | 11.0772 | 9.6624 | 9.1656 | 8.4454 | 8.1142 | 7.4522 | 7.0528 | 6.3982 | 5.8845 | 5.2054 | 4.623 | 3.7985 | 3.1216 | 2.2654 | 1.4791 | 0.56923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Senior financing costs deductible (all grandfathered) | USD m |  | 385.2811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.1128 | 20.2423 | 21.032 | 23.9195 | 21.9829 | 21.3192 | 19.2486 | 16.8801 | 16.2158 | 15.8213 | 15.2633 | 14.8395 | 14.3083 | 13.8248 | 13.2397 | 12.6932 | 12.0301 | 11.4363 | 10.7421 | 10.0931 | 9.3669 | 8.6551 | 7.8846 | 7.1412 | 6.4661 | 5.8525 | 4.9851 | 4.0986 | 3.1655 | 2.2107 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non-holiday share of operating months | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Taxable income before losses and deferred depreciation | USD m |  | 1302.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4689 | 10.2723 | 11.2705 | 12.567 | 13.7741 | 1.1763 | 16.3254 | 18.0089 | 19.4326 | 21.1709 | 22.7432 | 24.4687 | 25.9365 | 23.6957 | 27.9004 | 28.5305 | 29.3116 | 30.384 | 31.4199 | 32.4483 | 33.6326 | 18.1288 | 36.0778 | 36.2573 | 36.4406 | 36.6643 | 36.8274 | 36.9286 | 37.1534 | 33.5454 | 40.7669 | 56.0609 | 56.2613 | 56.5056 | 56.6835 | 56.7911 | 57.0683 | 37.3953 | 57.3952 | 57.5528 | 26.4172
| Tax losses used | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation used | USD m |  | 216.3775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4689 | 10.2723 | 11.2705 | 12.567 | 13.7741 | 1.1763 | 16.3254 | 18.0089 | 19.4326 | 21.1709 | 22.7432 | 24.4687 | 25.9365 | 17.7622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred depreciation pool, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.6063 | 25.244 | 46.8818 | 68.5195 | 90.1573 | 111.795 | 133.4328 | 155.0705 | 176.7083 | 198.346 | 214.9086 | 204.6364 | 193.3658 | 180.7988 | 167.0247 | 165.8484 | 149.523 | 131.5141 | 112.0815 | 90.9106 | 68.1674 | 43.6987 | 17.7622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tax losses carried forward, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taxable income | USD m |  | 1086.4825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9335 | 27.9004 | 28.5305 | 29.3116 | 30.384 | 31.4199 | 32.4483 | 33.6326 | 18.1288 | 36.0778 | 36.2573 | 36.4406 | 36.6643 | 36.8274 | 36.9286 | 37.1534 | 33.5454 | 40.7669 | 56.0609 | 56.2613 | 56.5056 | 56.6835 | 56.7911 | 57.0683 | 37.3953 | 57.3952 | 57.5528 | 26.4172
| Applicable CIT rate (month-weighted) | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.175 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Corporate income tax | USD m |  | 325.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.78 | 8.3701 | 8.5592 | 8.7935 | 9.1152 | 9.426 | 9.7345 | 10.0898 | 5.4386 | 10.8233 | 10.8772 | 10.9322 | 10.9993 | 11.0482 | 11.0786 | 11.146 | 10.0636 | 12.2301 | 16.8183 | 16.8784 | 16.9517 | 17.005 | 17.0373 | 17.1205 | 11.2186 | 17.2186 | 17.2658 | 7.9252
| Minimum turnover tax | USD m |  | 16.8757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.062588 | 0.37759 | 0.37991 | 0.38254 | 0.38421 | 0.37907 | 0.38475 | 0.39094 | 0.39299 | 0.39472 | 0.39698 | 0.39963 | 0.40155 | 0.40218 | 0.40477 | 0.40872 | 0.41096 | 0.41285 | 0.41532 | 0.41822 | 0.4201 | 0.41454 | 0.42097 | 0.42815 | 0.4306 | 0.43267 | 0.43537 | 0.43854 | 0.44083 | 0.4416 | 0.4447 | 0.4494 | 0.45208 | 0.45434 | 0.4573 | 0.46075 | 0.46301 | 0.45695 | 0.46427 | 0.47263 | 0.3964
| Tax paid = max(CIT, MTT) | USD m |  | 330.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.062588 | 0.37759 | 0.37991 | 0.38254 | 0.38421 | 0.37907 | 0.38475 | 0.39094 | 0.39299 | 0.39472 | 0.39698 | 0.39963 | 0.40155 | 1.78 | 8.3701 | 8.5592 | 8.7935 | 9.1152 | 9.426 | 9.7345 | 10.0898 | 5.4386 | 10.8233 | 10.8772 | 10.9322 | 10.9993 | 11.0482 | 11.0786 | 11.146 | 10.0636 | 12.2301 | 16.8183 | 16.8784 | 16.9517 | 17.005 | 17.0373 | 17.1205 | 11.2186 | 17.2186 | 17.2658 | 7.9252
| Thin-cap disallowance | USD m |  | 7.431 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59455 | 2.8805 | 1.2167 | 0.72752 | 0.75937 | 0.84193 | 0.41039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Funding
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Funding: closed-form gross-up, drawdowns by tranche, IDC, fees, equity
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Month |  |  |  | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12
Constants
|  | Contract debt share of funding g = D/(D+E) | fraction | 0.74057
|  | Gearing used in the closed-form gross-up | fraction | 0.75
|  | ECA premium gross-up denominator 1 - prem x share x g | factor | 0.97559
|  | First installment share of remaining profile | fraction | 0.025482
|  | DSRA coefficient per USD of E balance | factor | 0.033979
|  | DSRA coefficient per USD of A balance | factor | 0.045542
|  | DSRA coefficient per USD of B balance | factor | 0.044285
|  | DSRA coefficient per USD of C balance | factor | 0.055418
|  | DSRA coefficient per USD of standby balance | factor | 0.049729
|  | DSRA constant (swap net payment) | USD m | 6.4374
Closed-form gross-up: debt balance = alpha + beta x T (FC-type cases)
|  | Blended loan rate per month (rho) | factor |  |  | 0.0054193 | 0.0052445 | 0.0054193 | 0.0052445 | 0.0054193 | 0.0057335 | 0.0051786 | 0.0057335 | 0.0055485 | 0.0057335 | 0.0055485 | 0.0051321 | 0.0051321 | 0.0049666 | 0.0051321 | 0.0049666 | 0.0051321 | 0.0048719 | 0.0045576 | 0.0048719 | 0.0047147 | 0.0048719 | 0.0047147 | 0.0034898 | 0.0034898 | 0.0033772 | 0.0034898 | 0.0033772 | 0.0034898 | 0.0033821 | 0.0030548 | 0.0033821 | 0.003273 | 0.0033821 | 0.003273 | 0.0033013 | 0.0033013 | 0.0031948 | 0.0033013 | 0.0031948 | 0.0033013 | 0.0034629 | 0.0031277 | 0.0034629 | 0.0033511 | 0.0034629 | 0.0033511 | 0.0057963 | 0.0057963 | 0.0056093 | 0.0057963 | 0.0056093 | 0.0057963
|  | Blended commitment fee per month (kappa) | factor |  |  | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00081216 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00078416 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00086817 | 0.00084017 | 0.00086817 | 0.00084017 | 0.00086817
|  | Costs independent of facility size | USD m |  |  | 108.0747 | 1.4865 | 1.9207 | 2.7338 | 3.8452 | 5.1647 | 6.7187 | 8.37 | 10.1246 | 11.8989 | 13.6596 | 15.4098 | 17.0513 | 18.5855 | 19.958 | 21.1815 | 22.1944 | 24.14 | 23.6223 | 23.9698 | 24.4619 | 24.3503 | 24.0318 | 23.8725 | 23.1108 | 22.1405 | 22.5422 | 21.2073 | 19.7212 | 18.6508 | 16.9671 | 15.2273 | 11.5689 | 11.1772 | 8.1666 | 5.96 | 3.6253 | 5.1675 | 2.4173 | 57.5739 | 6.5073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance, constant part (alpha) | USD m |  |  | 83.0843 | 84.5084 | 86.2806 | 88.6744 | 91.9407 | 96.255 | 101.7453 | 108.5605 | 116.7368 | 126.321 | 137.2792 | 149.5758 | 163.1746 | 177.9801 | 193.9066 | 210.8053 | 228.5586 | 247.8202 | 266.6938 | 285.9418 | 305.5991 | 325.2594 | 344.7031 | 363.7503 | 382.2502 | 400.0167 | 418.1526 | 435.2716 | 451.3099 | 466.5202 | 480.3783 | 493.0129 | 502.8288 | 512.3932 | 519.6298 | 525.1836 | 528.953 | 533.8832 | 536.7402 | 581.9727 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639 | 588.0639
|  | Balance per USD of total funding (beta) | factor |  |  | 0.0095643 | 0.010081 | 0.010617 | 0.011137 | 0.011677 | 0.012221 | 0.012715 | 0.013263 | 0.013795 | 0.014347 | 0.014884 | 0.015433 | 0.015984 | 0.016519 | 0.017074 | 0.017613 | 0.018171 | 0.018727 | 0.01925 | 0.019809 | 0.020353 | 0.020916 | 0.021463 | 0.022007 | 0.022551 | 0.02308 | 0.023627 | 0.024157 | 0.024707 | 0.025255 | 0.025751 | 0.026302 | 0.026835 | 0.027388 | 0.027923 | 0.028476 | 0.02903 | 0.029567 | 0.030123 | 0.030662 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569 | 0.057569
|  | Total funding requirement at this gearing, closed form T = alpha/(g - beta) | USD m | 849.2746
|  | Senior debt (committed tranches) | USD m | 633.256
|  | Debt share of monthly funding | fraction | 0.74057
Monthly funding schedule (USD m)
|  | ECA-covered tranche: opening balance | USD m |  |  | 0 | 26.9957 | 27.5455 | 28.203 | 29.0408 | 30.1416 | 31.5539 | 33.3017 | 35.4554 | 38.0081 | 40.9825 | 44.3598 | 48.1367 | 52.2995 | 56.8155 | 61.6682 | 66.8046 | 72.1987 | 78.0389 | 83.7556 | 89.5922 | 95.5458 | 101.5048 | 107.3954 | 113.1691 | 118.7808 | 124.1711 | 129.6752 | 134.8741 | 139.7573 | 144.3951 | 148.6197 | 152.495 | 155.5314 | 158.4979 | 160.7708 | 162.5497 | 163.8003 | 165.3906 | 166.3715 | 179.8971 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748
|  | ABDB A-loan: opening balance | USD m |  |  | 0 | 19.7969 | 20.2 | 20.6822 | 21.2966 | 22.1039 | 23.1395 | 24.4213 | 26.0006 | 27.8726 | 30.0538 | 32.5305 | 35.3002 | 38.353 | 41.6647 | 45.2233 | 48.99 | 52.9457 | 57.2285 | 61.4208 | 65.701 | 70.0669 | 74.4368 | 78.7567 | 82.9907 | 87.1059 | 91.0588 | 95.0952 | 98.9076 | 102.4887 | 105.8897 | 108.9877 | 111.8297 | 114.0564 | 116.2318 | 117.8986 | 119.2031 | 120.1202 | 121.2864 | 122.0057 | 131.9246 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215
|  | ABDB B-loan: opening balance | USD m |  |  | 0 | 8.9986 | 9.1818 | 9.401 | 9.6803 | 10.0472 | 10.518 | 11.1006 | 11.8185 | 12.6694 | 13.6608 | 14.7866 | 16.0456 | 17.4332 | 18.9385 | 20.5561 | 22.2682 | 24.0662 | 26.013 | 27.9185 | 29.8641 | 31.8486 | 33.8349 | 35.7985 | 37.723 | 39.5936 | 41.3904 | 43.2251 | 44.958 | 46.5858 | 48.1317 | 49.5399 | 50.8317 | 51.8438 | 52.8326 | 53.5903 | 54.1832 | 54.6001 | 55.1302 | 55.4572 | 59.9657 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916
|  | Commercial tranche: opening balance | USD m |  |  | 0 | 34.1946 | 34.8909 | 35.7238 | 36.785 | 38.1794 | 39.9682 | 42.1822 | 44.9101 | 48.1436 | 51.9112 | 56.1891 | 60.9731 | 66.246 | 71.9664 | 78.113 | 84.6191 | 91.4516 | 98.8493 | 106.0905 | 113.4835 | 121.0246 | 128.5727 | 136.0342 | 143.3475 | 150.4557 | 157.2834 | 164.2553 | 170.8405 | 177.0259 | 182.9004 | 188.2516 | 193.1603 | 197.0065 | 200.764 | 203.6431 | 205.8963 | 207.4804 | 209.4947 | 210.7372 | 227.8697 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281
|  | Standby facility: opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: interest | USD m |  | 7.0928 | 0 | 0.087061 | 0.091795 | 0.090955 | 0.096778 | 0.10953 | 0.10357 | 0.12101 | 0.12468 | 0.13812 | 0.14412 | 0.13561 | 0.14715 | 0.15472 | 0.17368 | 0.18244 | 0.20422 | 0.20268 | 0.20494 | 0.23512 | 0.24339 | 0.26822 | 0.27575 | 0.15906 | 0.16762 | 0.17025 | 0.18391 | 0.18587 | 0.19976 | 0.19255 | 0.17969 | 0.20476 | 0.20333 | 0.21429 | 0.21133 | 0.20905 | 0.21136 | 0.20612 | 0.21505 | 0.20935 | 0.23392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: interest | USD m |  | 10.6236 | 0 | 0.10179 | 0.10732 | 0.10634 | 0.11315 | 0.1241 | 0.11734 | 0.13711 | 0.14127 | 0.15649 | 0.16329 | 0.16387 | 0.17782 | 0.18697 | 0.20989 | 0.22046 | 0.24679 | 0.25349 | 0.25632 | 0.29407 | 0.30441 | 0.33546 | 0.34489 | 0.27263 | 0.28729 | 0.2918 | 0.31522 | 0.31857 | 0.34239 | 0.34419 | 0.3212 | 0.36602 | 0.36345 | 0.38304 | 0.37775 | 0.38681 | 0.39109 | 0.38138 | 0.39792 | 0.38737 | 0.43282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: interest | USD m |  | 4.561 | 0 | 0.044393 | 0.046807 | 0.046378 | 0.049348 | 0.054247 | 0.051293 | 0.059934 | 0.061751 | 0.068404 | 0.071378 | 0.071304 | 0.077375 | 0.081355 | 0.091326 | 0.095928 | 0.10738 | 0.11004 | 0.11127 | 0.12766 | 0.13215 | 0.14563 | 0.14972 | 0.11622 | 0.12246 | 0.12439 | 0.13437 | 0.1358 | 0.14595 | 0.14642 | 0.13664 | 0.15571 | 0.15461 | 0.16295 | 0.1607 | 0.16428 | 0.1661 | 0.16198 | 0.169 | 0.16452 | 0.18383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: interest | USD m |  | 22.4247 | 0 | 0.2096 | 0.221 | 0.21897 | 0.23299 | 0.25461 | 0.24075 | 0.28131 | 0.28984 | 0.32106 | 0.33502 | 0.3387 | 0.36753 | 0.38644 | 0.4338 | 0.45566 | 0.51007 | 0.52588 | 0.53174 | 0.61005 | 0.63151 | 0.69593 | 0.71548 | 0.5818 | 0.61308 | 0.62272 | 0.67268 | 0.67983 | 0.73066 | 0.73679 | 0.68757 | 0.78351 | 0.77801 | 0.81995 | 0.80863 | 0.83003 | 0.83922 | 0.8184 | 0.85389 | 0.83124 | 0.92878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: interest | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium on commercial tranche | USD m |  | 4.1568 | 0 | 0.029089 | 0.030671 | 0.03039 | 0.032336 | 0.033561 | 0.031734 | 0.03708 | 0.038204 | 0.04232 | 0.04416 | 0.049393 | 0.053598 | 0.056354 | 0.063261 | 0.06645 | 0.074384 | 0.08039 | 0.081287 | 0.093258 | 0.096539 | 0.10639 | 0.10937 | 0.11958 | 0.12601 | 0.12799 | 0.13826 | 0.13973 | 0.15018 | 0.15561 | 0.14522 | 0.16548 | 0.16432 | 0.17318 | 0.17079 | 0.17901 | 0.18099 | 0.1765 | 0.18415 | 0.17927 | 0.20031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Swap net payment | USD m |  | 13.6621 | 0 | 0.025634 | 0.021014 | 0.026832 | 0.022316 | -0.0012742 | 0.019501 | -0.001464 | 0.0066016 | -0.0017656 | 0.0080856 | 0.078754 | 0.087718 | 0.10813 | 0.10801 | 0.13205 | 0.13054 | 0.2055 | 0.2522 | 0.23974 | 0.27281 | 0.27166 | 0.30512 | 0.7904 | 0.82297 | 0.85602 | 0.87698 | 0.9026 | 0.91576 | 0.97483 | 0.99563 | 0.99526 | 1.0057 | 1.0746 | 1.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fees, senior tranches | USD m |  | 11.347 | 0.54978 | 0.45644 | 0.47006 | 0.45306 | 0.46573 | 0.46255 | 0.41409 | 0.4534 | 0.43275 | 0.43978 | 0.41727 | 0.4214 | 0.41047 | 0.38557 | 0.38536 | 0.35934 | 0.35645 | 0.34084 | 0.30304 | 0.30739 | 0.28113 | 0.27327 | 0.24777 | 0.23898 | 0.22227 | 0.19939 | 0.19044 | 0.16888 | 0.15946 | 0.14533 | 0.11914 | 0.11968 | 0.10497 | 0.099682 | 0.088158 | 0.084519 | 0.079371 | 0.073309 | 0.07115 | 0.066108 | 0.02917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commitment fee, standby facility | USD m |  | 0.95757 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.022233 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.021467 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0.023767 | 0.023 | 0.023767 | 0.023 | 0.023767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upfront and arrangement fees | USD m |  | 9.9548 | 9.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Agency fees during construction | USD m |  | 0.87125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0.02125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA initial funding (COD month) | USD m |  | 33.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uses before ECA premium | USD m |  |  | 118.5792 | 2.4148 | 2.8883 | 3.6799 | 4.8356 | 6.2033 | 7.6774 | 9.4599 | 11.2131 | 13.0651 | 14.8348 | 16.59 | 18.2852 | 19.8369 | 21.3153 | 22.5617 | 23.6937 | 25.6533 | 25.1109 | 25.6373 | 26.1511 | 26.1752 | 25.8748 | 25.3608 | 24.6495 | 23.6771 | 24.1771 | 22.836 | 21.4496 | 20.3717 | 18.5566 | 17.0225 | 13.3376 | 13.0303 | 9.984 | 7.8137 | 5.4935 | 6.9852 | 4.3085 | 59.4118 | 35.9206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Headroom on committed senior tranches | USD m |  |  | 633.256 | 543.2703 | 541.4378 | 539.2459 | 536.4534 | 532.7838 | 528.0764 | 522.2502 | 515.0715 | 506.5623 | 496.6476 | 485.39 | 472.8004 | 458.9243 | 443.8708 | 427.6954 | 410.5741 | 392.5938 | 373.1264 | 354.0706 | 334.6153 | 314.7701 | 294.9067 | 275.2712 | 256.0257 | 237.3201 | 219.3523 | 201.0052 | 183.6758 | 167.3984 | 151.9391 | 137.8571 | 124.9394 | 114.8179 | 104.9297 | 97.3532 | 91.4237 | 87.2549 | 81.954 | 78.6844 | 33.5989 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | 6.34
|  | Senior tranche drawdown (pro rata) | USD m |  | 626.916 | 89.9857 | 1.8325 | 2.1918 | 2.7925 | 3.6695 | 4.7074 | 5.8261 | 7.1788 | 8.5092 | 9.9147 | 11.2576 | 12.5896 | 13.876 | 15.0535 | 16.1754 | 17.1213 | 17.9803 | 19.4674 | 19.0558 | 19.4553 | 19.8451 | 19.8635 | 19.6355 | 19.2454 | 18.7057 | 17.9677 | 18.3471 | 17.3294 | 16.2773 | 15.4593 | 14.0819 | 12.9178 | 10.1214 | 9.8882 | 7.5765 | 5.9295 | 4.1688 | 5.3008 | 3.2696 | 45.0855 | 27.2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA premium (financed) | USD m |  | 20.4061 | 2.929 | 0.059649 | 0.071345 | 0.090897 | 0.11944 | 0.15323 | 0.18964 | 0.23367 | 0.27697 | 0.32272 | 0.36644 | 0.40979 | 0.45166 | 0.48999 | 0.52651 | 0.5573 | 0.58526 | 0.63366 | 0.62027 | 0.63327 | 0.64596 | 0.64656 | 0.63914 | 0.62644 | 0.60887 | 0.58485 | 0.5972 | 0.56407 | 0.52983 | 0.5032 | 0.45837 | 0.42047 | 0.32945 | 0.32186 | 0.24662 | 0.19301 | 0.13569 | 0.17254 | 0.10642 | 1.4675 | 0.88728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total uses of funds | USD m |  | 846.5288 | 121.5083 | 2.4745 | 2.9597 | 3.7708 | 4.955 | 6.3565 | 7.8671 | 9.6935 | 11.49 | 13.3878 | 15.2013 | 16.9998 | 18.7369 | 20.3269 | 21.8418 | 23.119 | 24.2789 | 26.2869 | 25.7312 | 26.2706 | 26.797 | 26.8218 | 26.5139 | 25.9873 | 25.2584 | 24.2619 | 24.7743 | 23.4001 | 21.9794 | 20.8749 | 19.0149 | 17.4429 | 13.667 | 13.3521 | 10.2306 | 8.0067 | 5.6292 | 7.1578 | 4.4149 | 60.8793 | 36.8078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funded pro rata from committed debt and equity | USD m |  | 846.5288 | 121.5083 | 2.4745 | 2.9597 | 3.7708 | 4.955 | 6.3565 | 7.8671 | 9.6935 | 11.49 | 13.3878 | 15.2013 | 16.9998 | 18.7369 | 20.3269 | 21.8418 | 23.119 | 24.2789 | 26.2869 | 25.7312 | 26.2706 | 26.797 | 26.8218 | 26.5139 | 25.9873 | 25.2584 | 24.2619 | 24.7743 | 23.4001 | 21.9794 | 20.8749 | 19.0149 | 17.4429 | 13.667 | 13.3521 | 10.2306 | 8.0067 | 5.6292 | 7.1578 | 4.4149 | 60.8793 | 36.8078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining uses after committed facilities | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delay LDs and DSU proceeds received | USD m |  | 17.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds applied | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LD and DSU proceeds held (Proceeds Account) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197 | 17.2197
|  | Standby facility drawdown (75%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingent equity (25%) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: drawdown | USD m |  | 188.0748 | 26.9957 | 0.54976 | 0.65755 | 0.83776 | 1.1009 | 1.4122 | 1.7478 | 2.1536 | 2.5528 | 2.9744 | 3.3773 | 3.7769 | 4.1628 | 4.5161 | 4.8526 | 5.1364 | 5.3941 | 5.8402 | 5.7167 | 5.8366 | 5.9535 | 5.959 | 5.8907 | 5.7736 | 5.6117 | 5.3903 | 5.5041 | 5.1988 | 4.8832 | 4.6378 | 4.2246 | 3.8753 | 3.0364 | 2.9665 | 2.273 | 1.7789 | 1.2506 | 1.5903 | 0.98088 | 13.5257 | 8.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: drawdown | USD m |  | 137.9215 | 19.7969 | 0.40316 | 0.48221 | 0.61436 | 0.8073 | 1.0356 | 1.2818 | 1.5793 | 1.872 | 2.1812 | 2.4767 | 2.7697 | 3.0527 | 3.3118 | 3.5586 | 3.7667 | 3.9557 | 4.2828 | 4.1923 | 4.2802 | 4.3659 | 4.37 | 4.3198 | 4.234 | 4.1152 | 3.9529 | 4.0364 | 3.8125 | 3.581 | 3.4011 | 3.098 | 2.8419 | 2.2267 | 2.1754 | 1.6668 | 1.3045 | 0.91714 | 1.1662 | 0.71931 | 9.9188 | 5.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: drawdown | USD m |  | 62.6916 | 8.9986 | 0.18325 | 0.21918 | 0.27925 | 0.36695 | 0.47074 | 0.58261 | 0.71788 | 0.85092 | 0.99147 | 1.1258 | 1.259 | 1.3876 | 1.5054 | 1.6175 | 1.7121 | 1.798 | 1.9467 | 1.9056 | 1.9455 | 1.9845 | 1.9863 | 1.9636 | 1.9245 | 1.8706 | 1.7968 | 1.8347 | 1.7329 | 1.6277 | 1.5459 | 1.4082 | 1.2918 | 1.0121 | 0.98882 | 0.75765 | 0.59295 | 0.41688 | 0.53008 | 0.32696 | 4.5086 | 2.7259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: drawdown | USD m |  | 238.2281 | 34.1946 | 0.69636 | 0.8329 | 1.0612 | 1.3944 | 1.7888 | 2.2139 | 2.7279 | 3.2335 | 3.7676 | 4.2779 | 4.7841 | 5.2729 | 5.7203 | 6.1467 | 6.5061 | 6.8325 | 7.3976 | 7.2412 | 7.393 | 7.5412 | 7.5481 | 7.4615 | 7.3133 | 7.1082 | 6.8277 | 6.9719 | 6.5852 | 6.1854 | 5.8746 | 5.3511 | 4.9087 | 3.8461 | 3.7575 | 2.8791 | 2.2532 | 1.5841 | 2.0143 | 1.2424 | 17.1325 | 10.3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: closing balance | USD m |  |  | 26.9957 | 27.5455 | 28.203 | 29.0408 | 30.1416 | 31.5539 | 33.3017 | 35.4554 | 38.0081 | 40.9825 | 44.3598 | 48.1367 | 52.2995 | 56.8155 | 61.6682 | 66.8046 | 72.1987 | 78.0389 | 83.7556 | 89.5922 | 95.5458 | 101.5048 | 107.3954 | 113.1691 | 118.7808 | 124.1711 | 129.6752 | 134.8741 | 139.7573 | 144.3951 | 148.6197 | 152.495 | 155.5314 | 158.4979 | 160.7708 | 162.5497 | 163.8003 | 165.3906 | 166.3715 | 179.8971 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748 | 188.0748
|  | ABDB A-loan: closing balance | USD m |  |  | 19.7969 | 20.2 | 20.6822 | 21.2966 | 22.1039 | 23.1395 | 24.4213 | 26.0006 | 27.8726 | 30.0538 | 32.5305 | 35.3002 | 38.353 | 41.6647 | 45.2233 | 48.99 | 52.9457 | 57.2285 | 61.4208 | 65.701 | 70.0669 | 74.4368 | 78.7567 | 82.9907 | 87.1059 | 91.0588 | 95.0952 | 98.9076 | 102.4887 | 105.8897 | 108.9877 | 111.8297 | 114.0564 | 116.2318 | 117.8986 | 119.2031 | 120.1202 | 121.2864 | 122.0057 | 131.9246 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215 | 137.9215
|  | ABDB B-loan: closing balance | USD m |  |  | 8.9986 | 9.1818 | 9.401 | 9.6803 | 10.0472 | 10.518 | 11.1006 | 11.8185 | 12.6694 | 13.6608 | 14.7866 | 16.0456 | 17.4332 | 18.9385 | 20.5561 | 22.2682 | 24.0662 | 26.013 | 27.9185 | 29.8641 | 31.8486 | 33.8349 | 35.7985 | 37.723 | 39.5936 | 41.3904 | 43.2251 | 44.958 | 46.5858 | 48.1317 | 49.5399 | 50.8317 | 51.8438 | 52.8326 | 53.5903 | 54.1832 | 54.6001 | 55.1302 | 55.4572 | 59.9657 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916 | 62.6916
|  | Commercial tranche: closing balance | USD m |  |  | 34.1946 | 34.8909 | 35.7238 | 36.785 | 38.1794 | 39.9682 | 42.1822 | 44.9101 | 48.1436 | 51.9112 | 56.1891 | 60.9731 | 66.246 | 71.9664 | 78.113 | 84.6191 | 91.4516 | 98.8493 | 106.0905 | 113.4835 | 121.0246 | 128.5727 | 136.0342 | 143.3475 | 150.4557 | 157.2834 | 164.2553 | 170.8405 | 177.0259 | 182.9004 | 188.2516 | 193.1603 | 197.0065 | 200.764 | 203.6431 | 205.8963 | 207.4804 | 209.4947 | 210.7372 | 227.8697 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281 | 238.2281
|  | Standby facility: closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity (USD m)
|  | Equity contributions (incl. LNTP credit in month 1) | USD m |  | 219.6128 | 31.5226 | 0.64195 | 0.76782 | 0.97825 | 1.2855 | 1.649 | 2.0409 | 2.5148 | 2.9808 | 3.4732 | 3.9436 | 4.4102 | 4.8609 | 5.2734 | 5.6664 | 5.9977 | 6.2986 | 6.8196 | 6.6754 | 6.8153 | 6.9519 | 6.9583 | 6.8784 | 6.7418 | 6.5527 | 6.2942 | 6.4271 | 6.0706 | 5.7021 | 5.4155 | 4.933 | 4.5252 | 3.5456 | 3.4639 | 2.6541 | 2.0772 | 1.4604 | 1.8569 | 1.1454 | 15.7938 | 9.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equity contributed in cash | USD m |  | 205.4128 | 17.3226 | 0.64195 | 0.76782 | 0.97825 | 1.2855 | 1.649 | 2.0409 | 2.5148 | 2.9808 | 3.4732 | 3.9436 | 4.4102 | 4.8609 | 5.2734 | 5.6664 | 5.9977 | 6.2986 | 6.8196 | 6.6754 | 6.8153 | 6.9519 | 6.9583 | 6.8784 | 6.7418 | 6.5527 | 6.2942 | 6.4271 | 6.0706 | 5.7021 | 5.4155 | 4.933 | 4.5252 | 3.5456 | 3.4639 | 2.6541 | 2.0772 | 1.4604 | 1.8569 | 1.1454 | 15.7938 | 9.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Share capital | USD m |  | 43.9226 | 6.3045 | 0.12839 | 0.15356 | 0.19565 | 0.25709 | 0.32981 | 0.40819 | 0.50295 | 0.59617 | 0.69463 | 0.78872 | 0.88204 | 0.97217 | 1.0547 | 1.1333 | 1.1995 | 1.2597 | 1.3639 | 1.3351 | 1.3631 | 1.3904 | 1.3917 | 1.3757 | 1.3484 | 1.3105 | 1.2588 | 1.2854 | 1.2141 | 1.1404 | 1.0831 | 0.9866 | 0.90504 | 0.70912 | 0.69278 | 0.53082 | 0.41543 | 0.29207 | 0.37138 | 0.22907 | 3.1588 | 1.9098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans advanced | USD m |  | 175.6903 | 25.2181 | 0.51356 | 0.61426 | 0.7826 | 1.0284 | 1.3192 | 1.6327 | 2.0118 | 2.3847 | 2.7785 | 3.1549 | 3.5282 | 3.8887 | 4.2187 | 4.5331 | 4.7982 | 5.0389 | 5.4556 | 5.3403 | 5.4523 | 5.5615 | 5.5666 | 5.5028 | 5.3934 | 5.2422 | 5.0354 | 5.1417 | 4.8565 | 4.5616 | 4.3324 | 3.9464 | 3.6201 | 2.8365 | 2.7711 | 2.1233 | 1.6617 | 1.1683 | 1.4855 | 0.91629 | 12.635 | 7.6392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest capitalized (to COD) | USD m |  | 29.7658 | 0 | 0.19691 | 0.2092 | 0.20889 | 0.22385 | 0.23395 | 0.22263 | 0.26145 | 0.27077 | 0.30122 | 0.31555 | 0.35407 | 0.3854 | 0.40634 | 0.4572 | 0.48141 | 0.54006 | 0.58507 | 0.59292 | 0.68169 | 0.70759 | 0.78176 | 0.80611 | 0.88388 | 0.93453 | 0.95262 | 1.0327 | 1.0476 | 1.1301 | 1.1761 | 1.1024 | 1.2612 | 1.2587 | 1.3337 | 1.3227 | 1.3946 | 1.4193 | 1.3937 | 1.4634 | 1.4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance | USD m |  |  | 25.2181 | 25.9285 | 26.752 | 27.7435 | 28.9957 | 30.5489 | 32.4043 | 34.6775 | 37.333 | 40.4127 | 43.8832 | 47.7654 | 52.0395 | 56.6645 | 61.6548 | 66.9344 | 72.5134 | 78.5541 | 84.4873 | 90.6212 | 96.8903 | 103.2387 | 109.5476 | 115.8249 | 122.0016 | 127.9896 | 134.164 | 140.0681 | 145.7599 | 151.2683 | 156.3171 | 161.1985 | 165.2937 | 169.3985 | 172.8445 | 175.9008 | 178.4883 | 181.3675 | 183.7472 | 197.8169 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561 | 205.4561
|  | Total debt drawdowns (incl. standby) | USD m |  | 626.916 | 89.9857 | 1.8325 | 2.1918 | 2.7925 | 3.6695 | 4.7074 | 5.8261 | 7.1788 | 8.5092 | 9.9147 | 11.2576 | 12.5896 | 13.876 | 15.0535 | 16.1754 | 17.1213 | 17.9803 | 19.4674 | 19.0558 | 19.4553 | 19.8451 | 19.8635 | 19.6355 | 19.2454 | 18.7057 | 17.9677 | 18.3471 | 17.3294 | 16.2773 | 15.4593 | 14.0819 | 12.9178 | 10.1214 | 9.8882 | 7.5765 | 5.9295 | 4.1688 | 5.3008 | 3.2696 | 45.0855 | 27.2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financing costs (IDC, fees, premium, VAT interest) | USD m |  | 107.5453 | 13.4786 | 1.0773 | 1.1251 | 1.1276 | 1.1978 | 1.2565 | 1.2307 | 1.3911 | 1.4419 | 1.5616 | 1.6071 | 1.7311 | 1.8402 | 1.9195 | 2.0684 | 2.1492 | 2.3014 | 2.4422 | 2.4503 | 2.6382 | 2.7063 | 2.8469 | 2.8905 | 3.0113 | 3.0777 | 3.0821 | 3.2162 | 3.1988 | 3.2786 | 3.2996 | 3.1341 | 3.3058 | 3.1929 | 3.3369 | 3.2787 | 2.1247 | 2.0774 | 2.0578 | 2.0623 | 3.3648 | 2.966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total funding requirement (sum of uses) | USD m | 846.5288
|  | Capitalized cost (book and tax) | USD m | 801.3981

## Debt
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Debt: tranches, scheduled repayment, waiver, refinancing, swap, sculpting
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Rates
|  | Commercial margin (step-ups) | % |  |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
|  | Waiver margin uplift | % |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: rate per period | factor |  |  | 0.01978 | 0.021217 | 0.018144 | 0.016481 | 0.0087911 | 0.0080444 | 0.0077178 | 0.0084969 | 0.021927 | 0.033376 | 0.039602 | 0.037605 | 0.038324 | 0.030309 | 0.030402 | 0.027141 | 0.027387 | 0.026287 | 0.026722 | 0.026685 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026685 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026685 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026685 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978 | 0.026685 | 0.026978 | 0.026538 | 0.026978 | 0.026538 | 0.026978
|  | ABDB A-loan: rate per period | factor |  |  | 0.031536 | 0.032781 | 0.0299 | 0.028109 | 0.020547 | 0.019608 | 0.019473 | 0.020061 | 0.033682 | 0.04494 | 0.051358 | 0.049232 | 0.05008 | 0.041873 | 0.042158 | 0.038705 | 0.039142 | 0.03785 | 0.038478 | 0.038312 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038312 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038312 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038312 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733 | 0.038312 | 0.038733 | 0.038102 | 0.038733 | 0.038102 | 0.038733
|  | ABDB B-loan: rate per period | factor |  |  | 0.030258 | 0.031524 | 0.028622 | 0.026845 | 0.019269 | 0.018351 | 0.018196 | 0.018804 | 0.032404 | 0.043683 | 0.05008 | 0.047968 | 0.048802 | 0.040616 | 0.04088 | 0.037448 | 0.037864 | 0.036593 | 0.0372 | 0.037048 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.037048 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.037048 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.037048 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456 | 0.037048 | 0.037456 | 0.036845 | 0.037456 | 0.036845 | 0.037456
|  | Commercial tranche: rate per period | factor |  |  | 0.037595 | 0.038937 | 0.035778 | 0.03376 | 0.025385 | 0.024301 | 0.024193 | 0.024804 | 0.03998 | 0.052447 | 0.05962 | 0.05723 | 0.0582 | 0.049039 | 0.049398 | 0.048313 | 0.048886 | 0.047363 | 0.048148 | 0.047906 | 0.048432 | 0.047642 | 0.048432 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050714 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050714 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050714 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272 | 0.050714 | 0.051272 | 0.050436 | 0.051272 | 0.050436 | 0.051272
|  | Standby facility: rate per period | factor |  |  | 0.036534 | 0.037816 | 0.03479 | 0.032848 | 0.024813 | 0.023765 | 0.023668 | 0.024247 | 0.038824 | 0.050785 | 0.057678 | 0.055379 | 0.056315 | 0.047513 | 0.047865 | 0.04581 | 0.046352 | 0.044899 | 0.045643 | 0.045416 | 0.045916 | 0.045167 | 0.045916 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.047102 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.047102 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.047102 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619 | 0.047102 | 0.047619 | 0.046843 | 0.047619 | 0.046843 | 0.047619
|  | 2025 project bond: rate per period | factor |  |  | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375 | 0.039375
Contract repayment profile
|  | Repayment profile, selected | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.02724 | 0.0282 | 0.029523 | 0.030345 | 0.031734 | 0.033467 | 0.035004 | 0.032582 | 0.034116 | 0.034823 | 0.036518 | 0.037549 | 0.039334 | 0.042479 | 0.044762 | 0.045108 | 0.047438 | 0.048907 | 0.051304 | 0.052816 | 0.055293 | 0.057844 | 0.050237 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining profile (this and later installments) | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.97452 | 0.94728 | 0.91908 | 0.88956 | 0.85921 | 0.82748 | 0.79401 | 0.75901 | 0.72642 | 0.69231 | 0.65749 | 0.62097 | 0.58342 | 0.54408 | 0.50161 | 0.45684 | 0.41173 | 0.3643 | 0.31539 | 0.26409 | 0.21127 | 0.15598 | 0.098133 | 0.047896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installment share of remaining balance | fraction |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025482 | 0.027953 | 0.029769 | 0.032122 | 0.034112 | 0.036934 | 0.040445 | 0.044085 | 0.042927 | 0.046964 | 0.050299 | 0.055542 | 0.060469 | 0.06742 | 0.078074 | 0.089237 | 0.098739 | 0.11521 | 0.13425 | 0.16267 | 0.2 | 0.26172 | 0.37085 | 0.51193 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Refinancing (2025H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Waiver deferral (2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_Deferred repayment (2024H1-2025H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flag_LD prepayment (2022H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECA-covered tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.0748 | 177.7368 | 172.7686 | 167.6254 | 165.4716 | 159.1296 | 152.5342 | 145.6225 | 138.4307 | 132.4883 | 126.2661 | 119.915 | 113.2547 | 106.4063 | 99.2324 | 91.4849 | 83.321 | 75.094 | 66.4421 | 57.5222 | 48.1652 | 38.5324 | 28.4478 | 17.8979 | 8.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2307 | 2.423 | 1.6153 | 0.80767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 75.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5981 | 3.8972 | 5.7663 | 6.6383 | 6.2225 | 6.0986 | 4.6231 | 4.4272 | 3.7572 | 3.6284 | 3.3191 | 3.2044 | 3.0221 | 2.8706 | 2.6334 | 2.4681 | 2.2112 | 2.0259 | 1.7632 | 1.5518 | 1.2853 | 1.0395 | 0.75494 | 0.48285 | 0.23182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 182.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7924 | 4.9682 | 5.1432 | 5.3845 | 5.5344 | 5.7877 | 6.1039 | 6.3842 | 5.9424 | 6.2222 | 6.3511 | 6.6603 | 6.8484 | 7.1739 | 7.7475 | 8.1639 | 8.2271 | 8.6519 | 8.9199 | 9.357 | 9.6329 | 10.0846 | 10.5499 | 9.1625 | 8.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 3.2307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 3.2307
|  | Deferred principal repaid | USD m |  | 3.2307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80767 | 0.80767 | 0.80767 | 0.80767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 182.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7924 | 4.9682 | 5.1432 | 2.1538 | 6.3421 | 6.5954 | 6.9116 | 7.1918 | 5.9424 | 6.2222 | 6.3511 | 6.6603 | 6.8484 | 7.1739 | 7.7475 | 8.1639 | 8.2271 | 8.6519 | 8.9199 | 9.357 | 9.6329 | 10.0846 | 10.5499 | 9.1625 | 8.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 5.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2307 | 2.423 | 1.6153 | 0.80767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.7368 | 172.7686 | 167.6254 | 165.4716 | 159.1296 | 152.5342 | 145.6225 | 138.4307 | 132.4883 | 126.2661 | 119.915 | 113.2547 | 106.4063 | 99.2324 | 91.4849 | 83.321 | 75.094 | 66.4421 | 57.5222 | 48.1652 | 38.5324 | 28.4478 | 17.8979 | 8.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 188.0748 | 177.7368 | 172.7686 | 167.6254 | 165.4716 | 159.1296 | 152.5342 | 145.6225 | 138.4307 | 132.4883 | 126.2661 | 119.915 | 113.2547 | 106.4063 | 99.2324 | 91.4849 | 83.321 | 75.094 | 66.4421 | 57.5222 | 48.1652 | 38.5324 | 28.4478 | 17.8979 | 8.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB A-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.9215 | 130.3404 | 126.697 | 122.9253 | 121.3459 | 116.695 | 111.8584 | 106.7899 | 101.5159 | 97.1581 | 92.5951 | 87.9377 | 83.0534 | 78.0313 | 72.7704 | 67.0889 | 61.1021 | 55.0689 | 48.7242 | 42.183 | 35.3212 | 28.2571 | 20.8617 | 13.1251 | 6.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3692 | 1.7769 | 1.1846 | 0.59229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 78.3106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7668 | 4.3902 | 5.6937 | 6.3132 | 5.9741 | 5.8441 | 4.6838 | 4.502 | 3.9292 | 3.803 | 3.5048 | 3.3836 | 3.182 | 3.0224 | 2.7727 | 2.5986 | 2.3281 | 2.133 | 1.8565 | 1.6339 | 1.3532 | 1.0945 | 0.79487 | 0.50838 | 0.24408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 133.8548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5145 | 3.6434 | 3.7717 | 3.9486 | 4.0585 | 4.2443 | 4.4762 | 4.6817 | 4.3578 | 4.563 | 4.6575 | 4.8842 | 5.0222 | 5.2609 | 5.6815 | 5.9868 | 6.0332 | 6.3447 | 6.5412 | 6.8618 | 7.0641 | 7.3954 | 7.7366 | 6.7192 | 6.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 2.3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 2.3692
|  | Deferred principal repaid | USD m |  | 2.3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59229 | 0.59229 | 0.59229 | 0.59229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 133.8548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5145 | 3.6434 | 3.7717 | 1.5795 | 4.6508 | 4.8366 | 5.0685 | 5.274 | 4.3578 | 4.563 | 4.6575 | 4.8842 | 5.0222 | 5.2609 | 5.6815 | 5.9868 | 6.0332 | 6.3447 | 6.5412 | 6.8618 | 7.0641 | 7.3954 | 7.7366 | 6.7192 | 6.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 4.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3692 | 1.7769 | 1.1846 | 0.59229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.3404 | 126.697 | 122.9253 | 121.3459 | 116.695 | 111.8584 | 106.7899 | 101.5159 | 97.1581 | 92.5951 | 87.9377 | 83.0534 | 78.0313 | 72.7704 | 67.0889 | 61.1021 | 55.0689 | 48.7242 | 42.183 | 35.3212 | 28.2571 | 20.8617 | 13.1251 | 6.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 137.9215 | 130.3404 | 126.697 | 122.9253 | 121.3459 | 116.695 | 111.8584 | 106.7899 | 101.5159 | 97.1581 | 92.5951 | 87.9377 | 83.0534 | 78.0313 | 72.7704 | 67.0889 | 61.1021 | 55.0689 | 48.7242 | 42.183 | 35.3212 | 28.2571 | 20.8617 | 13.1251 | 6.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABDB B-loan
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.6916 | 59.2456 | 57.5895 | 55.8751 | 55.1572 | 53.0432 | 50.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0769 | 0.80767 | 0.53845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 15.7121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1788 | 1.9198 | 2.5157 | 2.7982 | 2.6458 | 2.5886 | 2.0651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 12.5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5975 | 1.6561 | 1.7144 | 1.7948 | 1.8448 | 1.9292 | 2.0346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 1.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 1.0769
|  | Deferred principal repaid | USD m |  | 0.80767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26922 | 0.26922 | 0.26922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 12.3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5975 | 1.6561 | 1.7144 | 0.71793 | 2.114 | 2.1985 | 2.3039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 1.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 48.5408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.5408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0769 | 0.80767 | 0.53845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.2456 | 57.5895 | 55.8751 | 55.1572 | 53.0432 | 50.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 62.6916 | 59.2456 | 57.5895 | 55.8751 | 55.1572 | 53.0432 | 50.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial tranche
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.2281 | 225.1333 | 218.8402 | 212.3255 | 209.5974 | 201.5641 | 193.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0922 | 3.0692 | 2.0461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 72.2473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9089 | 9.0009 | 11.4775 | 12.6588 | 11.9953 | 11.731 | 9.4748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 47.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0704 | 6.2931 | 6.5147 | 6.8204 | 7.0102 | 7.3311 | 7.7317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 4.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 4.0922
|  | Deferred principal repaid | USD m |  | 3.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0231 | 1.0231 | 1.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 46.7485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0704 | 6.2931 | 6.5147 | 2.7281 | 8.0333 | 8.3542 | 8.7547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 7.0243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 184.4552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.4552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0922 | 3.0692 | 2.0461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.1333 | 218.8402 | 212.3255 | 209.5974 | 201.5641 | 193.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 238.2281 | 225.1333 | 218.8402 | 212.3255 | 209.5974 | 201.5641 | 193.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Standby facility
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled principal per profile | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal deferred under the waiver | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred amount at 2023-12-31 | USD m | 0
|  | Deferred principal repaid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performance LD prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinanced (prepaid from bond proceeds) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred principal, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment, LDs and refinancing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash sweep prepayment | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 project bond
|  | Opening balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233.9919 | 231.3614 | 227.4767 | 223.2342 | 219.004 | 214.4603 | 209.9075 | 205.0898 | 199.7926 | 194.1417 | 188.4376 | 182.4068 | 176.3558 | 170.0053 | 163.6273 | 156.9847 | 150.9564 | 145.4553 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest (incl. WHT gross-up where applicable) | USD m |  | 157.8919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2134 | 9.1099 | 8.9569 | 8.7898 | 8.6233 | 8.4444 | 8.2651 | 8.0754 | 7.8668 | 7.6443 | 7.4197 | 7.1823 | 6.944 | 6.694 | 6.4428 | 6.1813 | 5.9439 | 5.7273 | 5.5384 | 4.7176 | 3.8787 | 2.9956 | 2.0921 | 1.145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid | USD m |  | 233.9919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6305 | 3.8846 | 4.2425 | 4.2303 | 4.5437 | 4.5528 | 4.8177 | 5.2972 | 5.6509 | 5.7041 | 6.0307 | 6.051 | 6.3505 | 6.378 | 6.6427 | 6.0283 | 5.5011 | 4.7982 | 20.8457 | 21.3056 | 22.4278 | 22.946 | 24.0514 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance after scheduled payment | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231.3614 | 227.4767 | 223.2342 | 219.004 | 214.4603 | 209.9075 | 205.0898 | 199.7926 | 194.1417 | 188.4376 | 182.4068 | 176.3558 | 170.0053 | 163.6273 | 156.9847 | 150.9564 | 145.4553 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233.9919 | 231.3614 | 227.4767 | 223.2342 | 219.004 | 214.4603 | 209.9075 | 205.0898 | 199.7926 | 194.1417 | 188.4376 | 182.4068 | 176.3558 | 170.0053 | 163.6273 | 156.9847 | 150.9564 | 145.4553 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refinancing 2025 (USD m)
|  | Swap unwind discount factor at 3.68% | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98193 | 0.96419 | 0.94677 | 0.92966 | 0.91287 | 0.89637 | 0.88018 | 0.86428 | 0.84866 | 0.83333 | 0.81827 | 0.80349 | 0.78897 | 0.77472 | 0.76072 | 0.74697 | 0.73348 | 0.72023 | 0.70721 | 0.69444 | 0.68189 | 0.66957 | 0.65747 | 0.64559 | 0.63393 | 0.62247 | 0.61123 | 0.60018 | 0.58934 | 0.57869 | 0.56824 | 0.55797 | 0.54789 | 0.53799 | 0.52827 | 0.51873 | 0.50935 | 0.50015 | 0.49111 | 0.48224 | 0.47353 | 0.46497 | 0.45657
|  | Swap unwind receipt (terminated share, MTM at 3.68% flat) | USD m | 6.2985
|  | Principal prepaid (B-loan, commercial, standby) | USD m | 232.9961
|  | Bond face amount | USD m | 233.9919
|  | Swap unwind receipt | USD m |  | 6.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Refinancing costs (OID, underwriting, other, PCG upfront) | USD m |  | 7.2943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swap, premiums and fees (USD m)
|  | Swap share outstanding | fraction |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52
|  | Swap net payment (fixed 30/360 less floating ACT/360) | USD m |  | -33.5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4374 | -0.14038 | -5.5443 | -6.9937 | -5.9365 | -5.9947 | -3.5856 | -1.7851 | -1.0971 | -1.0749 | -0.84887 | -0.86086 | -0.81905 | -0.80209 | -0.69981 | -0.68645 | -0.58703 | -0.56309 | -0.46722 | -0.43043 | -0.34519 | -0.28706 | -0.19699 | -0.13102 | -0.061949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRI premium (commercial tranche) | USD m |  | 7.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2227 | 1.1746 | 1.1232 | 1.1078 | 1.0817 | 1.0517 | 0.99164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB PCG fee (bond) | USD m |  | 8.9542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5225 | 0.51663 | 0.50795 | 0.49848 | 0.48903 | 0.47889 | 0.46872 | 0.45796 | 0.44613 | 0.43352 | 0.42078 | 0.40731 | 0.3938 | 0.37962 | 0.36538 | 0.35054 | 0.33708 | 0.3248 | 0.31409 | 0.26754 | 0.21996 | 0.16988 | 0.11864 | 0.064937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver fee | USD m |  | 1.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interest, all tranches | USD m |  | 399.683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4527 | 19.208 | 25.4531 | 28.4085 | 26.8378 | 26.2623 | 20.8469 | 18.1427 | 16.7962 | 16.3883 | 15.6137 | 15.2113 | 14.6485 | 14.1581 | 13.4815 | 12.9335 | 12.1836 | 11.5786 | 10.802 | 10.1297 | 9.3325 | 8.5768 | 7.7311 | 6.9351 | 6.2032 | 5.5384 | 4.7176 | 3.8787 | 2.9956 | 2.0921 | 1.145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior financing costs (interest, swap, PRI, PCG) | USD m |  | 382.8884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.1128 | 20.2423 | 21.032 | 22.5226 | 21.9829 | 21.3192 | 18.2528 | 16.8801 | 16.2158 | 15.8213 | 15.2633 | 14.8395 | 14.3083 | 13.8248 | 13.2397 | 12.6932 | 12.0301 | 11.4363 | 10.7421 | 10.0931 | 9.3669 | 8.6551 | 7.8846 | 7.1412 | 6.4661 | 5.8525 | 4.9851 | 4.0986 | 3.1655 | 2.2107 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Principal paid, all tranches | USD m |  | 609.4267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9748 | 16.5608 | 17.144 | 7.1793 | 21.1402 | 21.9847 | 23.0387 | 15.0963 | 14.1848 | 15.0277 | 15.2388 | 16.0883 | 16.4233 | 17.2525 | 18.7261 | 19.8016 | 19.9644 | 21.0273 | 21.5121 | 22.5693 | 23.075 | 24.1226 | 24.3147 | 21.3828 | 19.9395 | 20.8457 | 21.3056 | 22.4278 | 22.946 | 24.0514 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt service | USD m |  | 992.3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.0876 | 36.8031 | 38.176 | 29.702 | 43.1231 | 43.3039 | 41.2916 | 31.9764 | 30.4006 | 30.849 | 30.5022 | 30.9278 | 30.7316 | 31.0773 | 31.9658 | 32.4947 | 31.9945 | 32.4636 | 32.2542 | 32.6624 | 32.4419 | 32.7777 | 32.1994 | 28.524 | 26.4056 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.916 | 592.4561 | 575.8954 | 558.7514 | 551.5721 | 530.4319 | 508.4472 | 486.4043 | 471.3079 | 457.1231 | 442.0955 | 426.8566 | 410.7684 | 394.3451 | 377.0926 | 358.3664 | 338.5648 | 318.6005 | 297.5732 | 276.061 | 253.4917 | 230.4167 | 206.2941 | 181.9794 | 160.5966 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior debt outstanding, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 626.916 | 592.4561 | 575.8954 | 558.7514 | 551.5721 | 530.4319 | 508.4472 | 486.4043 | 471.3079 | 457.1231 | 442.0955 | 426.8566 | 410.7684 | 394.3451 | 377.0926 | 358.3664 | 338.5648 | 318.6005 | 297.5732 | 276.061 | 253.4917 | 230.4167 | 206.2941 | 181.9794 | 160.5966 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSRA target: next period scheduled debt service (USD m)
|  | Commercial balance carried to next period | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 238.2281 | 225.1333 | 218.8402 | 212.3255 | 209.5974 | 201.5641 | 193.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECA-covered tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6.3905 | 8.8654 | 10.9095 | 12.0228 | 12.5645 | 12.694 | 11.5347 | 11.6191 | 9.6996 | 9.8506 | 9.6702 | 9.8647 | 9.8705 | 10.0445 | 10.3809 | 10.6319 | 10.4382 | 10.6777 | 10.6831 | 10.9088 | 10.9181 | 11.1241 | 11.3048 | 9.6454 | 8.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB A-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6.2813 | 8.0335 | 9.4654 | 10.2618 | 10.625 | 10.6807 | 9.7523 | 9.776 | 8.2869 | 8.3659 | 8.1622 | 8.2679 | 8.2041 | 8.2833 | 8.4542 | 8.5854 | 8.3613 | 8.4777 | 8.3977 | 8.4957 | 8.4173 | 8.4899 | 8.5314 | 7.2276 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ABDB B-loan: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.7763 | 3.5759 | 4.2301 | 4.5931 | 4.7598 | 4.7871 | 4.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commercial tranche: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11.9794 | 15.294 | 17.9922 | 19.4792 | 20.0286 | 20.0852 | 18.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Standby facility: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bond: next period debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3664 | 13.5111 | 13.7074 | 13.5186 | 13.656 | 13.476 | 13.5516 | 13.8306 | 13.9639 | 13.782 | 13.8712 | 13.6406 | 13.6883 | 13.4516 | 13.4509 | 12.5601 | 11.7821 | 10.8503 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSRA target (six months of next debt service) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 35.0876 | 36.8031 | 38.176 | 40.471 | 43.1231 | 43.3039 | 41.2916 | 31.9764 | 30.4006 | 30.849 | 30.5022 | 30.9278 | 30.7316 | 31.0773 | 31.9658 | 32.4947 | 31.9945 | 32.4636 | 32.2542 | 32.6624 | 32.4419 | 32.7777 | 32.1994 | 28.524 | 26.4056 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live sculpting check (FC base: constant-DSCR profile from CFADS)
|  | Flag_SculptingPeriod (first repayment to 2034H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpting rate on scheduled balance | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030384 | 0.034176 | 0.036905 | 0.040809 | 0.040079 | 0.040476 | 0.036109 | 0.03641 | 0.036322 | 0.036679 | 0.036097 | 0.036505 | 0.036299 | 0.036572 | 0.036177 | 0.036591 | 0.037242 | 0.037673 | 0.037249 | 0.037682 | 0.037402 | 0.0377 | 0.037309 | 0.037772 | 0.037216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PV of CFADS to 2034H1 at the sculpting rate | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.4126 | 786.1073 | 775.6844 | 768.5993 | 743.776 | 716.2019 | 688.5165 | 658.0215 | 630.2984 | 604.0576 | 576.3549 | 547.8609 | 517.8738 | 487.0023 | 454.5847 | 419.3658 | 382.1917 | 344.7146 | 305.2322 | 264.4714 | 221.647 | 177.5033 | 131.2185 | 84.0723 | 41.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted DSCR = PV(CFADS) / debt | x | 1.2734
|  | Debt capacity at the 1.35x target | USD m | 597.3427
|  | Debt at the 75% gearing cap (closed form) | USD m | 636.956
|  | Sculpted debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.1862 | 29.2822 | 28.0437 | 44.124 | 45.0623 | 44.505 | 43.47 | 40.5842 | 38.5841 | 39.1532 | 38.7131 | 39.2532 | 39.0043 | 39.443 | 40.5707 | 41.242 | 40.6071 | 41.2025 | 40.9367 | 41.4548 | 41.175 | 41.6012 | 40.8671 | 36.2024 | 33.5137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633.256 | 617.3108 | 609.1259 | 603.5621 | 584.069 | 562.4158 | 540.6751 | 516.7281 | 494.9578 | 474.3516 | 452.5973 | 430.2217 | 406.6735 | 382.4309 | 356.9742 | 329.3176 | 300.1257 | 270.6959 | 239.6913 | 207.6829 | 174.0539 | 139.3889 | 103.0427 | 66.0199 | 32.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9452 | 8.1849 | 5.5638 | 19.4931 | 21.6532 | 21.7406 | 23.947 | 21.7703 | 20.6062 | 21.7543 | 22.3756 | 23.5482 | 24.2426 | 25.4567 | 27.6566 | 29.1919 | 29.4298 | 31.0046 | 32.0084 | 33.629 | 34.665 | 36.3463 | 37.0227 | 33.7087 | 32.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sculpted principal less contract principal (FC base) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Reserves
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Reserves: MMRA, DSRA, handback reserve, Compensation Account
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| MMRA contribution (1/6 of next outlay) | USD m |  | 58.3765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46186 | 0.46186 | 0.46186 | 0.46186 | 0.46186 | 0.46186 | 0 | 0 | 2.2103 | 2.2103 | 2.2103 | 2.2103 | 2.2103 | 2.2103 | 0 | 0 | 0.55726 | 0.55726 | 0.55726 | 0.55726 | 0.55726 | 0.55726 | 0 | 0 | 2.6513 | 2.6513 | 2.6513 | 2.6513 | 2.6513 | 2.6513 | 0 | 0 | 0.66844 | 0.66844 | 0.66844 | 0.66844 | 0.66844 | 0.66844 | 0 | 0 | 3.1803 | 3.1803 | 3.1803 | 3.1803 | 3.1803 | 3.1803 | 0 | 0 | 0 | 0
| MMRA balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46186 | 0.92372 | 1.3856 | 1.8474 | 2.3093 | 2.7712 | 0 | 0 | 2.2103 | 4.4206 | 6.6309 | 8.8412 | 11.0515 | 13.2618 | 0 | 0 | 0.55726 | 1.1145 | 1.6718 | 2.2291 | 2.7863 | 3.3436 | 0 | 0 | 2.6513 | 5.3026 | 7.9539 | 10.6051 | 13.2564 | 15.9077 | 0 | 0 | 0.66844 | 1.3369 | 2.0053 | 2.6738 | 3.3422 | 4.0107 | 0 | 0 | 3.1803 | 6.3605 | 9.5408 | 12.721 | 15.9013 | 19.0815 | 0 | 0 | 0 | 0
| DSRA opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.8418 | 35.0876 | 36.8031 | 37.2891 | 34.8251 | 43.1231 | 43.3039 | 41.2916 | 31.9764 | 30.4006 | 30.849 | 30.5022 | 30.9278 | 30.7316 | 31.0773 | 31.9658 | 32.4947 | 31.9945 | 32.4636 | 32.2542 | 32.6624 | 32.4419 | 32.7777 | 32.1994 | 28.524 | 26.4056 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA drawing | USD m |  | 2.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA top-up | USD m |  | 20.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2457 | 1.7155 | 0.48606 | 0 | 8.298 | 0.1808 | 0 | 0 | 0 | 0.44842 | 0 | 0.4256 | 0 | 0.34561 | 0.88856 | 0.52893 | 0 | 0.46912 | 0 | 0.40819 | 0 | 0.33586 | 0 | 0 | 0 | 0.29259 | 0 | 0.23576 | 0 | 0.15067 | 4.0285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA release of excess | USD m |  | 51.8617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0123 | 9.3152 | 1.5759 | 0 | 0.34681 | 0 | 0.19611 | 0 | 0 | 0 | 0.50028 | 0 | 0.20939 | 0 | 0.2205 | 0 | 0.5784 | 3.6753 | 2.1185 | 0 | 0.40742 | 0 | 0.41503 | 0 | 0 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DSRA closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 35.0876 | 36.8031 | 37.2891 | 34.8251 | 43.1231 | 43.3039 | 41.2916 | 31.9764 | 30.4006 | 30.849 | 30.5022 | 30.9278 | 30.7316 | 31.0773 | 31.9658 | 32.4947 | 31.9945 | 32.4636 | 32.2542 | 32.6624 | 32.4419 | 32.7777 | 32.1994 | 28.524 | 26.4056 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Handback reserve contribution | USD m |  | 21.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28042 | 1.7018 | 1.7212 | 1.7409 | 1.7608 | 1.781 | 1.8013 | 1.8219 | 1.8428 | 1.8638 | 1.8851 | 1.9067 | 1.6071
| Handback reserve release at expiry | USD m |  | 21.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7148
| Handback reserve balance | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28042 | 1.9822 | 3.7034 | 5.4443 | 7.2052 | 8.9861 | 10.7874 | 12.6094 | 14.4521 | 16.3159 | 18.2011 | 20.1078 | 0
| Compensation Account (performance LDs held) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Waterfall
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Waterfall: CFADS, debt service, reserves, tests, sweeps, distributions
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
|  | CFADS | USD m |  | 2303.3212 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 44.8074 | 37.2891 | 35.712 | 56.1892 | 57.3841 | 56.6744 | 55.3564 | 51.6815 | 49.1345 | 49.8592 | 49.2987 | 49.9866 | 49.6696 | 50.2282 | 51.6643 | 52.5192 | 51.7106 | 52.4688 | 52.1304 | 52.7902 | 52.4338 | 52.9766 | 52.0418 | 46.1015 | 42.6776 | 43.1505 | 42.492 | 42.8731 | 42.2023 | 42.4458 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.6822 | 46.3569 | 44.9012 | 36.4923 | 37.2076 | 36.7978 | 37.5041 | 37.0897 | 37.6779 | 45.9614 | 40.9896 | 40.6055 | 43.5986
|  | Cash brought forward (lock-up and trapped cash) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17.2197 | 9.6813 | 0 | 0 | 0 | 16.7923 | 30.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.9271 | 54.4888 | 37.2891 | 35.712 | 56.1892 | 74.1764 | 87.547 | 55.3564 | 51.6815 | 49.1345 | 49.8592 | 49.2987 | 49.9866 | 49.6696 | 50.2282 | 51.6643 | 52.5192 | 51.7106 | 52.4688 | 52.1304 | 52.7902 | 52.4338 | 52.9766 | 52.0418 | 46.1015 | 42.6776 | 43.1505 | 42.492 | 42.8731 | 42.2023 | 42.4458 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.6822 | 46.3569 | 44.9012 | 36.4923 | 37.2076 | 36.7978 | 37.5041 | 37.0897 | 37.6779 | 45.9614 | 40.9896 | 40.6055 | 43.5986
|  | Senior debt service and fees due | USD m |  | 993.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.0876 | 36.8031 | 38.176 | 31.0989 | 43.1231 | 43.3039 | 41.2916 | 31.9764 | 30.4006 | 30.849 | 30.5022 | 30.9278 | 30.7316 | 31.0773 | 31.9658 | 32.4947 | 31.9945 | 32.4636 | 32.2542 | 32.6624 | 32.4419 | 32.7777 | 32.1994 | 28.524 | 26.4056 | 26.6981 | 26.2907 | 26.5265 | 26.1114 | 26.2621 | 30.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall before DSRA | USD m |  | 2.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortfall after DSRA (must be zero) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash after debt service | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.9271 | 19.4012 | 0.48606 | 0 | 25.0903 | 31.0534 | 44.2431 | 14.0648 | 19.705 | 18.7339 | 19.0103 | 18.7966 | 19.0588 | 18.938 | 19.151 | 19.6985 | 20.0245 | 19.7162 | 20.0053 | 19.8762 | 20.1278 | 19.9919 | 20.1989 | 19.8424 | 17.5775 | 16.2721 | 16.4524 | 16.2013 | 16.3466 | 16.0908 | 16.1837 | 18.6662 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.6822 | 46.3569 | 44.9012 | 36.4923 | 37.2076 | 36.7978 | 37.5041 | 37.0897 | 37.6779 | 45.9614 | 40.9896 | 40.6055 | 43.5986
|  | Cash after DSRA movements | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.6813 | 17.6857 | 0 | 0 | 16.7923 | 30.8726 | 46.2554 | 23.38 | 21.2809 | 18.2855 | 19.3571 | 18.371 | 19.2549 | 18.5924 | 18.2624 | 19.1696 | 20.5247 | 19.2471 | 20.2147 | 19.468 | 20.3483 | 19.656 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.6822 | 46.3569 | 44.9012 | 36.4923 | 37.2076 | 36.7978 | 37.5041 | 37.0897 | 37.6779 | 45.9614 | 40.9896 | 40.6055 | 43.5986
|  | Cash available for distribution tests | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.6813 | 17.6857 | 0 | 0 | 16.7923 | 30.8726 | 46.2554 | 23.38 | 21.2809 | 18.2855 | 19.3571 | 18.371 | 19.2549 | 18.5924 | 18.2624 | 19.1696 | 20.5247 | 19.2471 | 20.2147 | 19.468 | 20.3483 | 19.656 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 63.7064
Ratios and tests
|  | DSCR, period | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.277 | 1.0132 | 0.93546 | 1.8918 | 1.3307 | 1.3088 | 1.3406 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCR, historic 12 months (cash basis) | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.277 | 1.142 | 0.97362 | 1.3539 | 1.5595 | 1.3197 | 1.3243 | 1.4609 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First repayment made | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Event of default (historic DSCR < 1.10x) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tests waived (2023H1, 2023H2) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waiver regime (from 2023H1) | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up released under the waiver | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Distributions permitted | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Lock-up | flag |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consecutive lock-ups | count |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sweeps and distributions (USD m)
|  | Lock-up cash sweep (after two consecutive lock-ups) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Soft mini-perm sweep (50%, commercial tranche, from 2027) | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lock-up account, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.6813 | 0 | 0 | 0 | 16.7923 | 30.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cash available for distribution | USD m |  | 1360.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.6857 | 0 | 0 | 0 | 0 | 46.2554 | 23.38 | 21.2809 | 18.2855 | 19.3571 | 18.371 | 19.2549 | 18.5924 | 18.2624 | 19.1696 | 20.5247 | 19.2471 | 20.2147 | 19.468 | 20.3483 | 19.656 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 63.7064
|  | Share capital contributed | USD m | 43.9226
|  | Shareholder loan balance, opening | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 205.4561 | 207.1138 | 199.1852 | 208.7242 | 218.5571 | 229.0239 | 239.8728 | 205.105 | 191.3874 | 179.2721 | 169.432 | 158.1891 | 147.2703 | 135.0682 | 122.874 | 110.4961 | 96.532 | 80.6302 | 65.1816 | 48.0885 | 30.8859 | 12.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan interest paid | USD m |  | 104.4822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.757 | 0 | 0 | 0 | 0 | 11.4876 | 9.6624 | 9.1656 | 8.4454 | 8.1142 | 7.4522 | 7.0528 | 6.3982 | 5.8845 | 5.2054 | 4.623 | 3.7985 | 3.1216 | 2.2654 | 1.4791 | 0.56923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan principal repaid | USD m |  | 247.8014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9286 | 0 | 0 | 0 | 0 | 34.7678 | 13.7176 | 12.1153 | 9.8401 | 11.2429 | 10.9187 | 12.2021 | 12.1942 | 12.3779 | 13.9642 | 15.9018 | 15.4486 | 17.0931 | 17.2026 | 18.8691 | 12.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loan balance, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 207.1138 | 199.1852 | 208.7242 | 218.5571 | 229.0239 | 239.8728 | 205.105 | 191.3874 | 179.2721 | 169.432 | 158.1891 | 147.2703 | 135.0682 | 122.874 | 110.4961 | 96.532 | 80.6302 | 65.1816 | 48.0885 | 30.8859 | 12.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Distributable reserves (retained earnings + current profit) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7341 | 14.0037 | 20.5045 | 23.6444 | 26.4942 | 33.1786 | 41.8806 | 52.2821 | 66.6012 | 82.4359 | 97.7981 | 106.855 | 116.6084 | 127.2667 | 138.7683 | 141.4565 | 154.7435 | 169.2027 | 184.6564 | 201.3252 | 219.0924 | 238.0648 | 250.9926 | 249.0463 | 247.3027 | 249.822 | 256.6046 | 263.2575 | 271.5298 | 279.7259 | 289.5724 | 292.3513 | 270.8929 | 254.0078 | 238.2597 | 221.8946 | 206.0476 | 189.596 | 173.7039 | 155.0278 | 139.003 | 124.4071 | 118.3801 | 111.8286 | 105.8316 | 99.2241 | 93.2455 | 72.9284 | 58.3489 | 48.8727 | 19.7839
|  | Dividends within distributable reserves | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.07 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 19.7839
|  | Cash trapped by the dividend restriction | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.9226
|  | Liquidation distribution at PPA expiry | USD m |  | 43.9226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.9226
|  | Dividends | USD m |  | 1008.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.07 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 63.7064
|  | Trapped cash, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retained earnings, closing | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7341 | 14.0037 | 20.5045 | 23.6444 | 26.4942 | 33.1786 | 41.8806 | 52.2821 | 66.6012 | 82.4359 | 97.7981 | 106.855 | 116.6084 | 127.2667 | 138.7683 | 141.4565 | 154.7435 | 169.2027 | 184.6564 | 201.3252 | 219.0924 | 230.9947 | 230.2154 | 225.5285 | 227.6067 | 233.8425 | 239.7448 | 247.2919 | 254.7682 | 263.7857 | 277.4172 | 243.3945 | 226.3838 | 210.5074 | 193.9857 | 178.0245 | 161.5021 | 145.4526 | 129.3022 | 110.3727 | 95.8231 | 89.6558 | 82.9333 | 76.8118 | 70.1289 | 63.9563 | 57.4103 | 28.8308 | 19.2444 | 10.1739 | -43.9226
|  | Distributions to shareholders (SHL interest + principal + dividends) | USD m |  | 1360.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.6857 | 0 | 0 | 0 | 0 | 46.2554 | 23.38 | 21.2809 | 18.2855 | 19.3571 | 18.371 | 19.2549 | 18.5924 | 18.2624 | 19.1696 | 20.5247 | 19.2471 | 20.2147 | 19.468 | 20.3483 | 19.656 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 63.7064

## Financials
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Financials: income statement and balance sheet (IFRS basis, USD functional currency)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
|  | Label | Unit | Constant | Total
|  | Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
Income statement (USD m)
|  | Book depreciation (straight line over the 25-year PPA term) | USD m |  | 801.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6713 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 16.028 | 13.3566
|  | Finance costs (senior, swap, PRI, PCG, fees, SHL interest) | USD m |  | 532.1086 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6577 | 28.8698 | 29.7814 | 30.8649 | 34.3863 | 32.8317 | 32.8068 | 28.911 | 26.0457 | 24.6612 | 23.9355 | 22.7155 | 21.8923 | 20.7065 | 19.7092 | 18.4451 | 17.3161 | 15.8285 | 14.5579 | 13.0075 | 11.5722 | 9.9361 | 8.6551 | 7.8846 | 7.1412 | 6.4661 | 5.8525 | 4.9851 | 4.0986 | 3.1655 | 2.2107 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tax written-down value | USD m |  |  | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 797.7918 | 776.154 | 754.5163 | 732.8785 | 711.2408 | 689.603 | 667.9653 | 646.3276 | 624.6898 | 603.0521 | 581.815 | 562.5815 | 543.3479 | 524.1143 | 504.8808 | 485.6472 | 466.4137 | 447.1801 | 427.9466 | 408.713 | 389.4795 | 370.2459 | 351.0124 | 331.7788 | 312.5453 | 293.3117 | 274.0781 | 254.8446 | 235.611 | 216.3775 | 197.1439 | 177.9104 | 158.6768 | 139.4433 | 120.2097 | 100.9762 | 81.7426 | 62.5091 | 43.2755 | 24.0419 | 7.8804 | 7.079 | 6.2776 | 5.4762 | 4.6748 | 3.8734 | 3.072 | 2.2706 | 1.4692 | 0.66783 | 0
|  | Book value of plant (from COD) | USD m |  |  | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 801.3981 | 798.7268 | 782.6988 | 766.6708 | 750.6429 | 734.6149 | 718.5869 | 702.559 | 686.531 | 670.5031 | 654.4751 | 638.4471 | 622.4192 | 606.3912 | 590.3633 | 574.3353 | 558.3073 | 542.2794 | 526.2514 | 510.2234 | 494.1955 | 478.1675 | 462.1396 | 446.1116 | 430.0836 | 414.0557 | 398.0277 | 381.9998 | 365.9718 | 349.9438 | 333.9159 | 317.8879 | 301.8599 | 285.832 | 269.804 | 253.7761 | 237.7481 | 221.7201 | 205.6922 | 189.6642 | 173.6363 | 157.6083 | 141.5803 | 125.5524 | 109.5244 | 93.4964 | 77.4685 | 61.4405 | 45.4126 | 29.3846 | 13.3566 | 0
|  | Deferred tax liability (asset if negative) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -0.8014 | -5.6098 | -10.4182 | -15.2266 | -20.035 | -24.8433 | -29.6517 | -34.4601 | -39.2685 | -44.0769 | -47.4829 | -43.4396 | -39.0968 | -34.365 | -29.2711 | -27.9565 | -22.0972 | -15.7329 | -8.9414 | -1.6284 | 6.1562 | 14.4585 | 23.2011 | 29.4914 | 30.4531 | 31.4148 | 32.3765 | 33.3382 | 34.2998 | 35.2615 | 36.2232 | 37.1849 | 38.1465 | 39.1082 | 40.0699 | 41.0316 | 41.9933 | 42.9549 | 43.9166 | 44.8783 | 44.9184 | 40.3504 | 35.7824 | 31.2145 | 26.6465 | 22.0785 | 17.5105 | 12.9426 | 8.3746 | 3.8066 | 0
|  | Deferred tax expense | USD m |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.8014 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -4.8084 | -3.4061 | 4.0434 | 4.3428 | 4.7318 | 5.0939 | 1.3146 | 5.8593 | 6.3643 | 6.7915 | 7.313 | 7.7846 | 8.3023 | 8.7426 | 6.2903 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.96168 | 0.04007 | -4.568 | -4.568 | -4.568 | -4.568 | -4.568 | -4.568 | -4.568 | -4.568 | -4.568 | -3.8066
|  | Net income | USD m |  | 964.4646 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7341 | 9.2696 | 6.5008 | 3.1399 | 2.8499 | 6.6843 | 8.702 | 10.4015 | 14.3191 | 15.8347 | 15.3622 | 9.0569 | 9.7534 | 10.6583 | 11.5016 | 2.6883 | 13.2869 | 14.4592 | 15.4537 | 16.6689 | 17.7671 | 18.9724 | 19.9979 | 18.8309 | 21.7742 | 22.2153 | 22.762 | 23.5127 | 24.2379 | 24.9577 | 25.7867 | 14.9341 | 27.4984 | 27.6241 | 27.7523 | 27.909 | 28.0231 | 28.0939 | 28.2513 | 25.7257 | 28.6303 | 28.584 | 28.7243 | 28.8953 | 29.0198 | 29.0952 | 29.2892 | 15.5181 | 29.518 | 29.6284 | 9.6099
Balance sheet (USD m, period end)
|  | Plant (construction in progress before COD) | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 798.7268 | 782.6988 | 766.6708 | 750.6429 | 734.6149 | 718.5869 | 702.559 | 686.531 | 670.5031 | 654.4751 | 638.4471 | 622.4192 | 606.3912 | 590.3633 | 574.3353 | 558.3073 | 542.2794 | 526.2514 | 510.2234 | 494.1955 | 478.1675 | 462.1396 | 446.1116 | 430.0836 | 414.0557 | 398.0277 | 381.9998 | 365.9718 | 349.9438 | 333.9159 | 317.8879 | 301.8599 | 285.832 | 269.804 | 253.7761 | 237.7481 | 221.7201 | 205.6922 | 189.6642 | 173.6363 | 157.6083 | 141.5803 | 125.5524 | 109.5244 | 93.4964 | 77.4685 | 61.4405 | 45.4126 | 29.3846 | 13.3566 | 0
|  | Cash in project accounts (DSRA, MMRA, handback, lock-up, trapped, compensation) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.2539 | 37.2649 | 38.2129 | 36.2107 | 61.7629 | 76.4858 | 44.0627 | 31.9764 | 30.4006 | 33.0593 | 34.9228 | 37.5587 | 39.5729 | 42.1288 | 45.2276 | 32.4947 | 31.9945 | 33.0208 | 33.3687 | 34.3342 | 34.6709 | 35.5641 | 35.5429 | 28.524 | 26.4056 | 29.3494 | 31.5933 | 34.4803 | 36.7166 | 39.5185 | 46.1983 | 0 | 0 | 0.66844 | 1.3369 | 2.0053 | 2.6738 | 3.3422 | 4.2911 | 1.9822 | 3.7034 | 8.6246 | 13.5657 | 18.5269 | 23.5085 | 28.5106 | 33.5336 | 16.3159 | 18.2011 | 20.1078 | 0
|  | Receivables (incl. overdue) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38.2208 | 58.1231 | 107.9608 | 152.607 | 111.557 | 75.6304 | 53.1089 | 41.4735 | 41.2039 | 43.1534 | 42.6134 | 43.664 | 43.145 | 44.365 | 43.7928 | 43.6569 | 43.4734 | 45.9813 | 45.3416 | 46.4395 | 45.8778 | 47.178 | 46.653 | 47.222 | 46.7656 | 48.9173 | 48.2388 | 49.4136 | 48.8193 | 50.2165 | 49.561 | 49.3995 | 49.1977 | 52.0942 | 51.3738 | 52.6317 | 52.0022 | 53.5042 | 52.9097 | 53.5504 | 53.0437 | 55.532 | 54.7661 | 56.1141 | 55.4465 | 57.0619 | 56.3151 | 56.124 | 55.901 | 59.252 | 0
|  | Spares inventory | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 5.35 | 0
|  | Deferred tax asset | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.8014 | 5.6098 | 10.4182 | 15.2266 | 20.035 | 24.8433 | 29.6517 | 34.4601 | 39.2685 | 44.0769 | 47.4829 | 43.4396 | 39.0968 | 34.365 | 29.2711 | 27.9565 | 22.0972 | 15.7329 | 8.9414 | 1.6284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total assets | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 906.3529 | 889.0466 | 928.6127 | 960.0371 | 933.3197 | 900.8965 | 834.7324 | 799.791 | 786.726 | 780.1147 | 768.8162 | 752.4314 | 733.5558 | 716.572 | 697.9768 | 667.7655 | 645.1945 | 626.3364 | 603.2252 | 581.9476 | 564.0663 | 550.2316 | 533.6575 | 511.1797 | 492.5768 | 481.6444 | 467.1819 | 455.2157 | 440.8297 | 429.0009 | 418.9972 | 356.6094 | 340.3797 | 327.9167 | 311.8367 | 297.7351 | 281.7461 | 267.8886 | 252.215 | 234.5189 | 219.7055 | 211.0869 | 199.2342 | 189.5154 | 177.8014 | 168.391 | 156.6393 | 123.2025 | 108.8367 | 98.0664 | 0
|  | Senior debt | USD m |  |  | 100.4722 | 147.866 | 240.6622 | 357.9848 | 465.8575 | 535.9028 | 626.916 | 592.4561 | 575.8954 | 558.7514 | 551.5721 | 530.4319 | 508.4472 | 486.4043 | 471.3079 | 457.1231 | 442.0955 | 426.8566 | 410.7684 | 394.3451 | 377.0926 | 358.3664 | 338.5648 | 318.6005 | 297.5732 | 276.061 | 253.4917 | 230.4167 | 206.2941 | 181.9794 | 160.5966 | 140.6571 | 119.8114 | 98.5058 | 76.078 | 53.132 | 29.0806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shareholder loans (incl. capitalized interest) | USD m |  |  | 28.9957 | 43.8832 | 72.5134 | 109.5476 | 145.7599 | 172.8445 | 207.1138 | 199.1852 | 208.7242 | 218.5571 | 229.0239 | 239.8728 | 205.105 | 191.3874 | 179.2721 | 169.432 | 158.1891 | 147.2703 | 135.0682 | 122.874 | 110.4961 | 96.532 | 80.6302 | 65.1816 | 48.0885 | 30.8859 | 12.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Payables (incl. deferred SNHK/GCK payables) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.6665 | 39.479 | 79.566 | 115.1616 | 82.3069 | 53.4907 | 35.3771 | 25.7948 | 25.6222 | 27.201 | 26.811 | 27.5269 | 27.1882 | 28.1637 | 27.6973 | 27.488 | 27.3334 | 29.4291 | 28.9846 | 29.7529 | 29.3867 | 30.4391 | 30.0243 | 30.2577 | 29.9978 | 31.8074 | 31.3266 | 32.1572 | 31.7612 | 32.8991 | 32.3537 | 32.1075 | 31.9268 | 34.3785 | 33.8586 | 34.7565 | 34.3282 | 35.5586 | 35.0736 | 35.3453 | 35.0415 | 37.1582 | 36.5959 | 37.5666 | 37.1034 | 38.4337 | 37.7959 | 37.5065 | 37.2951 | 40.1632 | 0
|  | Deferred tax liability | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1562 | 14.4585 | 23.2011 | 29.4914 | 30.4531 | 31.4148 | 32.3765 | 33.3382 | 34.2998 | 35.2615 | 36.2232 | 37.1849 | 38.1465 | 39.1082 | 40.0699 | 41.0316 | 41.9933 | 42.9549 | 43.9166 | 44.8783 | 44.9184 | 40.3504 | 35.7824 | 31.2145 | 26.6465 | 22.0785 | 17.5105 | 12.9426 | 8.3746 | 3.8066 | 0
|  | Share capital | USD m |  |  | 7.0392 | 10.3597 | 16.8611 | 25.0809 | 32.6386 | 37.5461 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226 | 43.9226
|  | Retained earnings | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7341 | 14.0037 | 20.5045 | 23.6444 | 26.4942 | 33.1786 | 41.8806 | 52.2821 | 66.6012 | 82.4359 | 97.7981 | 106.855 | 116.6084 | 127.2667 | 138.7683 | 141.4565 | 154.7435 | 169.2027 | 184.6564 | 201.3252 | 219.0924 | 230.9947 | 230.2154 | 225.5285 | 227.6067 | 233.8425 | 239.7448 | 247.2919 | 254.7682 | 263.7857 | 277.4172 | 243.3945 | 226.3838 | 210.5074 | 193.9857 | 178.0245 | 161.5021 | 145.4526 | 129.3022 | 110.3727 | 95.8231 | 89.6558 | 82.9333 | 76.8118 | 70.1289 | 63.9563 | 57.4103 | 28.8308 | 19.2444 | 10.1739 | -43.9226
|  | Total liabilities and equity | USD m |  |  | 136.5071 | 202.1089 | 330.0367 | 492.6133 | 644.256 | 746.2933 | 906.3529 | 889.0466 | 928.6127 | 960.0371 | 933.3197 | 900.8965 | 834.7324 | 799.791 | 786.726 | 780.1147 | 768.8162 | 752.4314 | 733.5558 | 716.572 | 697.9768 | 667.7655 | 645.1945 | 626.3364 | 603.2252 | 581.9476 | 564.0663 | 550.2316 | 533.6575 | 511.1797 | 492.5768 | 481.6444 | 467.1819 | 455.2157 | 440.8297 | 429.0009 | 418.9972 | 356.6094 | 340.3797 | 327.9167 | 311.8367 | 297.7351 | 281.7461 | 267.8886 | 252.215 | 234.5189 | 219.7055 | 211.0869 | 199.2342 | 189.5154 | 177.8014 | 168.391 | 156.6393 | 123.2025 | 108.8367 | 98.0664 | 3.0347e-11
|  | Balance check (assets less liabilities and equity) | USD m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Ratios
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Ratios: DSCR, LLCR, PLCR
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Period ending |  |  |  | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| All-in senior cost per period (financing costs / opening debt) | factor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030487 | 0.034167 | 0.036521 | 0.040309 | 0.039855 | 0.040192 | 0.035899 | 0.034704 | 0.034406 | 0.034611 | 0.034525 | 0.034765 | 0.034833 | 0.035058 | 0.03511 | 0.035419 | 0.035533 | 0.035895 | 0.036099 | 0.036561 | 0.036951 | 0.037563 | 0.03822 | 0.039242 | 0.040263 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Final maturity period | index | 38
| Rate in final maturity period | factor | 0.041608
| Discount rate used | factor |  |  | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.030487 | 0.034167 | 0.036521 | 0.040309 | 0.039855 | 0.040192 | 0.035899 | 0.034704 | 0.034406 | 0.034611 | 0.034525 | 0.034765 | 0.034833 | 0.035058 | 0.03511 | 0.035419 | 0.035533 | 0.035895 | 0.036099 | 0.036561 | 0.036951 | 0.037563 | 0.03822 | 0.039242 | 0.040263 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608 | 0.041608
| PV of CFADS to final maturity | USD m |  |  | 677 | 705.1686 | 734.5093 | 765.0707 | 796.9037 | 830.0613 | 864.5985 | 906.8653 | 889.7055 | 882.8147 | 879.3436 | 858.5998 | 835.4351 | 812.3387 | 786.1446 | 761.7453 | 738.8194 | 714.5311 | 689.9015 | 663.8991 | 637.3551 | 609.471 | 579.2051 | 547.201 | 514.9339 | 480.9488 | 446.1801 | 409.7027 | 372.4081 | 333.4202 | 294.1219 | 259.5622 | 227.3353 | 193.6437 | 159.2088 | 122.9601 | 85.8739 | 47.0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV of CFADS to PPA expiry | USD m |  |  | 808.9471 | 842.6057 | 877.6649 | 914.1827 | 952.22 | 991.84 | 1033.1084 | 1082.3866 | 1070.5779 | 1069.8669 | 1073.2271 | 1060.2985 | 1045.1726 | 1030.5059 | 1012.1438 | 995.5876 | 980.7072 | 964.7908 | 948.8015 | 931.7996 | 914.5874 | 896.4223 | 876.2313 | 854.7477 | 833.4085 | 810.8551 | 787.9957 | 764.0155 | 739.8133 | 714.6263 | 689.8978 | 670.8691 | 655.2024 | 639.3135 | 623.422 | 606.4883 | 589.5208 | 571.6037 | 546.4303 | 524.657 | 502.9865 | 479.6408 | 455.7275 | 430.1439 | 403.8979 | 376.0211 | 345.3097 | 314.7761 | 291.3811 | 266.2972 | 240.5795 | 213.0855 | 184.8618 | 154.8756 | 115.3583 | 79.1685 | 41.8571
| LLCR = (PV CFADS + DSRA) / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5025 | 1.5638 | 1.5977 | 1.6361 | 1.6348 | 1.6566 | 1.6789 | 1.682 | 1.6807 | 1.6837 | 1.6852 | 1.6887 | 1.6911 | 1.695 | 1.701 | 1.7069 | 1.7107 | 1.7181 | 1.7246 | 1.7346 | 1.7442 | 1.7585 | 1.7723 | 1.773 | 1.7807 | 1.806 | 1.8357 | 1.8855 | 1.9595 | 2.1105 | 2.6578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LLCR excluding DSRA | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4466 | 1.5017 | 1.5329 | 1.5738 | 1.5566 | 1.575 | 1.5977 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLCR = PV CFADS to expiry / debt | x |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7265 | 1.807 | 1.8577 | 1.9208 | 1.9223 | 1.9704 | 2.0268 | 2.0809 | 2.1124 | 2.1454 | 2.1823 | 2.2228 | 2.2684 | 2.3193 | 2.3772 | 2.4451 | 2.5246 | 2.6158 | 2.7249 | 2.8544 | 3.014 | 3.2108 | 3.4641 | 3.7911 | 4.1774 | 4.6582 | 5.336 | 6.3288 | 7.9719 | 11.0954 | 19.6558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR (debt-service weighted) | x | #VALUE!
| LLCR at first debt service period | x | 1.5025
| PLCR at first debt service period | x | 1.7265

## Returns
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Returns: dated cash flows for XIRR (column J = LNTP 2018-02-05, then months, then half-years)
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Flow |  |  |  | LNTP | 2018-08 | 2018-09 | 2018-10 | 2018-11 | 2018-12 | 2019-01 | 2019-02 | 2019-03 | 2019-04 | 2019-05 | 2019-06 | 2019-07 | 2019-08 | 2019-09 | 2019-10 | 2019-11 | 2019-12 | 2020-01 | 2020-02 | 2020-03 | 2020-04 | 2020-05 | 2020-06 | 2020-07 | 2020-08 | 2020-09 | 2020-10 | 2020-11 | 2020-12 | 2021-01 | 2021-02 | 2021-03 | 2021-04 | 2021-05 | 2021-06 | 2021-07 | 2021-08 | 2021-09 | 2021-10 | 2021-11 | 2021-12 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2022-06 | 2022-07 | 2022-08 | 2022-09 | 2022-10 | 2022-11 | 2022-12 | 2018H2 | 2019H1 | 2019H2 | 2020H1 | 2020H2 | 2021H1 | 2021H2 | 2022H1 | 2022H2 | 2023H1 | 2023H2 | 2024H1 | 2024H2 | 2025H1 | 2025H2 | 2026H1 | 2026H2 | 2027H1 | 2027H2 | 2028H1 | 2028H2 | 2029H1 | 2029H2 | 2030H1 | 2030H2 | 2031H1 | 2031H2 | 2032H1 | 2032H2 | 2033H1 | 2033H2 | 2034H1 | 2034H2 | 2035H1 | 2035H2 | 2036H1 | 2036H2 | 2037H1 | 2037H2 | 2038H1 | 2038H2 | 2039H1 | 2039H2 | 2040H1 | 2040H2 | 2041H1 | 2041H2 | 2042H1 | 2042H2 | 2043H1 | 2043H2 | 2044H1 | 2044H2 | 2045H1 | 2045H2 | 2046H1 | 2046H2
| Cash flow date | date |  |  | 2018-02-05 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2018-12-31 | 2019-06-30 | 2019-12-31 | 2020-06-30 | 2020-12-31 | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30 | 2026-12-31 | 2027-06-30 | 2027-12-31 | 2028-06-30 | 2028-12-31 | 2029-06-30 | 2029-12-31 | 2030-06-30 | 2030-12-31 | 2031-06-30 | 2031-12-31 | 2032-06-30 | 2032-12-31 | 2033-06-30 | 2033-12-31 | 2034-06-30 | 2034-12-31 | 2035-06-30 | 2035-12-31 | 2036-06-30 | 2036-12-31 | 2037-06-30 | 2037-12-31 | 2038-06-30 | 2038-12-31 | 2039-06-30 | 2039-12-31 | 2040-06-30 | 2040-12-31 | 2041-06-30 | 2041-12-31 | 2042-06-30 | 2042-12-31 | 2043-06-30 | 2043-12-31 | 2044-06-30 | 2044-12-31 | 2045-06-30 | 2045-12-31 | 2046-06-30 | 2046-12-31
| Equity cash flow (contributions negative) | USD m |  | 1141.0579 | -14.2 | -17.3226 | -0.64195 | -0.76782 | -0.97825 | -1.2855 | -1.649 | -2.0409 | -2.5148 | -2.9808 | -3.4732 | -3.9436 | -4.4102 | -4.8609 | -5.2734 | -5.6664 | -5.9977 | -6.2986 | -6.8196 | -6.6754 | -6.8153 | -6.9519 | -6.9583 | -6.8784 | -6.7418 | -6.5527 | -6.2942 | -6.4271 | -6.0706 | -5.7021 | -5.4155 | -4.933 | -4.5252 | -3.5456 | -3.4639 | -2.6541 | -2.0772 | -1.4604 | -1.8569 | -1.1454 | -15.7938 | -9.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.6857 | 0 | 0 | 0 | 0 | 46.2554 | 23.38 | 21.2809 | 18.2855 | 19.3571 | 18.371 | 19.2549 | 18.5924 | 18.2624 | 19.1696 | 20.5247 | 19.2471 | 20.2147 | 19.468 | 20.3483 | 19.656 | 20.7773 | 23.5178 | 19.696 | 15.9795 | 16.8598 | 15.9656 | 16.7616 | 15.9402 | 12.1552 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.4017 | 44.6551 | 43.1799 | 34.7514 | 35.4468 | 35.0168 | 35.7027 | 35.2678 | 35.8352 | 44.0976 | 39.1045 | 38.6988 | 63.7064
| Project cash flow, post-tax (uses before financing; CFADS) | USD m |  | 1598.1796 | 0 | -108.0297 | -1.3972 | -1.8346 | -2.6432 | -3.7572 | -5.1 | -6.6364 | -8.3024 | -10.0481 | -11.8263 | -13.5942 | -15.2687 | -16.8967 | -18.4073 | -19.7734 | -20.9699 | -21.9775 | -23.8447 | -23.2809 | -23.6324 | -24.0907 | -23.9749 | -23.6234 | -22.976 | -22.1807 | -21.1798 | -21.5581 | -20.2013 | -18.7008 | -17.5752 | -15.8809 | -14.1371 | -10.4741 | -10.0152 | -6.9519 | -5.882 | -3.5518 | -5.1 | -2.3526 | -57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 44.8074 | 37.2891 | 35.712 | 56.1892 | 57.3841 | 56.6744 | 55.3564 | 51.6815 | 49.1345 | 49.8592 | 49.2987 | 49.9866 | 49.6696 | 50.2282 | 51.6643 | 52.5192 | 51.7106 | 52.4688 | 52.1304 | 52.7902 | 52.4338 | 52.9766 | 52.0418 | 46.1015 | 42.6776 | 43.1505 | 42.492 | 42.8731 | 42.2023 | 42.4458 | 48.9568 | 44.5091 | 43.5005 | 44.274 | 43.8701 | 44.5455 | 44.1435 | 44.6822 | 46.3569 | 44.9012 | 36.4923 | 37.2076 | 36.7978 | 37.5041 | 37.0897 | 37.6779 | 45.9614 | 40.9896 | 40.6055 | 43.5986
| Project cash flow, pre-tax | USD m |  | 1928.8518 | 0 | -108.0297 | -1.3972 | -1.8346 | -2.6432 | -3.7572 | -5.1 | -6.6364 | -8.3024 | -10.0481 | -11.8263 | -13.5942 | -15.2687 | -16.8967 | -18.4073 | -19.7734 | -20.9699 | -21.9775 | -23.8447 | -23.2809 | -23.6324 | -24.0907 | -23.9749 | -23.6234 | -22.976 | -22.1807 | -21.1798 | -21.5581 | -20.2013 | -18.7008 | -17.5752 | -15.8809 | -14.1371 | -10.4741 | -10.0152 | -6.9519 | -5.882 | -3.5518 | -5.1 | -2.3526 | -57.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.2926 | 44.8074 | 37.2891 | 35.712 | 56.1892 | 57.3841 | 56.6744 | 55.3564 | 51.6815 | 49.1345 | 49.9218 | 49.6763 | 50.3665 | 50.0522 | 50.6124 | 52.0434 | 52.904 | 52.1016 | 52.8618 | 52.5251 | 53.1871 | 52.8334 | 53.3782 | 53.8218 | 54.4717 | 51.2368 | 51.944 | 51.6072 | 52.2991 | 51.9368 | 52.5356 | 54.3954 | 55.3324 | 54.3777 | 55.2062 | 54.8694 | 55.5937 | 55.222 | 55.8282 | 56.4205 | 57.1312 | 53.3105 | 54.086 | 53.7494 | 54.5091 | 54.1271 | 54.7984 | 57.18 | 58.2082 | 57.8713 | 51.5238
| Cumulative equity cash flow | USD m |  |  | -14.2 | -31.5226 | -32.1645 | -32.9323 | -33.9106 | -35.1961 | -36.8451 | -38.886 | -41.4008 | -44.3816 | -47.8548 | -51.7984 | -56.2087 | -61.0695 | -66.3429 | -72.0092 | -78.007 | -84.3056 | -91.1251 | -97.8005 | -104.6158 | -111.5677 | -118.526 | -125.4045 | -132.1463 | -138.699 | -144.9932 | -151.4203 | -157.4909 | -163.193 | -168.6085 | -173.5415 | -178.0667 | -181.6123 | -185.0762 | -187.7303 | -189.8075 | -191.2678 | -193.1247 | -194.2701 | -210.0639 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -219.6128 | -201.9271 | -201.9271 | -201.9271 | -201.9271 | -201.9271 | -155.6717 | -132.2917 | -111.0108 | -92.7253 | -73.3682 | -54.9972 | -35.7423 | -17.1499 | 1.1125 | 20.2821 | 40.8068 | 60.0539 | 80.2685 | 99.7366 | 120.0848 | 139.7408 | 160.5181 | 184.0359 | 203.7319 | 219.7114 | 236.5712 | 252.5367 | 269.2984 | 285.2385 | 297.3938 | 346.3505 | 390.8596 | 434.3601 | 478.6341 | 522.5042 | 567.0497 | 611.1932 | 655.5949 | 700.25 | 743.4299 | 778.1813 | 813.6281 | 848.6449 | 884.3477 | 919.6155 | 955.4507 | 999.5482 | 1038.6527 | 1077.3515 | 1141.0579
| Equity IRR (XIRR) | % | 13.44%
| Project IRR, post-tax (XIRR) | % | 10.54%
| Project IRR, pre-tax (XIRR) | % | 11.2%
| Equity NPV at 16.0%, at financial close (2018-07-17) | USD m | -38.0551

## Checks
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Checks: every check shows 0 when passing
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Sources less uses (construction) | check | 0
| Committed debt drawn in full (FC-type), USD m | check | 0
| Closed-form T less live T (re-grossed cases), USD m | check | 0
| Balance sheet balances (max abs difference) | check | 0
| No unpaid debt service after DSRA | check | 0
| Debt repaid by final maturity | check | 0
| FC base: live sculpting equals contract profile (max abs, USD m) | check | 0
| FC base: debt not above DSCR capacity or gearing cap | check | 0
| VAT facility within limit | check | 0
| Standby and contingent equity within commitments | check | 0
| ECA tranche within cap (USD 224.1m) | check | 0
| MMRA never negative | check | 0
| Sum of checks (0 = all pass) | check | 0

## Outputs
Case P: Belanou Combined Cycle Power Project, Republic of Kessara
Outputs: dashboard for the selected scenario
Units in column E; constants in column F; row totals in column G; first period in column J. Inputs: blue on yellow. Links from other sheets: green.
| Label | Unit | Constant | Total
| Total funding requirement | USD m | 846.5288
| Senior debt (four tranches) | USD m | 633.256
| Equity (incl. LNTP) | USD m | 219.6128
| Gearing (debt incl. standby / total funding) | % | 74.06%
| Interest during construction incl. swap and PRI | USD m | 62.521
| Commitment, upfront and agency fees | USD m | 23.1306
| ECA premium | USD m | 20.4061
| DSRA initial funding | USD m | 33.8418
| Standby drawn | USD m | 0
| Contingent equity drawn | USD m | 0
| Minimum DSCR | x | #VALUE!
| Average DSCR | x | #VALUE!
| LLCR at first debt service period (incl. DSRA) | x | 1.5025
| PLCR at first debt service period | x | 1.7265
| Equity IRR | % | 13.44%
| Project IRR, post-tax | % | 10.54%
| Equity NPV at 16.0% (at FC) | USD m | -38.0551
| All checks | check | 0